## Front Page
Contract (Design and Build)/Ugovor (Projektovanje i izgradnja) | Bar-Boljare Highway, Section Smokovac-Uvac-Matesevo/Autoput Bar-Boljare, dionica Smokovac-Uvač-Mateševo
Employer/Poslodavac | The Government of Montenegro, Ministry of Transport and Maritime Affairs
Contractor/Izvođač | China Road and Bridge Corporation ltd. Bejing, PR China, Part of foreign company Podgorica/China Road and Bridge Corporation d.o.o. Peking, NR Kina, Dio stranog društva Podgorica
Engineer/Inženjer | INGEROP CONSEIL & GEODATA Engineering S.P.A
Accepted Contract Amount (A.C.A.)/Prihvaćeni ugovorni iznos (P.U.I.) (Sub Clause/ Potklauzula 1.1.4.1) | 809577356.14
Advance Payment Total Amount/Ukupan iznos avansa (Sub Clause/ Potklauzula 14.2) | 161915471.228
Amount of agreed Variations/Iznos dogovorenih izmjena | 0
Amount of agreed Employers Claims/ Iznos dogovorenih potraživanja Investitora (Sub Clause/Potklauzula 2.5) | EUR 0.00
Amount of agreed Contractor's Claims/Iznos dogovorenih potraživanja Izvođača (Sub Clause/ Potklauzula 20.1) | 0
Maximum Amount of Retention Money/ Maksimalni iznos garantnog depozita (Sub Clause/ Potklauzula 14.3) | 40478867.807
Minimum Amount of Interim Payment Certificate/Minimalni iznos privremene situacije (Sub Clause/ Potklauzula 14.6) | 1000000
INTERIM PAYMENT CERTIFICATE (IPC) / IZDAVANJE PRIVREMENE SITUACIJE (IPS)
Number of IPC/Broj IPS-a | 14
Referenced Period for IPC/Period na koji se odnosi IPS | 01/10/2017-31/10/2017
Date of IPS submission/Datum predavanja ZPS-a | 2017-11-13
Date of IPC (Interim Payment Certificate) issuance/Datum izdavanja IPS-a (Privremene Situacije)
Payment Due Date (42 days after IPS Submission)/Datum dospijeća naplate (42 dana nakon izdavanja ZPS-a) | 2017-12-25
| Cumulative Previous /Kumulativno prethodno | Current Cumulative/ Kumulativno tekuće | Value for Payment/Iznos za plaćanje
A - Contractor's payments/Plaćanja Izvođača
Contracted Works/Ugovorni radovi | 145696491.7639 | 169027176.404 | 23330684.6401
Variations/Izmjene (Clause/Klauzula 13) | 0 | 0 | 0
Substantiated Contractor's Claims/Potkrijepljena potraživanja Izvođača (Sub-clause/Potklauzula 20.1) | 0 | 0 | 0
Total/Ukupno A | 145696491.7639 | 169027176.404 | 23330684.6401
B - Retention Money/Garantni depozit
5% of the amount of each Payment Certificate/ 5% od iznosa svake Potvrde o plaćanju (Sub-Clause /Potklauzula 14.3) | 7284824.5882 | 8451358.8202 | 1166534.232
Total/Ukupno B | 7284824.5882 | 8451358.8202 | 1166534.232
C - Advance payment amortization/Amortizacija avansnog plaćanja
20% of each Payment Certificate, when value of Executed Works has reached 20% of the A.C.A./20% svake Potvrde o plaćanju, kada vrijednost Izvedenih radova dostigne 20% PUI (Sub Clause/ Potklauzula 14.2) | 0 | 1422341.0352 | 1422341.0352
Total/Ukupno C | 0 | 1422341.0352 | 1422341.0352
D - Non Conformity/Neusaglašenost
Value of Non Conformity and closing of NCN's/Vrijednost Neusaglašenosti i zatvaranje OoN | -1197000 | -1227000 | -30000
Total/Ukupno D | -1197000 | -1227000 | -30000
E - Deductions/Odbici
Amount withheld based on Sub-clause 14.6 a/b /Iznos zadržan na osnovu Potklauzule 14.6 a/b | 0 | 0
Delay Damages/obeštećenja za kašnjenje (Sub-clause/Potklauzula 8.7) | 0 | 0
Agreed Employer's Claims/Dogovorena potraživanja Investitora (Sub-clause/Potklauzula 2.5) | 0 | 0
Total/Ukupno E | 0 | 0 | 0
Value of this IPC/Iznos ove IPS (A-B-C-D-E) | 137214667.1757 | 157926476.5486 | 20711809.3729
Total amount due for this IPC/Ukupan dospijeli iznos za ovaj IPS-u | 20711809.3729 | Twenty Million Seven Hundred and Thirteen Thousand and Nine point three seven Euro | dvadesetmilionasedamstotrinaesthiljadadevetevraitridesetsedamcenti
MTMA Portion-Payable in Euro (15%)/ Dio MSiP-a - plativo u EUR (15%) | 3106771.4059 | Three Million One Hundred and Six Thousand Nine Hundred and Fifty One point four one EUR | trimilionastosestshiljadadevetstopedesetjedanevroicetrdesetjedancent
Exim Bank portion-Payable in USD (85%) expressed in Euro/ Dio Exim banke - plativo u USD (85%) izraženo u EUR | 17605037.967 | Seventeen Million Six Hundred and Six Thousand and Fifty Seven point nine six Euros | sedamnaestmilionasestosesthiljadapedesetsedamevraidevedesetsestcenti
Exim Bank portion-Payable in USD (85%) expressed in USD/ Dio Exim banke - plativo u USD, izraženo u USD, (exchange rate/ kurs 1 Eur= 1.3718 USD | 24150591.0831 | Twenty Four Million One Hundred and Fifty One Thousand Nine Hundred and Ninety point three one USD | dvadesetcetirimilionastopedesetjednahiljadadevetstodevedesetdolaratridesetjedancent
Execution progress/Napredak izvođenja (Executed Contracted Works/ A.C.A. / Izvedeni ugovorni radovi/P.U.I.) |  | 20.88% | 2.882%
We hereby confirm that this IPC is based on the actual and correct elements of works, performed by the Contractor in accordance with the agreed method of measurement , and that it is in full compliance with the Contract/ Ovim potvrđujemo da se ova IPS temelji na tačnim i pravilnim elementima rada, izvedenim od strane Izvođača u skladu s dogovrenim metodama mjerenja, i da je potpuno u skladu sa Ugovorom.
Amount approved By Engineer/Iznos odobren od strane Inzenjera | Name/ Ime | Signature/ Potpis | Date/Datum
Jan Lorange
Amount approved by the Project Manager/Iznos odobren od strane Upravljaca projektom | Name/ Ime | Signature/ Potpis | Date/Datum
Approved Payment for Employer/ Iznos odobren od strane Investitora | Name/ Ime | Signature/ Potpis | Date/Datum

## Summary
Summary Calculation IPC No 14/Sumarni proračun IPS No 14
Item/Stavka | Value/Iznos | Value of Previous Cumulative / Prethodni iznos kumulativno | Value of Payment for this IPC / Iznos placanja za ovaj IPS | Total Value to date/ Ukupan iznos | Balance/Saldo
| 1 | 2 | 3 | 4=2+3 | 5 (1-4)
Contracted Works(A.C.A)/Ugovorni radovi (P.U.I.) | 809577356.14 | 145696491.7639 | 23330684.6401 | 169027176.404 | 640550179.736
Variations/Izmjene | 0 | 0 | 0 | 0 | 0
Employers Claims/Potrazivanja | 0 | 0 | 0 | 0 | 0
Contractor Claims/Potrazivanja | 0 | 0 | 0 | 0 | 0
Non Conformity/ Neusaglasenost |  | -1197000 | -30000 | -1227000
Total | 809577356.14 | 144499491.7639 | 23300684.6401 | 167800176.404 | 640550179.736
Repayment of Advance/Isplata avansa
Item/Stavka | Value/Iznos | Repayment advance Previous IPC/Avansna isplata Prethodna IPS | Value of Advance Repayment this IPC / Iznos avansa u ovom IPS | Value of Advance Repayment based on Value of Current Contracted works / Iznos avansa na osnovu Vrijednosti tekucih Ugovorenih radova | Value of remaining advance/Iznos preostalog avansa
| 1 | 2 | 3 | 4 | 5 (1-4)
Advance/Avans | 161915471.228 | 0 | 1422341.0352 | 1422341.0352 | 160493130.1928
Total/Ukupno | 161915471.228 | 0 | 1422341.0352 | 1422341.0352 | 160493130.1928

## Variations
BAR-BOLJARE HIGHWAY/AUTOPUT, SECTION/DIONICA SMOKOVAC-UVAC-MATESEVO
DESIGN AND BUILT CONTRACT/UGOVOR ZA PROJEKTOVANJE I IZGRADNJU
EMPLOYER/INVESTITOR: |  |  | The Government of Montenegro, Ministry of Transport and Maritime Affairs/Vlada Crne Gore, Ministarstvo saobraćaja i pomorstva
CONTRACTOR/IZVOĐAČ: |  |  | China Road and Bridge Corporation
ENGINEER/INŽENJER: |  |  | Ingerop-Geodata JV
VARIATIONS CALCULATION/PRORAČUN IZMJENA
VARIATION NO/IZMJENA BR | VARIATION BASIS/ OSNOVA ZA IZMJENU | VARIATION AMOUNT AGREED WITH ENGINEER/ IZNOS IZMJENE DOGOVOREN SA INŽENJEROM | First included in IPC No/Prvi put uključeno u IPS br. | IPC No 0014/ IPS br. 014
|  |  |  | Cumulative previous/ Kumulativno prethodno | Cumulative Current / Kumulativno trenutno | Value for Payment this IPC / Iznos placanja za ovu IPS
| TOTAL/UKUPNO | 0
Subtotal/ suma stavke 1 | Value Engineering/ Tehnika vrednovanja (Sub-Clause/Potklauzula 13.2) | 0
Subtotal/ suma stavke 2 | Adjustments for Changes in Legislation/Prilagođavanja zbog izmjena u zakonu (Sub-Clause/Potklauzula 13.7) | 0
Subtotal/ suma stavke 3 | Subsequent/ Naknadno (Sub-Clause/Potklauzula 13.9) | 0
Subtotal/ suma stavke 4 | Unforeseeable/Nepredvidljivo (Sub-Clause/Potklauzula 13.9) | 0
Subtotal/ suma stavke 5 | Other Variations/Ostale izmjene | 0
0

## Employer's Claims Status
BAR-BOLJARE HIGHWAY/AUTOPUT, SECTION/DIONICA SMOKOVAC-UVAC-MATESEVO
DESIGN AND BUILT CONTRACT/UGOVOR ZA PROJEKTOVANJE I IZGRADNJU
EMPLOYER/INVESTITOR: |  |  | The Government of Montenegro, Ministry of Transport and Maritime Affairs/ Vlada Crne Gore, Ministarstvo saobraćaja i pomorstva
CONTRACTOR/IZVOĐAČ: |  |  | China Road and Bridge Corporation l.t.d. Beijing, PR China, part of foreign company Podgorica/ China Road and Bridge Corporation, d.o.o. Peking, NR Kina, Dio stranog društva Podgorica
ENGINEER/INŽENJER: |  |  | Ingerop-Geodata JV
EMPLOYER'S CLAIMS/ POTRAŽIVANJA INVESTITORA (SUBCLAUSE/ POTKLAUZULA 2.5)
CLAIM NO/ POTRAŽIVANJE BR. | CLAIMS AMOUNT AGREED WITH ENGINEER. VALUE OF CLAIM DETERMINED BY SUB CLAUSE 3.5 / IZNOS POTRAŽIVANJA DOGOVOREN SA INŽENJEROM. VRIJEDNOST POTRAZIVANJA UTVRDJENA SHODNO POD-KLAUZULI 3.5 | First included in IPC No/Prvi put uključeno u IPS br. | IPC No 014/IPS br. 014
|  |  | Cumulative previous/ Kumulativno prethodno | This Period/ Ovaj period | Total Value to Date/ Ukupan iznos do danas
|  |  | 1 | 2 | 3 = 2 + 1
| TOTAL/UKUPNO |  | 0 | 0 | 0

## Contractor CLaims Status
BAR-BOLJARE HIGHWAY/ AUTOPUT, SECTION/ DIONICA SMOKOVAC-UVAC-MATESEVO
DESIGN AND BUILT CONTRACT/UGOVOR ZA PROJEKTOVANJE I IZGRADNJU
EMPLOYER/ INVESTITOR: |  |  |  | The Government of Montenegro, Ministry of Transport and Maritime Affairs/ Vlada Crne Gore, Ministarstvo saobraćaja i pomorstva
CONTRACTOR/ IZVOĐAČ |  |  |  | China Road and Bridge Corporation l.t.d. Beijing, PR China, part of foreign company Podgorica/ China Road and Bridge Corporation, d.o.o. Peking, NR Kina, Dio stranog društva Podgorica
ENGINEER/ INŽENJER: |  |  |  | Ingerop-Geodata JV
CONTRACTOR'S CLAIMS-ADDITIONAL PAYMENT CALCULATION/ POTRAŽIVANJA IZVOĐAČA-PRORAČUN DODATNOG PLAĆANJA (Sub Clause/ Potklauzula 20.1)
CLAIM NO/ POTRAŽIVANJE BR. | CLAIMS AMOUNT AGREED WITH ENGINEER. VALUE OF CLAIM AS DETERMINED BY SUBCLAUSE 3.5 / IZNOS POTRAŽIVANJA DOGOVOREN SA INŽENJEROM. VRIJEDNOST POTRAZIVANJA UTVRDJENA SHODNO POD-KLAUZULI 3.5 | Status/Status | First included in IPC No / Prvi put uključeno u IPS br. | IPC No 014/ IPS Br. 014
|  |  |  | Cumulative previous/ Kumulativno prethodno | This period/ Ovaj period | Total Value to date/ Ukupan iznos do danas
|  |  |  | 1 | 2 | 3 = 2 + 1
| TOTAL/ UKUPNO |  |  | 0 | 0 | 0

## NCN Status
BAR-BOLJARE HIGHWAY/AUTOPUT, SECTION/DIONICA SMOKOVAC-UVAC-MATESEVO
DESIGN AND BUILT CONTRACT/UGOVOR ZA PROJEKTOVANJE I IZGRADNJU
EMPLOYER/INVESTITOR: |  |  | The Government of Montenegro, Ministry of Transport and Maritime Affairs/Vlada Crne Gore, Ministarstvo saobraćaja i pomorstva
CONTRACTOR/IZVOĐAČ: |  |  | China Road and Bridge Corporation
ENGINEER/INŽENJER: |  |  | Ingerop-Geodata JV
NON CONFORMITY/NEUSAGLAŠENOST (Sub Clause/ Potklauzula 7.1)
NCN No/OoN br. | Description/Opis | First included in IPC No/Prvi put uključeno u IPS br. | Status this IPC/Status ove IPS | IPC No 0014/IPS Br. 0014
|  |  |  | Value Previous Cumulative/ Prethodni iznos kumulativno | This period/ Ovaj period | Total to date/ Ukupno do danas
46 | Acces Road C6, works without approval/Izvođenje radova na pristupnom putu C6 | 3 | Open/ otvoreno | -12000 | 0 | -12000
55 | Quarry Lopate, Absence of Permanent Rescue Unit and Rescue Station/Nedostatak stalne službe spasavanja I stanice za spasavanje | 3 | Open/ otvoreno | -15000 | 0 | -15000
90 | Performing Works on Access Road C7 not in accordance to approved design./Izvođenje radova na pristupnom putu C7 suprotno odobrenom projektu. | 3 | Open/ otvoreno | -7000 | 0 | -7000
113 | Failure to implement adequate Fencing and Security of the Site, South portal tunnel Mrke, camp Mrke/Nesprovođenje adekvatnog obezbjeđenja gradilišta, južni portal tunela Mrke, kamp Mrke | 3 | Open/ otvoreno | -15000 | 0 | -15000
130 | Works on access road in private properties without approved design/Radovi na pristupnom putu na privatnoj imovini bez prihvaćenog projekta | 3 | Open/ otvoreno | -6000 | 0 | -6000
164 | Landfill at location of Lopate. Non/Deponija na lokaciji Lopate | 3 | Open/ otvoreno | -15000 | 0 | -15000
176 | Works without approved Method Statement/Radovi bez odobrene Tehnologije izvođenja | 3 | Open/ otvoreno | -12000 | 0 | -12000
185 | Performing Works on connections on road R19 without traffic management plan and consent of the State Traffic Directorate/Izvođenje radova na priključcima na put R19 bez plana upravljanja saobraćajem i saglasnosti Direkcije za saobraćaj | 3 | Open/ otvoreno | -5000 | 0 | -5000
218 | Steel structures work platform. Lack of safeguard measures / Čelična radna platforma. Nedostatak zaštitnih mjera | 4 | Open/ otvoreno | -15000 | 0 | -15000
231 | Drainage and waste water treatment at location of South portal of tunnel Jabučki krš.Odvodnjavanje i prečišćavanje otpadnih voda na lokaciji južni portal tunela Jabučki krš. | 5 | Closed/zatvoren | -15000 | 15000 | 0
232 | Deficiency of waste water treatment at location of North portal of tunnel Jabučki krš. | 5 | Open/ otvoreno | -15000 | 0 | -15000
250 | Jabučki krš-North. Steel structures work platform. Lack of safeguard measures .Jabučki krš – sjever. Nedostatak zaštitnih mjera na čeličnoj radnoj platformi | 5 | Open/ otvoreno | -15000 | 0 | -15000
278 | Tunnel Jabučki Krš. Lack of Rescue Station; / Tunel Jabučki Krš. Nedostatak Stanice za spasavanje | 6 | Closed/zatvoren | -15000 | 15000 | 0
314 | Interruption of stream at location of South portal of tunnel Kosman. / Prekid toka potoka na lokaciji južni portal tunela Kosman. | 7 | Closed/zatvoren | -15000 | 15000 | 0
315 | Lack of maintenance of waste water treatment and housekeeping at location of North portal of tunnel Kosman. / Nedostatak održavanje tretman otpadnih voda i gradilišta na lokaciji sjeverni portal tunela Kosman. | 7 | Open/ otvoreno | -15000 | 0 | -15000
316 | Lack of waste water treatment and housekeeping at location of South portal of tunnel Mala Trava./ Nedostatak tretman otpadnih voda I održavanje gradilišta na lokaciji južni portal tunela Mala Trava. | 7 | Open/ otvoreno | -15000 | 0 | -15000
317 | Interruption of stream at location of North portal of tunnel Mala trava. / Prekid toka potoka na lokaciji sjeverni portal tunela Mala Trava. | 7 | Open/ otvoreno | -15000 | 0 | -15000
321 | Maintenance of waste water treatment at location of North portal of tunnel Jabučki krš. / Održavanje tretman otpadnih voda I gradilišta na lokaciji sjeverni portal tunela Jabučki krš. | 7 | Open/ otvoreno | -15000 | 0 | -15000
358 | Disturbance of Jabucki stream. / Poremećaj Jabučkog potoka. | 8 | Open/ otvoreno | -15000 | 0 | -15000
363 | Moračica Bridge. Lack of Safety due to the use of an improvised platform / Most Moračica. Nedostatak bezbjednosti pri korištenju improvizirajuće platforme | 9 | Open/ otvoreno | -15000 | 0 | -15000
364 | Moračica Bridge. Lack of Safety due to the use of the improvised Ramp / Most Moračica. Nedostatak bezbjednosti pri korištenju improvizovane rampe | 9 | Open/ otvoreno | -15000 | 0 | -15000
377 | Failure to implement adequate Fencing and Security of the Bridge Gornje Mrke construction site / Nesprovođenje adekvatnog ograđivanja I obezbjeđenja gradilišta mosta Gornje Mrke | 9 | Closed/zatvoren | -15000 | 15000 | 0
384 | Bridge No.17 Jabuka, Bridge left 2. Performing the piles cup above the piles under the pier S11 and installation of pier S11 reinforcement. / Most Br.17 Jabuka, most lijevo 2. Izvođenje naglavne grede iznad šipova ispod stuba S11 i ugradnja armature stuba S11 | 11 | Open/ otvoreno | -15000 | 0 | -15000
387 | Disturbance of Jabsenicki steam/ Poremećaj Jabsenicki potoka. | 8 | Open/ otvoreno | -15000 | 0 | -15000
390 | Lack of maintenance of washing area at location of North portal of tunnel Mala Trava./ Nedostatak održavanje prostor za pranje na lokaciji sjeverni portal tunela Mala Trava | 9 | Open/ otvoreno | -15000 | 0 | -15000
400 | Casing of Lopatski stream/Ucjevljenje Lopatskog potoka | 9 | Open/ otvoreno | -15000 | 0 | -15000
415 | Most Moračica. Health and Safety implementation is missing/ Most Moračica. Nedostatak primjene mjera zaštite na radu | 10 | Open/ otvoreno | -15000 | 0 | -15000
429 | Deficiency and Maintenance of waste water treatment at location of North portal of tunnel Mala trava. /Nedostatak i održavanja za prečišćavanje otpadnih voda na lokaciji sjeverni portal tunela Mala trava. | 10 | Closed/zatvoren | -15000 | 15000 | 0
443 | Tunnel Vjeternik - south portal. Lack of Health and Safety implementation measures /Tunel Vjeternik-južni portal. Nedostatak primjene mjera zaštite na radu | 10 | Open/ otvoreno | -15000 | 0 | -15000
444 | The procedure of sampling of aggregate and lacks within the procedure of storing and labelling of aggregates at concrete batching plant Jabuka. / Procedure uzorkovanja agregata i grešaka u proceduri skladištenja i označavanja agregata na fabrici betona Jabuka. | 11 | Open/ otvoreno | -15000 | 0 | -15000
445 | Bridge No.17 Jabuka, Bridge left 2. Performing the piles cup above the piles under the pier S11 and installation of pier S11 reinforcement. / Most Br.17 Jabuka, most lijevo 2. Izvođenje naglavne grede iznad šipova ispod stuba S11 i ugradnja armature stuba S11 | 11 | Closed/zatvoren | -15000 | 15000 | 0
446 | Moracica Bridge – A1. Slope protection - installing of hexagonal mesh. /Most Moračica – A1. Zaštita kosina – ugradnja putarske mreže | 13 | Open/ otvoreno | -15000 | 0 | -15000
448 | Most Mrke. Lack of Health and Safety implementation measures/ Most Mrke. Nedostatak primjene mjera zaštite na radu | 11 | Closed/zatvoren | -15000 | 15000 | 0
455 | Pollution of Čestogaz stream at location of Mala trava camp. / Zagađenje potoka Čestogaz na lokaciji kampa Mala trava. | 11 | Open/ otvoreno | -15000 | 0 | -15000
457 | Concrete and Waste water at location of access road C7 and Landfill III-13. / Betonska i Otpadna voda na lokaciji pristupnog puta C7 i deponija III-13. | 11 | Open/ otvoreno | -15000 | 0 | -15000
458 | Concrete and Waste water at location of concrete mix plant Trebješica. / Upravljanje betonska I otpadna voda na lokaciji betonska baza Trebješica. | 11 | Open/ otvoreno | -15000 | 0 | -15000
461 | Uvac 4 Bridge – S8. Protection of foundation pit Most Uvač 4 – S8. Zaštita temeljne jame | 13 | Open/ otvoreno | -15000 | 0 | -15000
465 | Tunnel Kosman north portal left tube element NL1-2 - Lack of Superintendence - Works on permanent lining cast not according to Main Design, MS and Construction standards./ Tunel Kosman, sjeverni portal lijeva cijev element NL1-2 – Nedostatak internog nadzora – Radovi na betoniranju sekundarne obloge nijesu u skladu sa Glavnim projektom, TI i standardima izgradnje. | 11 | Open/ otvoreno | -15000 | 0 | -15000
477 | Tunnel Vilac. Lack of Health and Safety measures implementation / Tunel Vilac. Nedostatak primjene mjera zaštite na radu | 11 | Open/ otvoreno | -15000 | 0 | -15000
481 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Vezesnik tunnel left tube /Geotehnički monitoring i mjerenja u lijevoj cijevi tunela Vežešnik nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
482 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Vezesnik tunnel right tube/ Geotehnički monitoring i mjerenja u desnoj cijevi tunela Vežešnik nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
483 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Mrke tunnel left tube /Geotehnički monitoring i mjerenja u lijevoj cijevi tunela Mrke nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
484 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Mrke tunnel right tube/ Geotehnički monitoring i mjerenja u desnoj cijevi tunela Mrke nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
485 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Klopot tunnel left tube /Geotehnički monitoring i mjerenja u lijevoj cijevi tunela Klopot nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
486 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Klopot tunnel right tube/Geotehnički monitoring i mjerenja u desnoj cijevi tunela Klopot nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
487 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Vilac tunnel left tube /Geotehnički monitoring i mjerenja u lijevoj cijevi tunela Vilac nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
488 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Vilac tunnel right tube/ Geotehnički monitoring i mjerenja u desnoj cijevi tunela Vilac nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
489 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Vjeternik tunnel left tube/ Geotehnički monitoring i mjerenja u lijevoj cijevi tunela Vjeternik nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
490 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Vjeternik tunnel right tube /Geotehnički monitoring i mjerenja u desnoj cijevi tunela Vjeternik nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
491 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Mrki Krs tunnel left tube /Geotehnički monitoring i mjerenja u lijevoj cijevi tunela Mrki Krš nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
492 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Mrki Krs tunnel right tube /Geotehnički monitoring i mjerenja u desnoj cijevi tunela Mrki Krš nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
493 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Kosman tunnel left tube /Geotehnički monitoring i mjerenja u lijevoj cijevi tunela Kosman nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
494 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Kosman tunnel right tube /Geotehnički monitoring i mjerenja u desnoj cijevi tunela Kosman nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
495 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Mala Trava tunnel left tube/ Geotehnički monitoring i mjerenja u lijevoj cijevi tunela Mala Trava nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
496 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Mala Trava tunnel right tube /Geotehnički monitoring i mjerenja u desnoj cijevi tunela Mala Trava nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
497 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Zecka tunnel left tube /Geotehnički monitoring i mjerenja u lijevoj cijevi tunela Zecka nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
498 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Zecka tunnel right tube/ Geotehnički monitoring i mjerenja u desnoj cijevi tunela Zecka nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
499 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Jabucki Krs tunnel left tube/ Geotehnički monitoring i mjerenja u lijevoj cijevi tunela Jabučki Krš nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
500 | Geotechnical monitoring and measurements not according to Main Design and Technical Specifications on Jabucki Krs tunnel right tube /Geotehnički monitoring i mjerenja u desnoj cijevi tunela Jabučki Krš nijesu u skladu sa Glavnim projektom i Tehničkim specifikacijama | 12 | Open/ otvoreno | -15000 | 0 | -15000
501 | On the Batching Plant Mrke – Bemax, were appeared lacks in the procedure of quality control of aggregates / Na fabrici betona Mrke - Bemax, pojavili su se nedostaci u postupku kontrole kvaliteta agregata. | 12 | Open/ otvoreno | -15000 | 0 | -15000
505 | Waste water treatment at location of concrete mix plant Lopate./ Prečišćavanje otpadnih voda na lokaciji betonska baza Lopate. | 12 | Open/ otvoreno | -15000 | 0 | -15000
507 | Crossing of the Tara river / Prelazak preko rijeke Tare | 12 | Closed/zatvoren | -15000 | 15000 | 0
513 | Insufficient quality control of aggregates - Vjeternik North / Nedovoljna kontrola kvaliteta agregata na Vjeternik sjever | 12 | Open/ otvoreno | -15000 | 0 | -15000
516 | Jabuka Right Bridge. Abutment O1. Top surfacecracks / Most Jabuka Desno. Oporac O1. Gornja površina – prsline | 12 | Open/ otvoreno | -15000 | 0 | -15000
518 | Mistakes regard to using of aggregates at batching Plant Mrke -Bemax / Greške u pogledu korišćenja agregata na fabrici betona Mrke - Bemax | 12 | Open/ otvoreno | -15000 | 0 | -15000
523 | Concrete sludge from washing mixers in the Tara basin/ Betonski mulj od pranja miksera u koritu rijeke Tare. | 13 | Closed/zatvoren | -15000 | 15000 | 0
527 | Bridge Ratkov Laz. Sub-section 2.2. Lack of Health and Safety implementation measures /Most Ratkov Laz. Podsekcija 2.2. Nedostatak primjene mjera zaštite na radu | 13 | Open/ otvoreno | -15000 | 0 | -15000
532 | Tunnel Kosman Left tube – H&S, ventilation not working, workers work on reinforcement installation on an improvised scaffolding without safety belts at 6 m height/ Tunel Kosman, lijeva tunelska cijev – zaštita na radu, ventilacija nije u funkciji, radnici rade na izradi armature sa improvizovane skele bez zaštitnih pojaseva na visini od 6 m. | 13 | Open/ otvoreno | -15000 | 0 | -15000
533 | Tunnel Mrki Krš south portal storage of materials and maitanance of tunnel formwork /Tunel Mrki Krš južni portal skladištenje materijala i održavanje oplate za tunelsku oblogu | 13 | Open/ otvoreno | -15000 | 0 | -15000
539 | Concrete sludge and waste water at location of Landfill subsection 1.4. /Betonski mulj i otpadna voda na lokaciji deponija pod-dionica 1.4. | 13 | Open/ otvoreno | -15000 | 0 | -15000
540 | Concrete sludge and waste water at location of Landfill II-9. Betonskog ostatak i Otpadna voda na lokaciji Deponija II-9. | 13 | Open/ otvoreno | -15000 | 0 | -15000
541 | Concrete sludge and waste water at location of South portal of tunnel Vjeternik./ Betonskog mulja i Otpadna voda na lokaciji južnog portal tunela Vjeternik. | 13 | Closed/zatvoren | -15000 | 15000 | 0
542 | Pollution of Suvovara stream at location of North portal of tunnel Vjeternik. / Zagađenje potoka Suvovara na lokaciji sjeverni portal tunela Vjeternik. | 13 | Open/ otvoreno | -15000 | 0 | -15000
543 | Washing area at location of South portal of tunnel Mrki Krs. Otpadnih voda na lokaciji južnog portal tunela Mrki Krs | 13 | Open/ otvoreno | -15000 | 0 | -15000
544 | Storage of materials and trucks parking into Tara’s riverbed at location of Uvac 4./ Skladištenje materijala i parkiranje kamiona u koritu rijeke Tare na lokaciji Uvac 4 | 13 | Closed/zatvoren | -15000 | 15000 | 0
545 | Lack of WWTS and Washing area at location of Zecka tunnel Nedostatak tretmana otpadnih voda I prostor za pranje na lokaciji tunela Zecka | 13 | Open/ otvoreno | -15000 | 0 | -15000
546 | Disturbance and interruption of stream at location of Zecka tunnel. / Poremećaj I Prekid toka potoka na lokaciji tunela Zecka | 13 | Open/ otvoreno | -15000 | 0 | -15000
547 | Works into Tara’s riverbed at the location of Uvac 4. Radovi u koritu rijeke Tare na lokaciji Uvac 4. | 13 | Open/ otvoreno | -15000 | 0 | -15000
552 | Tunnel Vilac-left tube. Lack of Health and Safety implementation measures /Tunel Vilac-lijeva cijev. Nedostatak primjene mjera zaštite na radu | 13 | Closed/zatvoren | -15000 | 15000 | 0
553 | Tunnel Klopot-left tube. Lack of Health and Safety implementation measures /Tunel Klopot-lijeva cijev. Nedostatak primjene mjera zaštite na radu | 13 | Open/ otvoreno | -15000 | 0 | -15000
559 | Subsection 3.1- Bridge Suvovara, Foundations S2, S4- Usage of reinforcement from not approved producer /Podsekcija 3.1- Most Suvovara, Temelji S2, S4- Korišćenje armature neodobrenog proizvođača | 13 | Open/ otvoreno | -15000 | 0 | -15000
560 | Subsection 3.1, retaining wall no. 21, it was noted that installed reinforcement in segment 2 is from unrecognized Producer. Podsekcije 3.1, potporni zid br. 21 primećeno je da na segmentu 2 instalirana armatura od nepoznatog Proizvođača | 13 | Open/ otvoreno | -15000 | 0 | -15000
563 | Lack of maintenance of the concrete area and the presence of cement milk in the Tara River./ Nedostatak održavanja prostora betonjerke i prisustvo cementnog mlijeka u rijeci Tari. | 14 | Open/ otvoreno |  | -15000 | -15000
566 | Improper storage and damage of the drainage pipes for the tunnels / Nepropisno skladištenje i oštećenje cijevi za odvodnju u tunelima | 14 | Open/ otvoreno |  | -15000 | -15000
568 | Bridge Uvač 4. Lack of Health and Safety implementation measures / Most Uvač 4. Nedostatak sprovođenja mjera zaštite na radu | 14 | Open/ otvoreno |  | -15000 | -15000
569 | Bridge Jabuka. Lack of Health and Safety implementation measures / Most Jabuka. Nedostatak sprovođenja mjera zaštite na radu | 14 | Open/ otvoreno |  | -15000 | -15000
572 | Tunnel Vilac north portal right tube Tunel Vilac sjeverni portal, desna tunelska cijev | 14 | Open/ otvoreno |  | -15000 | -15000
581 | Tunnel Vilac – works in aggravated conditions due to insufficient ventilation in tunnels. Lack of Health and Safety implementation measures / Tunel Vilac. Rad u otežanim uslovima zbog nedovoljne provjetrenosti tunela. Nedostatak sprovođenja mjera zaštite na radu | 14 | Open/ otvoreno |  | -15000 | -15000
582 | Tunnel Vjeternik south portal, left tube. Works in aggravated conditions due to insufficient ventilation in the tunnel. Lack of Health and Safety implementation measures/ Tunel Vjeternik, južni portal,-lijeva cijev. Rad u otežanim uslovima zbog nedovoljne provjetrenosti tunela.Nedostatak sprovođenja mjera zaštite naradu | 14 | Open/ otvoreno |  | -15000 | -15000
584 | Absence of regular sampling of aggregates at batching Plant Jabuka/ Izostanak redovnog uzorkovanja agregata na fabrici betona Jabuka | 14 | Open/ otvoreno |  | -15000 | -15000
588 | Tunnel Vilac, south portal, left tube – Works in aggravated conditions due to insufficient ventilation in the tunnel. Lack of Health and Safety implementation measures /Tunel Vilac, južni portal, lijeva cijev. Rad u otežanim uslovima zbog nedovoljne provjetrenosti tunela. Nedostatak sprovođenja mjera zaštite na radu | 14 | Open/ otvoreno |  | -15000 | -15000
589 | Tunnel Vjeternik, south portal, left tube – Works in aggravated conditions due to insufficient ventilation in the tunnel. Lack of Health and Safety implementation measures Tunel Vjeternik, južni portal, lijeva cijev – Rad u otežanim uslovima zbog nedovoljne provjetrenosti tunela. Nedostatak sprovođenja mjera zaštite na radu | 14 | Open/ otvoreno |  | -15000 | -15000
590 | Pollution of ground by concrete sludge and waste water from the mixer. / Zagađenje zemljišta betonskim muljem i otpadnom vodom iz miksera. | 14 | Open/ otvoreno |  | -15000 | -15000
591 | Lack of maintenance of space for washing machines and systems with wastewater treatment. /Nedostatak održavanja prostora za pranje mašina i sistema za prečišćavanje otpadnih voda. | 14 | Open/ otvoreno |  | -15000 | -15000
592 | Lack of maintenance of site cleanliness and pollution of ground by concrete sludge and waste water from mixers. /Neodržavanje čistoće gradilišta I zagađenje zemljišta betonskim muljem i otpadnom vodom iz miksera. | 14 | Open/ otvoreno |  | -15000 | -15000
593 | Lack maintenance of assess road D10 and pollution of Jabucki stream. Neodržavanje pristupnog puta D10 i zagađenje Jabučkog potoka. | 14 | Open/ otvoreno |  | -15000 | -15000
|  |  | TOTAL/UKUPNO | -1197000 | -30000 | -1227000

## SUMMARY DESIGN AND CONST
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
IPC No/IPS Br. | 14
SUMMARY OF PAYMENT FOR DESIGN AND BUILD (CONTRACTED WORKS)/REZIME PLAĆANJA ZA PROJEKTOVANJE I IZGRADNJU (UGOVORNI RADOVI)
Cost Center No./ Troškovno mjesto Br. | Description/Opis | Value of Works/Vrijednost radova | Previous Cumulative/ Prethodno kumulativno | This period/ Ovaj period | Total Value to date/ Ukupan iznos do danas | Balance/ Saldo
|  | 1 | 2 | 3 | 4=2+3 | 5=1-4
Cost Center/ Troškovno mjesto A | Design Costs/ Projektni troškovi
| Main design/Glavni projekat | 9724671.92 | 8625783.21 | 0 | 8625783.21 | 1098888.71
| Subtotal/suma stavke Cost Center/ Troškovno mjesto A | 9724671.92 | 8625783.21 | 0 | 8625783.21 | 1098888.71
Cost Center/ Troškovno mjesto B | Construction Works/ Građevinski radovi
Completion of/Završetak:
Cost Center/ Troškovno mjesto 01 | Subsection/Podsekcija 1.1 (LK0- LK4+760.00, RK0-RK4+751.60)
Cost Center/ Troškovno mjesto 1.1 | Road Works/ Radovi na putevima (LK0—LK0+405.00, RK0—RK0+481.00) | 3162301.0696 | 0 | 0 | 0 | 3162301.0696
Cost Center/ Troškovno mjesto 1.2 | Construction of tunnel Suka/Izgradnja tunela Suka (LK0+405.000—LK1+125.000 , length 720m RK0+481.000—RK1+085.000, length 604m) | 13486263.29 | 0 | 0 | 0 | 13486263.29
Cost Center/ Troškovno mjesto 1.3 | Road Works/Radovi na putevima (LK1+125.000—LK1+208.014 RK1+085.000—RK1+340.000 | 1215873.2806 | 0 | 0 | 0 | 1215873.2806
Cost Center/ Troškovno mjesto 1.4 | Road Works/ Radovi na putevima (LK1+208.014—LK1+248.000 RK1+340.000—RK1+348.000) | 122509.5895 | 0 | 0 | 0 | 122509.5895
Cost Center/ Troškovno mjesto 1.5 | Construction of tunnel/Izgradnja tunela Vezesnik (LK1+248.000—LK3+722.000 RK1+348.000—RK3+762.000) | 44741364.89 | 4639691.2764 | 1235841.9025 | 5875533.1789 | 38865831.7111
Cost Center/ Troškovno mjesto 1.6 | Road Works/Radovi na putevima (LK3+722.000—LK3+847.873 RK3+762.000—RK3+840.000) | 520493.3829 | 0 | 0 | 0 | 520493.3829
Cost Center/ Troškovno mjesto 1.7 | Road Works/Radovi na putevima (LK3+847.873—LK4+760.000 RK3+840.000—RK4+751.597) | 4645299.4919 | 0 | 0 | 0 | 4645299.4919
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 01 | 67894104.9946 | 4639691.2764 | 1235841.9025 | 5875533.1789 | 62018571.8111
Cost Center/ Troškovno mjesto 02 | Subsection/Podsekcija 1.2 (LK4+760.00 - LK6+440, RK4+751.60 - RK6+435)
Cost Center/ Troškovno mjesto 2.1 | Road Works/Radovi na putevima (LK4+760—LK4+843.115, RK4+751.60—RK4+830.54) | 390638.74 | 0 | 0 | 0 | 390638.74
Cost Center/ Troškovno mjesto 2.2 | Construction of bridge Gornje Mrke/ Izgradnja mosta Gornje Mrke Lk 4+843.115-LK 5+139.155, RK 4+834.540-RK 5+126.54 | 4834301.08 | 343217.47 | 77513.8704 | 420731.3404 | 4413569.7396
Cost Center/ Troškovno mjesto 2.3 | Road Works/ Radovi na putevima (LK5+139.115—LK5+152.612, RK5+126.540—RK5+143.377) | 136204.02 | 0 | 0 | 0 | 136204.02
Cost Center/ Troškovno mjesto 2.4 | Construction of tunnel Mrke/ Izgradnja tunela Mrke LK 5+152.612- LK 5+991.612, RK 5+143.377- RK 5+947.377 | 16770010.76 | 3630489.2421 | 708224.4753 | 4338713.7174 | 12431297.0426
Cost Center/ Troškovno mjesto 2.5 | Road Works/ Radovi na putevima (LK5+991.612—LK6+440.00, RK5+949.377—RK6+435.000) | 4494623.88 | 0 | 0 | 0 | 4494623.88
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 02 | 26625778.48 | 3973706.7121 | 785738.3458 | 4759445.0578 | 21866333.4222
Cost Center/ Troškovno mjesto 03 | Subsection/Podsekcija 1.3 (LK6+440.000-LK7+445.350, RK6+435.000 - RK7+440.63)
Cost Center/ Troškovno mjesto 3.1 | Road Works/Radovi na putevima (LK6+440.000 - LK6+482.138, RK6+435.000 - RK6+476.572) | 120175.8996 | 0 | 0 | 0 | 120175.8996
Cost Center/ Troškovno mjesto 3.2 | Construction of bridge Moracica/ Izgradnja mosta Moračica LK6+482.138- LK 7+442.333, RK 6+476.572- RK 7+436.377 | 74518071.95 | 40187442.1232 | 3099091.9199 | 43286534.0431 | 31231537.9069
Cost Center/ Troškovno mjesto 3.3 | Road Works/Radovi na putevima (LK7+442.333—LK7+445.350 RK7+436.377—RK7+440.630) | 10435.972 | 0 | 0 | 0 | 10435.972
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 03 | 74648683.8216 | 40187442.1232 | 3099091.9199 | 43286534.0431 | 31362149.7785
Cost Center/ Troškovno mjesto 04 | Subsection/Podsekcija 1.4 (LK7+445.35—LK11+200.00, RK7+440.63—RK11+194.958)
Cost Center/ Troškovno mjesto 4.1 | Road Works/ Radovi na putevima (LK7+445.35—LK11+200.00, RK7+440.63—RK11+194.958) | 22060276.9365 | 872369.5328 | 1180569.4146 | 2052938.9474 | 20007337.9891
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 04 | 22060276.9365 | 872369.5328 | 1180569.4146 | 2052938.9474 | 20007337.9891
Cost Center/ Troškovno mjesto 05 | Subsection/Podsekcija 2.1 (LK11+200.00-LK14+700.000, RK11+194.958 - RK14+740.000)
Cost Center/ Troškovno mjesto 5.1 | Road Works/Radovi na putevima (LK11+200.00 -LK11+495.000, RK11+194.958 - RK11+595.000) | 1999483.17 | 0 | 0 | 0 | 1999483.17
Cost Center/ Troškovno mjesto 5.2 | Construction of tunnel Klopot/ Izgradnja tunela Klopot LK 11+495.00- LK 12+480.000, RK 11+595.000, RK 11+595.000- 12+410.000 | 26346166.79 | 7989758.9792 | 320584.5359 | 8310343.5151 | 18035823.2749
Cost Center/ Troškovno mjesto 5.3 | Road Works/ Radovi na putevima (LK12+480.000—LK13+885.000, RK12+410.000—RK13+790.000) | 7247436.3242 | 877290.338 | 94852.7547 | 972143.0927 | 6275293.2315
Cost Center/ Troškovno mjesto 5.4 | Construction of tunnel/ Izgradnja tunela Vilac LK 13+885.000 - LK 14+700.000, RK 13+790.000- RK 14+740.000 | 21341905.88 | 5489224.8976 | 2093720.8176 | 7582945.7153 | 13758960.1647
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 05 | 56934992.1642 | 14356274.2148 | 2509158.1082 | 16865432.323 | 40069559.8412
Cost Center/ Troškovno mjesto 06 | Subsection/Podsekcija 2.2 (LK14+700.00-LK19+305, RK14+740-RK19+349.00)
Cost Center/ Troškovno mjesto 6.1 | Road Works/ Radovi na putevima (LK14+700.00—LK16+241, RK14+740.00—RK15+993.453) | 7557533.9018 | 241228.12 | 0 | 241228.12 | 7316305.7818
Cost Center/ Troškovno mjesto 6.2 | Construction of interchange/Izgradnja petlje (LK16+241.111—LK16+937.953 RK15+993.453—RK16+787.903) | 5712241.38 | 0 | 0 | 0 | 5712241.38
Cost Center/ Troškovno mjesto 6.3 | Road Works/Radovi na putevima (LK16+937.953—LK16+974.980 RK16+787.903—RK17+022.056) | 733818.5359 | 0 | 0 | 0 | 733818.5359
Cost Center/ Troškovno mjesto 6.4 | Construction of bridge/Izgradnja mosta Djuricev Laz (LK16+974.980—LK17+325.673 RK17+022.056—RK17+347.268) | 7131612.39 | 0 | 24602.54 | 24602.54 | 7107009.85
Cost Center/ Troškovno mjesto 6.5 | Road Works/ Radovi na putevima (LK17+325.673 —LK17+895.654 RK17+347.268—RK17+946.301) | 3875535.8209 | 93025.5366 | 0 | 93025.5366 | 3782510.2842
Cost Center/ Troškovno mjesto 6.6 | Construction of bridge/ Izgradnja mosta Ratkov Laz (LK17+895.654—LK18+245.699 RK17+946.301—RK18+272.128) | 7085868.1 | 45097.22 | 140051.64 | 185148.86 | 6900719.24
Cost Center/ Troškovno mjesto 6.7 | Road Works/ Radovi na putevima (LK18+245.699—LK18+551.474 RK18+272.128—RK18+642.024) | 1682302.8105 | 0 | 0 | 0 | 1682302.8105
Cost Center/ Troškovno mjesto 6.8 | Construction of bridge/ Izgradnja mosta Lutovo (LK18+551.474 —LK18+763.474 RK18+642.024—RK18+770.024) | 3696130.11 | 0 | 0 | 0 | 3696130.11
Cost Center/ Troškovno mjesto 6.9 | Road Works/ Radovi na putevima (LK18+763.474—LK19+305.000 RK18+770.024—RK19+349.000) | 3429156.518 | 100183.7233 | 290013.2015 | 390196.9248 | 3038959.5932
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 06 | 40904199.567 | 479534.5999 | 454667.3815 | 934201.9814 | 39969997.5856
Cost Center/ Troškovno mjesto 07 | Subsection/Podsekcija 2.3 (LK19+305.00-LK22+730.00, RK19+349.00-RK22+735.00)
Cost Center/ Troškovno mjesto 7.1 | Road Works/ Radovi na putevima (LK19+305.000—LK19+655.919, RK19+349.000—RK19+719.643) | 1852888.5217 | 101091.9 | 50545.95 | 151637.85 | 1701250.6717
Cost Center/ Troškovno mjesto 7.2 | Construction of tunnel/ Izgradnja tunela Vjeternik (LK 19+655.919- LK 22+649.920, RK 19+719.643- RK 22+571.640) | 66869012.38 | 13353944.5049 | 3998723.3596 | 17352667.8644 | 49516344.5156
Cost Center/ Troškovno mjesto 7.3 | Road Works/ Radovi na putevima (LK22+694.920—LK22+730.000, RK22+571.640—RK22+735.000) | 735921.1923 | 0 | 0 | 0 | 735921.1923
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 07 | 69457822.0941 | 13455036.4049 | 4049269.3096 | 17504305.7144 | 51953516.3796
Cost Center/ Troškovno mjesto 08 | Subsection/ Podsekcija 3.1 (LK22+730.000-LK24+778.000, RK22+735.000-RK24+915.000)
Cost Center/ Troškovno mjesto 8.1 | Road Works/Radovi na putevima (LK22+730.000—LK22+747.790, RK22+735.000—RK22+751.640) | 480020.24 | 0 | 0 | 0 | 480020.24
Cost Center/ Troškovno mjesto 8.2 | Construction of bridge/ Izgradnja mosta Suvovara (LK 22+747.790 - LK 22+931.790, RK 22+751.640- RK 22+991.640) | 4602196.49 | 0 | 0 | 0 | 4602196.49
Cost Center/ Troškovno mjesto 8.3 | Road Works/ Radovi na putevima (LK22+931.790—LK23+412.120, RK22+991.640—RK23+441.042) | 3885705.13 | 0 | 0 | 0 | 3885705.13
Cost Center/ Troškovno mjesto 8.4 | Construction of bridge/ Izgradnja mosta Krkor ( LK 23+412.12- LK 23+746.12, RK 23+441.042 - RK 23+731.042) | 6748832.06 | 0 | 0 | 0 | 6748832.06
Cost Center/ Troškovno mjesto 8.5 | Road Works/ Radovi na putevima (LK23+746.12—LK23+752.474, RK23+731.042—RK23+806.016) | 930956.53 | 0 | 0 | 0 | 930956.53
Cost Center/ Troškovno mjesto 8.6 | Construction of Verusa interchange/ Izgradnja petlje Veruša (LK 23+752.474- LK 24+762.820, RK 23+806.016- RK 24+892.257) | 14291712.83 | 0 | 0 | 0 | 14291712.83
Cost Center/ Troškovno mjesto 8.7 | Construction of bridge/ Izgradnja mosta Mistica (LK 24+173.92-LK24+345.92, RK 24+204.14-RK24+428.14) | 3846801 | 0 | 0 | 0 | 3846801
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 08 | 34786224.28 | 0 | 0 | 0 | 34786224.28
Cost Center/ Troškovno mjesto 09 | Subsection/ Podsekcija 3.2 (LK24+778.00-LK26+502.72,RK24+915.00-RK26+557.71)
Cost Center/ Troškovno mjesto 9.1 | Construction of tunnel/ Izgradnja tunela Mrki Krs (LK 42+778000- LK 25+495.00, RK 24+915.000-RK 25+507.000) | 20387428.962 | 3212113.5108 | 663504.9443 | 3875618.4551 | 16511810.5069
Cost Center/ Troškovno mjesto 9.2 | Road Works/Radovi na putevima (LK25+495.00—LK25+828.000, RK25+507.000—RK25+955.000) | 3714421.36 | 0 | 0 | 0 | 3714421.36
Cost Center/ Troškovno mjesto 9.3 | Construction of tunnel/Izgradnja tunela Durilovac (LK25+828.000- LK 26+237.000, RK 25+955.000-RK 26+345.000) | 12304869.22 | 0 | 0 | 0 | 12304869.22
Cost Center/ Troškovno mjesto 9.4 | Road Works/Radovi na putevima (LK26+327.40—LK26+387.920, RK26+345.000—RK26+393.143) | 246246.36 | 0 | 0 | 0 | 246246.36
Cost Center/ Troškovno mjesto 9.5 | Construction of bridge/Izgradnja mosta Zagrade (LK 26.387.920- LK 26+487.920, RK 26+393.143- RK 26+539.143) | 1908719.5746 | 0 | 0 | 0 | 1908719.5746
Cost Center/ Troškovno mjesto 9.6 | Road Works/Radovi na putevima (LK26+487.920—LK26+502.720, RK26+539.143—RK26+557.71) | 100691.4 | 0 | 0 | 0 | 100691.4
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 09 | 38662376.8766 | 3212113.5108 | 663504.9443 | 3875618.4551 | 34786758.4215
Cost Center/ Troškovno mjesto 10 | Subsection/Podsekcija 3.3 (LK26+502.72-LK29+317.00, RK26+557.71-RK29+350.00)
Cost Center/ Troškovno mjesto 10.1 | Road Works/Radovi na putevima (LK 26+502.72- LK 26+512.921, RK26+557.71—RK26+724.643) | 1854135.85 | 0 | 0 | 0 | 1854135.85
Cost Center/ Troškovno mjesto 10.2 | Construction of tunnel/Izgradnja tunela Kosman (LK 26+512.921 - LK 29+174.921 , RK 26+724.643- RK 29+231.643) | 58179591.01 | 12716946.3667 | 2869345.0864 | 15586291.4531 | 42593299.5569
Cost Center/ Troškovno mjesto 10.3 | Road Works/Radovi na putevima (LK29+174.921—LK29+317.20 , RK29+231.643—RK29+350.00) | 960130.46 | 0 | 0 | 0 | 960130.46
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 10 | 60993857.32 | 12716946.3667 | 2869345.0864 | 15586291.4531 | 45407565.8669
Cost Center/ Troškovno mjesto 11 | Subsection/Podsekcija 3.4 (LK29+317.20-LK31+556.000, RK29+350.00- RK31+624.00)
Cost Center/ Troškovno mjesto 11.1 | Road Works/Radovi na putevima LK29+317.200—LK29+489.000 RK29+350.000—RK29+710.000 | 1100737.6343 | 0 | 0 | 0 | 1100737.6343
Cost Center/ Troškovno mjesto 11.3 | Bridge/Most Podovi LK29+489.000—LK29+661.000 | 2428583.88 | 0 | 0 | 0 | 2428583.88
Cost Center/ Troškovno mjesto 11.4 | Road Works/Radovi na putevima LK29+661.000—LK29+670.000 | 1195.1797 | 0 | 0 | 0 | 1195.1797
Cost Center/ Troškovno mjesto 11.5 | Road Works/Radovi na putevima LK29+670.000—LK29+683.000 RK29+710.000—RK29+722.000 | 3187.1459 | 0 | 0 | 0 | 3187.1459
Cost Center/ Troškovno mjesto 11.2 | Construction of tunnel/Izgradnja tunela Mala Trava LK29+683.000—LK31+556.000 RK29+722.000—RK31+624.000 | 44539413.67 | 12514520.3884 | 2333102.7243 | 14847623.1127 | 29691790.5573
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 11 | 48073117.51 | 12514520.3884 | 2333102.7243 | 14847623.1127 | 33225494.3973
Cost Center/ Troškovno mjesto 12 | Subsection/Podsekcija 4.1 (LK31+556.000-LK35+425.00, RK31+624.000-RK35+480.00)
Cost Center/ Troškovno mjesto 12.1 | Open Route/Otvorena trasa LK31+556.000 —LK31+587.000 RK31+624.000—RK31+658.000 | 87843.62 | 0 | 0 | 0 | 87843.62
Cost Center/ Troškovno mjesto 12.2 | BRIDGE/MOST ČESTOGAZ LK31+587.000—LK31+681.000 RK31+658.000—RK31+752.000 | 2898324.11 | 0 | 0 | 0 | 2898324.11
Cost Center/ Troškovno mjesto 12.3 | Road Works/ Radovi na putevima (LK31+681.000—LK32.201.200, RK31+752.000—RK32+231.500) | 4583095.5 | 0 | 0 | 0 | 4583095.5
Cost Center/ Troškovno mjesto 12.4 | Construction of bridge/Izgradnja mosta Uvac 1 (LK 32.201.200- LK 32+489.20, RK 32+231.500- RK 32+579.500) | 4766405.81 | 307809.0687 | 0 | 307809.0687 | 4458596.7413
Cost Center/ Troškovno mjesto 12.5 | Road Works/Radovi na putevima (LK32+489.200—LK32+633.000, RK32+579.500—RK32+702.500) | 1416070.65 | 0 | 0 | 0 | 1416070.65
Cost Center/ Troškovno mjesto 12.6 | Construction of bridge/Izgradnja mosta Uvac 2 (LK 32+633.000- LK 32.793.00, RK 32.702.500-RK 32.862.500) | 3058932.14 | 0 | 0 | 0 | 3058932.14
Cost Center/ Troškovno mjesto 12.7 | Road Works/Radovi na putevima (LK32+793.000—LK32+820.000, RK32+862.500—RK32+885.000) | 227150.06 | 0 | 0 | 0 | 227150.06
Cost Center/ Troškovno mjesto 12.8 | Construction of tunnel/Izgradnja tunela Vitanovice (LK 32+820.000- LK 32+950.000, RK 32+885.000- RK 33+035.000) | 7639500.7 | 0 | 0 | 0 | 7639500.7
Cost Center/ Troškovno mjesto 12.9 | Open Route/Otvorena trasa LK32+950.000—LK32+962.500 RK33+035.000—RK33+059.000 | 144065.03 | 0 | 0 | 0 | 144065.03
Cost Center/ Troškovno mjesto 12.10 | Construction of bridge/Izgradnja mosta Uvac 3 (LK 32+962.500-LK 33+108.500, RK 33+059.000-RK 33+153.00) | 2765521.37 | 0 | 0 | 0 | 2765521.37
Cost Center/ Troškovno mjesto 12.11 | Open Route/Otvorena trasa LK33+108.500—LK33+189.000 RK33+153.000—RK33+248.300 | 878949.53 | 0 | 0 | 0 | 878949.53
Cost Center/ Troškovno mjesto 12.12 | Construction of bridge/Izgradnja mosta Uvac 4 (LK 33+189.000- LK33+283.00, LK 33+352.500-LK 34+062.500, RK 33+248.300-RK 34+138.300) | 18005855.85 | 816872.6344 | 2125520.3966 | 2942393.031 | 15063462.819
Cost Center/ Troškovno mjesto 12.13 | Open Route/Otvorena trasa LK33+283.000—LK33+352.500 | 326647.7 | 0 | 0 | 0 | 326647.7
Cost Center/ Troškovno mjesto 12.14 | Open Route/Otvorena trasa LK34+062.500—LK34+078.000 RK34+138.300—RK34+148.000 | 113378.73 | 0 | 0 | 0 | 113378.73
Cost Center/ Troškovno mjesto 12.15 | Construction of tunnel/Izgradnja tunela Zecka (LK 34+078.000-LK 34+768.000, RK 34+148.000- RK 34+815.000) | 22367156.54 | 0 | 0 | 0 | 22367156.54
Cost Center/ Troškovno mjesto 12.16 | Road Works/Radovi na putevima (LK34+768.000—LK34+810.500, RK34+815.000—RK34+841.500) | 141860.49 | 0 | 0 | 0 | 141860.49
Cost Center/ Troškovno mjesto 12.17 | Construction of bridge/Izgradnja mosta Pajkov Vir (LK 34+810.500- LK 34+904.500, RK 34+841.500-RK 34+961.500) | 3053462.36 | 0 | 0 | 0 | 3053462.36
Cost Center/ Troškovno mjesto 12.18 | Road Works/ Radovi na putevima(LK34+904.500- LK 34+920.000, RK 34+961.500- RK 35+085.000) | 761234.42 | 0 | 0 | 0 | 761234.42
Cost Center/ Troškovno mjesto 12.19 | Construction of tunnel/Izgradnja tunela Pajkov Vir (LK 34+920.000-LK 35+285.000, RK 35+085.000-RK 35+290.000) | 10719840.5 | 0 | 0 | 0 | 10719840.5
Cost Center/ Troškovno mjesto 12.20 | Road Works/ Radovi na putevima (LK35+285.000—LK35+425.000, RK35+290.000—RK35+480.000 | 1321720.21 | 0 | 0 | 0 | 1321720.21
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 12 | 85277015.32 | 1124681.7032 | 2125520.3966 | 3250202.0997 | 82026813.2203
Cost Center/ Troškovno mjesto 13 | Subsection/ Podsekcija 4.2 (LK35+425.00-LK36+894.00, RK35+480.00-RK36+924.439)
Cost Center/ Troškovno mjesto 13.1 | Road Works/ Radovi na putevima (LK35+425.00-LK36+439.00,RK35+480.00-RK36+564.439.00) | 8067973.24 | 0 | 0 | 0 | 8067973.24
Cost Center/ Troškovno mjesto 13.2 | Construction of tunnel/ Izgradnja tunela Jabucki Krs (LK 35+439.000- LK 36+894.00, RK 35+564.439- RK 36+924.439) | 31554472.96 | 16608977.0444 | 0 | 16608977.0444 | 14945495.9156
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 13 | 39622446.2 | 16608977.0444 | 0 | 16608977.0444 | 23013469.1556
Cost Center/ Troškovno mjesto 14 | Subsection/Podsekcija 4.3 (LK36+894.000-LK37+733.287, RK36+924.439 - RK38+366.284)
Cost Center/ Troškovno mjesto 14.1 | Road Works/Radovi na putevima LK36+894.000—LK36+989.000 RK36+924.439—RK36+949.884 | 1048627.48 | 0 | 0 | 0 | 1048627.48
Cost Center/ Troškovno mjesto 14.2 | Construction of bridge/Izgradnja mosta Preslo (RK 36+949.884- RK 37+017.884) | 1322976.56 | 94681.77 | 34225.6347 | 128907.4047 | 1194069.1553
Cost Center/ Troškovno mjesto 14.3 | Road Works/ Radovi na putevima (RK37+017.884—RK37+033.000) | 59931.03 | 0 | 0 | 0 | 59931.03
Cost Center/ Troškovno mjesto 14.4 | Construction of tunnel/Izgradnja tunela Preslo (LK 36+989.000- LK 37+484.00, RK 37+433.00- RK 37+433.000) | 10892775.47 | 0 | 0 | 0 | 10892775.47
Cost Center/ Troškovno mjesto 14.5 | Road Works/Radovi na putevima (LK37+484.000—LK37+545.087, RK37+433.00—RK37+581.884) | 650033.2 | 0 | 0 | 0 | 650033.2
Cost Center/ Troškovno mjesto 14.6 | Construction of bridge/Izgradnja mosta Jabuka (LK 37+545.087 - LK 37+617.087, LK 37.733.287- LK 38+309.087, RK 37+581.884- 38+366.284) | 29314076.39 | 12834732.9264 | 1990649.4717 | 14825382.3981 | 14488693.9919
Cost Center/ Troškovno mjesto 14.7 | Road Works/ Radovi na putevima (LK37+617.087 —LK37+733.287) | 497543.62 | 0 | 0 | 0 | 497543.62
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 14 | 43785963.75 | 12929414.6964 | 2024875.1065 | 14954289.8029 | 28831673.9471
Cost Center/ Troškovno mjesto 15 | Subsection/ Podsekcija 4.4 (LK38+309.087-LK40+798.773 RK38+366.284-RK40+817.854)
Cost Center/ Troškovno mjesto 15.1 | Road Works/Radovi na putevima (LK38+309.087—LK38+381.440, RK38+366.284—RK38+675.997) | 1566672.78 | 0 | 0 | 0 | 1566672.78
Cost Center/ Troškovno mjesto 15.2 | Construction of Matesevo interchange/ Izgradnja petlje Mateševo ( LK38+381.440- LK 39+188.394, RK 38+675.997- RK 39.246.583) | 8422955.41 | 0 | 0 | 0 | 8422955.41
Cost Center/ Troškovno mjesto 15.3 | Construction of bridge/ Izgradnja mosta Tara 1 (LK 38+646.087- LK 38+880.087, RK 38+686.584- RK 38+920.584) | 8674559.05 | 0 | 0 | 0 | 8674559.05
Cost Center/ Troškovno mjesto 15.4 | Road Works/ Radovi na putevima (LK39+188.394—LK39+376.887, RK39+246.583—RK39+436.384) | 2052852.45 | 0 | 0 | 0 | 2052852.45
Cost Center/ Troškovno mjesto 15.5 | Construction of bridge/ Izgradnja mosta Tara 2 (LK39+376.887-LK 39+830.687, RK 39+436.384- RK 39+834.184) | 14660392.18 | 0 | 0 | 0 | 14660392.18
Cost Center/ Troškovno mjesto 15.6 | Road Works/ Radovi na putevima (LK39+830+687—LK39+872.817, RK39+834.184—RK39+892.714) | 437926.2 | 0 | 0 | 0 | 437926.2
Cost Center/ Troškovno mjesto 15.7 | Construction of tunnel/ Izgradnja tunela Matesevo (LK39+872.817 - LK 40+424.817, RK 39+892.714- RK 40+452.714) | 12554365.03 | 0 | 0 | 0 | 12554365.03
Cost Center/ Troškovno mjesto 15.8 | Road Works/ Radovi na putevima (LK40+424.817—LK40+798.773, RK40+452.714—RK40+871.854) | 3454843.48 | 0 | 0 | 0 | 3454843.48
| Subtotal/suma stavke Cost Center/ Troškovno mjesto 15 | 51824566.58 | 0 | 0 | 0 | 51824566.58
Cost Center/ Troškovno mjesto C | General Costs/ Opšti troškovi
Cost Center/ Troškovno mjesto C.1 | Guardrails/ Zaštitne ograde | 4649330 | 0 | 0 | 0 | 4649330
Cost Center/ Troškovno mjesto C.2 | Road marking and signalisation/Oznake i signalizacija na putu | 4510614.76 | 0 | 0 | 0 | 4510614.76
Cost Center/ Troškovno mjesto C.3 | Traffic control equipment/Oprema za kontrolu saobraćaja | 23234617.93 | 0 | 0 | 0 | 23234617.93
Cost Center/ Troškovno mjesto C.4 | Low voltage equipment/Niskonaponska oprema | 702888 | 0 | 0 | 0 | 702888
Cost Center/ Troškovno mjesto C.5 | Tolling system and station/Sistem i stanica za naplatu putarine | 5203807.64 | 0 | 0 | 0 | 5203807.64
| Subtotal/suma stavke Cost Center/ Troškovno mjesto C | 38301258.33 | 0 | 0 | 0 | 38301258.33
| TOTAL/UKUPNO | 809577356.1445 | 145696491.7639 | 23330684.6401 | 169027176.404 | 640550179.716
169027176.404

## COST CENTER 0A
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Payments/Raspored plaćanja
COST CENTER A/TROŠKOVNI CENTAR A
Cost Center No./ Troškovno mjesto Br. | A | Parts/ Dijelovi 1-4
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost Center/ Troškovni centar A | Completion of Main Design/ Završetak Glavnog projekta
A.1 | Main design/ Glavni projekat
A.1.1 | Subsection/ Podsekcija 1.1.1 (Construction works/ Građevinski radovi) | 449612.88 | 17 | 25 | 449612.88 | 0 | 449612.88
| Subsection/ Podsekcija 1.1.2 (Construction works/ Građevinski radovi) | 449612.8785 | 17 | 22 | 449612.88 | 0 | 449612.88
| Subsection/ Podsekcija 1.1.3 (Construction works/ Građevinski radovi) | 99913.97 | 17 |  | 0 | 0 | 0
A.1.2 | Subsection/ Podsekcija 1.2 (Construction works/ Građevinski radovi) | 353307.99 | 17 | 18 | 353307.99 | 0 | 353307.99
A.1.3 | Subsection/ Podsekcija 1.3 (Construction works/ Građevinski radovi) | 211243.18 | 15 | 12 | 211243.18 | 0 | 211243.18
A.1.4 | Subsection/ Podsekcija 1.4 (Construction works/ Građevinski radovi) | 788885.02 | 17 | 22 | 788885.02 | 0 | 788885.02
A.1.5 | Subsection/ Podsekcija 2.1 (Construction works/ Građevinski radovi) | 741819.66 | 17 | 19 | 741819.66 | 0 | 741819.66
A.1.6 | Subsection/ Podsekcija 2.2 (Construction works/ Građevinski radovi) | 1026816.95 | 17 | 20 | 1026816.95 | 0 | 1026816.95
A.1.7 | Subsection/ Podsekcija 2.3 (Construction works/ Građevinski radovi) | 637830.47 | 15 | 12 | 637830.47 | 0 | 637830.47
A.1.8 | Subsection/ Podsekcija 3.1 (Construction works/ Građevinski radovi) | 423845.63 | 19 | 24 | 423845.63 | 0 | 423845.63
A.1.9 | Subsection/ Podsekcija 3.2 (Construction works/ Građevinski radovi) | 390919.3 | 17 | 24 | 390919.3 | 0 | 390919.3
A.1.10 | Subsection/ Podsekcija 3.3 (Construction works/ Građevinski radovi) | 588962.54 | 15 | 15 | 588962.54 | 0 | 588962.54
A.1.11 | Subsection/ Podsekcija 3.4.1 (Construction works/ Građevinski radovi) | 236432.41 | 17 | 24 | 236432.41 | 0 | 236432.41
| Subsection/ Podsekcija 3.4.2 (Construction works/ Građevinski radovi) | 236432.41 | 17 | 18 | 236432.41 | 0 | 236432.41
A.1.12 | Subsection/ Podsekcija 4.1 (Construction works/ Građevinski radovi) | 773549.52 | 19 | 24 | 773549.52 | 0 | 773549.52
A.1.13 | Subsection/ Podsekcija 4.2 (Construction works/ Građevinski radovi) | 511904.75 | 15 | 14 | 511904.75 | 0 | 511904.75
A.1.14 | Subsection/ Podsekcija 4.3 (Construction works/ Građevinski radovi) | 300964.11 | 17 | 19 | 300964.11 | 0 | 300964.11
A.1.15 | Subsection/ Podsekcija 4.4.1 (Construction works/ Građevinski radovi) | 503643.51 | 19 | 24 | 503643.51 | 0 | 503643.51
| Subsection/ Podsekcija 4.4.2 (Construction works/ Građevinski radovi) | 26507.55 | 19 |  | 0 | 0 | 0
A.1.16 | Various designs (signalization, facilities, landscaping, etc.)/ Razni projekti (signalizacija, objekti, uređenje pejzaža, itd.) | 972467.19 | 20 |  | 0 | 0 | 0
| TOTAL/UKUPNO | 9724671.9185 |  |  | 8625783.21 | 0 | 8625783.21

## COST CENTER 01
0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
276000
Schedule of Milestone Payments/Raspored repera plaćanja
COST CENTER 01/TROŠKOVNI CENTAR 01 rev tunnels and earthworks
Cost Center No./ Troškovno mjesto Br. | 01 | Subsection/Podsekcija 1.1 (LK0- LK4+760.00, RK0-RK4+751.60)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost Center/ Troškovni centar 1.1 | Road Works/ Radovi na putevima (LK0—LK0+405.00, RK0—RK0+481.00)
Completion of/Završetak:
1.1.1 | Subgrade/Posteljica
1.1.1.1 | Top soil removal/ Uklanjanje humusa
1.1.1.1.1 | RK0+000.000-RK0+250.000 (Inc.0-250 m LK&RK) | 48197.2754 | 17 |  | 0 | 0 | 0
1.1.1.1.2 | RK0+250.000-RK0+481.000 (Inc. 250 - 405.00 m (LK), 250-481.00 m (RK) | 37208.2966 | 17 |  | 0 | 0 | 0
1.1.1.2 | Earthworks/Zemljani radovi |  | 26
At every 250 m and 4 m height /Na svakih 250m visini od 4m
1.1.1.2.1 | 0+000.00 - 0+25.00, layers 1,2,3,4,5,6,7,8,9,10
1.1.1.2.1.1 | 0+000.00 - 0+250.00, layer 1 | 53050.2872 |  |  | 0 | 0 | 0
1.1.1.2.1.2 | 0+000.00 - 0+250.00, layer 2 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.1.3 | 0+000.00 - 0+250.00, layer 3 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.1.4 | 0+000.00 - 0+250.00, layer 4 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.1.5 | 0+000.00 - 0+250.00, layer 5 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.1.6 | 0+000.00 - 0+250.00, layer 6 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.1.7 | 0+000.00 - 0+250.00, layer 7 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.1.8 | 0+000.00 - 0+250.00, layer 8 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.1.9 | 0+000.00 - 0+250.00, layer 9 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.1.10 | 0+000.00 - 0+250.00, layer 10 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.2 | 0+250.00 - 0+481.00, leyers 11,12,13,14,15,16,17, 18,19,20,21,22,23
1.1.1.2.2.11 | 0+250.00 - 0+481.00, leyer 11 | 62140.3645 |  |  | 0 | 0 | 0
1.1.1.2.2.12 | 0+250.00 - 0+481.00, leyer 12 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.2.13 | 0+250.00 - 0+481.00, leyer 13 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.2.14 | 0+250.00 - 0+481.00, leyer 14 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.2.15 | 0+250.00 - 0+481.00, leyer 15 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.2.16 | 0+250.00 - 0+481.00, leyer 16 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.2.17 | 0+250.00 - 0+481.00, leyer 17 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.2.18 | 0+250.00 - 0+481.00, leyer 18 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.2.19 | 0+250.00 - 0+481.00, leyer 19 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.2.20 | 0+250.00 - 0+481.00, leyer 20 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.2.21 | 0+250.00 - 0+481.00, leyer 21 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.2.22 | 0+250.00 - 0+481.00, leyer 22 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.2.2.23 | 0+250.00 - 0+481.00, leyer 23 | 59607.0643 |  |  | 0 | 0 | 0
1.1.1.3 | Road Foundation/Temelj puta
1.1.1.3.1 | 0 - 250 m, right side/desna strana | 23136.0031 | 27 |  | 0 | 0 | 0
1.1.1.3.2 | 0 - 250 m, left side/lijeva strana | 23136.0031 | 28 |  | 0 | 0 | 0
1.1.1.3.3 | 250 - 481.00, right side/desna strana | 21377.6668 | 29 |  | 0 | 0 | 0
1.1.1.3.4 | 250 - 405.00, left side/lijeva strana | 14344.3219 | 30 |  | 0 | 0 | 0
1.1.2 | Engineering structures/Inženjerske konstrukcije
1.1.2.1 | Reinforced earth wall / Ojačani zemljani zid |  | 28 |  | 0 | 0 | 0
The milestone is 2.20 m height of each layer and no matter on the length / Reper je visina 2.2m za svaki sloj, bez obzira na dužinu
1.1.2.1.1 | Reinforced soil retaining wall RK 0+000 - RK 0+110 / Potporni zid od armirane zemlje
1.1.2.1.1.1 | Layer/Sloj 1 (0.0 -2.2 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.1.2 | Layer/Sloj 2 (2.2 -4.4 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.1.3 | Layer/Sloj 3 (4.4 -6.6 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.1.4 | Layer/Sloj 4 (6.6 -8.8m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.1.5 | Layer/Sloj 5 (8.8 -11.0 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.1.6 | Layer/Sloj 6 (11.0 -12.03 m height) | 13727.676 |  |  | 0 | 0 | 0
1.1.2.1.2 | Reinforced soil retaining wall RK 0+250 - RK 0+440 / Potporni zid od armirane zemlje
1.1.2.1.2.1 | Layer/Sloj 1 (0.0 -2.2 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.2.2 | Layer/Sloj 2 (2.2 -4.4 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.2.3 | Layer/Sloj 3 (4.4 -6.6 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.2.4 | Layer/Sloj 4 (6.6 -8.8m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.2.5 | Layer/Sloj 5 (8.8 -11.0 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.2.6 | Layer/Sloj 6 (11.0 -13.2 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.2.7 | Layer/Sloj 7 (13.2 -15.4 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.2.8 | Layer/Sloj 8 (15.4 -17.60 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.2.9 | Layer/Sloj 9 (17.60 -17.75 m height) | 1999.1761 |  |  | 0 | 0 | 0
1.1.2.1.3 | Reinforced soil retaining wall RK 1+093 - RK 1+334 / Potporni zid od armirane zemlje
1.1.2.1.3.1 | Layer/Sloj 1 (0.0 -2.2 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.2 | Layer/Sloj 2 (2.2 -4.4 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.3 | Layer/Sloj 3 (4.4 -6.6 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.4 | Layer/Sloj 4 (6.6 -8.8m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.5 | Layer/Sloj 5 (8.8 -11.0 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.6 | Layer/Sloj 6 (11.0 -13.2 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.7 | Layer/Sloj 7 (13.2 -15.4 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.8 | Layer/Sloj 8 (15.4 -17.6 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.9 | Layer/Sloj 9 (17.6 -19.8 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.10 | Layer/Sloj 10 (19.8 -22.0 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.11 | Layer/Sloj 11 (22.0 -24.2 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.12 | Layer/Sloj 12 (24.2 -26.4 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.13 | Layer/Sloj 13 (26.4 -28.6 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.14 | Layer/Sloj 14 (28.6 -30.8 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.15 | Layer/Sloj 15 (30.8 -33.0 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.16 | Layer/Sloj 16 (33.0 -35.2 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.17 | Layer/Sloj 17 (35.2 -37.40 m height) | 29321.2497 |  |  | 0 | 0 | 0
1.1.2.1.3.18 | Layer/Sloj 18 (37.4 -38.43 m height) | 13727.676 |  |  | 0 | 0 | 0
1.1.2.2 | Culvert/propust | 9148.0219 | 29 |  | 0 | 0 | 0
1.1.3 | Water drainage/Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
1.1.3.1 | LK0+000.000—LK0+405.000 (405m) | 171177.8225 | 35 |  | 0 | 0 | 0
1.1.3.2 | RK0+000.000—RK0+481.000 (481m) | 203300.0806 | 35 |  | 0 | 0 | 0
1.1.4 | Pavement structure/Kolovozna konstrukcija
1.1.4.1 | Asphalt concrete layer/Sloj asfaltnog betona 1 right side/desna strana | 58498.9895 | 38 |  | 0 | 0 | 0
1.1.4.2 | Asphalt concrete layer/Sloj asfaltnog betona 1 left side/lijeva strana | 49255.9059 | 38 |  | 0 | 0 | 0
1.1.4.3 | Asphalt concrete layer/Sloj asfaltnog betona 2 right side/desna strana | 58498.9895 | 39 |  | 0 | 0 | 0
1.1.4.4 | Asphalt concrete layer/Sloj asfaltnog betona 2 left side/lijeva strana | 49255.9059 | 39 |  | 0 | 0 | 0
1.1.4.5 | Asphalt concrete layer/Sloj asfaltnog betona 3 right side/desna strana | 65002.7337 | 40 |  | 0 | 0 | 0
1.1.4.6 | Asphalt concrete layer/Sloj asfaltnog betona 3 left side/lijeva strana | 54732.0315 | 40 |  | 0 | 0 | 0
| Sub Total/Suma stavke 1.1 | 3162301.0696 |  |  | 0 | 0 | 0
Cost Center/ Troškovni centar 1.2 | Construction of tunnel Suka/Izgradnja tunela Suka (LK0+405.000—LK1+125.000 , length 720m RK0+481.000—RK1+085.000, length 604m)
Completion of/Završetak:
1.2.1 | Portal construction/Izgradnja portala
1.2.1.1 | 20% complete/završeno (portal 1) | 59566.03 | 18 |  | 0 | 0 | 0
1.2.1.2 | 40% complete/završeno (portal 2) | 59566.03 | 18 |  | 0 | 0 | 0
1.2.1.3 | 60% complete/završeno (portal 3) | 59566.03 | 19 |  | 0 | 0 | 0
1.2.1.4 | 80% complete/završeno (portal 4) | 59566.03 | 19 |  | 0 | 0 | 0
1.2.1.5 | 85% (portal 1 complete/završen) | 14891.5075 | 31 |  | 0 | 0 | 0
1.2.1.6 | 90% (portal 2 complete/završen) | 14891.5075 | 31 |  | 0 | 0 | 0
1.2.1.7 | 95% (portal 3 complete/završen) | 14891.5075 | 32 |  | 0 | 0 | 0
1.2.1.8 | 100% (portal 4 complete/završen) | 14891.4875 | 32 |  | 0 | 0 | 0
1.2.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
1.2.2.1 | 20 m | 82364.8132 | 20 |  | 0 | 0 | 0
1.2.2.2 | 40 m | 82364.8132 | 20 |  | 0 | 0 | 0
1.2.2.3 | 60 m | 82364.8132 | 20 |  | 0 | 0 | 0
1.2.2.4 | 80 m | 82364.8132 | 21 |  | 0 | 0 | 0
1.2.2.5 | 100 m | 82364.8132 | 21 |  | 0 | 0 | 0
1.2.2.6 | 120 m | 82364.8132 | 21 |  | 0 | 0 | 0
1.2.2.7 | 140 m | 82364.8132 | 22 |  | 0 | 0 | 0
1.2.2.8 | 160 m | 82364.8132 | 22 |  | 0 | 0 | 0
1.2.2.9 | 180 m | 82364.8132 | 22 |  | 0 | 0 | 0
1.2.2.10 | 200 m | 82364.8132 | 22 |  | 0 | 0 | 0
1.2.2.11 | 220 m | 82364.8132 | 22 |  | 0 | 0 | 0
1.2.2.12 | 240 m | 82364.8132 | 22 |  | 0 | 0 | 0
1.2.2.13 | 260 m | 82364.8132 | 22 |  | 0 | 0 | 0
1.2.2.14 | 280 m | 82364.8132 | 22 |  | 0 | 0 | 0
1.2.2.15 | 300 m | 82364.8132 | 23 |  | 0 | 0 | 0
1.2.2.16 | 320 m | 82364.8132 | 23 |  | 0 | 0 | 0
1.2.2.17 | 340 m | 82364.8132 | 23 |  | 0 | 0 | 0
1.2.2.18 | 360 m | 82364.8132 | 23 |  | 0 | 0 | 0
1.2.2.19 | 380 m | 82364.8132 | 23 |  | 0 | 0 | 0
1.2.2.20 | 400 m | 82364.8132 | 23 |  | 0 | 0 | 0
1.2.2.21 | 420 m | 82364.8132 | 23 |  | 0 | 0 | 0
1.2.2.22 | 440 m | 82364.8132 | 23 |  | 0 | 0 | 0
1.2.2.23 | 460 m | 82364.8132 | 24 |  | 0 | 0 | 0
1.2.2.24 | 480 m | 82364.8132 | 24 |  | 0 | 0 | 0
1.2.2.25 | 500 m | 82364.8132 | 24 |  | 0 | 0 | 0
1.2.2.26 | 520 m | 82364.8132 | 24 |  | 0 | 0 | 0
1.2.2.27 | 540 m | 82364.8132 | 24 |  | 0 | 0 | 0
1.2.2.28 | 560 m | 82364.8132 | 24 |  | 0 | 0 | 0
1.2.2.29 | 580 m | 82364.8132 | 24 |  | 0 | 0 | 0
1.2.2.30 | 600 m | 82364.8132 | 25 |  | 0 | 0 | 0
1.2.2.31 | 620 m | 82364.8132 | 25 |  | 0 | 0 | 0
1.2.2.32 | 640 m | 82364.8132 | 25 |  | 0 | 0 | 0
1.2.2.33 | 660 m | 82364.8132 | 25 |  | 0 | 0 | 0
1.2.2.34 | 680 m | 82364.8132 | 25 |  | 0 | 0 | 0
1.2.2.35 | 700 m | 82364.8132 | 25 |  | 0 | 0 | 0
1.2.2.36 | 720 m | 82364.8132 | 25 |  | 0 | 0 | 0
1.2.2.37 | 740 m | 82364.8132 | 26 |  | 0 | 0 | 0
1.2.2.38 | 760 m | 82364.8132 | 26 |  | 0 | 0 | 0
1.2.2.39 | 780 m | 82364.8132 | 26 |  | 0 | 0 | 0
1.2.2.40 | 800 m | 82364.8132 | 26 |  | 0 | 0 | 0
1.2.2.41 | 820 m | 82364.8132 | 26 |  | 0 | 0 | 0
1.2.2.42 | 840 m | 82364.8132 | 26 |  | 0 | 0 | 0
1.2.2.43 | 860 m | 82364.8132 | 26 |  | 0 | 0 | 0
1.2.2.44 | 880 m | 82364.8132 | 26 |  | 0 | 0 | 0
1.2.2.45 | 900 m | 82364.8132 | 27 |  | 0 | 0 | 0
1.2.2.46 | 920 m | 82364.8132 | 27 |  | 0 | 0 | 0
1.2.2.47 | 940 m | 82364.8132 | 27 |  | 0 | 0 | 0
1.2.2.48 | 960 m | 82364.8132 | 27 |  | 0 | 0 | 0
1.2.2.49 | 980 m | 82364.8132 | 27 |  | 0 | 0 | 0
1.2.2.50 | 1000 m | 82364.8132 | 27 |  | 0 | 0 | 0
1.2.2.51 | 1020 m | 82364.8132 | 27 |  | 0 | 0 | 0
1.2.2.52 | 1040 m | 82364.8132 | 28 |  | 0 | 0 | 0
1.2.2.53 | 1060 m | 82364.8132 | 28 |  | 0 | 0 | 0
1.2.2.54 | 1080 m | 82364.8132 | 28 |  | 0 | 0 | 0
1.2.2.55 | 1100 m | 82364.8132 | 28 |  | 0 | 0 | 0
1.2.2.56 | 1120 m | 82364.8132 | 28 |  | 0 | 0 | 0
1.2.2.57 | 1140 m | 82364.8132 | 28 |  | 0 | 0 | 0
1.2.2.58 | 1160 m | 82364.8132 | 28 |  | 0 | 0 | 0
1.2.2.59 | 1180 m | 82364.8132 | 28 |  | 0 | 0 | 0
1.2.2.60 | 1200 m | 82364.8132 | 29 |  | 0 | 0 | 0
1.2.2.61 | 1220 m | 82364.8132 | 29 |  | 0 | 0 | 0
1.2.2.62 | 1240 m | 82364.8132 | 29 |  | 0 | 0 | 0
1.2.2.63 | 1260 m | 82364.8132 | 29 |  | 0 | 0 | 0
1.2.2.64 | 1280 m | 82364.8132 | 29 |  | 0 | 0 | 0
1.2.2.65 | 1290 m | 41182.4066 | 29 |  | 0 | 0 | 0
1.2.3 | Construction of waterproofing and drainage & Construction of secondary lining / Konstrukcija hidroizolacije i drenaže & Konstrukcija sekundarne obloge
1.2.3.1 | 20 m | 83582.369 | 22 |  | 0 | 0 | 0
1.2.3.2 | 40 m | 83582.369 | 22 |  | 0 | 0 | 0
1.2.3.3 | 60 m | 83582.369 | 22 |  | 0 | 0 | 0
1.2.3.4 | 80 m | 83582.369 | 22 |  | 0 | 0 | 0
1.2.3.5 | 100 m | 83582.369 | 23 |  | 0 | 0 | 0
1.2.3.6 | 120 m | 83582.369 | 23 |  | 0 | 0 | 0
1.2.3.7 | 140 m | 83582.369 | 23 |  | 0 | 0 | 0
1.2.3.8 | 160 m | 83582.369 | 24 |  | 0 | 0 | 0
1.2.3.9 | 180 m | 83582.369 | 24 |  | 0 | 0 | 0
1.2.3.10 | 200 m | 83582.369 | 24 |  | 0 | 0 | 0
1.2.3.11 | 220 m | 83582.369 | 24 |  | 0 | 0 | 0
1.2.3.12 | 240 m | 83582.369 | 25 |  | 0 | 0 | 0
1.2.3.13 | 260 m | 83582.369 | 25 |  | 0 | 0 | 0
1.2.3.14 | 280 m | 83582.369 | 25 |  | 0 | 0 | 0
1.2.3.15 | 300 m | 83582.369 | 25 |  | 0 | 0 | 0
1.2.3.16 | 320 m | 83582.369 | 26 |  | 0 | 0 | 0
1.2.3.17 | 340 m | 83582.369 | 26 |  | 0 | 0 | 0
1.2.3.18 | 360 m | 83582.369 | 26 |  | 0 | 0 | 0
1.2.3.19 | 380 m | 83582.369 | 26 |  | 0 | 0 | 0
1.2.3.20 | 400 m | 83582.369 | 26 |  | 0 | 0 | 0
1.2.3.21 | 420 m | 83582.369 | 26 |  | 0 | 0 | 0
1.2.3.22 | 440 m | 83582.369 | 26 |  | 0 | 0 | 0
1.2.3.23 | 460 m | 83582.369 | 27 |  | 0 | 0 | 0
1.2.3.24 | 480 m | 83582.369 | 27 |  | 0 | 0 | 0
1.2.3.25 | 500 m | 83582.369 | 27 |  | 0 | 0 | 0
1.2.3.26 | 520 m | 83582.369 | 27 |  | 0 | 0 | 0
1.2.3.27 | 540 m | 83582.369 | 27 |  | 0 | 0 | 0
1.2.3.28 | 560 m | 83582.369 | 27 |  | 0 | 0 | 0
1.2.3.29 | 580 m | 83582.369 | 27 |  | 0 | 0 | 0
1.2.3.30 | 600 m | 83582.369 | 27 |  | 0 | 0 | 0
1.2.3.31 | 620 m | 83582.369 | 28 |  | 0 | 0 | 0
1.2.3.32 | 640 m | 83582.369 | 28 |  | 0 | 0 | 0
1.2.3.33 | 660 m | 83582.369 | 28 |  | 0 | 0 | 0
1.2.3.34 | 680 m | 83582.369 | 28 |  | 0 | 0 | 0
1.2.3.35 | 700 m | 83582.369 | 28 |  | 0 | 0 | 0
1.2.3.36 | 720 m | 83582.369 | 28 |  | 0 | 0 | 0
1.2.3.37 | 740 m | 83582.369 | 28 |  | 0 | 0 | 0
1.2.3.38 | 760 m | 83582.369 | 28 |  | 0 | 0 | 0
1.2.3.39 | 780 m | 83582.369 | 29 |  | 0 | 0 | 0
1.2.3.40 | 800 m | 83582.369 | 29 |  | 0 | 0 | 0
1.2.3.41 | 820 m | 83582.369 | 29 |  | 0 | 0 | 0
1.2.3.42 | 840 m | 83582.369 | 29 |  | 0 | 0 | 0
1.2.3.43 | 860 m | 83582.369 | 29 |  | 0 | 0 | 0
1.2.3.44 | 880 m | 83582.369 | 29 |  | 0 | 0 | 0
1.2.3.45 | 900 m | 83582.369 | 29 |  | 0 | 0 | 0
1.2.3.46 | 920 m | 83582.369 | 29 |  | 0 | 0 | 0
1.2.3.47 | 940 m | 83582.369 | 29 |  | 0 | 0 | 0
1.2.3.48 | 960 m | 83582.369 | 30 |  | 0 | 0 | 0
1.2.3.49 | 980 m | 83582.369 | 30 |  | 0 | 0 | 0
1.2.3.50 | 1000 m | 83582.369 | 30 |  | 0 | 0 | 0
1.2.3.51 | 1020 m | 83582.369 | 30 |  | 0 | 0 | 0
1.2.3.52 | 1040 m | 83582.369 | 30 |  | 0 | 0 | 0
1.2.3.53 | 1060 m | 83582.369 | 30 |  | 0 | 0 | 0
1.2.3.54 | 1080 m | 83582.369 | 31 |  | 0 | 0 | 0
1.2.3.55 | 1100 m | 83582.369 | 31 |  | 0 | 0 | 0
1.2.3.56 | 1120 m | 83582.369 | 31 |  | 0 | 0 | 0
1.2.3.57 | 1140 m | 83582.369 | 31 |  | 0 | 0 | 0
1.2.3.58 | 1160 m | 83582.369 | 31 |  | 0 | 0 | 0
1.2.3.59 | 1180 m | 83582.369 | 31 |  | 0 | 0 | 0
1.2.3.60 | 1200 m | 83582.369 | 31 |  | 0 | 0 | 0
1.2.3.61 | 1220 m | 83582.369 | 32 |  | 0 | 0 | 0
1.2.3.62 | 1240 m | 83582.369 | 32 |  | 0 | 0 | 0
1.2.3.63 | 1260 m | 83582.369 | 32 |  | 0 | 0 | 0
1.2.3.64 | 1280 m | 83582.369 | 32 |  | 0 | 0 | 0
1.2.3.65 | 1290 m | 41791.1845 | 32 |  | 0 | 0 | 0
1.2.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi I ploca, drenazni sistem)
1.2.4.1 | 200 m | 80000 | 26 |  | 0 | 0 | 0
1.2.4.2 | 400 m | 80000 | 27 |  | 0 | 0 | 0
1.2.4.3 | 600 m | 80000 | 28 |  | 0 | 0 | 0
1.2.4.4 | 800 m | 80000 | 30 |  | 0 | 0 | 0
1.2.4.5 | 1000 m | 80000 | 31 |  | 0 | 0 | 0
1.2.4.6 | 1200 m | 80000 | 32 |  | 0 | 0 | 0
1.2.4.7 | 1290 m | 36000 | 33 |  | 0 | 0 | 0
1.2.5 | Construction of pavement/ Konstrukcija kolovoza
1.2.5.1 | Left tube/Lijeva cijev (L 720 m) |  |  |  | 0 | 0 | 0
| 0-500 m |  |  |  | 0 | 0 | 0
1.2.5.1.1 | Layer/Sloj 1 | 36950.5363 | 32 |  | 0 | 0 | 0
1.2.5.1.2 | Layer/Sloj 2 | 36950.5363 | 33 |  | 0 | 0 | 0
1.2.5.1.3 | Layer/Sloj 3 | 41569.3618 | 33 |  | 0 | 0 | 0
| 500-720.00 m |  |  |  | 0 | 0 | 0
1.2.5.1.3 | Layer/Sloj 1 | 16258.236 | 32 |  | 0 | 0 | 0
1.2.5.1.3 | Layer/Sloj 2 | 16258.236 | 33 |  | 0 | 0 | 0
1.2.5.1.3 | Layer/Sloj 3 | 18290.5192 | 33 |  | 0 | 0 | 0
1.2.5.2 | Right tube/Desna cijev (R 604 m) |  |  |  | 0 | 0 | 0
| 0-500 m |  |  |  | 0 | 0 | 0
1.2.5.2.1 | Layer/Sloj 1 | 36950.5363 | 32 |  | 0 | 0 | 0
1.2.5.2.2 | Layer/Sloj 2 | 36950.5363 | 33 |  | 0 | 0 | 0
1.2.5.2.3 | Layer/Sloj 3 | 41569.3618 | 33 |  | 0 | 0 | 0
| 500-604.00 m |  |  |  | 0 | 0 | 0
1.2.5.2.3 | Layer/Sloj 1 | 7685.7115 | 32 |  | 0 | 0 | 0
1.2.5.2.3 | Layer/Sloj 2 | 7685.7115 | 33 |  | 0 | 0 | 0
1.2.5.2.3 | Layer/Sloj 3 | 8646.4273 | 33 |  | 0 | 0 | 0
1.2.6 | Tunnel facilities/Tunelski objekti
1.2.6.1 | Construction of Power Station/Izgradnja elektro-stanice | 165282.22 | 34 |  | 0 | 0 | 0
1.2.7 | Tunnel Equipment /Tunelska oprema
1.2.7.1 | Right tube/Desna cijev
1.2.7.1.1 | 90% (Equipment installed/Oprema postavljena) | 625553.52 | 34 |  | 0 | 0 | 0
1.2.7.1.2 | 10% (Equipment tested/Oprema ispitana) | 69505.95 | 34 |  | 0 | 0 | 0
1.2.7.2 | Left tube/Lijeva cijev
1.2.7.2.1 | 90% (Equipment installed/Oprema postavljena) | 722459.26 | 34 |  | 0 | 0 | 0
1.2.7.2.2 | 10% (Equipment tested/Oprema ispitana) | 80273.25 | 34 |  | 0 | 0 | 0
| Sub Total/Suma stavke 1.2 | 13486263.29 |  |  | 0 | 0 | 0
Cost Center/ Troškovni centar 1.3 | Road Works/Radovi na putevima (LK1+125.000—LK1+208.014 RK1+085.000—RK1+340.000
Completion of/Završetak:
1.3.1 | Subgrade/Posteljica
1.3.1.1 | Top soil removal/Uklanjanje humusa
1.3.1.1.1 | RK1+085.000—RK1+340.000 - 255m (Inc.0-83.014 m(LK); 0-255.000 m (RK). | 39419.8178 | 16 |  | 0 | 0 | 0
1.3.1.2 | Earthworks/Zemljani radovi
| At every 250 m and 4 m height /Na svakih 250m visini od 4m |  | 33
1.3.1.2.1 | 1+085.00-1+340.00, layers 1,2,3,4,5,6,7,8,9,10,11,12
1.3.1.2.1.1 | 1+085.00-1+340.00, layers 1 | 54732.1826 |  |  | 0 | 0 | 0
1.3.1.2.1.2 | 1+085.00-1+340.00, layers 2 | 73962.409 |  |  | 0 | 0 | 0
1.3.1.2.1.3 | 1+085.00-1+340.00, layers 3 | 73962.409 |  |  | 0 | 0 | 0
1.3.1.2.1.4 | 1+085.00-1+340.00, layers 4 | 73962.409 |  |  | 0 | 0 | 0
1.3.1.2.1.5 | 1+085.00-1+340.00, layers 5 | 73962.409 |  |  | 0 | 0 | 0
1.3.1.2.1.6 | 1+085.00-1+340.00, layers 6 | 73962.409 |  |  | 0 | 0 | 0
1.3.1.2.1.7 | 1+085.00-1+340.00, layers 7 | 73962.409 |  |  | 0 | 0 | 0
1.3.1.2.1.8 | 1+085.00-1+340.00, layers 8 | 73962.409 |  |  | 0 | 0 | 0
1.3.1.2.1.9 | 1+085.00-1+340.00, layers 9 | 73962.409 |  |  | 0 | 0 | 0
1.3.1.2.1.10 | 1+085.00-1+340.00, layers 10 | 73962.409 |  |  | 0 | 0 | 0
1.3.1.2.1.11 | 1+085.00-1+340.00, layers 11 | 73962.409 |  |  | 0 | 0 | 0
1.3.1.2.1.12 | 1+085.00-1+340.00, layers 12 | 73962.409 |  |  | 0 | 0 | 0
1.3.1.3 | Road Foundation/Temelj puta
1.3.1.3.1 | 0 - 255.000 m,right side/desna strana | 23598.7231 | 34 |  | 0 | 0 | 0
1.3.1.3.2 | 0 - 83.014 m,left side/lijeva strana | 7682.4486 | 35 |  | 0 | 0 | 0
1.3.2 | Engineering structures/Inženjerske konstrukcije
1.3.2.1 | Culvert/propust
1.3.2.1.1 | Culvert RK1+090.56, length 117.5 | 6090.4866 | 28 |  | 0 | 0 | 0
1.3.3 | Water drainage/Drenaža vode
per one direction of 500m /Na 500m dužine u jednom pravcu
1.3.3.1 | LK1+125.000—LK1+208.014 (83.014 m) | 35086.8043 | 36 |  | 0 | 0 | 0
1.3.3.2 | RK1+085.000—RK1+340.000 (255m) | 107778.629 | 36 |  | 0 | 0 | 0
1.3.4 | Pavement structure/Kolovozna konstrukcija
1.3.4.1 | Asphalt concrete layer/Sloj asfaltnog betona 1 right side/desna strana | 31012.9778 | 38 |  | 0 | 0 | 0
1.3.4.2 | Asphalt concrete layer/Sloj asfaltnog betona 1 left side/lijeva strana | 10096.1229 | 38 |  | 0 | 0 | 0
1.3.4.3 | Asphalt concrete layer/Sloj asfaltnog betona 2 right side/desna strana | 31012.9778 | 39 |  | 0 | 0 | 0
1.3.4.4 | Asphalt concrete layer/Sloj asfaltnog betona 2 left side/lijeva strana | 10096.1229 | 39 |  | 0 | 0 | 0
1.3.4.5 | Asphalt concrete layer/Sloj asfaltnog betona 3 right side/desna strana | 34460.9087 | 40 |  | 0 | 0 | 0
1.3.4.6 | Asphalt concrete layer/Sloj asfaltnog betona 3 left side/lijeva strana | 11218.5799 | 40 |  | 0 | 0 | 0
| Sub Total/Suma stavke 1.3 | 1215873.2806 |  |  | 0 | 0 | 0
Cost Center/ Troškovni centar 1.4 | Road Works/ Radovi na putevima (LK1+208.014—LK1+248.000 RK1+340.000—RK1+348.000)
Completion of/Završetak:
1.4.1 | Subgrade/Posteljica
1.4.1.1 | Top soil removal/ Uklanjanje humusa
1.4.1.1.1 | RK1+340.000—RK1+348.000 (Inc.0 - 39.986 m (LK); 0 - 8.000 m (RK) | 5596.2161 | 17 |  | 0 | 0 | 0
1.4.1.2 | Earthworks/Zemljani radovi
| At every 250 m and 4 m height /Na svakih 250m visini od 4m |  | 26
1.4.1.2.1 | 1+340.00-1+348.00, layers 1,2,3,
1.4.1.2.1.1 | 1+340.00-1+348.00, layers 1 | 26346.5433 |  |  | 0 | 0 | 0
1.4.1.2.1.2 | 1+340.00-1+348.00, layers 2 | 26346.5433 |  |  | 0 | 0 | 0
1.4.1.2.1.3 | 1+340.00-1+348.00, layers 3 | 21340.7001 |  |  | 0 | 0 | 0
1.4.1.3 | Road Foundation/Temelj puta
1.4.1.3.1 | 0 - 8.000 m, right side/desna strana | 740.3521 | 27 |  | 0 | 0 | 0
1.4.1.3.2 | 0 - 39.986 m, left side/lijeva strana | 3700.4649 | 28 |  | 0 | 0 | 0
1.4.2 | Engineering structures/Inženjerske konstrukcije
1.4.3 | Water drainage/Drenaža vode
per one direction of 500m /Na 500m dužine u jednom pravcu
1.4.3.1 | LK1+208.014—LK1+248.000 (39.986 m) | 16900.5343 | 35 |  | 0 | 0 | 0
1.4.3.2 | RK1+340.000—RK1+348.000 (8 m) | 3381.2903 | 35 |  | 0 | 0 | 0
1.4.4 | Pavement structure/Kolovozna konstrukcija
1.4.4.1 | Asphalt concrete layer/Sloj asfaltnog betona 1 right side/desna strana | 972.9562 | 38 |  | 0 | 0 | 0
1.4.4.2 | Asphalt concrete layer/Sloj asfaltnog betona 1 left side/lijeva strana | 4863.0782 | 38 |  | 0 | 0 | 0
1.4.4.3 | Asphalt concrete layer/Sloj asfaltnog betona 2 right side/desna strana | 972.9562 | 39 |  | 0 | 0 | 0
1.4.4.4 | Asphalt concrete layer/Sloj asfaltnog betona 2 left side/lijeva strana | 4863.0782 | 39 |  | 0 | 0 | 0
1.4.4.5 | Asphalt concrete layer/Sloj asfaltnog betona 3 right side/desna strana | 1081.1265 | 40 |  | 0 | 0 | 0
1.4.4.6 | Asphalt concrete layer/Sloj asfaltnog betona 3 left side/lijeva strana | 5403.75 | 40 |  | 0 | 0 | 0
| Sub Total/Suma stavke 1.4 | 122509.5895 |  |  | 0 | 0 | 0
Cost Center/ Troškovni centar 1.5 | Construction of tunnel/Izgradnja tunela Vezesnik (LK1+248.000—LK3+722.000 RK1+348.000—RK3+762.000)
Completion of/Završetak:
1.5.1 | Portal construction/Izgradnja portala
1.5.1.1 | 20% complete/završeno (portal 1) | 95326.45 | 20 | 25 | 95326.45 | 0 | 95326.45
1.5.1.2 | 40% complete/završeno (portal 2) | 95326.45 | 20 | 25 | 95326.45 | 0 | 95326.45
1.5.1.3 | 60% complete/završeno (portal 3) | 95326.45 | 21 |  | 0 | 0 | 0
1.5.1.4 | 80% complete/završeno (portal 4) | 95326.45 | 21 | 26 | 95326.45 | 0 | 95326.45
1.5.1.5 | 85% (portal 1 complete/završen) | 23831.6125 | 37 |  | 0 | 0 | 0
1.5.1.6 | 90% (portal 2 complete/završen) | 23831.6125 | 38 |  | 0 | 0 | 0
1.5.1.7 | 95% (portal 3 complete/završen) | 23831.6125 | 39 |  | 0 | 0 | 0
1.5.1.8 | 100% (portal 4 complete/završen) | 23831.5925 | 40 |  | 0 | 0 | 0
1.5.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
1.5.2.1 | 75 m (S-R, RK 1+360.00- LK1+436.0) | 305728.108 | 21 | 27 | 305728.11 | 0 | 305728.11
1.5.2.2 | 150 m (S-R, RK 1+436.00- LK1+510.6) | 305728.108 | 21 | 28 | 305728.11 | 0 | 305728.11
1.5.2.3 | 225 m (N-L, LK 3+710.00- LK3+625.70) | 305728.108 | 21 | 28 | 305728.11 | 0 | 305728.11
1.5.2.4 | 300 m (N-R, RK 3+750.00- LK3+674.50) | 305728.108 | 21 | 28 | 305728.11 | 0 | 305728.11
1.5.2.5 | 320 m (S-R(150-170M) RK1+510.60 - RK1+530.60) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.6 | 340 m (S-R(170-190M) RK1+530.60 - RK1+550.60) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.7 | 360 m (S-R(190-210M) RK1+550.60 - RK1+570.60) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.8 | 380 m (S-R(210-230M) RK1+570.60 - RK1+591.50) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.9 | 400 m (S-L(0-20M) LK1+260.00 - LK1+280.00) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.10 | 420 m (S-L(20-40M) LK1+280.00 - LK1+300.00) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.11 | 440 m (S-L(40-60M) LK1+300.00 - LK1+320.00) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.12 | 460 m (S-R(230-250M) RK1+591.50 - RK1+611.50) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.13 | 480 m (S-R(250-270M) RK1+611.50 - RK1+631.50) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.14 | 500 m (S-R(270-290M) RK1+631.50 - RK1+651.50) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.15 | 520 m (S-R(290-310M) RK1+651.50 - RK1+672.00) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.16 | 540 m (S-R(310-330M) RK1+672.00 - RK1+692.00) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.17 | 560 m (S-R(330-350M) RK1+692.00 - RK1+712.00) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.18 | 580 m (S-R(350-370M) RK1+712.00 - RK1+732.00) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.19 | 600 m (S-R(370-390M) RK1+732.00 - RK1+752.00) | 82389.4602 | 22 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.20 | 620 m | 82389.4602 | 23 |  | 0 | 0 | 0
1.5.2.21 | 640 m (N-R(75-95M) RK3+674.50 - RK3+654.50) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.22 | 660 m (N-R(95-115M) RK3+654.50 - RK3+634.50) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.23 | 680 m (N-R(115-135M) RK3+634.50 - RK3+612.90) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.24 | 700 m (N-L(75-95M) LK3+635.50 - LK3+615.50) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.25 | 720 m (N-L(95-115M) LK3+615.50 - LK3+595.50) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.26 | 740 m (N-L(115-135M) LK3+595.50 - LK3+575.50) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.27 | 760 m (N-L(135-155M) LK3+575.50 - LK3+554.80) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.28 | 780 m (N-R(135-155M) RK3+612.90 - RK3+592.90) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.29 | 800 m (N-R(155-175M) RK3+592.90 - RK3+572.90) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.30 | 820 m (N-R(175-195M) RK3+572.90 - RK3+552.20) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.31 | 840 m (N-L(155-175M) LK3+554.80 - LK3+534.80) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.32 | 860 m (N-L(175-195M) LK3+534.80 - LK3+514.80) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.33 | 880 m (N-L(195-215M) LK3+514.80 - LK3+494.80) | 82389.4602 | 23 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.34 | 900 m (N-L(215-235M) LK3+494.80 - LK3+476.50) | 82389.4602 | 24 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.35 | 920 m (N-R(195-215M) RK3+552.20 - RK3+532.20) | 82389.4602 | 24 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.36 | 940 m (N-R(215-235M) RK3+532.20 - RK3+512.20) | 82389.4602 | 24 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.37 | 960 m (N-R(235-255M) RK3+512.20 - RK3+493.50) | 82389.4602 | 24 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.38 | 980 m (N-L(235-255M) LK3+476.50 - LK3+456.50) | 82389.4602 | 24 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.39 | 1000 m (N-L(255-275M) LK3+456.50 - LK3+436.80) | 82389.4602 | 24 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.40 | 1020 m (N-R(255-275M) RK3+493.50 - RK3+473.50) | 82389.4602 | 24 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.41 | 1040 m (N-R(275-295M) RK3+473.50 - RK3+455.00) | 82389.4602 | 25 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.42 | 1060 m (N-L(275-295M) LK3+436.80 - LK3+416.80) | 82389.4602 | 25 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.43 | 1080 m (N-L(295-315M) LK3+416.80 - LK3+395.10) | 82389.4602 | 25 | 29 | 82389.4602 | 0 | 82389.4602
1.5.2.44 | 1100 m | 82389.4602 | 25 |  | 0 | 0 | 0
1.5.2.45 | 1120 m (S-R(390-410M) RK1+752.00 - RK1+772.00) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.46 | 1140 m (S-R(410-430M) RK1+772.00 - RK1+792.00) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.47 | 1160 m (S-R(430-450M) RK1+792.00 - RK1+813.50) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.48 | 1180 m (S-R(450-470M) RK1+813.50 - RK1+833,50) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.49 | 1200 m (S-R(470-490M) RK1+833.50 - RK1+853,50) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.50 | 1220 m | 82389.4602 | 25 | 0 | 0 | 0 | 0
1.5.2.51 | 1240 m (N-L(315-335M) LK3+395.10 - LK3+375.10) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.52 | 1260 m(N-L(335-355M) LK3+375.10 - LK3+355.10) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.53 | 1280 m (N-L(355-375M) LK3+355.10 - LK3+335.10) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.54 | 1300 m (N-L(375-395M) LK3+335.10 - LK3+316.30) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.55 | 1320 m (N-L(395-415M) LK3+316.30 - LK3+296.30) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.56 | 1340 m (N-L(415-435M) LK3+296.30 - LK3+276.30) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.57 | 1360 m (N-R(295-315M) RK3+455.00 - RK3+435.00) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.58 | 1380 m (N-R(315-335M) RK3+435.00 - RK3+415.00) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.59 | 1400 m (N-R(335-355M) RK3+415.00 - RK3+395.00) | 82389.4602 | 25 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.60 | 1420 m (N-R(355-375M) RK3+395.00 - RK3+375.00) | 82389.4602 | 26 | 30 | 0 | 82389.4602 | 82389.4602
1.5.2.61 | 1440 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.62 | 1460 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.63 | 1480 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.64 | 1500 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.65 | 1520 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.66 | 1540 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.67 | 1560 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.68 | 1580 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.69 | 1600 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.70 | 1620 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.71 | 1640 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.72 | 1660 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.73 | 1680 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.74 | 1700 m | 82389.4602 | 26 |  | 0 | 0 | 0
1.5.2.75 | 1720 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.76 | 1740 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.77 | 1760 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.78 | 1780 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.79 | 1800 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.80 | 1820 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.81 | 1840 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.82 | 1860 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.83 | 1880 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.84 | 1900 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.85 | 1920 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.86 | 1940 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.87 | 1960 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.88 | 1980 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.89 | 2000 m | 82389.4602 | 27 |  | 0 | 0 | 0
1.5.2.90 | 2020 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.91 | 2040 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.92 | 2060 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.93 | 2080 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.94 | 2100 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.95 | 2120 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.96 | 2140 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.97 | 2160 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.98 | 2180 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.99 | 2200 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.100 | 2220 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.101 | 2240 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.102 | 2260 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.103 | 2280 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.104 | 2300 m | 82389.4602 | 28 |  | 0 | 0 | 0
1.5.2.105 | 2320 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.106 | 2340 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.107 | 2360 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.108 | 2380 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.109 | 2400 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.110 | 2420 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.111 | 2440 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.112 | 2460 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.113 | 2480 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.114 | 2500 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.115 | 2520 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.116 | 2540 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.117 | 2560 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.118 | 2580 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.119 | 2600 m | 82389.4602 | 29 |  | 0 | 0 | 0
1.5.2.120 | 2620 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.121 | 2640 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.122 | 2660 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.123 | 2680 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.124 | 2700 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.125 | 2720 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.126 | 2740 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.127 | 2760 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.128 | 2780 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.129 | 2800 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.130 | 2820 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.131 | 2840 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.132 | 2860 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.133 | 2880 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.134 | 2900 m | 82389.4602 | 30 |  | 0 | 0 | 0
1.5.2.135 | 2920 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.136 | 2940 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.137 | 2960 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.138 | 2980 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.139 | 3000 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.140 | 3020 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.141 | 3040 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.142 | 3060 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.143 | 3080 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.144 | 3100 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.145 | 3120 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.146 | 3140 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.147 | 3160 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.148 | 3180 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.149 | 3200 m | 82389.4602 | 31 |  | 0 | 0 | 0
1.5.2.150 | 3220 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.151 | 3240 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.152 | 3260 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.153 | 3280 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.154 | 3300 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.155 | 3320 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.156 | 3340 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.157 | 3360 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.158 | 3380 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.159 | 3400 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.160 | 3420 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.161 | 3440 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.162 | 3460 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.163 | 3480 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.164 | 3500 m | 82389.4602 | 32 |  | 0 | 0 | 0
1.5.2.165 | 3520 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.166 | 3540 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.167 | 3560 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.168 | 3580 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.169 | 3600 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.170 | 3620 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.171 | 3640 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.172 | 3660 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.173 | 3680 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.174 | 3700 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.175 | 3720 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.176 | 3740 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.177 | 3760 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.178 | 3780 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.179 | 3800 m | 82389.4602 | 33 |  | 0 | 0 | 0
1.5.2.180 | 3820 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.181 | 3840 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.182 | 3860 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.183 | 3880 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.184 | 3900 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.185 | 3920 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.186 | 3940 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.187 | 3960 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.188 | 3980 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.189 | 4000 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.190 | 4020 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.191 | 4040 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.192 | 4060 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.193 | 4080 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.194 | 4100 m | 82389.4602 | 34 |  | 0 | 0 | 0
1.5.2.195 | 4120 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.196 | 4140 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.197 | 4160 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.198 | 4180 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.199 | 4200 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.200 | 4220 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.201 | 4240 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.202 | 4260 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.203 | 4280 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.204 | 4300 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.205 | 4320 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.206 | 4340 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.207 | 4360 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.208 | 4380 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.209 | 4400 m | 82389.4602 | 35 |  | 0 | 0 | 0
1.5.2.210 | 4420 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.211 | 4440 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.212 | 4460 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.213 | 4480 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.214 | 4500 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.215 | 4520 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.216 | 4540 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.217 | 4560 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.218 | 4580 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.219 | 4600 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.220 | 4620 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.221 | 4640 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.222 | 4660 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.223 | 4680 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.224 | 4700 m | 82389.4602 | 36 |  | 0 | 0 | 0
1.5.2.225 | 4720 m | 82389.4602 | 37 |  | 0 | 0 | 0
1.5.2.226 | 4740 m | 82389.4602 | 37 |  | 0 | 0 | 0
1.5.2.227 | 4760 m | 82389.4602 | 37 |  | 0 | 0 | 0
1.5.2.228 | 4780 m | 82389.4602 | 37 |  | 0 | 0 | 0
1.5.2.229 | 4800 m | 82389.4602 | 37 |  | 0 | 0 | 0
1.5.2.230 | 4820 m | 82389.4602 | 37 |  | 0 | 0 | 0
1.5.2.231 | 4840 m | 82389.4602 | 37 |  | 0 | 0 | 0
1.5.3 | Construction of waterproofing and drainage & Construction of secondary lining / Konstrukcija hidroizolacije i drenaže & Konstrukcija sekundarne obloge
1.5.3.1 | 20 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.2 | 40 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.3 | 60 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.4 | 80 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.5 | 100 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.6 | 120 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.7 | 140 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.8 | 160 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.9 | 180 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.10 | 200 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.11 | 220 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.12 | 240 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.13 | 260 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.14 | 280 m | 67208.791 | 23 |  | 0 | 0 | 0
1.5.3.15 | 300 m | 67208.791 | 24 |  | 0 | 0 | 0
1.5.3.16 | 320 m | 67208.791 | 24 |  | 0 | 0 | 0
1.5.3.17 | 340 m | 67208.791 | 24 |  | 0 | 0 | 0
1.5.3.18 | 360 m | 67208.791 | 24 |  | 0 | 0 | 0
1.5.3.19 | 380 m | 67208.791 | 24 |  | 0 | 0 | 0
1.5.3.20 | 400 m | 67208.791 | 24 |  | 0 | 0 | 0
1.5.3.21 | 420 m | 67208.791 | 24 |  | 0 | 0 | 0
1.5.3.22 | 440 m | 67208.791 | 24 |  | 0 | 0 | 0
1.5.3.23 | 460 m | 67208.791 | 24 |  | 0 | 0 | 0
1.5.3.24 | 480 m | 67208.791 | 24 |  | 0 | 0 | 0
1.5.3.25 | 500 m | 67208.791 | 24 |  | 0 | 0 | 0
1.5.3.26 | 520 m | 67208.791 | 24 |  | 0 | 0 | 0
1.5.3.27 | 540 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.28 | 560 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.29 | 580 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.30 | 600 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.31 | 620 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.32 | 640 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.33 | 660 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.34 | 680 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.35 | 700 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.36 | 720 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.37 | 740 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.38 | 760 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.39 | 780 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.40 | 800 m | 67208.791 | 25 |  | 0 | 0 | 0
1.5.3.41 | 820 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.42 | 840 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.43 | 860 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.44 | 880 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.45 | 900 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.46 | 920 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.47 | 940 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.48 | 960 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.49 | 980 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.50 | 1000 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.51 | 1020 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.52 | 1040 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.53 | 1060 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.54 | 1080 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.55 | 1100 m | 67208.791 | 26 |  | 0 | 0 | 0
1.5.3.56 | 1120 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.57 | 1140 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.58 | 1160 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.59 | 1180 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.60 | 1200 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.61 | 1220 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.62 | 1240 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.63 | 1260 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.64 | 1280 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.65 | 1300 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.66 | 1320 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.67 | 1340 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.68 | 1360 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.69 | 1380 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.70 | 1400 m | 67208.791 | 27 |  | 0 | 0 | 0
1.5.3.71 | 1420 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.72 | 1440 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.73 | 1460 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.74 | 1480 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.75 | 1500 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.76 | 1520 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.77 | 1540 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.78 | 1560 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.79 | 1580 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.80 | 1600 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.81 | 1620 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.82 | 1640 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.83 | 1660 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.84 | 1680 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.85 | 1700 m | 67208.791 | 28 |  | 0 | 0 | 0
1.5.3.86 | 1720 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.87 | 1740 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.88 | 1760 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.89 | 1780 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.90 | 1800 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.91 | 1820 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.92 | 1840 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.93 | 1860 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.94 | 1880 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.95 | 1900 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.96 | 1920 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.97 | 1940 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.98 | 1960 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.99 | 1980 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.100 | 2000 m | 67208.791 | 29 |  | 0 | 0 | 0
1.5.3.101 | 2020 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.102 | 2040 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.103 | 2060 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.104 | 2080 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.105 | 2100 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.106 | 2120 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.107 | 2140 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.108 | 2160 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.109 | 2180 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.110 | 2200 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.111 | 2220 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.112 | 2240 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.113 | 2260 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.114 | 2280 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.115 | 2300 m | 67208.791 | 30 |  | 0 | 0 | 0
1.5.3.116 | 2320 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.117 | 2340 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.118 | 2360 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.119 | 2380 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.120 | 2400 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.121 | 2420 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.122 | 2440 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.123 | 2460 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.124 | 2480 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.125 | 2500 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.126 | 2520 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.127 | 2540 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.128 | 2560 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.129 | 2580 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.130 | 2600 m | 67208.791 | 31 |  | 0 | 0 | 0
1.5.3.131 | 2620 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.132 | 2640 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.133 | 2660 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.134 | 2680 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.135 | 2700 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.136 | 2720 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.137 | 2740 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.138 | 2760 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.139 | 2780 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.140 | 2800 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.141 | 2820 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.142 | 2840 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.143 | 2860 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.144 | 2880 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.145 | 2900 m | 67208.791 | 32 |  | 0 | 0 | 0
1.5.3.146 | 2920 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.147 | 2940 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.148 | 2960 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.149 | 2980 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.150 | 3000 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.151 | 3020 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.152 | 3040 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.153 | 3060 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.154 | 3080 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.155 | 3100 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.156 | 3120 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.157 | 3140 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.158 | 3160 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.159 | 3180 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.160 | 3200 m | 67208.791 | 33 |  | 0 | 0 | 0
1.5.3.161 | 3220 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.162 | 3240 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.163 | 3260 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.164 | 3280 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.165 | 3300 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.166 | 3320 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.167 | 3340 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.168 | 3360 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.169 | 3380 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.170 | 3400 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.171 | 3420 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.172 | 3440 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.173 | 3460 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.174 | 3480 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.175 | 3500 m | 67208.791 | 34 |  | 0 | 0 | 0
1.5.3.176 | 3520 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.177 | 3540 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.178 | 3560 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.179 | 3580 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.180 | 3600 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.181 | 3620 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.182 | 3640 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.183 | 3660 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.184 | 3680 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.185 | 3700 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.186 | 3720 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.187 | 3740 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.188 | 3760 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.189 | 3780 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.190 | 3800 m | 67208.791 | 35 |  | 0 | 0 | 0
1.5.3.191 | 3820 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.192 | 3840 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.193 | 3860 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.194 | 3880 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.195 | 3900 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.196 | 3920 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.197 | 3940 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.198 | 3960 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.199 | 3980 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.200 | 4000 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.201 | 4020 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.202 | 4040 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.203 | 4060 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.204 | 4080 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.205 | 4100 m | 67208.791 | 36 |  | 0 | 0 | 0
1.5.3.206 | 4120 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.207 | 4140 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.208 | 4160 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.209 | 4180 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.210 | 4200 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.211 | 4220 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.212 | 4240 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.213 | 4260 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.214 | 4280 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.215 | 4300 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.216 | 4320 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.217 | 4340 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.218 | 4360 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.219 | 4380 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.220 | 4400 m | 67208.791 | 37 |  | 0 | 0 | 0
1.5.3.221 | 4420 m | 67208.791 | 38 |  | 0 | 0 | 0
1.5.3.222 | 4440 m | 67208.791 | 38 |  | 0 | 0 | 0
1.5.3.223 | 4460 m | 67208.791 | 38 |  | 0 | 0 | 0
1.5.3.224 | 4480 m | 67208.791 | 38 |  | 0 | 0 | 0
1.5.3.225 | 4500 m | 67208.791 | 38 |  | 0 | 0 | 0
1.5.3.226 | 4520 m | 67208.791 | 38 |  | 0 | 0 | 0
1.5.3.227 | 4540 m | 67208.791 | 38 |  | 0 | 0 | 0
1.5.3.228 | 4560 m | 67208.791 | 38 |  | 0 | 0 | 0
1.5.3.229 | 4580 m | 67208.791 | 38 |  | 0 | 0 | 0
1.5.3.230 | 4600 m | 67208.791 | 38 |  | 0 | 0 | 0
1.5.3.231 | 4620 m | 67208.791 | 38 |  | 0 | 0 | 0
1.5.3.232 | 4640 m | 67208.791 | 38 |  | 0 | 0 | 0
1.5.3.233 | 4660 m | 67208.791 | 39 |  | 0 | 0 | 0
1.5.3.234 | 4680 m | 67208.791 | 39 |  | 0 | 0 | 0
1.5.3.235 | 4700 m | 67208.791 | 39 |  | 0 | 0 | 0
1.5.3.236 | 4720 m | 67208.791 | 39 |  | 0 | 0 | 0
1.5.3.237 | 4740 m | 67208.791 | 39 |  | 0 | 0 | 0
1.5.3.238 | 4760 m | 67208.791 | 39 |  | 0 | 0 | 0
1.5.3.239 | 4780 m | 67208.791 | 39 |  | 0 | 0 | 0
1.5.3.240 | 4800 m | 67208.791 | 39 |  | 0 | 0 | 0
1.5.3.241 | 4820 m | 67208.791 | 39 |  | 0 | 0 | 0
1.5.3.242 | 4840 m | 67208.791 | 39 |  | 0 | 0 | 0
1.5.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi I ploca, drenazni sistem)
1.5.4.1 | 200 m | 80000 | 25 |  | 0 | 0 | 0
1.5.4.2 | 400 m | 80000 | 26 |  | 0 | 0 | 0
1.5.4.3 | 600 m | 80000 | 27 |  | 0 | 0 | 0
1.5.4.4 | 800 m | 80000 | 28 |  | 0 | 0 | 0
1.5.4.5 | 1000 m | 80000 | 28 |  | 0 | 0 | 0
1.5.4.6 | 1200 m | 80000 | 29 |  | 0 | 0 | 0
1.5.4.7 | 1400 m | 80000 | 29 |  | 0 | 0 | 0
1.5.4.8 | 1600 m | 80000 | 30 |  | 0 | 0 | 0
1.5.4.9 | 1800 m | 80000 | 31 |  | 0 | 0 | 0
1.5.4.10 | 2000 m | 80000 | 32 |  | 0 | 0 | 0
1.5.4.11 | 2200 m | 80000 | 32 |  | 0 | 0 | 0
1.5.4.12 | 2400 m | 80000 | 33 |  | 0 | 0 | 0
1.5.4.13 | 2600 m | 80000 | 34 |  | 0 | 0 | 0
1.5.4.14 | 2800 m | 80000 | 34 |  | 0 | 0 | 0
1.5.4.15 | 3000 m | 80000 | 35 |  | 0 | 0 | 0
1.5.4.16 | 3200 m | 80000 | 36 |  | 0 | 0 | 0
1.5.4.17 | 3400 m | 80000 | 36 |  | 0 | 0 | 0
1.5.4.18 | 3600 m | 80000 | 37 |  | 0 | 0 | 0
1.5.4.19 | 3800 m | 80000 | 37 |  | 0 | 0 | 0
1.5.4.20 | 4000 m | 80000 | 38 |  | 0 | 0 | 0
1.5.4.21 | 4200 m | 80000 | 39 |  | 0 | 0 | 0
1.5.4.22 | 4400 m | 80000 | 39 |  | 0 | 0 | 0
1.5.4.23 | 4600 m | 80000 | 40 |  | 0 | 0 | 0
1.5.4.24 | 4800 m | 80000 | 40 |  | 0 | 0 | 0
1.5.4.25 | 4840 m | 16000 | 41 |  | 0 | 0 | 0
1.5.5 | Construction of pavement/ Konstrukcija kolovoza
1.5.5.1 | Left tube/Lijeva cijev
1.5.5.2 | 0-500 m
1.5.5.3 | Layer/Sloj 1 | 35508.5994 | 40 |  | 0 | 0 | 0
1.5.5.4 | Layer/Sloj 2 | 35508.5994 | 41 |  | 0 | 0 | 0
1.5.5.5 | Layer/Sloj 3 | 39947.1726 | 42 |  | 0 | 0 | 0
1.5.5.6 | 500-1000 m
1.5.5.7 | Layer/Sloj 1 | 35508.5994 | 40 |  | 0 | 0 | 0
1.5.5.8 | Layer/Sloj 2 | 35508.5994 | 41 |  | 0 | 0 | 0
1.5.5.9 | Layer/Sloj 3 | 39947.1726 | 42 |  | 0 | 0 | 0
1.5.5.10 | 1000-1500 m
1.5.5.11 | Layer/Sloj 1 | 35508.5994 | 40 |  | 0 | 0 | 0
1.5.5.12 | Layer/Sloj 2 | 35508.5994 | 41 |  | 0 | 0 | 0
1.5.5.13 | Layer/Sloj 3 | 39947.1726 | 42 |  | 0 | 0 | 0
1.5.5.14 | 1500-2000 m
1.5.5.15 | Layer/Sloj 1 | 35508.5994 | 40
1.5.5.16 | Layer/Sloj 2 | 35508.5994 | 41 |  | 0 | 0 | 0
1.5.5.17 | Layer/Sloj 3 | 39947.1726 | 42 |  | 0 | 0 | 0
1.5.5.18 | 2000-2474 m |  |  |  | 0 | 0 | 0
1.5.5.19 | Layer/Sloj 1 | 33662.1523 | 40
1.5.5.20 | Layer/Sloj 2 | 33662.1523 | 41 |  | 0 | 0 | 0
1.5.5.21 | Layer/Sloj 3 | 37869.9196 | 42 |  | 0 | 0 | 0
1.5.5.22 | Right tube/Desna cijev
1.5.5.23 | 0-500 m
1.5.5.24 | Layer/Sloj 1 | 29614.6272 | 40 |  | 0 | 0 | 0
1.5.5.25 | Layer/Sloj 2 | 29614.6272 | 41 |  | 0 | 0 | 0
1.5.5.26 | Layer/Sloj 3 | 33316.4561 | 42 |  | 0 | 0 | 0
1.5.5.27 | 500-1000 m
1.5.5.28 | Layer/Sloj 1 | 29614.6272 | 40 |  | 0 | 0 | 0
1.5.5.29 | Layer/Sloj 2 | 29614.6272 | 41 |  | 0 | 0 | 0
1.5.5.30 | Layer/Sloj 3 | 33316.4561 | 42 |  | 0 | 0 | 0
1.5.5.31 | 1000-1500 m
1.5.5.32 | Layer/Sloj 1 | 29614.6272 | 40 |  | 0 | 0 | 0
1.5.5.33 | Layer/Sloj 2 | 29614.6272 | 41 |  | 0 | 0 | 0
1.5.5.34 | Layer/Sloj 3 | 33316.4561 | 42 |  | 0 | 0 | 0
1.5.5.35 | 1500-2000 m
1.5.5.36 | Layer/Sloj 1 | 29614.6272 | 40 |  | 0 | 0 | 0
1.5.5.37 | Layer/Sloj 2 | 29614.6272 | 41 |  | 0 | 0 | 0
1.5.5.38 | Layer/Sloj 3 | 33316.4561 | 42 |  | 0 | 0 | 0
1.5.5.39 | 2000-2414 m
1.5.5.40 | Layer/Sloj 1 | 24520.9113 | 40 |  | 0 | 0 | 0
1.5.5.41 | Layer/Sloj 2 | 24520.9113 | 41 |  | 0 | 0 | 0
1.5.5.42 | Layer/Sloj 3 | 27586.0256 | 42 |  | 0 | 0 | 0
1.5.6 | Tunnel facilities/Tunelski objekti
1.5.6.1 | Construction of Power Station/Izgradnja elektro-stanice | 165282.22 | 43 |  | 0 | 0 | 0
1.5.6.2 | Construction of antifire reservoir | 86312.55 | 43 |  | 0 | 0 | 0
1.5.7 | Tunnel Equipment/ Tunelska oprema
1.5.7.1 | Right tube/Desna cijev
1.5.7.1.1 | 90% (Equipment installed/Oprema postavljena) | 2174123.74 | 43 |  | 0 | 0 | 0
1.5.7.1.2 | 10% (Equipment tested/Oprema ispitana) | 241569.3 | 44 |  | 0 | 0 | 0
1.5.7.2 | Left tube/Lijeva cijev
1.5.7.2.1 | 90% (Equipment installed/Oprema postavljena) | 2228161.61 | 43 |  | 0 | 0 | 0
1.5.7.2.2 | 10% (Equipment tested/Oprema ispitana) | 247573.52 | 44 |  | 0 | 0 | 0
| Sub Total/Suma stavke 1.5 | 44741364.89 |  |  | 4639691.2764 | 1235841.9025 | 5875533.1789
Cost Center/ Troškovni centar 1.6 | Road Works/Radovi na putevima (LK3+722.000—LK3+847.873 RK3+762.000—RK3+840.000)
Completion of/Završetak:
1.6.1 | Subgrade/Posteljica
1.6.1.1 | Top soil removal/Uklanjanje humusa
1.6.1.1.1 | RK3+762.000—RK3+840.000 (Inc.0 - 125.873m (LK);0 - 78.000m (RK). | 23776.0463 | 15 |  | 0 | 0 | 0
1.6.1.2 | Earthworks/Zemljani radovi |  | 30
At every 250 m and 4m height /Na svakih 250m i 4m visini
1.6.1.2.1 | 3+762.00 - 3+840.00 layers 1,2,3,4
1.6.1.2.1.1 | 3+762.00 - 3+840.00 layer 1 | 86116.2088 |  |  | 0 | 0 | 0
1.6.1.2.1.2 | 3+762.00 - 3+840.00 layer 2 | 86116.2088 |  |  | 0 | 0 | 0
1.6.1.2.1.3 | 3+762.00 - 3+840.00 layer 3 | 86116.2088 |  |  | 0 | 0 | 0
1.6.1.2.1.4 | 3+762.00 - 3+840.00 layer 4 | 56190.8263 |  |  | 0 | 0 | 0
1.6.1.3 | Road Foundation/Temelj puta
1.6.1.3.1 | 0 - 78.000 m, right side/desna strana | 7218.433 | 33 |  | 0 | 0 | 0
1.6.1.3.2 | 0 - 125.873 m, left side/lijeva strana | 11648.7924 | 34 |  | 0 | 0 | 0
1.6.2 | Engineering structures/Inženjerske konstrukcije
1.6.3 | Water drainage/Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
1.6.3.1 | LK3+722.000—LK3+847.873 (125.873 m) | 53201.6446 | 32 |  | 0 | 0 | 0
1.6.3.2 | RK3+762.000—RK3+840.000 (78 m) | 32967.5806 | 32 |  | 0 | 0 | 0
1.6.4 | Pavement structure/Kolovozna konstrukcija
1.6.4.1 | Asphalt concrete layer/Sloj asfaltnog betona 1 right side/desna strana | 9486.3226 | 38 |  | 0 | 0 | 0
1.6.4.2 | Asphalt concrete layer/Sloj asfaltnog betona 1 left side/lijeva strana | 15308.6139 | 38 |  | 0 | 0 | 0
1.6.4.3 | Asphalt concrete layer/Sloj asfaltnog betona 2 right side/desna strana | 9486.3226 | 39 |  | 0 | 0 | 0
1.6.4.4 | Asphalt concrete layer/Sloj asfaltnog betona 2 left side/lijeva strana | 15308.61 | 39 |  | 0 | 0 | 0
1.6.4.5 | Asphalt concrete layer/Sloj asfaltnog betona 3 right side/desna strana | 10540.9838 | 40 |  | 0 | 0 | 0
1.6.4.6 | Asphalt concrete layer/Sloj asfaltnog betona 3 left side/lijeva strana | 17010.5802 | 40 |  | 0 | 0 | 0
| Sub Total/Suma stavke 1.6 | 520493.3829 |  |  | 0 | 0 | 0
Cost Center/ Troškovni centar 1.7 | Road Works/Radovi na putevima (LK3+847.873—LK4+760.000 RK3+840.000—RK4+751.597)
Completion of/Završetak:
1.7.1 | Subgrade/Posteljica
1.7.1.1 | Top soil removal/Uklanjanje humusa
1.7.1.1.1 | RK3+840.000—RK4+090.000 (Inc. 0-250 m (LK&RK) | 74293.6375 | 15 |  | 0 | 0 | 0
1.7.1.1.2 | RK4+090.000 - RK4+340.000 (Inc. 250 - 500 m (LK&RK) | 74293.6375 | 15 |  | 0 | 0 | 0
1.7.1.1.3 | RK4+340.000 - RK4+590.000 (Inc.500 - 750 m (LK&RK) | 74293.6375 | 15 |  | 0 | 0 | 0
1.7.1.1.4 | RK4+590.000—RK4+751.597 (Inc. 750-912.127 (LK); 750-911.597(RK) | 48101.267 | 15 |  | 0 | 0 | 0
1.7.1.2 | Earthworks/Zemljani radovi |  | 28
At every 250 m and certain high /Na svakih 250m i određenoj visini
1.7.1.2.1 | 3+840.00 - 4+090.00 layers 1,2,3,4,5
1.7.1.2.1.1 | 3+840.00 - 4+090.00 layer 1 | 224663.7955 |  |  | 0 | 0 | 0
1.7.1.2.1.2 | 3+840.00 - 4+090.00 layer 2 | 186830.5992 |  |  | 0 | 0 | 0
1.7.1.2.1.3 | 3+840.00 - 4+090.00 layer 3 | 186830.5992 |  |  | 0 | 0 | 0
1.7.1.2.1.4 | 3+840.00 - 4+090.00 layer 4 | 186830.5992 |  |  | 0 | 0 | 0
1.7.1.2.1.5 | 3+840.00 - 4+090.00 layer 5 | 186830.5992 |  |  | 0 | 0 | 0
1.7.1.2.2 | 4+090.00 - 4+340.00 layers 6,7,8,9
1.7.1.2.2.6 | 4+090.00 - 4+340.00 layers 6 | 186830.5992 |  |  | 0 | 0 | 0
1.7.1.2.2.7 | 4+090.00 - 4+340.00 layers 7 | 186830.5992 |  |  | 0 | 0 | 0
1.7.1.2.2.8 | 4+090.00 - 4+340.00 layers 8 | 186830.5992 |  |  | 0 | 0 | 0
1.7.1.2.2.9 | 4+090.00 - 4+340.00 layers 9 | 186830.5992 |  |  | 0 | 0 | 0
1.7.1.2.3 | 4.340.00 - 4+590.00 layers 10,11,12,13,
1.7.1.2.3.10 | 4.340.00 - 4+590.00 layers 10 | 177489.0692 |  |  | 0 | 0 | 0
1.7.1.2.3.11 | 4.340.00 - 4+590.00 layers 11 | 186830.5992 |  |  | 0 | 0 | 0
1.7.1.2.3.12 | 4.340.00 - 4+590.00 layers 12 | 186830.5992 |  |  | 0 | 0 | 0
1.7.1.2.3.13 | 4.340.00 - 4+590.00 layers 13 | 144793.7144 |  |  | 0 | 0 | 0
1.7.1.2.4 | 4+590.00 - 4+751.6 layers 14,15
1.7.1.2.4.14 | 4+590.00 - 4+751.6 layers 14 | 211585.6536 |  |  | 0 | 0 | 0
1.7.1.2.4.15 | 4+590.00 - 4+751.6 layers 15 | 186830.5992 |  |  | 0 | 0 | 0
1.7.1.3 | Road Foundation/Temelj puta
1.7.1.3.1 | 0 - 250 m, right side/desna strana | 23136.0031 | 29 |  | 0 | 0 | 0
1.7.1.3.2 | 0 - 250 m, left side/lijeva strana | 23136.0031 | 29 |  | 0 | 0 | 0
1.7.1.3.3 | 250 - 500 m, right side/desna strana | 23136.0031 | 30 |  | 0 | 0 | 0
1.7.1.3.4 | 250 - 500 m, left side/lijeva strana | 23136.0031 | 30 |  | 0 | 0 | 0
1.7.1.3.5 | 500 - 750 m, right side/desna strana | 23136.0031 | 31 |  | 0 | 0 | 0
1.7.1.3.6 | 500 - 750 m, left side/lijeva strana | 23136.0031 | 31 |  | 0 | 0 | 0
1.7.1.3.7 | 750-911.597m, right side/desna strana | 14954.8347 | 32 |  | 0 | 0 | 0
1.7.1.3.8 | 50-912.127m, left side/lijeva strana | 15003.8831 | 32 |  | 0 | 0 | 0
1.7.2 | Engineering structures/Inženjerske konstrukcije
1.7.2.1 | Culvert/propust
1.7.2.1.1 | RK4+100.00 | 7722.6937 | 27 |  | 0 | 0 | 0
1.7.2.1.2 | RK4+294.53 | 6349.7221 | 27 |  | 0 | 0 | 0
1.7.2.1.3 | RK4+670.00 | 4757.6825 | 27 |  | 0 | 0 | 0
1.7.3 | Water drainage/Drenaža vode
per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP)
1.7.3.1 | LK3+847.873—LK4+760.000 (912.127 m)
1.7.3.1.1 | LK3+847.873—LK4+347.873 (500 m) | 211330.6451 | 32 |  | 0 | 0 | 0
1.7.3.1.2 | LK4+347.873—LK4+760.000 (412.127 m) | 174190.1295 | 32 |  | 0 | 0 | 0
1.7.3.2 | RK3+840.000—RK4+751.597 (911.597)
1.7.3.2.1 | RK3+840.000—RK4+340.000 (500 m) | 211330.6451 | 32 |  | 0 | 0 | 0
1.7.3.2.2 | RK4+340.000—RK4+751.597 (411.597 m) | 173966.119 | 32 |  | 0 | 0 | 0
1.7.4 | Pavement structure/Kolovozna konstrukcija
1.7.4.1 | Asphalt concrete layer/Sloj asfaltnog betona 1 right side/desna strana 0-500m | 44137.8954 | 33 |  | 0 | 0 | 0
1.7.4.2 | Asphalt concrete layer/Sloj asfaltnog betona 1 left side/lijeva strana 0-500m | 44137.8954 | 33 |  | 0 | 0 | 0
1.7.4.3 | Asphalt concrete layer/Sloj asfaltnog betona 1 right side/desna strana 500-911.597m | 36334.0507 | 33 |  | 0 | 0 | 0
1.7.4.4 | Asphalt concrete layer/Sloj asfaltnog betona 1 left side/lijeva strana 500-912.127 m | 36380.8369 | 33 |  | 0 | 0 | 0
1.7.4.5 | Asphalt concrete layer/Sloj asfaltnog betona 2 right side/desna strana 0-500m | 44137.8954 | 34 |  | 0 | 0 | 0
1.7.4.6 | Asphalt concrete layer/Sloj asfaltnog betona 2 left side/lijeva strana 0-500m | 44137.8954 | 34 |  | 0 | 0 | 0
1.7.4.7 | Asphalt concrete layer/Sloj asfaltnog betona 2 right side/desna strana 500-911.597m | 36334.0507 | 34 |  | 0 | 0 | 0
1.7.4.8 | Asphalt concrete layer/Sloj asfaltnog betona 2 left side/lijeva strana 500-912.127 m | 36380.8369 | 34 |  | 0 | 0 | 0
1.7.4.9 | Asphalt concrete layer/Sloj asfaltnog betona 3 right side/desna strana 0-500m | 76833.1059 | 35 |  | 0 | 0 | 0
1.7.4.10 | Asphalt concrete layer/Sloj asfaltnog betona 3 left side/lijeva strana 0-500m | 76833.1059 | 35 |  | 0 | 0 | 0
1.7.4.11 | Asphalt concrete layer/Sloj asfaltnog betona 3 right side/desna strana 500-911.597 m | 63248.5518 | 36 |  | 0 | 0 | 0
1.7.4.12 | Asphalt concrete layer/Sloj asfaltnog betona 3 left side/lijeva strana 500-912.127 | 63329.9949 | 36 |  | 0 | 0 | 0
| Sub Total/Suma stavke 1.7 | 4645299.4919 |  |  | 0 | 0 | 0
| TOTAL COST CENTER/UKUPNO TROŠKOVNO MJESTO 01 | 67894104.9946 |  |  | 4639691.2764 | 1235841.9025 | 5875533.1789

## COST CENTER 02
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
COST CENTER 2/TROŠKOVNI CENTAR 02 rev Bridge Piers , Tunnel and Open Route
Cost Center No./ Troškovno mjesto Br. | 02 | Subsection/Podsekcija 1.2 (LK4+760.00 - LK6+440, RK4+751.60 - RK6+435)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost Center/ Troškovno mjesto 2.1 | Road Works/Radovi na putevima (LK4+760—LK4+843.115, RK4+751.60—RK4+830.54)
Completion of/Završetak:
2.1.1 | Subgrade/Posteljica
2.1.1.1 | Top soil removal/ Uklanjanje humusa
2.1.1.1.1 | RK4+751.597—RK4+830.540 (Inc. 0 - 83.115m (LK); 0 - 78.943m (RK) | 17844.31 | 16 |  | 0 | 0 | 0
2.1.1.2 | Earthworks/ Zemljani radovi |  | 28
At every 250 m and 4m height /Na svakih 250m i visini od 4m
2.1.1.2.1 | 4+751.56 - 4+830.54, layers 1, 2
2.1.1.2.1.1 | 4+751.56 - 4+830.54, layers 1 | 109658.9539 |  |  | 0 | 0 | 0
2.1.1.2.1.2 | 4+751.56 - 4+830.54, layers 2 | 126408.0161 |  |  | 0 | 0 | 0
2.1.1.3 | Road Foundation/ Temelj puta
2.1.1.3.1 | 0 - 78.943m, Right side/ Desna strana | 6897.8113 | 34 |  | 0 | 0 | 0
2.1.1.3.2 | 0 - 83.115m, Left side/ Lijeva strana | 7262.3487 | 35 |  | 0 | 0 | 0
2.1.2 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
2.1.2.1 | LK4+760.000—LK4+843.115 ( 53.115m) | 26011.4602 | 39 |  | 0 | 0 | 0
2.1.2.2 | RK4+751.597—RK4+830.540 ( 78.943 m) | 38659.9398 | 39 |  | 0 | 0 | 0
2.1.3 | Pavement structure/ Kolovozna konstrukcija
2.1.3.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 Right side/ Desna strana | 9064.97 | 39 |  | 0 | 0 | 0
2.1.3.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 Left side/ Lijeva strana | 9544.03 | 39 |  | 0 | 0 | 0
2.1.3.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 Right side/ Desna strana | 9064.97 | 40 |  | 0 | 0 | 0
2.1.3.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 Left side/ Lijeva strana | 9544.03 | 40 |  | 0 | 0 | 0
2.1.3.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 Right side/ Desna strana | 10072.79 | 41 |  | 0 | 0 | 0
2.1.3.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 Left side/ Lijeva strana | 10605.11 | 41 |  | 0 | 0 | 0
| Sub Total / Suma stavke 2.1 | 390638.74 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 2.2 | Construction of bridge Gornje Mrke/ Izgradnja mosta Gornje Mrke Lk 4+843.115-LK 5+139.155, RK 4+834.540-RK 5+126.54
Completion of/Završetak:
Left Bridge/ Lijevi most
2.2.1 | Foundation concrete/ Temeljni beton
2.2.1.1 | A1 | 34299.95 | 18 | 27 | 34299.95 | 0 | 34299.95
2.2.1.2 | P1 | 15811.33 | 19 | 26 | 15811.33 | 0 | 15811.33
2.2.1.3 | P2 | 15811.33 | 20 | 25 | 15811.33 | 0 | 15811.33
2.2.1.4 | P3 | 15811.33 | 21 | 25 | 15811.33 | 0 | 15811.33
2.2.1.5 | P4 | 15811.33 | 22 | 26 | 15811.33 | 0 | 15811.33
2.2.1.6 | P5 | 15811.33 | 23 | 26 | 15811.33 | 0 | 15811.33
2.2.1.7 | P6 | 15811.33 | 24 | 27 | 15811.33 | 0 | 15811.33
2.2.1.8 | P7 | 15811.33 | 25 | 27 | 15811.33 | 0 | 15811.33
2.2.1.9 | P8 | 15811.33 | 26 | 28 | 15811.33 | 0 | 15811.33
2.2.1.10 | P9 | 15811.33 | 27 | 30 | 0 | 15811.33 | 15811.33
2.2.1.11 | P10 | 15811.33 | 28 | 29 | 15811.33 | 0 | 15811.33
2.2.1.12 | A2 | 34299.95 | 29 |  | 0 | 0 | 0
2.2.2 | Abutments and Piers elevation/ Elevacija mosnih stubova
2.2.2.1 | A1 | 37820.01 | 19 |  | 0 | 0 | 0
2.2.2.2 | P1 stage 1 (3.3m) | 5496.0842 | 20 |  | 0 | 0 | 0
2.2.2.3 | P1 stage 2 (2.9m) | 4829.8922 | 21 |  | 0 | 0 | 0
2.2.2.4 | P1 stage 3 (2m) | 3330.9601 | 22 |  | 0 | 0 | 0
2.2.2.5 | P2 stage 1 (3.2m) | 5329.5362 | 21 |  | 0 | 0 | 0
2.2.2.6 | P2 stage 2 (1.7m) | 2831.3161 | 21 |  | 0 | 0 | 0
2.2.2.7 | P2 stage 3 (3.2m) | 5329.5362 | 22 |  | 0 | 0 | 0
2.2.2.8 | P2 stage 4 (2.9m) | 4829.8922 | 22 | 30 | 0 | 4829.8922 | 4829.8922
2.2.2.9 | P2 stage 5 (2m) | 3330.9601 | 22 |  | 0 | 0 | 0
2.2.2.10 | P3 stage 1 (1.8m) | 2997.8641 | 21 | 30 | 0 | 2997.8641 | 2997.8641
2.2.2.11 | P3 stage 2 (4.9m) | 8160.8523 | 21 | 30 | 0 | 8160.8523 | 8160.8523
2.2.2.12 | P3 stage 3 (1.7m) | 2831.3161 | 21 | 30 | 0 | 2831.3161 | 2831.3161
2.2.2.13 | P3 stage 4 (3.2m) | 5329.5362 | 22 | 30 | 0 | 5329.5362 | 5329.5362
2.2.2.14 | P3 stage 5 (2.9m) | 4829.8922 | 22 |  | 0 | 0 | 0
2.2.2.15 | P3 stage 6 (2m) | 3330.9601 | 22 |  | 0 | 0 | 0
2.2.2.16 | P4 stage 1 (4m) | 6661.9202 | 22 |  | 0 | 0 | 0
2.2.2.17 | P4 stage 2 (4.9m) | 8160.8523 | 22 |  | 0 | 0 | 0
2.2.2.18 | P4 stage 3 (1.7m) | 2831.3161 | 22 |  | 0 | 0 | 0
2.2.2.19 | P4 stage 4 (3.2m) | 5329.5362 | 23 |  | 0 | 0 | 0
2.2.2.20 | P4 stage 5 (2.9m) | 4829.8922 | 23 |  | 0 | 0 | 0
2.2.2.21 | P4 stage 6 (2m) | 3330.9601 | 23 |  | 0 | 0 | 0
2.2.2.22 | P5 stage 1 (2.38m) | 3963.8425 | 24 |  | 0 | 0 | 0
2.2.2.23 | P5 stage 2 (4.9m) | 8160.8523 | 24 |  | 0 | 0 | 0
2.2.2.24 | P5 stage 3 (4.9m) | 8160.8523 | 24 |  | 0 | 0 | 0
2.2.2.25 | P5 stage 4 (2.07m) | 3447.5437 | 24 |  | 0 | 0 | 0
2.2.2.26 | P5 stage 5 (2.83m) | 4713.3086 | 25 |  | 0 | 0 | 0
2.2.2.27 | P5 stage 6 (4.9m) | 8160.8523 | 25 |  | 0 | 0 | 0
2.2.2.28 | P5 stage 7 (0.92m) | 1532.2417 | 25 |  | 0 | 0 | 0
2.2.2.29 | P6 stage 1 (3.18m) | 5296.2266 | 25 |  | 0 | 0 | 0
2.2.2.30 | P6 stage 2 (4.9m) | 8160.8523 | 25 |  | 0 | 0 | 0
2.2.2.31 | P6 stage 3 (4.9m) | 8160.8523 | 25 |  | 0 | 0 | 0
2.2.2.32 | P6 stage 4 (4.9m) | 8160.8523 | 25 |  | 0 | 0 | 0
2.2.2.33 | P6 stage 5 (2.07m) | 3447.5437 | 26 |  | 0 | 0 | 0
2.2.2.34 | P6 stage 6 (2.83m) | 4713.3086 | 26 |  | 0 | 0 | 0
2.2.2.35 | P6 stage 7 (4.9m) | 8160.8523 | 26 |  | 0 | 0 | 0
2.2.2.36 | P6 stage 8 (0.92m) | 1532.2417 | 26 |  | 0 | 0 | 0
2.2.2.37 | P7 stage 1 (1.98m) | 3297.6505 | 27 |  | 0 | 0 | 0
2.2.2.38 | P7 stage 2 (4.9m) | 8160.8523 | 27 |  | 0 | 0 | 0
2.2.2.39 | P7 stage 3 (4.9m) | 8160.8523 | 27 |  | 0 | 0 | 0
2.2.2.40 | P7 stage 4 (4.9m) | 8160.8523 | 27 |  | 0 | 0 | 0
2.2.2.41 | P7 stage 5 (4.9m) | 8160.8523 | 27 |  | 0 | 0 | 0
2.2.2.42 | P7 stage 6 (2.07m) | 3447.5437 | 28 |  | 0 | 0 | 0
2.2.2.43 | P7 stage 7 (2.83m) | 4713.3086 | 28 |  | 0 | 0 | 0
2.2.2.44 | P7 stage 8 (4.9m) | 8160.8523 | 28 |  | 0 | 0 | 0
2.2.2.45 | P7 stage 9 (0.92m) | 1532.2417 | 28 |  | 0 | 0 | 0
2.2.2.46 | P8 stage 1 (2.68m) | 4463.4866 | 26 |  | 0 | 0 | 0
2.2.2.47 | P8 stage 2 (4.9m) | 8160.8523 | 26 |  | 0 | 0 | 0
2.2.2.48 | P8 stage 3 (4.9m) | 8160.8523 | 26 |  | 0 | 0 | 0
2.2.2.49 | P8 stage 4 (4.9m) | 8160.8523 | 27 |  | 0 | 0 | 0
2.2.2.50 | P8 stage 5 (4.9m) | 8160.8523 | 27 |  | 0 | 0 | 0
2.2.2.51 | P8 stage 6 (2.07m) | 3447.5437 | 27 |  | 0 | 0 | 0
2.2.2.52 | P8 stage 7 (2.83m) | 4713.3086 | 28 |  | 0 | 0 | 0
2.2.2.53 | P8 stage 8 (4.9m) | 8160.8523 | 28 |  | 0 | 0 | 0
2.2.2.54 | P8 stage 9 (0.92m) | 1532.2417 | 28 |  | 0 | 0 | 0
2.2.2.55 | P9 stage 1 (1.28m) | 2131.8145 | 27 |  | 0 | 0 | 0
2.2.2.56 | P9 stage 2 (4.9m) | 8160.8523 | 27 |  | 0 | 0 | 0
2.2.2.57 | P9 stage 3 (4.9m) | 8160.8523 | 27 |  | 0 | 0 | 0
2.2.2.58 | P9 stage 4 (4.9m) | 8160.8523 | 27 |  | 0 | 0 | 0
2.2.2.59 | P9 stage 5 (2.07m) | 3447.5437 | 28 |  | 0 | 0 | 0
2.2.2.60 | P9 stage 6 (2.83m) | 4713.3086 | 28 |  | 0 | 0 | 0
2.2.2.61 | P9 stage 7 (4.9m) | 8160.8523 | 28 |  | 0 | 0 | 0
2.2.2.62 | P9 stage 8 (0.92m) | 1532.2417 | 28 |  | 0 | 0 | 0
2.2.2.63 | P10 stage 1 (2.4m) | 3997.1521 | 29 |  | 0 | 0 | 0
2.2.2.64 | P10 stage 2 (1.7m) | 2831.3161 | 29 |  | 0 | 0 | 0
2.2.2.65 | P10 stage 3 (3.2m) | 5329.5362 | 29 |  | 0 | 0 | 0
2.2.2.66 | P10 stage 4 (2.9m) | 4829.8922 | 29 |  | 0 | 0 | 0
2.2.2.67 | P10 stage 5 (2m) | 3330.9601 | 29 |  | 0 | 0 | 0
2.2.2.68 | A2 | 37820.01 | 29 |  | 0 | 0 | 0
2.2.3 | Bridge deck superstructure/Gornji stroj mosne ploče
2.2.3.1 | A1-P1 | 52105.93 | 36 |  | 0 | 0 | 0
2.2.3.2 | P1-P2 | 66316.64 | 36 |  | 0 | 0 | 0
2.2.3.3 | P2-P3 | 66316.64 | 37 |  | 0 | 0 | 0
2.2.3.4 | P3-P4 | 66316.64 | 37 |  | 0 | 0 | 0
2.2.3.5 | P4-P5 | 66316.64 | 37 |  | 0 | 0 | 0
2.2.3.6 | P5-P6 | 66316.64 | 38 |  | 0 | 0 | 0
2.2.3.7 | P6-P7 | 66316.64 | 38 |  | 0 | 0 | 0
2.2.3.8 | P7-P8 | 66316.64 | 38 |  | 0 | 0 | 0
2.2.3.9 | P8-P9 | 66316.64 | 39 |  | 0 | 0 | 0
2.2.3.10 | P9-P10 | 66316.64 | 39 |  | 0 | 0 | 0
2.2.3.11 | P10-A2 | 52105.93 | 39 |  | 0 | 0 | 0
2.2.4 | Bridge deck prestressing/ Prednaprezanje mosne ploče
2.2.4.1 | A1-P1 | 43967.21 | 36 |  | 0 | 0 | 0
2.2.4.2 | P1-P2 | 55958.27 | 37 |  | 0 | 0 | 0
2.2.4.3 | P2-P3 | 55958.27 | 37 |  | 0 | 0 | 0
2.2.4.4 | P3-P4 | 55958.27 | 37 |  | 0 | 0 | 0
2.2.4.5 | P4-P5 | 55958.27 | 38 |  | 0 | 0 | 0
2.2.4.6 | P5-P6 | 55958.27 | 38 |  | 0 | 0 | 0
2.2.4.7 | P6-P7 | 55958.27 | 38 |  | 0 | 0 | 0
2.2.4.8 | P7-P8 | 55958.27 | 39 |  | 0 | 0 | 0
2.2.4.9 | P8-P9 | 55958.27 | 39 |  | 0 | 0 | 0
2.2.4.10 | P9-P10 | 55958.27 | 39 |  | 0 | 0 | 0
2.2.4.11 | P10-A2 | 43967.21 | 39 |  | 0 | 0 | 0
2.2.5 | Bridge Furniture/ Mosna estetika
2.2.5.1 | 50m | 55196.57 | 36 |  | 0 | 0 | 0
2.2.5.2 | 100m | 55196.57 | 37 |  | 0 | 0 | 0
2.2.5.3 | 150m | 55196.57 | 37 |  | 0 | 0 | 0
2.2.5.4 | 200m | 55196.57 | 38 |  | 0 | 0 | 0
2.2.5.5 | 250m | 55196.57 | 38 |  | 0 | 0 | 0
2.2.5.6 | 296m | 50780.84 | 39 |  | 0 | 0 | 0
2.2.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
2.2.6.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/hidroizolacija | 83585.42 | 38 |  | 0 | 0 | 0
2.2.6.2 | Asphalt layer/ Sloj asfalta 2 + joints/spojnice | 64336.52 | 39 |  | 0 | 0 | 0
Right Bridge/ Desni most
2.2.7 | Foundation concrete/ Temeljni beton
2.2.7.1 | A1 | 34900.1 | 18 | 29 | 34900.1 | 0 | 34900.1
2.2.7.2 | P1 | 14635.05 | 19 | 27 | 14635.05 | 0 | 14635.05
2.2.7.3 | P2 | 14635.05 | 20 | 26 | 14635.05 | 0 | 14635.05
2.2.7.4 | P3 | 14635.05 | 21 | 27 | 14635.05 | 0 | 14635.05
2.2.7.5 | P4 | 14635.05 | 22 | 27 | 14635.05 | 0 | 14635.05
2.2.7.6 | P5 | 14635.05 | 23 | 27 | 14635.05 | 0 | 14635.05
2.2.7.7 | P6 | 14635.05 | 24 | 26 | 14635.05 | 0 | 14635.05
2.2.7.8 | P7 | 14635.05 | 25 | 28 | 14635.05 | 0 | 14635.05
2.2.7.9 | P8 | 14635.05 | 26 | 29 | 14635.05 | 0 | 14635.05
2.2.7.10 | P9 | 28482.85 | 27 |  | 0 | 0 | 0
2.2.7.11 | P10 | 14635.05 | 28 | 28 | 14635.05 | 0 | 14635.05
2.2.7.12 | A2 | 34900.1 | 29 |  | 0 | 0 | 0
2.2.8 | Abutments and Piers elevation/ Elevacija mosnih stubova
2.2.8.1 | A1 | 43375.51 | 19 |  | 0 | 0 | 0
2.2.8.2 | P1 stage 1 (3.7m) | 6175.3953 | 20 |  | 0 | 0 | 0
2.2.8.3 | P1 stage 2 (2.9m) | 4840.1747 | 20 |  | 0 | 0 | 0
2.2.8.4 | P1 stage 3 (2m) | 3338.0515 | 20 |  | 0 | 0 | 0
2.2.8.5 | P2 stage 1 (1.8m) | 3004.2464 | 21 | 30 | 0 | 3004.2464 | 3004.2464
2.2.8.6 | P2 stage 2 (1.7m) | 2837.3438 | 21 | 30 | 0 | 2837.3438 | 2837.3438
2.2.8.7 | P2 stage 3 (3.2m) | 5340.8824 | 22 | 30 | 0 | 5340.8824 | 5340.8824
2.2.8.8 | P2 stage 4 (2.9m) | 4840.1747 | 22 | 30 | 0 | 4840.1747 | 4840.1747
2.2.8.9 | P2 stage 5 (2m) | 3338.0515 | 22 |  | 0 | 0 | 0
2.2.8.10 | P3 stage 1 (5.1m) | 8512.0314 | 21 | 30 | 0 | 8512.0314 | 8512.0314
2.2.8.11 | P3 stage 2 (1.7m) | 2837.3438 | 21 | 30 | 0 | 2837.3438 | 2837.3438
2.2.8.12 | P3 stage 3 (3.2m) | 5340.8824 | 22 | 30 | 0 | 5340.8824 | 5340.8824
2.2.8.13 | P3 stage 4 (2.9m) | 4840.1747 | 22 | 30 | 0 | 4840.1747 | 4840.1747
2.2.8.14 | P3 stage 5 (2m) | 3338.0515 | 22 |  | 0 | 0 | 0
2.2.8.15 | P4 stage 1 (1.8m) | 3004.2464 | 22 |  | 0 | 0 | 0
2.2.8.16 | P4 stage 2 (4.9m) | 8178.2262 | 22 |  | 0 | 0 | 0
2.2.8.17 | P4 stage 3 (1.7m) | 2837.3438 | 22 |  | 0 | 0 | 0
2.2.8.18 | P4 stage 4 (3.2m) | 5340.8824 | 23 |  | 0 | 0 | 0
2.2.8.19 | P4 stage 5 (2.9m) | 4840.1747 | 23 |  | 0 | 0 | 0
2.2.8.20 | P4 stage 6 (2m) | 3338.0515 | 23 |  | 0 | 0 | 0
2.2.8.21 | P5 stage 1 (1.08m) | 1802.5478 | 24 |  | 0 | 0 | 0
2.2.8.22 | P5 stage 2 (4.9m) | 8178.2262 | 24 |  | 0 | 0 | 0
2.2.8.23 | P5 stage 3 (4.9m) | 8178.2262 | 24 |  | 0 | 0 | 0
2.2.8.24 | P5 stage 4 (2.07m) | 3454.8833 | 25 |  | 0 | 0 | 0
2.2.8.25 | P5 stage 5 (2.83m) | 4723.3429 | 25 |  | 0 | 0 | 0
2.2.8.26 | P5 stage 6 (4.9m) | 8178.2262 | 25 |  | 0 | 0 | 0
2.2.8.27 | P5 stage 7 (0.92m) | 1535.5037 | 25 |  | 0 | 0 | 0
2.2.8.28 | P6 stage 1 (2.48m) | 4139.1839 | 24 |  | 0 | 0 | 0
2.2.8.29 | P6 stage 2 (4.9m) | 8178.2262 | 24 |  | 0 | 0 | 0
2.2.8.30 | P6 stage 3 (4.9m) | 8178.2262 | 24 |  | 0 | 0 | 0
2.2.8.31 | P6 stage 4 (4.9m) | 8178.2262 | 24 |  | 0 | 0 | 0
2.2.8.32 | P6 stage 5 (2.07m) | 3454.8833 | 25 |  | 0 | 0 | 0
2.2.8.33 | P6 stage 6 (2.83m) | 4723.3429 | 25 |  | 0 | 0 | 0
2.2.8.34 | P6 stage 7 (4.9m) | 8178.2262 | 25 |  | 0 | 0 | 0
2.2.8.35 | P6 stage 8 (0.92m) | 1535.5037 | 25 |  | 0 | 0 | 0
2.2.8.36 | P7 stage 1 (2.78m) | 4639.8916 | 25 |  | 0 | 0 | 0
2.2.8.37 | P7 stage 2 (4.9m) | 8178.2262 | 25 |  | 0 | 0 | 0
2.2.8.38 | P7 stage 3 (4.9m) | 8178.2262 | 25 |  | 0 | 0 | 0
2.2.8.39 | P7 stage 4 (4.9m) | 8178.2262 | 25 |  | 0 | 0 | 0
2.2.8.40 | P7 stage 5 (4.9m) | 8178.2262 | 26 |  | 0 | 0 | 0
2.2.8.41 | P7 stage 6 (2.07m) | 3454.8833 | 26 |  | 0 | 0 | 0
2.2.8.42 | P7 stage 7 (2.83m) | 4723.3429 | 26 |  | 0 | 0 | 0
2.2.8.43 | P7 stage 8 (4.9m) | 8178.2262 | 27 |  | 0 | 0 | 0
2.2.8.44 | P7 stage 9 (0.92m) | 1535.5037 | 27 |  | 0 | 0 | 0
2.2.8.45 | P8 stage 1 (4.18m) | 6976.5277 | 27 |  | 0 | 0 | 0
2.2.8.46 | P8 stage 2 (4.9m) | 8178.2262 | 26 |  | 0 | 0 | 0
2.2.8.47 | P8 stage 3 (4.9m) | 8178.2262 | 26 |  | 0 | 0 | 0
2.2.8.48 | P8 stage 4 (4.9m) | 8178.2262 | 26 |  | 0 | 0 | 0
2.2.8.49 | P8 stage 5 (4.9m) | 8178.2262 | 26 |  | 0 | 0 | 0
2.2.8.50 | P8 stage 6 (2.07m) | 3454.8833 | 27 |  | 0 | 0 | 0
2.2.8.51 | P8 stage 7 (2.83m) | 4723.3429 | 27 |  | 0 | 0 | 0
2.2.8.52 | P8 stage 8 (4.9m) | 8178.2262 | 27 |  | 0 | 0 | 0
2.2.8.53 | P8 stage 9 (0.92m) | 1535.5037 | 27 |  | 0 | 0 | 0
2.2.8.54 | P9 stage 1 (3.98m) | 6642.7225 | 27 |  | 0 | 0 | 0
2.2.8.55 | P9 stage 2 (4.9m) | 8178.2262 | 27 |  | 0 | 0 | 0
2.2.8.56 | P9 stage 3 (4.9m) | 8178.2262 | 27 |  | 0 | 0 | 0
2.2.8.57 | P9 stage 4 (2.07m) | 3454.8833 | 27 |  | 0 | 0 | 0
2.2.8.58 | P9 stage 5 (2.83m) | 4723.3429 | 27 |  | 0 | 0 | 0
2.2.8.59 | P9 stage 6 (4.9m) | 8178.2262 | 28 |  | 0 | 0 | 0
2.2.8.60 | P9 stage 7 (0.92m) | 1535.5037 | 28 |  | 0 | 0 | 0
2.2.8.61 | P10 stage 1 (2.5m) | 4172.5644 | 28 |  | 0 | 0 | 0
2.2.8.62 | P10 stage 2 (4.9m) | 8178.2262 | 28 |  | 0 | 0 | 0
2.2.8.63 | P10 stage 3 (1.7m) | 2837.3438 | 28 |  | 0 | 0 | 0
2.2.8.64 | P10 stage 4 (3.2m) | 5340.8824 | 29 |  | 0 | 0 | 0
2.2.8.65 | P10 stage 5 (2.9m) | 4840.1747 | 29 |  | 0 | 0 | 0
2.2.8.66 | P10 stage 6 (2m) | 3338.0515 | 29 |  | 0 | 0 | 0
2.2.8.67 | A2 | 43375.51 | 29 |  | 0 | 0 | 0
2.2.9 | Bridge deck superstructure/Gornji stroj mosne ploče
2.2.9.1 | A1-P1 | 52106.05 | 36 |  | 0 | 0 | 0
2.2.9.2 | P1-P2 | 66316.79 | 36 |  | 0 | 0 | 0
2.2.9.3 | P2-P3 | 66316.79 | 37 |  | 0 | 0 | 0
2.2.9.4 | P3-P4 | 66316.79 | 37 |  | 0 | 0 | 0
2.2.9.5 | P4-P5 | 66316.79 | 37 |  | 0 | 0 | 0
2.2.9.6 | P5-P6 | 66316.79 | 38 |  | 0 | 0 | 0
2.2.9.7 | P6-P7 | 66316.79 | 38 |  | 0 | 0 | 0
2.2.9.8 | P7-P8 | 66316.79 | 38 |  | 0 | 0 | 0
2.2.9.9 | P8-P9 | 66316.79 | 39 |  | 0 | 0 | 0
2.2.9.10 | P9-P10 | 66316.79 | 39 |  | 0 | 0 | 0
2.2.9.11 | P10-A2 | 52106.05 | 39 |  | 0 | 0 | 0
2.2.10 | Bridge deck prestressing/ Prednaprezanje mosne ploče
2.2.10.1 | A1-P1 | 43967.21 | 36 |  | 0 | 0 | 0
2.2.10.2 | P1-P2 | 55958.27 | 36 |  | 0 | 0 | 0
2.2.10.3 | P2-P3 | 55958.27 | 37 |  | 0 | 0 | 0
2.2.10.4 | P3-P4 | 55958.27 | 37 |  | 0 | 0 | 0
2.2.10.5 | P4-P5 | 55958.27 | 37 |  | 0 | 0 | 0
2.2.10.6 | P5-P6 | 55958.27 | 38 |  | 0 | 0 | 0
2.2.10.7 | P6-P7 | 55958.27 | 38 |  | 0 | 0 | 0
2.2.10.8 | P7-P8 | 55958.27 | 38 |  | 0 | 0 | 0
2.2.10.9 | P8-P9 | 55958.27 | 39 |  | 0 | 0 | 0
2.2.10.10 | P9-P10 | 55958.27 | 39 |  | 0 | 0 | 0
2.2.10.11 | P10-A2 | 43967.21 | 39 |  | 0 | 0 | 0
2.2.11 | Bridge Furniture/ Mosna estetika
2.2.11.1 | 50m | 51175.85 | 36 |  | 0 | 0 | 0
2.2.11.2 | 100m | 51175.85 | 37 |  | 0 | 0 | 0
2.2.11.3 | 150m | 51175.85 | 37 |  | 0 | 0 | 0
2.2.11.4 | 200m | 51175.85 | 38 |  | 0 | 0 | 0
2.2.11.5 | 250m | 51175.85 | 38 |  | 0 | 0 | 0
2.2.11.6 | 296m | 47081.81 | 39 |  | 0 | 0 | 0
2.2.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
2.2.12.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/hidroizolacija | 83566.08 | 38 |  | 0 | 0 | 0
2.2.12.2 | Asphalt layer/ Sloj asfalta 2 + joints/spojnice | 64331.7 | 39 |  | 0 | 0 | 0
| Sub Total / Suma stavke 2.2 | 4834301.08 |  |  | 343217.47 | 77513.8704 | 420731.3404
Cost Center/ Troškovno mjesto 2.3 | Road Works/ Radovi na putevima (LK5+139.115—LK5+152.612, RK5+126.540—RK5+143.377)
Completion of/Završetak:
2.3.1 | Subgrade/Posteljica
2.3.1.1 | Top soil removal/ Uklanjanje humusa
2.3.1.1.1 | RK5+126.540—RK5+143.377 (Inc. 0 - 13.497m (LK); 0 - 16.837m (RK) | 6221.78 | 17 |  | 0 | 0 | 0
2.3.1.2 | Earthworks/ Zemljani radovi |  | 30
At every 250 m and 4m height /Na svakih 250m i visini od 4m
2.3.1.2.1 | 5+126.54 - 5+143.38, layers 1, 2
2.3.1.2.1.1 | 5+126.54 - 5+143.38, layers 1 | 41518.0227 |  |  | 0 | 0 | 0
2.3.1.2.1.2 | 5+126.54 - 5+143.38, layers 2 | 40791.4573 |  |  | 0 | 0 | 0
2.3.1.3 | Road Foundation/ Temelj puta
2.3.1.3.1 | 0 - 16.837m, Right side/ Desna strana | 2740.4224 | 33 |  | 0 | 0 | 0
2.3.1.3.2 | 0 - 13.497m, Left side/ Lijeva strana | 2196.7976 | 34 |  | 0 | 0 | 0
2.3.2 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
2.3.2.1 | LK5+139.115—LK5+152.612 (13.497 m) | 10033.0844 | 26 |  | 0 | 0 | 0
2.3.2.2 | RK5+126.540—RK5+143.377 (16.837m) | 12515.8956 | 26 |  | 0 | 0 | 0
2.3.3 | Pavement structure/ Kolovozna konstrukcija
2.3.3.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 Right side/ Desna strana | 3601.41 | 36 |  | 0 | 0 | 0
2.3.3.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 Left side/ Lijeva strana | 2886.99 | 36 |  | 0 | 0 | 0
2.3.3.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 Right side/ Desna strana | 3601.41 | 37 |  | 0 | 0 | 0
2.3.3.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 Left side/ Lijeva strana | 2886.99 | 37 |  | 0 | 0 | 0
2.3.3.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 Right side/ Desna strana | 4001.8 | 38 |  | 0 | 0 | 0
2.3.3.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 Left side/ Lijeva strana | 3207.96 | 38 |  | 0 | 0 | 0
| Sub Total / Suma stavke 2.3 | 136204.02 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 2.4 | Construction of tunnel Mrke/ Izgradnja tunela Mrke LK 5+152.612- LK 5+991.612, RK 5+143.377- RK 5+947.377
Completion of/Završetak:
2.4.1 | Portal construction/ Izgradnja portala
2.4.1.1 | 20% complete/završeno (portal 1) | 47167.07 | 16 | 22 | 47167.07 | 0 | 47167.07
2.4.1.2 | 40% complete/završeno (portal 2) | 47167.07 | 17 | 22 | 47167.07 | 0 | 47167.07
2.4.1.3 | 60% complete/završeno (portal 3) | 47167.07 | 18 |  | 0 | 0 | 0
2.4.1.4 | 80% complete/završeno (portal 4) | 47167.07 | 18 |  | 0 | 0 | 0
2.4.1.5 | 85% (portal 1 complete/završen) | 11791.7675 | 34 |  | 0 | 0 | 0
2.4.1.6 | 90% (portal 2 complete/završen) | 11791.7675 | 34 |  | 0 | 0 | 0
2.4.1.7 | 95% (portal 3 complete/završen) | 11791.7675 | 35 |  | 0 | 0 | 0
2.4.1.8 | 100% (portal 4 complete/završen) | 11791.7775 | 35 |  | 0 | 0 | 0
2.4.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
2.4.2.1 | 75 m (S-R, RK 5+161.2- RK 5+236.30) | 296727.49 | 19 | 24 | 296727.49 | 0 | 296727.49
2.4.2.2 | 150 m (S-L, LK 5+168.80- LK 5+245.20) | 296727.49 | 20 | 24 | 296727.49 | 0 | 296727.49
2.4.2.3 | 225 m (S-L, LK 5+245.20- LK5+320.20) | 296727.49 | 21 | 25 | 296727.49 | 0 | 296727.49
2.4.2.4 | 300 m (S-R, RK 5+236.30- RK 5+313.40) | 296727.49 | 22 | 26 | 296727.49 | 0 | 296727.49
2.4.2.5 | 375 m (S-L, LK 5+320.3- LK5+394.50) | 296727.49 | 22 | 26 | 296727.49 | 0 | 296727.49
2.4.2.6 | 450 m (S-R, RK 5+313.40- RK 5+369.40) | 296727.49 | 23 | 27 | 296727.49 | 0 | 296727.49
2.4.2.7 | 525 m (S-L, LK 5+394.5- LK5+470.40) | 296727.49 | 23 | 28 | 296727.49 | 0 | 296727.49
2.4.2.8 | 600 m (S-R, RK 5+369.40- RK 5+465.20) | 296727.49 | 24 | 28 | 296727.49 | 0 | 296727.49
2.4.2.9 | 675 m (S-L, LK 5+470.40- LK5+546.10) | 296727.49 | 24 | 28 | 296727.49 | 0 | 296727.49
2.4.2.10 | 695 m (S-R(300-320M) RK5+465.20 - RK5+485.20) | 78691.6084 | 25 | 29 | 78691.6084 | 0 | 78691.6084
2.4.2.11 | 715 m (S-R(320-340M) RK5+485.20 - RK5+505.20) | 78691.6084 | 25 | 29 | 78691.6084 | 0 | 78691.6084
2.4.2.12 | 735 m (S-R(340-360M) RK5+505.20 - RK5+525.20) | 78691.6084 | 25 | 29 | 78691.6084 | 0 | 78691.6084
2.4.2.13 | 755 m (S-R(360-380M) RK5+525.20 - RK5+546.60) | 78691.6084 | 25 | 29 | 78691.6084 | 0 | 78691.6084
2.4.2.14 | 775 m (S-L(375-395M) LK5+546.10 - LK5+566.10) | 78691.6084 | 25 | 29 | 78691.6084 | 0 | 78691.6084
2.4.2.15 | 795 m (S-L(395-415M) LK5+566.10 - LK5+586.50) | 78691.6084 | 25 | 29 | 78691.6084 | 0 | 78691.6084
2.4.2.16 | 815 m (S-R(380-400M) RK5+546.60 - RK5+566.60) | 78691.6084 | 25 | 29 | 78691.6084 | 0 | 78691.6084
2.4.2.17 | 835 m (S-R(400-420M) RK5+566.60 - RK5+586.60) | 78691.6084 | 26 | 29 | 78691.6084 | 0 | 78691.6084
2.4.2.18 | 855 m (S-R(420-440M) RK5+586.60 - RK5+606.30) | 78691.6084 | 26 | 29 | 78691.6084 | 0 | 78691.6084
2.4.2.19 | 875 m (S-L(415-435M) LK5+586.50 - LK5+606.50) | 78691.6084 | 26 | 29 | 78691.6084 | 0 | 78691.6084
2.4.2.20 | 895 m (S-L(435-455M) LK5+606.50 - LK5+626.60) | 78691.6084 | 26 | 29 | 78691.6084 | 0 | 78691.6084
2.4.2.21 | 915 m (S-R (440-460) RK5+606.30 - RK5+626.30) | 78691.6084 | 26 | 30 | 0 | 78691.6084 | 78691.6084
2.4.2.22 | 935 m (S-R (460-480) RK5+626.30 - RK5+646.30) | 78691.6084 | 26 | 30 | 0 | 78691.6084 | 78691.6084
2.4.2.23 | 955 m (S-R (480-500) RK5+646.30 - RK5+666.30) | 78691.6084 | 26 | 30 | 0 | 78691.6084 | 78691.6084
2.4.2.24 | 975 m (S-R (500-520) RK5+666.30 - RK5+685.50) | 78691.6084 | 27 | 30 | 0 | 78691.6084 | 78691.6084
2.4.2.25 | 995 m (S-R (520-540) RK5+685.30 - RK5+707,60) | 78691.6084 | 27 | 30 | 0 | 78691.6084 | 78691.6084
2.4.2.26 | 1015 m (S-L (455-475) LK5+626.60 - LK5+646.60) | 78691.6084 | 27 | 30 | 0 | 78691.6084 | 78691.6084
2.4.2.27 | 1035 m (S-L (475-495) LK5+646.60 - LK5+666.60) | 78691.6084 | 27 | 30 | 0 | 78691.6084 | 78691.6084
2.4.2.28 | 1055 m (S-L (495-515) LK5+666.60 - LK5+686.60) | 78691.6084 | 27 | 30 | 0 | 78691.6084 | 78691.6084
2.4.2.29 | 1075 m (S-L (515-535) LK5+686.60 - LK5+706.70) | 78691.6084 | 27 | 30 | 0 | 78691.6084 | 78691.6084
2.4.2.30 | 1095 m | 78691.6084 | 27 |  | 0 | 0 | 0
2.4.2.31 | 1115 m | 78691.6084 | 28 |  | 0 | 0 | 0
2.4.2.32 | 1135 m | 78691.6084 | 28 |  | 0 | 0 | 0
2.4.2.33 | 1155 m | 78691.6084 | 28 |  | 0 | 0 | 0
2.4.2.34 | 1175 m | 78691.6084 | 28 |  | 0 | 0 | 0
2.4.2.35 | 1195 m | 78691.6084 | 28 |  | 0 | 0 | 0
2.4.2.36 | 1215 m | 78691.6084 | 28 |  | 0 | 0 | 0
2.4.2.37 | 1235 m | 78691.6084 | 28 |  | 0 | 0 | 0
2.4.2.38 | 1255 m | 78691.6084 | 28 |  | 0 | 0 | 0
2.4.2.39 | 1275 m | 78691.6084 | 29 |  | 0 | 0 | 0
2.4.2.40 | 1295 m | 78691.6084 | 29 |  | 0 | 0 | 0
2.4.2.41 | 1315 m | 78691.6084 | 29 |  | 0 | 0 | 0
2.4.2.42 | 1335 m | 78691.6084 | 29 |  | 0 | 0 | 0
2.4.2.43 | 1355 m | 78691.6084 | 29 |  | 0 | 0 | 0
2.4.2.44 | 1375 m | 78691.6084 | 29 |  | 0 | 0 | 0
2.4.2.45 | 1395 m | 78691.6084 | 29 |  | 0 | 0 | 0
2.4.2.46 | 1415 m | 78691.6084 | 29 |  | 0 | 0 | 0
2.4.2.47 | 1435 m | 78691.6084 | 30 |  | 0 | 0 | 0
2.4.2.48 | 1455 m | 78691.6084 | 30 |  | 0 | 0 | 0
2.4.2.49 | 1475 m | 78691.6084 | 30 |  | 0 | 0 | 0
2.4.2.50 | 1495 m | 78691.6084 | 30 |  | 0 | 0 | 0
2.4.2.51 | 1515 m | 78691.6084 | 30 |  | 0 | 0 | 0
2.4.2.52 | 1535 m | 78691.6084 | 30 |  | 0 | 0 | 0
2.4.2.53 | 1555 m | 78691.6084 | 30 |  | 0 | 0 | 0
2.4.2.54 | 1575 m | 78691.6084 | 30 |  | 0 | 0 | 0
2.4.2.55 | 1583 m | 31476.6433 | 30 |  | 0 | 0 | 0
2.4.3 | Construction of waterproofing and drainage & Construction of secondary lining/ Konstrukcija hidroizolacije i drenaže & Konstrukcija sekundarne obloge
2.4.3.1 | 20 m | 90220.2859 | 19 |  | 0 | 0 | 0
2.4.3.2 | 40 m | 90220.2859 | 19 |  | 0 | 0 | 0
2.4.3.3 | 60 m | 90220.2859 | 20 |  | 0 | 0 | 0
2.4.3.4 | 80 m | 90220.2859 | 20 |  | 0 | 0 | 0
2.4.3.5 | 100 m | 90220.2859 | 20 |  | 0 | 0 | 0
2.4.3.6 | 120 m | 90220.2859 | 20 |  | 0 | 0 | 0
2.4.3.7 | 140 m | 90220.2859 | 21 |  | 0 | 0 | 0
2.4.3.8 | 160 m | 90220.2859 | 21 |  | 0 | 0 | 0
2.4.3.9 | 180 m | 90220.2859 | 21 |  | 0 | 0 | 0
2.4.3.10 | 200 m | 90220.2859 | 21 |  | 0 | 0 | 0
2.4.3.11 | 220 m | 90220.2859 | 21 |  | 0 | 0 | 0
2.4.3.12 | 240 m | 90220.2859 | 22 |  | 0 | 0 | 0
2.4.3.13 | 260 m | 90220.2859 | 22 |  | 0 | 0 | 0
2.4.3.14 | 280 m | 90220.2859 | 22 |  | 0 | 0 | 0
2.4.3.15 | 300 m | 90220.2859 | 22 |  | 0 | 0 | 0
2.4.3.16 | 320 m | 90220.2859 | 22 |  | 0 | 0 | 0
2.4.3.17 | 340 m | 90220.2859 | 22 |  | 0 | 0 | 0
2.4.3.18 | 360 m | 90220.2859 | 22 |  | 0 | 0 | 0
2.4.3.19 | 380 m | 90220.2859 | 23 |  | 0 | 0 | 0
2.4.3.20 | 400 m | 90220.2859 | 23 |  | 0 | 0 | 0
2.4.3.21 | 420 m | 90220.2859 | 23 |  | 0 | 0 | 0
2.4.3.22 | 440 m | 90220.2859 | 23 |  | 0 | 0 | 0
2.4.3.23 | 460 m | 90220.2859 | 23 |  | 0 | 0 | 0
2.4.3.24 | 480 m | 90220.2859 | 23 |  | 0 | 0 | 0
2.4.3.25 | 500 m | 90220.2859 | 23 |  | 0 | 0 | 0
2.4.3.26 | 520 m | 90220.2859 | 24 |  | 0 | 0 | 0
2.4.3.27 | 540 m | 90220.2859 | 24 |  | 0 | 0 | 0
2.4.3.28 | 560 m | 90220.2859 | 24 |  | 0 | 0 | 0
2.4.3.29 | 580 m | 90220.2859 | 24 |  | 0 | 0 | 0
2.4.3.30 | 600 m | 90220.2859 | 24 |  | 0 | 0 | 0
2.4.3.31 | 620 m | 90220.2859 | 24 |  | 0 | 0 | 0
2.4.3.32 | 640 m | 90220.2859 | 24 |  | 0 | 0 | 0
2.4.3.33 | 660 m | 90220.2859 | 25 |  | 0 | 0 | 0
2.4.3.34 | 680 m | 90220.2859 | 25 |  | 0 | 0 | 0
2.4.3.35 | 700 m | 90220.2859 | 25 |  | 0 | 0 | 0
2.4.3.36 | 720 m | 90220.2859 | 25 |  | 0 | 0 | 0
2.4.3.37 | 740 m | 90220.2859 | 25 |  | 0 | 0 | 0
2.4.3.38 | 760 m | 90220.2859 | 25 |  | 0 | 0 | 0
2.4.3.39 | 780 m | 90220.2859 | 25 |  | 0 | 0 | 0
2.4.3.40 | 800 m | 90220.2859 | 25 |  | 0 | 0 | 0
2.4.3.41 | 820 m | 90220.2859 | 26 |  | 0 | 0 | 0
2.4.3.42 | 840 m | 90220.2859 | 26 |  | 0 | 0 | 0
2.4.3.43 | 860 m | 90220.2859 | 26 |  | 0 | 0 | 0
2.4.3.44 | 880 m | 90220.2859 | 26 |  | 0 | 0 | 0
2.4.3.45 | 900 m | 90220.2859 | 26 |  | 0 | 0 | 0
2.4.3.46 | 920 m | 90220.2859 | 26 |  | 0 | 0 | 0
2.4.3.47 | 940 m | 90220.2859 | 26 |  | 0 | 0 | 0
2.4.3.48 | 960 m | 90220.2859 | 27 |  | 0 | 0 | 0
2.4.3.49 | 980 m | 90220.2859 | 27 |  | 0 | 0 | 0
2.4.3.50 | 1000 m | 90220.2859 | 27 |  | 0 | 0 | 0
2.4.3.51 | 1020 m | 90220.2859 | 27 |  | 0 | 0 | 0
2.4.3.52 | 1040 m | 90220.2859 | 27 |  | 0 | 0 | 0
2.4.3.53 | 1060 m | 90220.2859 | 27 |  | 0 | 0 | 0
2.4.3.54 | 1080 m | 90220.2859 | 27 |  | 0 | 0 | 0
2.4.3.55 | 1100 m | 90220.2859 | 27 |  | 0 | 0 | 0
2.4.3.56 | 1120 m | 90220.2859 | 28 |  | 0 | 0 | 0
2.4.3.57 | 1140 m | 90220.2859 | 28 |  | 0 | 0 | 0
2.4.3.58 | 1160 m | 90220.2859 | 28 |  | 0 | 0 | 0
2.4.3.59 | 1180 m | 90220.2859 | 28 |  | 0 | 0 | 0
2.4.3.60 | 1200 m | 90220.2859 | 28 |  | 0 | 0 | 0
2.4.3.61 | 1220 m | 90220.2859 | 28 |  | 0 | 0 | 0
2.4.3.62 | 1240 m | 90220.2859 | 28 |  | 0 | 0 | 0
2.4.3.63 | 1260 m | 90220.2859 | 29 |  | 0 | 0 | 0
2.4.3.64 | 1280 m | 90220.2859 | 29 |  | 0 | 0 | 0
2.4.3.65 | 1300 m | 90220.2859 | 29 |  | 0 | 0 | 0
2.4.3.66 | 1320 m | 90220.2859 | 29 |  | 0 | 0 | 0
2.4.3.67 | 1340 m | 90220.2859 | 29 |  | 0 | 0 | 0
2.4.3.68 | 1360 m | 90220.2859 | 29 |  | 0 | 0 | 0
2.4.3.69 | 1380 m | 90220.2859 | 29 |  | 0 | 0 | 0
2.4.3.70 | 1400 m | 90220.2859 | 29 |  | 0 | 0 | 0
2.4.3.71 | 1420 m | 90220.2859 | 30 |  | 0 | 0 | 0
2.4.3.72 | 1440 m | 90220.2859 | 30 |  | 0 | 0 | 0
2.4.3.73 | 1460 m | 90220.2859 | 30 |  | 0 | 0 | 0
2.4.3.74 | 1480 m | 90220.2859 | 30 |  | 0 | 0 | 0
2.4.3.75 | 1500 m | 90220.2859 | 30 |  | 0 | 0 | 0
2.4.3.76 | 1520 m | 90220.2859 | 30 |  | 0 | 0 | 0
2.4.3.77 | 1540 m | 90220.2859 | 30 |  | 0 | 0 | 0
2.4.3.78 | 1560 m | 90220.2859 | 30 |  | 0 | 0 | 0
2.4.3.79 | 1580 m | 90220.2859 | 30 |  | 0 | 0 | 0
2.4.3.80 | 1583 m | 13533.0429 | 30 |  | 0 | 0 | 0
2.4.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi I ploca, drenazni sistem)
2.4.4.1 | 200 m | 80000 | 23 |  | 0 | 0 | 0
2.4.4.2 | 400 m | 80000 | 24 |  | 0 | 0 | 0
2.4.4.3 | 600 m | 80000 | 26 |  | 0 | 0 | 0
2.4.4.4 | 800 m | 80000 | 27 |  | 0 | 0 | 0
2.4.4.5 | 1000 m | 80000 | 28 |  | 0 | 0 | 0
2.4.4.6 | 1200 m | 80000 | 29 |  | 0 | 0 | 0
2.4.4.7 | 1400 m | 80000 | 30 |  | 0 | 0 | 0
2.4.4.8 | 1583 m | 73200 | 31 |  | 0 | 0 | 0
2.4.5 | Construction of pavement/ Izgradnja kolovoza
2.4.5.1 | Left tube/ Lijeva cijev
0-500 m
2.4.5.1.1 | Layer/Sloj 1 | 36324.46 | 34 |  | 0 | 0 | 0
2.4.5.1.2 | Layer/Sloj 2 | 36324.46 | 35 |  | 0 | 0 | 0
2.4.5.1.3 | Layer/Sloj 3 | 40865.02 | 35 |  | 0 | 0 | 0
500-829 m
2.4.5.1.4 | Layer/Sloj 1 | 23901.5 | 34 |  | 0 | 0 | 0
2.4.5.1.5 | Layer/Sloj 2 | 23901.5 | 35 |  | 0 | 0 | 0
2.4.5.1.6 | Layer/Sloj 3 | 26889.18 | 35 |  | 0 | 0 | 0
2.4.5.2 | Right tube/ Desna cijev
0-500 m
2.4.5.2.1 | Layer/Sloj 1 | 36324.46 | 34 |  | 0 | 0 | 0
2.4.5.2.2 | Layer/Sloj 2 | 36324.46 | 35 |  | 0 | 0 | 0
2.4.5.2.3 | Layer/Sloj 3 | 40865.02 | 35 |  | 0 | 0 | 0
500-800 m
2.4.5.2.4 | Layer/Sloj 1 | 21794.68 | 34 |  | 0 | 0 | 0
2.4.5.2.5 | Layer/Sloj 2 | 21794.68 | 35 |  | 0 | 0 | 0
2.4.5.2.6 | Layer/Sloj 3 | 24519.02 | 35 |  | 0 | 0 | 0
2.4.6 | Tunnel facilities/ Tunelski objekti
2.4.6.1 | Construction of Power Station/ Izgradnja elektro-stanice | 249149.36 | 32 |  | 0 | 0 | 0
2.4.6.2 | Construction of antifire reservoir/ Izgradnja protivpožarnog rezervoara | 86312.55 | 33 |  | 0 | 0 | 0
2.4.7 | Tunnel Equipment / Tunelska oprema
2.4.7.1 | Right tube/ Desna cijev
2.4.7.1.1 | 90% (Equipment installed/Oprema postavljena) | 800708.5 | 36 |  | 0 | 0 | 0
2.4.7.1.2 | 10% (Equipment tested/Oprema ispitana) | 88967.61 | 37 |  | 0 | 0 | 0
2.4.7.2 | Left tube/ Lijeva cijev
2.4.7.2.1 | 90% (Equipment installed/Oprema postavljena) | 829734.19 | 37 |  | 0 | 0 | 0
2.4.7.2.2 | 10% (Equipment tested/Oprema ispitana) | 92192.69 | 38 |  | 0 | 0 | 0
| Sub Total / Suma stavke 2.4 | 16770010.76 |  |  | 3630489.2421 | 708224.4753 | 4338713.7174
Cost Center/ Troškovno mjesto 2.5 | Road Works/ Radovi na putevima (LK5+991.612—LK6+440.00, RK5+949.377—RK6+435.000)
Completion of/Završetak:
2.5.1 | Subgrade/Posteljica
2.5.1.1.1 | RK5+947.377 - RK6+197.377 (Inc.0 - 250 m (LK&RK) | 58310.2389 | 17 |  | 0 | 0 | 0
2.5.1.1.2 | RK6+197.377 - RK6+435.000 (Inc. 250 - 448.388m (LK); 250 - 487.623m (RK) | 50847.8111 | 18 |  | 0 | 0 | 0
2.5.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and 4m height /Na svakih 250m I visini od 4m |  | 34
2.5.1.2.1 | 5+5947.38 -6+197.38,layers 1,2,3,4,5,6,7,8,9
2.5.1.2.1.1 | 5+5947.38 -6+197.38,layer 1 | 81006.9208 |  |  | 0 | 0 | 0
2.5.1.2.1.2 | 5+5947.38 -6+197.38,layer 2 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.2.1.3 | 5+5947.38 -6+197.38,layer 3 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.2.1.4 | 5+5947.38 -6+197.38,layer 4 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.2.1.5 | 5+5947.38 -6+197.38,layer 5 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.2.1.6 | 5+5947.38 -6+197.38,layer 6 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.2.1.7 | 5+5947.38 -6+197.38,layer 7 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.2.1.8 | 5+5947.38 -6+197.38,layer 8 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.2.1.9 | 5+5947.38 -6+197.38,layer 9 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.2.2 | 6+197.38 - 6+435,00, layers 10.11.12.13.14.15
2.5.1.2.2.10 | 6+197.38 - 6+435,00, layer 10 | 58936.9238 |  |  | 0 | 0 | 0
2.5.1.2.2.11 | 6+197.38 - 6+435,00, layer 11 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.2.2.12 | 6+197.38 - 6+435,00, layer 12 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.2.2.13 | 6+197.38 - 6+435,00, layer 13 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.2.2.14 | 6+197.38 - 6+435,00, layer 14 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.2.2.15 | 6+197.38 - 6+435,00, layer 15 | 100318.1681 |  |  | 0 | 0 | 0
2.5.1.3 | Road Foundation/ Temelj puta
2.5.1.3.1 | 0 - 250 m, Right side/ Desna strana | 23136 | 34 |  | 0 | 0 | 0
2.5.1.3.2 | 0 - 250 m, Left side/ Lijeva strana | 23136 | 35 |  | 0 | 0 | 0
2.5.1.3.3 | 250 - 487.623 m, Right side/ Desna strana | 21990.326 | 36 |  | 0 | 0 | 0
2.5.1.3.4 | 250 - 448.388 m, Left side/ Lijeva strana | 18358.864 | 37 |  | 0 | 0 | 0
2.5.2 | Engineering structures/ Inžinjerske konstrukcije
2.5.2.1 | Reinforced earth wall / Ojačani zemljani zid The milestone is 2.20 m height of each layer and no matter on the length / Reper je visina 2.2m za svaki sloj, bez obzira na dužinu
2.5.2.1.1 | Reinforced soil retaining wall RK 5+960 - RK 6+372 / Potporni zid od armirane zemlje
2.5.2.1.1.1 | Layer/Sloj 1 (0.0 -2.2 m height) | 195770.6285 |  |  | 0 | 0 | 0
2.5.2.1.1.2 | Layer/Sloj 2 (2.2 -4.4 m height) | 195770.6285 |  |  | 0 | 0 | 0
2.5.2.1.1.3 | Layer/Sloj 3 (4.4 -6.6 m height) | 195770.6285 |  |  | 0 | 0 | 0
2.5.2.1.1.4 | Layer/Sloj 4 (6.6 -8.8m height) | 195770.6285 |  |  | 0 | 0 | 0
2.5.2.1.1.5 | Layer/Sloj 5 (8.8 -11.0 m height) | 195770.6285 |  |  | 0 | 0 | 0
2.5.2.1.1.6 | Layer/Sloj 6 (11.0 -13.2 m height) | 195770.6285 |  |  | 0 | 0 | 0
2.5.2.1.1.7 | Layer/Sloj 7 (13.2 -15.4 m height) | 195770.6285 |  |  | 0 | 0 | 0
2.5.2.1.1.8 | Layer/Sloj 8 (15.4 -17.6 m height) | 195770.6285 |  |  | 0 | 0 | 0
2.5.2.1.1.9 | Layer/Sloj 9 (17.6 -19.8 m height) | 195770.6285 |  |  | 0 | 0 | 0
2.5.2.1.1.10 | Layer/Sloj 10 (19.8 -22.0 m height) | 195770.6285 |  |  | 0 | 0 | 0
2.5.2.1.1.11 | Layer/Sloj 11 (22.0 -23.47m height) | 130810.3745 |  |  | 0 | 0 | 0
2.5.2.2 | Culvert/ Propust
2.5.2.2.1 | Culvert RK5+971.58 length 64.6m | 16473.47 | 28 |  | 0 | 0 | 0
2.5.3 | Water drainage/ Drenaža vode
2.5.3.1 | per one direction of 500m / Na 500m dužine u jednom pravcu
| LK5+991.612 - LK6+440.000 ( 448.388 m) | 189514.0197 | 36 |  | 0 | 0 | 0
| RK5+947.377 - RK6+435.000 ( 487.623 m) | 206096.9403 | 36 |  | 0 | 0 | 0
2.5.4 | Pavement structure/ Kolovozna konstrukcija
2.5.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 Right side/ Desna strana | 59303.77 | 38 |  | 0 | 0 | 0
2.5.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 Left side/ Lijeva strana | 54532.09 | 38 |  | 0 | 0 | 0
2.5.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 Right side/ Desna strana | 59303.77 | 39 |  | 0 | 0 | 0
2.5.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 Left side/ Lijeva strana | 54532.09 | 39 |  | 0 | 0 | 0
2.5.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 Right side/ Desna strana | 65896.99 | 40 |  | 0 | 0 | 0
2.5.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 Left side/ Lijeva strana | 60594.81 | 40 |  | 0 | 0 | 0
| Sub Total / Suma stavke 2.5 | 4494623.88 |  |  | 0 | 0 | 0
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 02 | 26625778.48 |  |  | 3973706.7121 | 785738.3458 | 4759445.0578

## COST CENTER 03
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
COST CENTER 03/TROŠKOVNI CENTAR 03 rev Open Route
Cost Center No./ Troškovno mjesto Br. | 03 | Subsection/Podsekcija 1.3 (LK6+440.000-LK7+445.350, RK6+435.000 - RK7+440.63)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost Center/Troškovno mjesto 3.1 | Road Works/Radovi na putevima (LK6+440.000 - LK6+482.138, RK6+435.000 - RK6+476.572)
Completion of/Završetak:
3.1.1 | Subgrade/ Posteljica
3.1.1.1 | Top soil removal/ Uklanjanje humusa
3.1.1.1.1 | RK6+435.000—RK6+476.572 (Inc. 0 - 42.138m (LK); 0 - 41.572m (RK)) | 5489.6113 | 18 |  | 0 | 0 | 0
3.1.1.2 | Earthworks/ Zemljani radovi
At every 250 m and 4 m height /Na svakih 250m visini od 4m
3.1.1.2.1 | 6+435.00 - 6+476.57 layers 1,2,3
3.1.1.2.1.1 | 6+435.00 - 6+476.57 layers 1 | 12292.4565 |  |  | 0 | 0 | 0
3.1.1.2.1.2 | 6+435.00 - 6+476.57 layers 2 | 30165.5375 |  |  | 0 | 0 | 0
3.1.1.2.1.3 | 6+435.00 - 6+476.57 layers 3 | 30165.5375 |  |  | 0 | 0 | 0
3.1.1.3 | Road Foundation/ Temelj puta
3.1.1.3.1 | 0 - 41.572 m, Right side/ Desna strana | 2163.3844 | 32 |  | 0 | 0 | 0
3.1.1.3.2 | 0 - 42.138 m, Left side/ Lijeva strana | 2192.8387 | 33 |  | 0 | 0 | 0
3.1.2 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
3.1.2.1 | LK6+440.000—LK6+482.138 (42.138 m) | 10015.0002 | 33 |  | 0 | 0 | 0
3.1.2.2 | RK6+435.000—RK6+476.572 ( 41.572m) | 9880.4782 | 33 |  | 0 | 0 | 0
3.1.3 | Pavement structure/ Kolovozna konstrukcija
3.1.3.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 Right side/ Desna strana | 2843.0807 | 34 |  | 0 | 0 | 0
3.1.3.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 Left side/ Lijeva strana | 2881.789 | 35 |  | 0 | 0 | 0
3.1.3.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 Right side/ Desna strana | 2843.0807 | 36 |  | 0 | 0 | 0
3.1.3.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 Left side/ Lijeva strana | 2881.789 | 37 |  | 0 | 0 | 0
3.1.3.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 Right side/ Desna strana | 3159.1613 | 38 |  | 0 | 0 | 0
3.1.3.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 Left side/ Lijeva strana | 3202.1547 | 39 |  | 0 | 0 | 0
| Sub Total / Suma stavke 3.1 | 120175.8996 |  |  | 0 | 0 | 0
Cost Center/Troškovno mjesto 3.2 | Construction of bridge Moracica/ Izgradnja mosta Moračica LK6+482.138- LK 7+442.333, RK 6+476.572- RK 7+436.377
Completion of/Završetak:
3.2.1 | Foundation excavation/ Iskopavanje temelja
3.2.1.1 | A0 | 40072.89 | 16 | 15 | 40072.89 | 0 | 40072.89
3.2.1.2 | P1 | 245168.2 | 22 | 26 | 245168.2 | 0 | 245168.2
3.2.1.3 | P2 | 273692.3 | 15 | 13 | 273692.3 | 0 | 273692.3
3.2.1.4 | P3 | 273692.3 | 15 | 12 | 273692.3 | 0 | 273692.3
3.2.1.5 | P4 | 273692.3 | 15 | 13 | 273692.3 | 0 | 273692.3
3.2.1.6 | P5 | 245029.07 | 17 | 22 | 245029.07 | 0 | 245029.07
3.2.1.7 | A1 | 40072.89 | 17 | 29 | 40072.89 | 0 | 40072.89
3.2.2 | Foundation construction/ Izgradnja temelja
A0
3.2.2.1 | A0 | 648026.97 | 17 | 19 | 648026.97 | 0 | 648026.97
P1
3.2.2.2 | P1 - stage/ faza 1 | 984216.58 | 23 | 26 | 984216.58 | 0 | 984216.58
3.2.2.3 | P1 - stage/ faza 2 | 661961.27 | 24 | 26 | 661961.27 | 0 | 661961.27
3.2.2.4 | P1 - stage/ faza 3 | 403691.67 | 25 | 26 | 403691.67 | 0 | 403691.67
P2
3.2.2.5 | P2 - stage/ faza 1 | 1081940.22 | 16 | 18 | 1081940.22 | 0 | 1081940.22
3.2.2.6 | P2 - stage/ faza 2 | 742234.26 | 17 | 19 | 742234.26 | 0 | 742234.26
3.2.2.7 | P2 - stage/ faza 3 | 464187.25 | 18 | 19 | 464187.25 | 0 | 464187.25
P3
3.2.2.8 | P3 - stage/ faza 1 | 1081940.22 | 15 | 17 | 1081940.22 | 0 | 1081940.22
3.2.2.9 | P3 - stage/ faza 2 | 742234.26 | 16 | 19 | 742234.26 | 0 | 742234.26
3.2.2.10 | P3 - stage/ faza 3 | 464187.25 | 17 | 19 | 464187.25 | 0 | 464187.25
P4
3.2.2.11 | P4 - stage/ faza 1 | 1081940.22 | 16 | 19 | 1081940.22 | 0 | 1081940.22
3.2.2.12 | P4 - stage/ faza 2 | 742234.26 | 17 | 20 | 742234.26 | 0 | 742234.26
3.2.2.13 | P4 - stage/ faza 3 | 464187.25 | 18 | 21 | 464187.25 | 0 | 464187.25
P5
3.2.2.14 | P5 - stage/ faza 1 | 984216.58 | 22 | 24 | 984216.58 | 0 | 984216.58
3.2.2.15 | P5 - stage/ faza 2 | 661961.27 | 22 | 24 | 661961.27 | 0 | 661961.27
3.2.2.16 | P5 - stage/ faza 3 | 402528.29 | 23 | 23 | 402528.29 | 0 | 402528.29
A1
3.2.2.17 | A1 | 648026.96 | 17 | 29 | 648026.96 | 0 | 648026.96
3.2.3 | Abutments and Piers elevation/ Elevacija mosnih stubova
A0
3.2.3.1 | A0 | 769083.34 | 23 | 22 | 769083.34 | 0 | 769083.34
P1
3.2.3.2 | P1 - stage/ faza 1 | 582547.0882 | 27 | 28 | 582547.09 | 0 | 582547.09
3.2.3.2/1 | P1- stage 1 - first segment (6.1m)
3.2.3.2/2 | P1- stage 1 - second segment (6.0 m)
3.2.3.3 | P1 - stage/ faza 2 | 577732.6494 | 28 | 28 | 577732.65 | 0 | 577732.65
3.2.3.3/1 | P1- stage 2 - first segment (6.0 m)
3.2.3.3/2 | P1- stage 2 - second segment (6.0 m)
3.2.3.4 | P1 - stage/ faza 3 | 577732.6494 | 29 | 29 | 577732.6494 | 0 | 577732.6494
3.2.3.4/1 | P1- stage 3 - first segment (6.0 m)
3.2.3.4/2 | P1- stage 3 - second segment (6.0 m)
3.2.3.5 | P1 - stage/ faza 4 | 621062.5981 | 30 | 30 | 0 | 621062.5981 | 621062.5981
3.2.3.5/1 | P1- stage 4 - first segment (6.0 m)
3.2.3.5/2 | P1- stage 4 - second segment (2.9 m)
3.2.3.5/3 | P1- stage 4 - third segment (4.0 m)
3.2.3.4/3 | P1- stage 3 - diaphragm
3.2.3.6 | P1 - stage/ faza 5 | 96288.7749 | 31 |  | 0 | 0 | 0
3.2.3.6/1-1 | P1- stage 5 - first segment (2.0 m)
P2
3.2.3.7 | P2 - stage/ faza 1 | 613840.69 | 19 | 22 | 613840.69 | 0 | 613840.69
3.2.3.7/1 | P2- stage 1 - first segment (6.1 m)
3.2.3.7/2 | P2- stage 1 - second segment (6.0 m)
3.2.3.8 | P2 - stage/ faza 2 | 585454.9934 | 20 | 24 | 585454.99 | 0 | 585454.99
3.2.3.8/1 | P2- stage 2 - first segment (6.0 m)
3.2.3.8/2 | P2- stage 2 - second segment (6.0 m)
3.2.3.9 | P2 - stage/ faza 3 | 585454.9934 | 21 | 24 | 585454.99 | 0 | 585454.99
3.2.3.9/1 | P2- stage 3 - first segment (6.0 m)
3.2.3.9/2 | P2- stage 3 - second segment (6.0 m)
3.2.3.10 | P2 - stage/ faza 4 | 585454.9934 | 22 | 24 | 585454.99 | 0 | 585454.99
3.2.3.10/1 | P2- stage 4 - first segment (6.0 m)
3.2.3.10/2 | P2- stage 4 - second segment (6.0 m)
3.2.3.9/3 | P2- stage 3 - diaphragm
3.2.3.11 | P2 - stage/ faza 5 | 604970.1598 | 23 | 26 | 604970.16 | 0 | 604970.16
3.2.3.11/1 | P2- stage 5 - first segment (4.4 m)
3.2.3.11/2 | P2- stage 5 - second segment (6.0 m)
3.2.3.11/3 | P2- stage 5 - third segment (2.0 m)
3.2.3.12 | P2 - stage/ faza 6 | 590333.785 | 24 | 27 | 590333.78 | 0 | 590333.78
3.2.3.12/1 | P2- stage 6 - first segment (6.1 m)
3.2.3.12/2 | P2- stage 6 - second segment (6.0 m)
3.2.3.13 | P2 - stage/ faza 7 | 585454.9934 | 25 | 27 | 585454.99 | 0 | 585454.99
3.2.3.13/1 | P2- stage 7 - first segment (6.0 m)
3.2.3.13/2 | P2- stage 7 - second segment (6.0 m)
3.2.3.14 | P2 - stage/ faza 8 | 585454.9934 | 26 | 28 | 585454.99 | 0 | 585454.99
3.2.3.14/1 | P2- stage 8 - first segment (6.0 m)
3.2.3.14/2 | P2- stage 8 - second segment (6.0 m)
3.2.3.15 | P2 - stage/ faza 9 | 585454.9934 | 27 | 28 | 585454.99 | 0 | 585454.99
3.2.3.15/1 | P2- stage 9 - first segment (6.0 m)
3.2.3.15/2 | P2- stage 9 - second segment (6.0 m)
3.2.3.16 | P2 - stage/ faza 10 | 585454.9934 | 28 | 29 | 585454.9934 | 0 | 585454.9934
3.2.3.16/1 | P2- stage 10- first segment (6.0 m)
3.2.3.16/2 | P2- stage 10 - second segment (6.0 m)
3.2.3.15/3 | P2- stage 9 - diaphragm
3.2.3.17 | P2 - stage/ faza 11 | 585454.9934 | 29 | 29 | 585454.9934 | 0 | 585454.9934
3.2.3.17/1 | P2- stage 11 - first segment (6.0 m)
3.2.3.17/2 | P2- stage 11 - second segment (6.0 m)
3.2.3.18 | P2 - stage/ faza 12 | 580576.2017 | 30 | 29 | 580576.2017 | 0 | 580576.2017
3.2.3.18/1-1 | P2- stage 12 - first segment (6.0 m)
3.2.3.18/2-1 | P2- stage 12 - second segment (5.9 m)
3.2.3.19 | P2 - stage/ faza 13 | 292727.4967 | 31 |  | 0 | 0 | 0
3.2.3.19/1 | P2- stage 13 - first segment (4.0 m)
3.2.3.19/2 | P2- stage 13 - second segment (2.0 m)
P3
3.2.3.20 | P3 - stage/ faza 1 | 613840.69 | 19 | 21 | 613840.69 | 0 | 613840.69
3.2.3.18/1 | P3- stage 1 - first segment (6.1 m)
3.2.3.18/2 | P3- stage 1 - second segment (6.0 m)
3.2.3.21 | P3 - stage/ faza 2 | 643110.461 | 20 | 24 | 643110.46 | 0 | 643110.46
3.2.3.21/1 | P3- stage 2 - first segment (6.0 m)
3.2.3.21/2 | P3- stage 2 - second segment (6.0 m)
3.2.3.22 | P3 - stage/ faza 3 | 643110.461 | 21 | 24 | 643110.46 | 0 | 643110.46
3.2.3.22/1 | P3- stage 3 - first segment (6.0 m)
3.2.3.22/2 | P3- stage 3 - second segment (6.0 m)
3.2.3.23 | P3 - stage/ faza 4 | 643110.461 | 22 | 24 | 643110.46 | 0 | 643110.46
3.2.3.23/1 | P3- stage 4 - first segment (6.0 m)
3.2.3.23/2 | P3- stage 4 - second segment (6.0 m)
3.2.3.22/3 | P3- stage 3 diaphragm
3.2.3.24 | P3 - stage/ faza 5 | 643110.461 | 23 | 25 | 643110.46 | 0 | 643110.46
3.2.3.24/1 | P3- stage 5 - first segment (6.0 m)
3.2.3.24/2 | P3- stage 5 - second segment (6.0 m)
3.2.3.25 | P3 - stage/ faza 6 | 584158.6687 | 24 | 26 | 584158.67 | 0 | 584158.67
3.2.3.25/1 | P3- stage 6 - first segment (2.9 m)
3.2.3.25/2 | P3- stage 6 - second segment (6.0 m)
3.2.3.25/3 | P3- stage 6 - thired segment (2.0 m)
3.2.3.26 | P3 - stage/ faza 7 | 648469.7148 | 24 | 27 | 648469.71 | 0 | 648469.71
3.2.3.26/1 | P3- stage 7 - first segment (6.1 m)
3.2.3.26/2 | P3- stage 7 - second segment (6.0 m)
3.2.3.27 | P3 - stage/ faza 8 | 643110.461 | 25 | 27 | 643110.46 | 0 | 643110.46
3.2.3.27/1 | P3- stage 8 - first segment (6.0 m)
3.2.3.27/2 | P3- stage 8 - second segment (6.0 m)
3.2.3.28 | P3 - stage/ faza 9 | 643110.461 | 25 | 28 | 643110.46 | 0 | 643110.46
3.2.3.28/1 | P3- stage 9 - first segment (6.0 m)
3.2.3.28/2 | P3- stage 9 - second segment (6.0 m)
3.2.3.29 | P3 - stage/ faza 10 | 643110.461 | 26 | 29 | 643110.46 | 0 | 643110.46
3.2.3.29/1 | P3- stage 10 - first segment (6.0 m)
3.2.3.29/2 | P3- stage 10 - second segment (6.0 m)
3.2.3.30 | P3 - stage/ faza 11 | 643110.461 | 27 | 29 | 643110.46 | 0 | 643110.46
3.2.3.30/1 | P3- stage 11 - first segment (6.0 m)
3.2.3.30/2 | P3- stage 11 - second segment (6.0 m)
3.2.3.29/3 | P3- stage 10 diaphragm
3.2.3.31 | P3 - stage/ faza 12 | 643110.461 | 28 | 30 | 0 | 643110.461 | 643110.461
3.2.3.31/1 | P3- stage 12 - first segment (6.0 m)
3.2.3.31/2 | P3- stage 12 - second segment (6.0 m)
3.2.3.32 | P3 - stage/ faza 13 | 637751.2071 | 29 | 30 | 0 | 637751.2071 | 637751.2071
3.2.3.32/1 | P3- stage 13 - first segment (6.0 m)
3.2.3.32/2 | P3- stage 13 - second segment (5.9 m)
3.2.3.33 | P3 - stage/ faza 14 | 321555.2305 | 30 |  | 0 | 0 | 0
3.2.3.33/1 | P3- stage 14 - first segment (4.0 m)
3.2.3.33/2 | P3- stage 14 - second segment (2.0 m)
P4
3.2.3.34 | P4 - stage/ faza 1 | 613840.69 | 19 | 22 | 613840.69 | 0 | 613840.69
3.2.3.34/1 | P4- stage 1 - first segment (6.1m)
3.2.3.34/2 | P4- stage 1 - second segment (6.0 m)
3.2.3.35 | P4 - stage/ faza 2 | 640605.7107 | 20 | 24 | 640605.71 | 0 | 640605.71
3.2.3.35/1 | P4- stage 2 - first segment (6.0 m)
3.2.3.35/2 | P4- stage 2 - second segment (6.0 m)
3.2.3.36 | P4 - stage/ faza 3 | 640605.7107 | 21 | 24 | 640605.71 | 0 | 640605.71
3.2.3.36/1 | P4- stage 3 - first segment (6.0 m)
3.2.3.36/2 | P4- stage 3 - second segment (6.0 m)
3.2.3.37 | P4 - stage/ faza 4 | 640605.7107 | 22 | 24 | 640605.71 | 0 | 640605.71
3.2.3.37/1 | P4- stage 4 - first segment (6.0 m)
3.2.3.37/2 | P4- stage 4 - second segment (6.0 m)
3.2.3.36/3 | P4- stage 3 diaphragm
3.2.3.38 | P4 - stage/ faza 5 | 742034.9482 | 23 | 26 | 742034.95 | 0 | 742034.95
3.2.3.38/1 | P4- stage 5 - first segment (5.9 m)
3.2.3.38/2 | P4- stage 5 - second segment (6.0 m)
3.2.3.38/3 | P4- stage 5 - third segment (2.0 m)
3.2.3.39 | P4 - stage/ faza 6 | 645944.0916 | 24 | 27 | 645944.09 | 0 | 645944.09
3.2.3.39/1 | P4- stage 6 - first segment (6.1 m)
3.2.3.39/2 | P4- stage 6 - second segment (6.0 m)
3.2.3.40 | P4 - stage/ faza 7 | 640605.7107 | 25 | 28 | 640605.71 | 0 | 640605.71
3.2.3.40/1 | P4- stage 7 - first segment (6.0 m)
3.2.3.40/2 | P4- stage 7 - second segment (6.0 m)
3.2.3.41 | P4 - stage/ faza 8 | 640605.7107 | 26 | 28 | 640605.71 | 0 | 640605.71
3.2.3.41/1 | P4- stage 8 - first segment (6.0 m)
3.2.3.41/2 | P4- stage 8 - second segment (6.0 m)
3.2.3.42 | P4 - stage/ faza 9 | 640605.7107 | 26 | 28 | 640605.71 | 0 | 640605.71
3.2.3.42/1 | P4- stage 9 - first segment (6.0 m)
3.2.3.42/2 | P4- stage 9 - second segment (6.0 m)
3.2.3.43 | P4 - stage/ faza 10 | 640605.7107 | 27 | 29 | 640605.71 | 0 | 640605.71
3.2.3.43/1 | P4- stage 10 - first segment (6.0 m)
3.2.3.43/2 | P4- stage 10 - second segment (6.0 m)
3.2.3.42/3 | P4- stage 9 diaphragm
3.2.3.44 | P4 - stage/ faza 11 | 640605.7107 | 27 | 29 | 640605.71 | 0 | 640605.71
3.2.3.44/1 | P4- stage 11 - first segment (6.0 m)
3.2.3.44/2 | P4- stage 11 - second segment (6.0 m)
3.2.3.45 | P4 - stage/ faza 12 | 635267.3297 | 28 | 30 | 0 | 635267.3297 | 635267.3297
3.2.3.45/1 | P4- stage 12 - first segment (6.0 m)
3.2.3.45/2 | P4- stage 12 - second segment (5.9 m)
3.2.3.46 | P4 - stage/ faza 13 | 320302.8553 | 29 |  | 0 | 0 | 0
3.2.3.46/1 | P4- stage 13 - first segment (4.0 m)
3.2.3.46/2 | P4- stage 13 - second segment (2.0 m)
P5
3.2.3.47 | P5 - stage/ faza 1 | 571344.0268 | 25 | 26 | 571344.03 | 0 | 571344.03
3.2.3.47/1 | P5- stage 1 - first segment (6.1 m)
3.2.3.47/2 | P5- stage 1- second segment (6.0 m)
3.2.3.48 | P5 - stage/ faza 2 | 566622.1754 | 26 | 27 | 566622.18 | 0 | 566622.18
3.2.3.48/1 | P5- stage 2 - first segment (6.0 m)
3.2.3.48/2 | P5- stage 2- second segment (6.0 m)
3.2.3.49 | P5 - stage/ faza 3 | 566622.1754 | 27 | 28 | 566622.18 | 0 | 566622.18
3.2.3.49/1 | P5- stage 3 - first segment (6.0 m)
3.2.3.49/2 | P5- stage 3- second segment (6.0 m)
3.2.3.50 | P5 - stage/ faza 4 | 566622.1754 | 28 | 28 | 566622.18 | 0 | 566622.18
3.2.3.50/1 | P5- stage 4 - first segment (6.0 m)
3.2.3.50/2 | P5- stage 4 - second segment (6.0 m)
3.2.3.49/3 | P5- stage 3 diaphragm
3.2.3.51 | P5 - stage/ faza 5 | 566622.1754 | 29 | 29 | 566622.1754 | 0 | 566622.1754
3.2.3.51/1 | P5- stage 5 - first segment (6.0 m)
3.2.3.51/2 | P5- stage 5 - second segment (6.0 m)
3.2.3.52 | P5 - stage/ faza 6 | 561900.3239 | 30 | 30 | 0 | 561900.3239 | 561900.3239
3.2.3.52/1 | P5- stage 6 - first segment (5.9 m)
3.2.3.52/2 | P5- stage 6 - second segment (6.0 m)
3.2.3.53 | P5 - stage/ faza 7 | 283311.0877 | 31 |  | 0 | 0 | 0
3.2.3.53/1 | P5- stage 7 - first segment (4.0 m)
3.2.3.53/2 | P5- stage 7 - second segment (2.0 m)
A1
3.2.3.50 | A1 | 769083.34 | 23 |  | 0 | 0 | 0
3.2.4 | Bridge deck superstructure/ Gornji stroj mosne ploče
P1
3.2.4.1 | P1 - stage/ faza 1 | 885906.43 | 32 |  | 0 | 0 | 0
3.2.4.2 | P1 - stage/ faza 2-1 | 265381.66 | 33 |  | 0 | 0 | 0
3.2.4.3 | P1 - stage/ faza 2-2 | 29486.85 | 33 |  | 0 | 0 | 0
3.2.4.4 | P1 - stage/ faza 3-1 | 320799.6 | 34 |  | 0 | 0 | 0
3.2.4.5 | P1 - stage/ faza 3-2 | 35644.4 | 34 |  | 0 | 0 | 0
3.2.4.6 | P1 - stage/ faza 4-1 | 298944.64 | 35 |  | 0 | 0 | 0
3.2.4.7 | P1 - stage/ faza 4-2 | 33216.07 | 35 |  | 0 | 0 | 0
3.2.4.8 | P1 - stage/ faza 5-1 | 280133.76 | 36 |  | 0 | 0 | 0
3.2.4.9 | P1 - stage/ faza 5-2 | 31125.97 | 36 |  | 0 | 0 | 0
3.2.4.10 | P1 - stage/ faza 6-1 | 312916.2 | 37 |  | 0 | 0 | 0
3.2.4.11 | P1 - stage/ faza 6-2 | 34768.47 | 37 |  | 0 | 0 | 0
3.2.4.12 | P1 - stage/ faza 7-1 | 293012.58 | 38 |  | 0 | 0 | 0
3.2.4.13 | P1 - stage/ faza 7-2 | 32556.95 | 38 |  | 0 | 0 | 0
3.2.4.14 | P1 - stage/ faza 8-1 | 272562.58 | 39 |  | 0 | 0 | 0
3.2.4.15 | P1 - stage/ faza 8-2 | 30284.73 | 39 |  | 0 | 0 | 0
3.2.4.16 | P1 - stage/ faza 9-1 | 294027.27 | 40 |  | 0 | 0 | 0
3.2.4.17 | P1 - stage/ faza 9-2 | 32669.7 | 40 |  | 0 | 0 | 0
3.2.4.18 | P1 - stage/ faza 10-1 | 287939.11 | 41 |  | 0 | 0 | 0
3.2.4.19 | P1 - stage/ faza 10-2 | 31993.23 | 41 |  | 0 | 0 | 0
3.2.4.20 | P1 - stage/ faza 11-1 | 182879.19 | 45 |  | 0 | 0 | 0
3.2.4.21 | P1 - stage/ faza 11-2 | 20319.91 | 45 |  | 0 | 0 | 0
P2
3.2.4.22 | P2 - stage/ faza 1 | 930310.16 | 32 |  | 0 | 0 | 0
3.2.4.23 | P2 - stage/ faza 2-1 | 307374.41 | 33 |  | 0 | 0 | 0
3.2.4.24 | P2 - stage/ faza 2-2 | 34152.71 | 33 |  | 0 | 0 | 0
3.2.4.25 | P2 - stage/ faza 3-1 | 341874.03 | 34 |  | 0 | 0 | 0
3.2.4.26 | P2 - stage/ faza 3-2 | 37986 | 34 |  | 0 | 0 | 0
3.2.4.27 | P2 - stage/ faza 4-1 | 322985.1 | 35 |  | 0 | 0 | 0
3.2.4.28 | P2 - stage/ faza 4-2 | 35887.23 | 35 |  | 0 | 0 | 0
3.2.4.29 | P2 - stage/ faza 5-1 | 306281.66 | 36 |  | 0 | 0 | 0
3.2.4.30 | P2 - stage/ faza 5-2 | 34031.3 | 36 |  | 0 | 0 | 0
3.2.4.31 | P2 - stage/ faza 6-1 | 308623.27 | 37 |  | 0 | 0 | 0
3.2.4.32 | P2 - stage/ faza 6-2 | 34291.47 | 37 |  | 0 | 0 | 0
3.2.4.33 | P2 - stage/ faza 7-1 | 323843.68 | 38 |  | 0 | 0 | 0
3.2.4.34 | P2 - stage/ faza 7-2 | 35982.63 | 38 |  | 0 | 0 | 0
3.2.4.35 | P2 - stage/ faza 8-1 | 306437.77 | 39 |  | 0 | 0 | 0
3.2.4.36 | P2 - stage/ faza 8-2 | 34048.64 | 39 |  | 0 | 0 | 0
3.2.4.37 | P2 - stage/ faza 9-1 | 288953.8 | 40 |  | 0 | 0 | 0
3.2.4.38 | P2 - stage/ faza 9-2 | 32105.98 | 40 |  | 0 | 0 | 0
3.2.4.39 | P2 - stage/ faza 10-1 | 288017.15 | 41 |  | 0 | 0 | 0
3.2.4.40 | P2 - stage/ faza 10-2 | 32001.91 | 41 |  | 0 | 0 | 0
3.2.4.41 | P2 - stage/ faza 11-1 | 295198.07 | 42 |  | 0 | 0 | 0
3.2.4.42 | P2 - stage/ faza 11-2 | 32799.79 | 42 |  | 0 | 0 | 0
3.2.4.43 | P2 - stage/ faza 12-1 | 283958.38 | 43 |  | 0 | 0 | 0
3.2.4.44 | P2 - stage/ faza 12-2 | 31550.93 | 43 |  | 0 | 0 | 0
3.2.4.45 | P2 - stage/ faza 13-1 | 276465.25 | 44 |  | 0 | 0 | 0
3.2.4.46 | P2 - stage/ faza 13-2 | 30718.36 | 44 |  | 0 | 0 | 0
3.2.4.47 | P2 - stage/ faza 14-1 | 58618.13 | 45 |  | 0 | 0 | 0
3.2.4.48 | P2 - stage/ faza 14-2 | 6513.13 | 45 |  | 0 | 0 | 0
P3
3.2.4.49 | P3 - stage/ faza 1 | 930310.16 | 32 |  | 0 | 0 | 0
3.2.4.50 | P3 - stage/ faza 2-1 | 307374.41 | 33 |  | 0 | 0 | 0
3.2.4.51 | P3 - stage/ faza 2-2 | 34152.71 | 33 |  | 0 | 0 | 0
3.2.4.52 | P3 - stage/ faza 3-1 | 341874.03 | 34 |  | 0 | 0 | 0
3.2.4.53 | P3 - stage/ faza 3-2 | 37986 | 34 |  | 0 | 0 | 0
3.2.4.54 | P3 - stage/ faza 4-1 | 322985.1 | 35 |  | 0 | 0 | 0
3.2.4.55 | P3 - stage/ faza 4-2 | 35887.23 | 35 |  | 0 | 0 | 0
3.2.4.56 | P3 - stage/ faza 5-1 | 306281.66 | 36 |  | 0 | 0 | 0
3.2.4.57 | P3 - stage/ faza 5-2 | 34031.3 | 36 |  | 0 | 0 | 0
3.2.4.58 | P3 - stage/ faza 6-1 | 308623.27 | 37 |  | 0 | 0 | 0
3.2.4.59 | P3 - stage/ faza 6-2 | 34291.47 | 37 |  | 0 | 0 | 0
3.2.4.60 | P3 - stage/ faza 7-1 | 323843.68 | 38 |  | 0 | 0 | 0
3.2.4.61 | P3 - stage/ faza 7-2 | 35982.63 | 38 |  | 0 | 0 | 0
3.2.4.62 | P3 - stage/ faza 8-1 | 306437.77 | 39 |  | 0 | 0 | 0
3.2.4.63 | P3 - stage/ faza 8-2 | 34048.64 | 39 |  | 0 | 0 | 0
3.2.4.64 | P3 - stage/ faza 9-1 | 288953.8 | 40 |  | 0 | 0 | 0
3.2.4.65 | P3 - stage/ faza 9-2 | 32105.98 | 40 |  | 0 | 0 | 0
3.2.4.66 | P3 - stage/ faza 10-1 | 288017.15 | 41 |  | 0 | 0 | 0
3.2.4.67 | P3 - stage/ faza 10-2 | 32001.91 | 41 |  | 0 | 0 | 0
3.2.4.68 | P3 - stage/ faza 11-1 | 295198.07 | 42 |  | 0 | 0 | 0
3.2.4.69 | P3 - stage/ faza 11-2 | 32799.79 | 42 |  | 0 | 0 | 0
3.2.4.70 | P3 - stage/ faza 12-1 | 283958.38 | 43 |  | 0 | 0 | 0
3.2.4.71 | P3 - stage/ faza 12-2 | 31550.93 | 43 |  | 0 | 0 | 0
3.2.4.72 | P3 - stage/ faza 13-1 | 276465.25 | 45 |  | 0 | 0 | 0
3.2.4.73 | P3 - stage/ faza 13-2 | 30718.36 | 45 |  | 0 | 0 | 0
P4
3.2.4.74 | P4 - stage/ faza 1 | 930310.16 | 31 |  | 0 | 0 | 0
3.2.4.75 | P4 - stage/ faza 2-1 | 307374.41 | 32 |  | 0 | 0 | 0
3.2.4.76 | P4 - stage/ faza 2-2 | 34152.71 | 32 |  | 0 | 0 | 0
3.2.4.77 | P4 - stage/ faza 3-1 | 341874.03 | 33 |  | 0 | 0 | 0
3.2.4.78 | P4 - stage/ faza 3-2 | 37986 | 33 |  | 0 | 0 | 0
3.2.4.79 | P4 - stage/ faza 4-1 | 322985.1 | 34 |  | 0 | 0 | 0
3.2.4.80 | P4 - stage/ faza 4-2 | 35887.23 | 34 |  | 0 | 0 | 0
3.2.4.81 | P4 - stage/ faza 5-1 | 306281.66 | 35 |  | 0 | 0 | 0
3.2.4.82 | P4 - stage/ faza 5-2 | 34031.3 | 35 |  | 0 | 0 | 0
3.2.4.83 | P4 - stage/ faza 6-1 | 308623.27 | 36 |  | 0 | 0 | 0
3.2.4.84 | P4 - stage/ faza 6-2 | 34291.47 | 36 |  | 0 | 0 | 0
3.2.4.85 | P4 - stage/ faza 7-1 | 323843.68 | 37 |  | 0 | 0 | 0
3.2.4.86 | P4 - stage/ faza 7-2 | 35982.63 | 37 |  | 0 | 0 | 0
3.2.4.87 | P4 - stage/ faza 8-1 | 306437.77 | 38 |  | 0 | 0 | 0
3.2.4.88 | P4 - stage/ faza 8-2 | 34048.64 | 38 |  | 0 | 0 | 0
3.2.4.89 | P4 - stage/ faza 9-1 | 288953.8 | 39 |  | 0 | 0 | 0
3.2.4.90 | P4 - stage/ faza 9-2 | 32105.98 | 39 |  | 0 | 0 | 0
3.2.4.91 | P4 - stage/ faza 10-1 | 288017.15 | 40 |  | 0 | 0 | 0
3.2.4.92 | P4 - stage/ faza 10-2 | 32001.91 | 40 |  | 0 | 0 | 0
3.2.4.93 | P4 - stage/ faza 11-1 | 295198.07 | 41 |  | 0 | 0 | 0
3.2.4.94 | P4 - stage/ faza 11-2 | 32799.79 | 41 |  | 0 | 0 | 0
3.2.4.95 | P4 - stage/ faza 12-1 | 283958.38 | 42 |  | 0 | 0 | 0
3.2.4.96 | P4 - stage/ faza 12-2 | 31550.93 | 42 |  | 0 | 0 | 0
3.2.4.97 | P4 - stage/ faza 13-1 | 276465.25 | 43 |  | 0 | 0 | 0
3.2.4.98 | P4 - stage/ faza 13-2 | 30718.36 | 43 |  | 0 | 0 | 0
3.2.4.99 | P4 - stage/ faza 14-1 | 73253.14 | 45 |  | 0 | 0 | 0
3.2.4.100 | P4 - stage/ faza 14-2 | 8139.24 | 45 |  | 0 | 0 | 0
P5
3.2.4.101 | P5 - stage/ faza 1 | 930310.16 | 32 |  | 0 | 0 | 0
3.2.4.102 | P5 - stage/ faza 2-1 | 307374.41 | 33 |  | 0 | 0 | 0
3.2.4.103 | P5 - stage/ faza 2-2 | 34152.71 | 33 |  | 0 | 0 | 0
3.2.4.104 | P5 - stage/ faza 3-1 | 341874.03 | 34 |  | 0 | 0 | 0
3.2.4.105 | P5 - stage/ faza 3-2 | 37986 | 34 |  | 0 | 0 | 0
3.2.4.106 | P5 - stage/ faza 4-1 | 322985.1 | 35 |  | 0 | 0 | 0
3.2.4.107 | P5 - stage/ faza 4-2 | 35887.23 | 35 |  | 0 | 0 | 0
3.2.4.108 | P5 - stage/ faza 5-1 | 306281.66 | 36 |  | 0 | 0 | 0
3.2.4.109 | P5 - stage/ faza 5-2 | 34031.3 | 36 |  | 0 | 0 | 0
3.2.4.110 | P5 - stage/ faza 6-1 | 308623.27 | 37 |  | 0 | 0 | 0
3.2.4.111 | P5 - stage/ faza 6-2 | 34291.47 | 37 |  | 0 | 0 | 0
3.2.4.112 | P5 - stage/ faza 7-1 | 323843.68 | 38 |  | 0 | 0 | 0
3.2.4.113 | P5 - stage/ faza 7-2 | 35982.63 | 38 |  | 0 | 0 | 0
3.2.4.114 | P5 - stage/ faza 8-1 | 306437.77 | 39 |  | 0 | 0 | 0
3.2.4.115 | P5 - stage/ faza 8-2 | 34048.64 | 39 |  | 0 | 0 | 0
3.2.4.116 | P5 - stage/ faza 9-1 | 288953.8 | 40 |  | 0 | 0 | 0
3.2.4.117 | P5 - stage/ faza 9-2 | 32105.98 | 40 |  | 0 | 0 | 0
3.2.4.118 | P5 - stage/ faza 10-1 | 288017.15 | 41 |  | 0 | 0 | 0
3.2.4.119 | P5 - stage/ faza 10-2 | 32001.91 | 41 |  | 0 | 0 | 0
3.2.4.120 | P5 - stage/ faza 11-1 | 295198.07 | 42 |  | 0 | 0 | 0
3.2.4.121 | P5 - stage/ faza 11-2 | 32799.79 | 42 |  | 0 | 0 | 0
3.2.4.122 | P5 - stage/ faza 12-1 | 283958.38 | 43 |  | 0 | 0 | 0
3.2.4.123 | P5 - stage/ faza 12-2 | 31550.93 | 43 |  | 0 | 0 | 0
3.2.4.124 | P5 - stage/ faza 13-1 | 276465.25 | 44 |  | 0 | 0 | 0
3.2.4.125 | P5 - stage/ faza 13-2 | 30718.36 | 44 |  | 0 | 0 | 0
3.2.4.126 | P5 - stage/ faza 14-1 | 827444.49 | 45 |  | 0 | 0 | 0
3.2.4.127 | P5 - stage/ faza 14-2 | 91938.28 | 45 |  | 0 | 0 | 0
3.2.5 | Bridge furniture/ Mosna estetika
3.2.5.1 | 50 m | 170127.97 | 46 |  | 0 | 0 | 0
3.2.5.2 | 100 m | 170127.97 | 46 |  | 0 | 0 | 0
3.2.5.3 | 150 m | 170127.97 | 46 |  | 0 | 0 | 0
3.2.5.4 | 200 m | 170127.97 | 46 |  | 0 | 0 | 0
3.2.5.5 | 250 m | 170127.97 | 46 |  | 0 | 0 | 0
3.2.5.6 | 300 m | 170127.97 | 47 |  | 0 | 0 | 0
3.2.5.7 | 350 m | 170127.97 | 47 |  | 0 | 0 | 0
3.2.5.8 | 400 m | 170127.97 | 47 |  | 0 | 0 | 0
3.2.5.9 | 450 m | 170127.97 | 47 |  | 0 | 0 | 0
3.2.5.10 | 500 m | 170127.97 | 47 |  | 0 | 0 | 0
3.2.5.11 | 550 m | 170127.97 | 47 |  | 0 | 0 | 0
3.2.5.12 | 600 m | 170127.97 | 47 |  | 0 | 0 | 0
3.2.5.13 | 650 m | 170127.97 | 48 |  | 0 | 0 | 0
3.2.5.14 | 700 m | 170127.97 | 48 |  | 0 | 0 | 0
3.2.5.15 | 750 m | 170127.97 | 48 |  | 0 | 0 | 0
3.2.5.16 | 800 m | 170127.97 | 48 |  | 0 | 0 | 0
3.2.5.17 | 850 m | 170127.97 | 48 |  | 0 | 0 | 0
3.2.5.18 | 900 m | 170127.97 | 48 |  | 0 | 0 | 0
3.2.5.19 | 960 m | 204153.55 | 48 |  | 0 | 0 | 0
3.2.6 | Bridge deck (pavement and waterproofing)/ Mosna ploča (kolovoz i hidroizolacija)
3.2.6.1 | asphalt layer/ sloj asfalta 1 + waterproofing/ hidroizolacija 0-500 m RHS | 173453.99 | 47 |  | 0 | 0 | 0
3.2.6.2 | asphalt layer/ sloj asfalta 1 + waterproofing/ hidroizolacija 0-500 m LHS | 173453.99 | 47 |  | 0 | 0 | 0
3.2.6.3 | asphalt layer/ sloj asfalta 1 + waterproofing/ hidroizolacija 500-960 m RHS | 159577.67 | 47 |  | 0 | 0 | 0
3.2.6.4 | asphalt layer/ sloj asfalta 1 + waterproofing/ hidroizolacija 500-960 m LHS | 159577.67 | 47 |  | 0 | 0 | 0
3.2.6.5 | asphalt layer/ sloj asfalta 2 + joints/ spojnice 0-500 m RHS | 52019.36 | 48 |  | 0 | 0 | 0
3.2.6.6 | asphalt layer/ sloj asfalta 2 + joints/ spojnice 0-500 m LHS | 52019.36 | 48 |  | 0 | 0 | 0
3.2.6.7 | asphalt layer/ sloj asfalta 2 + joints/ spojnice 500-960 m LHS | 47857.81 | 48 |  | 0 | 0 | 0
3.2.6.8 | asphalt layer/ sloj asfalta 2 + joints/ spojnice 500-960 m RHS | 47857.81 | 48 |  | 0 | 0 | 0
| Sub Total / Suma stavke 3.2 | 74518071.95 |  |  | 40187442.1232 | 3099091.9199 | 43286534.0431
Cost Center/Troškovno mjesto 3.3 | Road Works/Radovi na putevima (LK7+442.333—LK7+445.350 RK7+436.377—RK7+440.630)
Completion of/Završetak:
3.3.1 | Subgrade/ Posteljica
3.3.1.1 | Top soil removal/ Uklanjanje humusa
3.3.1.1.1 | RK7+436.377—RK7+440.630 (Inc. 0 - 3.017m (LK); 0 - 4.253m (RK)) | 476.7587 | 18
3.3.1.2 | Earthworks/ Zemljani radovi |  | 35
At every 250 m and 4 m height /Na svakih 250m visini od 4m
3.3.1.2.1 | 7+436.38 - 7+440.63, layers 1.2.3
3.3.1.2.1.1 | 7+436.38 - 7+440.63, layers 1 | 858.2108
3.3.1.2.1.2 | 7+436.38 - 7+440.63, layers 2 | 2724.4788
3.3.1.2.1.3 | 7+436.38 - 7+440.63, layers 3 | 2724.4788
3.3.1.3 | Road Foundation/ Temelj puta
3.3.1.3.1 | 0 - 4.253 m,Right side/ Desna strana | 221.3238 | 32
3.3.1.3.2 | 0 - 3.017 m, Left side/ Lijeva strana | 157.003 | 33
3.3.2 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
3.3.2.1 | LK7+442.333—LK7+445.350 | 717.0548 | 33
3.3.2.2 | RK7+436.377—RK7+440.630 | 1010.8167 | 33
3.3.3 | Pavement structure/ Kolovozna konstrukcija
3.3.3.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 Right side/ Desna strana | 290.8598 | 34 |  | 0 | 0 | 0
3.3.3.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 Left side/ Lijeva strana | 206.3306 | 35 |  | 0 | 0 | 0
3.3.3.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 Right side/ Desna strana | 290.8598 | 36 |  | 0 | 0 | 0
3.3.3.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 Left side/ Lijeva strana | 206.3306 | 37 |  | 0 | 0 | 0
3.3.3.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 Right side/ Desna strana | 322.6112 | 38 |  | 0 | 0 | 0
3.3.3.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 Left side/ Lijeva strana | 228.8545 | 39 |  | 0 | 0 | 0
| Sub Total / Suma stavke 3.3 | 10435.972 |  |  | 0 | 0 | 0
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 03 | 74648683.8216 |  |  | 40187442.1232 | 3099091.9199 | 43286534.0431

## COST CENTER 04
Highway Bar-Boljare, Section Smokovac-Uvac-Matesevo |  | Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments |  | Schedule of Milestone Payments/Raspored repera plaćanja
COST CENTER 04/TROŠKOVNI CENTAR 04 rev Open Route
Cost Center No./ Troškovno mjesto Br. | 04 | Subsection/Podsekcija 1.4 (LK7+445.35—LK11+200.00, RK7+440.63—RK11+194.958)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost Center/ Troškovno mjesto 4.1 | Road Works/ Radovi na putevima (LK7+445.35—LK11+200.00, RK7+440.63—RK11+194.958)
Completion of/Završetak:
4.1.1 | Subgrade/ Posteljica
4.1.1.1 | Top soil removal/ Uklanjanje humusa
4.1.1.1.1 | 0 - 250 m (LK&RK) | 58310.92 | 15 |  | 0 | 0 | 0
4.1.1.1.2 | 250 - 500 m (LK&RK) | 58310.92 | 15 |  | 0 | 0 | 0
4.1.1.1.3 | 500 - 750 m (LK&RK) | 58310.92 | 15 |  | 0 | 0 | 0
4.1.1.1.4 | 750 - 1000 m (LK&RK) | 58310.92 | 15 |  | 0 | 0 | 0
4.1.1.1.5 | 1000 - 1250 m (LK&RK) | 58310.92 | 15 |  | 0 | 0 | 0
4.1.1.1.6 | 1250 - 1500 m (LK&RK) | 58310.92 | 15 | 29 | 58310.92 | 0 | 58310.92
4.1.1.1.7 | 1500 - 1750 m (LK&RK) | 58310.92 | 15 |  | 0 | 0 | 0
4.1.1.1.8 | 1750 - 2000 m (LK&RK) | 58310.92 | 15 |  | 0 | 0 | 0
4.1.1.1.9 | 2000 - 2250 m (LK&RK) | 58310.92 | 15 | 29 | 58310.92 | 0 | 58310.92
4.1.1.1.10 | 2250 - 2500 m (LK&RK) | 58310.92 | 15 |  | 0 | 0 | 0
4.1.1.1.11 | 2500 - 2750 m (LK&RK) | 58310.92 | 16 |  | 0 | 0 | 0
4.1.1.1.12 | 2750 - 3000 m (LK&RK) | 58310.92 | 16 |  | 0 | 0 | 0
4.1.1.1.13 | 3000 - 3250 m (LK&RK) | 58310.92 | 16 |  | 0 | 0 | 0
4.1.1.1.14 | 3250 - 3500 m (LK&RK) | 58310.92 | 16 |  | 0 | 0 | 0
4.1.1.1.15 | 3500 - 3754.650 m (LK); 3500 - 3754.328 m (RK) | 59474.88 | 16 |  | 0 | 0 | 0
4.1.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and 4m height /Na svakih 250m i visini od 4m |  | 36
4.1.1.2.1 | 7440.63-7690.63, layers 1,2,3,4,5,6,7,8,9,10,11
4.1.1.2.1.1 | 7440.63-7690.63, layer 1 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.1.2 | 7440.63-7690.63, layer 2 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.1.3 | 7440.63-7690.63, layer 3 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.1.4 | 7440.63-7690.63, layer 4 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.1.5 | 7440.63-7690.63, layer 5 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.1.6 | 7440.63-7690.63, layer 6 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.1.7 | 7440.63-7690.63, layer 7 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.1.8 | 7440.63-7690.63, layer 8 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.1.9 | 7440.63-7690.63, layer 9 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.1.10 | 7440.63-7690.63, layer 10 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.1.11 | 7440.63-7690.63, layer 11 | 33783.885 |  |  | 0 | 0 | 0
4.1.1.2.2 | 7690.63-7940.63, layers 12,13,14,15
4.1.1.2.2.12 | 7690.63-7940.63, layer 12 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.2.13 | 7690.63-7940.63, layer 13 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.2.14 | 7690.63-7940.63, layer 14 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.2.15 | 7690.63-7940.63, layer 15 | 82442.764 |  |  | 0 | 0 | 0
4.1.1.2.3 | 7940.63-8190.63, layers 16,17,18,19,20,21,22,23, 24,25,26,27,28
4.1.1.2.3.16 | 7940.63-8190.63, layer 16 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.3.17 | 7940.63-8190.63, layer 17 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.3.18 | 7940.63-8190.63, layer 18 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.3.19 | 7940.63-8190.63, layer 19 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.3.20 | 7940.63-8190.63, layer 20 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.3.21 | 7940.63-8190.63, layer 21 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.3.22 | 7940.63-8190.63, layer 22 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.3.23 | 7940.63-8190.63, layer 23 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.3.24 | 7940.63-8190.63, layer 24 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.3.25 | 7940.63-8190.63, layer 25 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.3.26 | 7940.63-8190.63, layer 26 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.3.27 | 7940.63-8190.63, layer 27 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.3.28 | 7940.63-8190.63, layer 28 | 96561.4025 |  |  | 0 | 0 | 0
4.1.1.2.4 | 8190.63-8440.63, layers 29,30,31,32,33,34,35
4.1.1.2.4.29 | 8190.63-8440.63, layer 29 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.4.30 | 8190.63-8440.63, layer 30 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.4.31 | 8190.63-8440.63, layer 31 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.4.32 | 8190.63-8440.63, layer 32 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.4.33 | 8190.63-8440.63, layer 33 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.4.34 | 8190.63-8440.63, layer 34 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.4.35 | 8190.63-8440.63, layer 35 | 123538.0868 |  |  | 0 | 0 | 0
4.1.1.2.5 | 8440.63-8690.63, layers 36,37,38,39,40,41,42,43,44
4.1.1.2.5.36 | 8440.63-8690.63, layer 36 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.5.37 | 8440.63-8690.63, layer 37 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.5.38 | 8440.63-8690.63, layer 38 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.5.39 | 8440.63-8690.63, layer 39 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.5.40 | 8440.63-8690.63, layer 40 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.5.41 | 8440.63-8690.63, layer 41 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.5.42 | 8440.63-8690.63, layer 42 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.5.43 | 8440.63-8690.63, layer 43 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.5.44 | 8440.63-8690.63, layer 44 | 111436.3966 |  |  | 0 | 0 | 0
4.1.1.2.6 | 8690.63-8940.63, layers 45,46,47,48,49,50
4.1.1.2.6.45 | 8690.63-8940.63, layer 45 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.6.46 | 8690.63-8940.63, layer 46 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.6.47 | 8690.63-8940.63, layer 47 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.6.48 | 8690.63-8940.63, layer 48 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.6.49 | 8690.63-8940.63, layer 49 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.6.50 | 8690.63-8940.63, layer 50 | 84459.7124 |  |  | 0 | 0 | 0
4.1.1.2.7 | 8940.63-9190.63, layers 51,52,53,54,55,56,57
4.1.1.2.7.51 | 8940.63-9190.63, layer 51 | 116730.8861 |  |  | 0 | 0 | 0
4.1.1.2.7.52 | 8940.63-9190.63, layer 52 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.7.53 | 8940.63-9190.63, layer 53 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.7.54 | 8940.63-9190.63, layer 54 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.7.55 | 8940.63-9190.63, layer 55 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.7.56 | 8940.63-9190.63, layer 56 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.7.57 | 8940.63-9190.63, layer 57 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.8 | 9190.63-9440.63, layers 58,59,60,61,62,63,64,65,66
4.1.1.2.8.58 | 9190.63-9440.63, layer 58 | 91771.1502 |  |  | 0 | 0 | 0
4.1.1.2.8.59 | 9190.63-9440.63, layer 59 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.8.60 | 9190.63-9440.63, layer 60 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.8.61 | 9190.63-9440.63, layer 61 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.8.62 | 9190.63-9440.63, layer 62 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.8.63 | 9190.63-9440.63, layer 63 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.8.64 | 9190.63-9440.63, layer 64 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.8.65 | 9190.63-9440.63, layer 65 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.8.66 | 9190.63-9440.63, layer 66 | 100847.4178 |  | 27 | 100847.42 | 0 | 100847.42
4.1.1.2.9 | 9440.63-9690.63, layers 67,68,69,70,71,72
4.1.1.2.9.67 | 9440.63-9690.63, layer 67 | 56978.791 |  |  | 0 | 0 | 0
4.1.1.2.9.68 | 9440.63-9690.63, layer 68 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.9.69 | 9440.63-9690.63, layer 69 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.9.70 | 9440.63-9690.63, layer 70 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.9.71 | 9440.63-9690.63, layer 71 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.9.72 | 9440.63-9690.63, layer 72 | 100847.4178 |  | 28 | 100847.42 | 0 | 100847.42
4.1.1.2.10 | 9690.63-9940.63, layers 73,74,75,76,77,78,79,80,81
4.1.1.2.10.73 | 9690.63-9940.63, layer 73 | 57483.0281 |  |  | 0 | 0 | 0
4.1.1.2.10.74 | 9690.63-9940.63, layer 74 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.10.75 | 9690.63-9940.63, layer 75 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.10.76 | 9690.63-9940.63, layer 76 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.10.77 | 9690.63-9940.63, layer 77 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.10.78 | 9690.63-9940.63, layer 78 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.10.79 | 9690.63-9940.63, layer 79 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.10.80 | 9690.63-9940.63, layer 80 | 100847.4178 |  | 29 | 100847.4178 | 0 | 100847.4178
4.1.1.2.10.81 | 9690.63-9940.63, layer 81 | 100847.4178 |  | 27 | 100847.42 | 0 | 100847.42
4.1.1.2.11 | 9940.63-10190.63, layers 82,83,84,85,86,87,88
4.1.1.2.11.82 | 9940.63-10190.63, layer 82 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.11.83 | 9940.63-10190.63, layer 83 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.11.84 | 9940.63-10190.63, layer 84 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.11.85 | 9940.63-10190.63, layer 85 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.11.86 | 9940.63-10190.63, layer 86 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.11.87 | 9940.63-10190.63, layer 87 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.11.88 | 9940.63-10190.63, layer 88 | 94796.5727 |  |  | 0 | 0 | 0
4.1.1.2.12 | 10190.63-10440.63, layers 89,90,91,92
4.1.1.2.12.89 | 10190.63-10440.63, layer 89 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.12.90 | 10190.63-10440.63, layer 90 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.12.91 | 10190.63-10440.63, layer 91 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.12.92 | 10190.63-10440.63, layer 92 | 74879.2077 |  |  | 0 | 0 | 0
4.1.1.2.13 | 10440.63-10690.63, layers 93,94,95,96,97,98,99,100
4.1.1.2.13.93 | 10440.63-10690.63, layer 93 | 86728.7793 |  |  | 0 | 0 | 0
4.1.1.2.13.94 | 10440.63-10690.63, layer 94 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.13.95 | 10440.63-10690.63, layer 95 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.13.96 | 10440.63-10690.63, layer 96 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.13.97 | 10440.63-10690.63, layer 97 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.13.98 | 10440.63-10690.63, layer 98 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.13.99 | 10440.63-10690.63, layer 99 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.13.100 | 10440.63-10690.63, layer 100 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.14 | 10690.63-10940.63, layers 101,102,103,104,105,106, 107,108,109,110
4.1.1.2.14.101 | 10690.63-10940.63, layer 101 | 52692.7758 |  |  | 0 | 0 | 0
4.1.1.2.14.102 | 10690.63-10940.63, layer 102 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.14.103 | 10690.63-10940.63, layer 103 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.14.104 | 10690.63-10940.63, layer 104 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.14.105 | 10690.63-10940.63, layer 105 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.14.106 | 10690.63-10940.63, layer 106 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.14.107 | 10690.63-10940.63, layer 107 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.14.108 | 10690.63-10940.63, layer 108 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.14.109 | 10690.63-10940.63, layer 109 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.14.110 | 10690.63-10940.63, layer 110 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.15 | 10940.63-11194.96, layers 111,112,113,114,115
4.1.1.2.15.111 | 10940.63-11194.96, layer 111 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.15.112 | 10940.63-11194.96, layer 112 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.15.113 | 10940.63-11194.96, layer 113 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.15.114 | 10940.63-11194.96, layer 114 | 100847.4178 |  |  | 0 | 0 | 0
4.1.1.2.15.115 | 10940.63-11194.96, layer 115 | 123790.2053 |  |  | 0 | 0 | 0
4.1.1.3 | Road Foundation/ Temelj puta
4.1.1.3.1 | 0 - 250 m right side/ desna strana | 23136 | 38 |  | 0 | 0 | 0
4.1.1.3.2 | 0 - 250 m left side/ lijeva strana | 23136 | 38 |  | 0 | 0 | 0
4.1.1.3.3 | 250 - 500 m right side/ desna strana | 23136 | 38 |  | 0 | 0 | 0
4.1.1.3.4 | 250 - 500 m left side/ lijeva strana | 23136 | 38 |  | 0 | 0 | 0
4.1.1.3.5 | 500 - 750 m right side/ desna strana | 23136 | 38 |  | 0 | 0 | 0
4.1.1.3.6 | 500 - 750 m left side/ lijeva strana | 23136 | 38 |  | 0 | 0 | 0
4.1.1.3.7 | 750 - 1000 m right side/ desna strana | 23136 | 38 |  | 0 | 0 | 0
4.1.1.3.8 | 750 - 1000 m left side/ lijeva strana | 23136 | 38 |  | 0 | 0 | 0
4.1.1.3.9 | 1000 - 1250 m right side/ desna strana | 23136 | 39 |  | 0 | 0 | 0
4.1.1.3.10 | 1000 - 1250 m left side/ lijeva strana | 23136 | 39 |  | 0 | 0 | 0
4.1.1.3.11 | 1250 - 1500 m right side/ desna strana | 23136 | 39 |  | 0 | 0 | 0
4.1.1.3.12 | 1250 - 1500 m left side/ lijeva strana | 23136 | 39 |  | 0 | 0 | 0
4.1.1.3.13 | 1500 - 1750 m right side/ desna strana | 23136 | 39 |  | 0 | 0 | 0
4.1.1.3.14 | 1500 - 1750 m left side/ lijeva strana | 23136 | 39 |  | 0 | 0 | 0
4.1.1.3.15 | 1750 - 2000 m right side/ desna strana | 23136 | 39 |  | 0 | 0 | 0
4.1.1.3.16 | 1750 - 2000 m left side/ lijeva strana | 23136 | 39 |  | 0 | 0 | 0
4.1.1.3.17 | 2000 - 2250 m right side/ desna strana | 23136 | 40 |  | 0 | 0 | 0
4.1.1.3.18 | 2000 - 2250 m left side/ lijeva strana | 23136 | 40 |  | 0 | 0 | 0
4.1.1.3.19 | 2250 - 2500 m right side/ desna strana | 23136 | 40 |  | 0 | 0 | 0
4.1.1.3.20 | 2250 - 2500 m left side/ lijeva strana | 23136 | 40 |  | 0 | 0 | 0
4.1.1.3.21 | 2500 - 2750 m right side/ desna strana | 23136 | 40 |  | 0 | 0 | 0
4.1.1.3.22 | 2500 - 2750 m left side/ lijeva strana | 23136 | 40 |  | 0 | 0 | 0
4.1.1.3.23 | 2750 - 3000 m right side/ desna strana | 23136 | 40 |  | 0 | 0 | 0
4.1.1.3.24 | 2750 - 3000 m left side/ lijeva strana | 23136 | 40 |  | 0 | 0 | 0
4.1.1.3.25 | 3000 - 3250 m right side/ desna strana | 23136 | 41 |  | 0 | 0 | 0
4.1.1.3.26 | 3000 - 3250 m left side/ lijeva strana | 23136 | 41 |  | 0 | 0 | 0
4.1.1.3.27 | 3250 - 3500 m right side/ desna strana | 23136 | 41 |  | 0 | 0 | 0
4.1.1.3.28 | 3250 - 3500 m left side/ lijeva strana | 23136 | 41 |  | 0 | 0 | 0
4.1.1.3.29 | 3500 - 3754.328 m right side/ desna strana | 23597.83 | 41 |  | 0 | 0 | 0
4.1.1.3.30 | 3500 - 3754.650 m left side/ lijeva strana | 23597.83 | 41 |  | 0 | 0 | 0
4.1.2 | Engineering structures/ Inženjerske konstrukcije
4.1.2.1 | Concrete wall/ Betonski zid |  | 30
80% for the concrete wall, the milestone is 50m lenth, no matter the hight+ 5% for the "after work" the whole lenth of each retaining wall + 5% for the "correction of the crown" the whole lenth of each retaining wall+10% for the "wall surface" the whole lenth of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
4.1.2.1.1 | Concrete wall/ Betonski zid RK7+975 - RK8+014 (39m)
4.1.2.1.1.1 | Concrete wall/ Betonski zid RK7+975 - RK8+014 - 80% | 120134.672 | 30 | 29 | 120134.672 | 0 | 120134.672
4.1.2.1.1.2 | Concrete wall/ Betonski zid RK7+975 - RK8+014 - After work 5% | 7508.417 |  |  | 0 | 0 | 0
4.1.2.1.1.3 | Concrete wall/ Betonski zid RK7+975 - RK8+014 - Correction of the crown 5% | 7508.417 |  |  | 0 | 0 | 0
4.1.2.1.1.4 | Concrete wall/ Betonski zid RK7+975 - RK8+014 - Wall surface 10% | 15016.834 |  |  | 0 | 0 | 0
4.1.2.1.2 | Concrete wall/ Betonski zid RK8+306 - RK8+565 (259m)
4.1.2.1.2.1 | Concrete wall/ Betonski zid RK8+306 - RK8+565 (259m) 80%, Layers 1,2,3,4,5,6
4.1.2.1.2.1.1 | Segment 1 RK8+306 - RK8+356 (50m) | 154018.8134 |  | 30 | 0 | 154018.8134 | 154018.8134
4.1.2.1.2.1.2 | Segment2 RK8+356 - RK8+406 (50m) | 154018.8134 |  | 30 | 0 | 154018.8134 | 154018.8134
4.1.2.1.2.1.3 | Segment 3 RK8+406 - RK8+456 (50m) | 154018.8134 |  | 30 | 0 | 154018.8134 | 154018.8134
4.1.2.1.2.1.4 | Segment 4 RK8+456 - RK8+506 (50m) | 154018.8134 |  | 30 | 0 | 154018.8134 | 154018.8134
4.1.2.1.2.1.5 | Segment 5 RK8+506 - RK8+556 (50m) | 154018.8134 |  | 30 | 0 | 154018.8134 | 154018.8134
4.1.2.1.2.1.6 | Segment 5 RK8+556 - RK8+565 (9m) | 27723.3864 |  | 30 | 0 | 27723.3864 | 27723.3864
4.1.2.1.2.1.7 | Concrete wall/ Betonski zid RK8+306 ~ RK8+565 (259m) After work 5% | 49863.5908 |  |  | 0 | 0 | 0
4.1.2.1.2.1.8 | Concrete wall/ Betonski zid RK8+306 ~ RK8+565 (259m) Correction of the crown 5% | 49863.5908 |  |  | 0 | 0 | 0
4.1.2.1.2.1.9 | Concrete wall/ Betonski zid RK8+306 ~ RK8+565 (259m) - Wall surface 10% | 99727.1817 |  |  | 0 | 0 | 0
4.1.2.2 | Culvert/ Propust
4.1.2.2.1 | RK7+657.33 (47m) | 12245.0656 | 35 |  | 0 | 0 | 0
4.1.2.2.2 | RK9+034,00 (83.87m) | 21850.9287 | 35 |  | 0 | 0 | 0
4.1.2.2.3 | RK10+360,00 (38.24m) | 9962.7938 | 35 |  | 0 | 0 | 0
4.1.2.2.4 | RK10+835,00 (56.5m) | 14720.132 | 35 |  | 0 | 0 | 0
4.1.3 | Water drainage/ Drenaža vode
| per one direction of 500m / Na 500m dužine u jednom pravcu |  | 35
4.1.3.1 | LK7+445.350 - LK11+200.000 (3754.650m)
4.1.3.1.1 | LK7+445.350 - LK7+945.350 (500m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.1.2 | LK7+945.350 - LK8+445.350 (500m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.1.3 | LK8+445.350 - LK8+945.350 (500m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.1.4 | LK8+945.350 - LK9+445.350 (500m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.1.5 | LK9+445.350 - LK9+945.350 (500m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.1.6 | LK9+945.350 - LK10+445.350 (500m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.1.7 | LK10+445.350 - LK10+945.350 (500m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.1.8 | LK10+945.350 - LK11+200.000 (500m) | 103509.6243 |  |  | 0 | 0 | 0
4.1.3.2 | RK7+440.630 - RK11+194.958 ( 4054.328 m)
4.1.3.2.1 | RK7+440.630 - RK7+940.630 ( 500 m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.2.2 | RK7+940.630 - RK8+440.630 ( 500 m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.2.3 | RK8+440.630 - RK8+940.630 ( 500 m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.2.4 | RK8+940.630 - RK9+440.630 ( 500 m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.2.5 | RK9+440.630 - RK9+940.630 ( 500 m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.2.6 | RK9+940.630 - RK11+440.630 ( 500 m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.2.7 | RK10+440.630 - RK10+940.630 ( 500 m) | 203239.0032 |  |  | 0 | 0 | 0
4.1.3.2.8 | RK10+940.630 - RK11+194.958 ( 554.328 m) | 225322.1404 |  |  | 0 | 0 | 0
4.1.4 | Pavement structure/ Kolovozna konstrukcija
4.1.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 0-500m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 0-500m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 500-1000m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 500-1000m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 1000-1500m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 1000-1500m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.7 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 1500-2000m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.8 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 1500-2000m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.9 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 2000-2500m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.10 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 2000-2500m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.11 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 2500-3000m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.12 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 2500-3000m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.13 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 3000-3500m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.14 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 3000-3500m | 60890.67 | 41 |  | 0 | 0 | 0
4.1.4.15 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 3500-3750m | 30445.34 | 41 |  | 0 | 0 | 0
4.1.4.16 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 3500-3750m | 30445.33 | 41 |  | 0 | 0 | 0
4.1.4.17 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 0-500m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.18 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 0-500m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.19 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 500-1000m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.20 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 500-1000m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.21 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 1000-1500m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.22 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 1000-1500m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.23 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 1500-2000m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.24 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 1500-2000m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.25 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 2000-2500m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.26 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 2000-2500m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.27 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 2500-3000m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.28 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 2500-3000m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.29 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 3000-3500m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.30 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 3000-3500m | 60890.67 | 42 |  | 0 | 0 | 0
4.1.4.31 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 3500-3750m | 30445.34 | 42 |  | 0 | 0 | 0
4.1.4.32 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 3500-3750m | 30445.33 | 42 |  | 0 | 0 | 0
4.1.4.33 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 0-500m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.34 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 0-500m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.35 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 500-1000m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.36 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 500-1000m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.37 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 1000-1500m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.38 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 1000-1500m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.39 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 1500-2000m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.40 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 1500-2000m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.41 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 2000-2500m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.42 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 2000-2500m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.43 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 2500-3000m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.44 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 2500-3000m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.45 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 3000-3500m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.46 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 3000-3500m | 67660.32 | 45 |  | 0 | 0 | 0
4.1.4.47 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 3500-3754.328m | 33830.16 | 45 |  | 0 | 0 | 0
4.1.4.48 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 3500-3754.650m | 33830.17 | 45 |  | 0 | 0 | 0
4.1.5 | Underpasses/ Podvožnjak
4.1.5.1 | LK9+252 (Pavlicici 2)
4.1.5.1.1 | Foundation (excavation and concreting)/ Temelj (iskopavanje i betoniranje) | 232223.343 | 19 | 29 | 232223.343 | 0 | 232223.343
4.1.5.1.2 | Box culvert/Kutijasti propust (100% complete/završen) | 239260.414 | 20 | 30 | 0 | 239260.414 | 239260.414
4.1.5.1.3 | Remaining works/ Preostali radovi | 277474.483 | 22 |  | 0 | 0 | 0
4.1.5.2 | LK9+661.38 (Bratonozicke njive 1)
4.1.5.2.1 | Foundation (excavation and concreting)/ Temelj (iskopavanje i betoniranje) | 143491.5471 | 19 | 30 | 0 | 143491.5471 | 143491.5471
4.1.5.2.2 | Box culvert/Kutijasti propust (100% complete/završen) | 147839.7758 | 20 |  | 0 | 0 | 0
4.1.5.2.3 | Remaining works/ Preostali radovi | 175163.8071 | 22 |  | 0 | 0 | 0
4.1.5.3 | LK10+474.45 (Bratonozicke njive 2)
4.1.5.3.1 | Foundation (excavation and concreting)/ Temelj (iskopavanje i betoniranje) | 143296.6656 | 19 |  | 0 | 0 | 0
4.1.5.3.2 | Box culvert/Kutijasti propust (100% complete/završen) | 147638.9888 | 20 |  | 0 | 0 | 0
4.1.5.3.3 | Remaining works/ Preostali radovi | 174483.2756 | 22 |  | 0 | 0 | 0
4.1.6 | Deviations of local roads
4.1.6.1 | Bratonožići - Pavličići 1 (K0+0.000 - K1+135.835, 135.8m) | 24506.468 |  |  | 0 | 0 | 0
4.1.6.2 | Bratonožići - Pavličići 2 (K0+0.000 - K0+268.914, 268.9m) | 48525.694 |  |  | 0 | 0 | 0
4.1.6.3 | Bratonožićke njive 1 (K0+0.000 - K0+391.465, 391.5m) | 70486.8516 |  |  | 0 | 0 | 0
4.1.6.4 | Bratonožićke njive 2 (K0+0.000 - K0+389.085, 389.1m) | 70216.986 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 4.1 | 22060276.9365 |  |  | 872369.5328 | 1180569.4146 | 2052938.9474
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 04 | 22060276.9365 |  |  | 872369.5328 | 1180569.4146 | 2052938.9474

## COST CENTER 05
Highway Bar-Boljare, Section Smokovac-Uvac-Matesevo |  | Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments |  | Schedule of Milestone Payments/Raspored repera plaćanja
| COST CENTER 05/TROŠKOVNI CENTAR 05 | revised Bridge Piers, Tunnels and Open Route
Cost Center No./ Troškovno mjesto Br. | 05 | Subsection/Podsekcija 2.1 (LK11+200.00-LK14+700.000, RK11+194.958 - RK14+740.000)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost Center/ Troškovno mjesto 5.1 | Road Works/Radovi na putevima (LK11+200.00 -LK11+495.000, RK11+194.958 - RK11+595.000)
5.1.1 | Subgrade/ Posteljica
5.1.1.1 | Top soil removal/ Uklanjanje humusa
5.1.1.1.1 | 0 - 250 m (LK&RK) | 58310.92 | 20 |  | 0 | 0 | 0
5.1.1.1.2 | 250 - 295.000 m (LK); 250 - 400.042 m (RK) | 21002.43 | 21 |  | 0 | 0 | 0
5.1.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and 4m height /Na svakih 250m i visini od 4m |  | 28
5.1.1.2.1 | 11194.96-11444.96, layers 1, 2, 3, 4, 5, 6, 7 |  |  |  | 0 | 0 | 0
5.1.1.2.1.1 | 11194.96-11444.96, layer 1 | 93559.5159 |  |  | 0 | 0 | 0
5.1.1.2.1.2 | 11194.96-11444.96, layer 2 | 75148.2056 |  |  | 0 | 0 | 0
5.1.1.2.1.3 | 11194.96-11444.96, layer 3 | 75148.2056 |  |  | 0 | 0 | 0
5.1.1.2.1.4 | 11194.96-11444.96, layer 4 | 75148.2056 |  |  | 0 | 0 | 0
5.1.1.2.1.5 | 11194.96-11444.96, layer 5 | 75148.2056 |  |  | 0 | 0 | 0
5.1.1.2.2.6 | 11194.96-11444.96, layer 6 | 75148.2056 |  |  | 0 | 0 | 0
5.1.1.2.2.7 | 11194.96-11444.96, layer 7 | 75148.2056 |  |  | 0 | 0 | 0
5.1.1.2.2 | 11444.96-11595.00, layers 8, 9, 10, 11, 12, 13, 14
5.1.1.2.2.8 | 11444.96-11595.00, layer 8 | 75148.2056 |  |  | 0 | 0 | 0
5.1.1.2.2.9 | 11444.96-11595.00, layer 9 | 75148.2056 |  |  | 0 | 0 | 0
5.1.1.2.2.10 | 11444.96-11595.00, layer 10 | 75148.2056 |  |  | 0 | 0 | 0
5.1.1.2.2.11 | 11444.96-11595.00, layer 11 | 75148.2056 |  |  | 0 | 0 | 0
5.1.1.2.2.12 | 11444.96-11595.00, layer 12 | 75148.2056 |  |  | 0 | 0 | 0
5.1.1.2.2.13 | 11444.96-11595.00, layer 13 | 75148.2056 |  |  | 0 | 0 | 0
5.1.1.2.2.14 | 11444.96-11595.00, layer 14 | 53918.8375 |  |  | 0 | 0 | 0
5.1.1.3 | Road Foundation/ Temelj puta
5.1.1.3.1 | 0 - 250 m right side/ desna strana | 22638.2938 | 30 |  | 0 | 0 | 0
5.1.1.3.2 | 0 - 250 m left side/ lijeva strana | 22638.2938 | 30 |  | 0 | 0 | 0
5.1.1.3.3 | 250 - 400.042 m, right side/ desna strana | 13586.7795 | 31 |  | 0 | 0 | 0
5.1.1.3.4 | 250 - 295.000 m, left side/ lijeva strana | 4074.8929 | 31 |  | 0 | 0 | 0
5.1.2 | Engineering structures/ Inženjerske konstrukcije
80% for the concrete wall, the milestone is 50m lenth, no matter the hight+ 5% for the "after work" the whole lenth of each retaining wall + 5% for the "correction of the crown" the whole lenth of each retaining wall+10% for the "wall surface" the whole lenth of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
5.1.2.1.1 | Concrete wall/ Betonski zid RK11+315 ~ RK11+353 (38m)
5.1.2.1.1.1 | Concrete wall/ Betonski zid RK11+315 ~ RK11+353 - 80% | 119040 |  |  | 0 | 0 | 0
5.1.2.1.1.2 | Concrete wall/ Betonski zid RK11+315 ~ RK11+353 - After work 5% | 7440 |  |  | 0 | 0 | 0
5.1.2.1.1.3 | Concrete wall/ Betonski zid RK11+315 ~ RK11+353 - Correction of the crown 5% | 7440 |  |  | 0 | 0 | 0
5.1.2.1.1.4 | Concrete wall/ Betonski zid RK11+315 ~ RK11+353 - - Wall surface 10% | 14880 |  |  | 0 | 0 | 0
5.1.2.2 | Culvert/ Propust
5.1.2.2.1 | RK11+235.80 (52.01m) | 10545.4734 | 20 |  | 0 | 0 | 0
5.1.2.2.2 | RK11+482.01 (43.1m) | 8728.7566 | 20 |  | 0 | 0 | 0
5.1.3 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
5.1.3.1 | LK11+200.000 —LK11+495.000 (295 m) | 121834.8771 | 36 |  | 0 | 0 | 0
5.1.3.2 | RK11+194.958—RK11+595.000 (401 m) | 165612.8329 | 36 |  | 0 | 0 | 0
5.1.4 | Pavement structure/ Kolovozna konstrukcija
5.1.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana | 47606.2769 | 38 |  | 0 | 0 | 0
5.1.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana | 35105.9431 | 39 |  | 0 | 0 | 0
5.1.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana | 47606.2654 | 40 |  | 0 | 0 | 0
5.1.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana | 35105.9346 | 41 |  | 0 | 0 | 0
5.1.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana | 52899.002 | 42 |  | 0 | 0 | 0
5.1.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana | 39008.918 | 43 |  | 0 | 0 | 0
5.1.5 | Deviation of local Road/
5.1.5.1 | Trimojevici | 95120.46 | 26
| Sub Total / Suma stavke 5.1 | 1999483.17 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 5.2 | Construction of tunnel Klopot/ Izgradnja tunela Klopot LK 11+495.00- LK 12+480.000, RK 11+595.000, RK 11+595.000- 12+410.000
Completion of/Završetak:
5.2.1 | Portal construction/ Izgradnja portala
5.2.1.1 | 20% complete/završeno (portal 1) | 104196.17 | 17 | 23 | 104196.17 | 0 | 104196.17
5.2.1.2 | 40% complete/završeno (portal 2) | 104196.17 | 17 | 23 | 104196.17 | 0 | 104196.17
5.2.1.3 | 60% complete/završeno (portal 3) | 104196.17 | 20 |  | 0 | 0 | 0
5.2.1.4 | 80% complete/završeno (portal 4) | 104196.17 | 20 |  | 0 | 0 | 0
5.2.1.5 | 85% (portal 1 complete/završen) | 26049.0425 | 31 |  | 0 | 0 | 0
5.2.1.6 | 90% (portal 2 complete/završen) | 26049.0425 | 32 |  | 0 | 0 | 0
5.2.1.7 | 95% (portal 3 complete/završen) | 26049.0425 | 33 |  | 0 | 0 | 0
5.2.1.8 | 100% (portal 4 complete/završen) | 26049.0625 | 34 |  | 0 | 0 | 0
5.2.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
5.2.2.1 | 75 m (N-R, RK 12+398.5 - RK 12+323.5) | 376275.76 | 17 | 25 | 376275.76 | 0 | 376275.76
5.2.2.2 | 150 m(N-L, LK 12+468.0 - LK 12+393.0) | 376275.76 | 19 | 25 | 376275.76 | 0 | 376275.76
5.2.2.3 | 225 m (N-R, RK 12+323.0 - RK 12+248.00) | 376275.76 | 19 | 25 | 376275.76 | 0 | 376275.76
5.2.2.4 | 300 m (N-R, RK 12+248.0 - RK 12+173.00) | 376275.76 | 20 | 25 | 376275.76 | 0 | 376275.76
5.2.2.5 | 375 m (N-L, LK 12+393.0 - LK 12+318.00) | 376275.76 | 20 | 25 | 376275.76 | 0 | 376275.76
5.2.2.6 | 450 m (N-L, LK 12+318 - LK 12+243.00) | 376275.76 | 21 | 25 | 376275.76 | 0 | 376275.76
5.2.2.7 | 525 m (N-R, RK 12+173.00 - RK 12+098.00) | 376275.76 | 21 | 26 | 376275.76 | 0 | 376275.76
5.2.2.8 | 600 m (N-L, LK 12+243 - LK 12+168.00) | 376275.76 | 22 | 27 | 376275.76 | 0 | 376275.76
5.2.2.9 | 675 m (N-R, RK 12+098.00 - RK 12+023.00) | 376275.76 | 22 | 26 | 376275.76 | 0 | 376275.76
5.2.2.10 | 750 m (N-L, LK 12+168 - LK 12+093.00) | 376275.76 | 23 | 26 | 376275.76 | 0 | 376275.76
5.2.2.11 | 825 m (N-R, RK 12+023.5 - RK 11+948.50) | 376275.76 | 23 | 27 | 376275.76 | 0 | 376275.76
5.2.2.12 | 900 m (N-L, LK 12+093.00 - LK 12+018.00) | 376275.76 | 24 | 27 | 376275.76 | 0 | 376275.76
5.2.2.13 | 975 m (N-R, RK 11+948.50 - RK 11+873.50) | 376275.76 | 24 | 28 | 376275.76 | 0 | 376275.76
5.2.2.14 | 1050 m (N-L, LK 12+018.00 - LK 11+943.00) | 376275.76 | 25 | 28 | 376275.76 | 0 | 376275.76
5.2.2.15 | 1125 m (N-R, RK 11+873.50 - RK 11+798.50) | 376275.76 | 25 | 28 | 376275.76 | 0 | 376275.76
5.2.2.16 | 1145 m (N-L, LK11+943.0~LK11+923.0) | 106861.512 | 25 | 29 | 106861.512 | 0 | 106861.512
5.2.2.17 | 1165 m (N-L, LK11+923.0~LK11+903.0) | 106861.512 | 25 | 29 | 106861.512 | 0 | 106861.512
5.2.2.18 | 1185 m (N-L, LK11+903.0~LK11+883.0) | 106861.512 | 25 | 29 | 106861.512 | 0 | 106861.512
5.2.2.19 | 1205 m (N-L, LK11+883.0~LK11+863.0) | 106861.512 | 26 | 29 | 106861.512 | 0 | 106861.512
5.2.2.20 | 1225 m (N-R, RK11+798.5~RK11+778.5) | 106861.512 | 26 | 29 | 106861.512 | 0 | 106861.512
5.2.2.21 | 1245 m (N-R, RK11+778.5~RK11+758.5) | 106861.512 | 26 | 29 | 106861.512 | 0 | 106861.512
5.2.2.22 | 1265 m (N-R, RK11+758.5~RK11+738.5) | 106861.512 | 26 | 29 | 106861.512 | 0 | 106861.512
5.2.2.23 | 1285 m (N-R, RK11+738.5~RK11+718.5) | 106861.512 | 26 | 29 | 106861.512 | 0 | 106861.512
5.2.2.24 | 1305 m (N-L, LK11+863.0~LK11+843.0) | 106861.512 | 26 | 29 | 106861.512 | 0 | 106861.512
5.2.2.25 | 1325 m (N-L, LK11+843.0~LK11+823.0) | 106861.512 | 26 | 29 | 106861.512 | 0 | 106861.512
5.2.2.26 | 1345 m (N-L, LK11+823.0~LK11+803.0) | 106861.512 | 27 | 29 | 106861.512 | 0 | 106861.512
5.2.2.27 | 1365 m (N-L, LK11+803.0~LK11+783.0) | 106861.512 | 27 | 29 | 106861.512 | 0 | 106861.512
5.2.2.28 | 1385 m (N-R, RK11+718.5~RK11+698.5) | 106861.512 | 27 | 29 | 106861.512 | 0 | 106861.512
5.2.2.29 | 1405 m (N-R, RK11+698.5~RK11+678.5) | 106861.512 | 27 | 29 | 106861.512 | 0 | 106861.512
5.2.2.30 | 1425 m (N-R, RK11+678.5~RK11+658.5) | 106861.512 | 27 | 29 | 106861.512 | 0 | 106861.512
5.2.2.31 | 1445 m (N-R, RK11+658.5~RK11+638.5) | 106861.512 | 27 | 29 | 106861.512 | 0 | 106861.512
5.2.2.32 | 1465 m (N-L, LK11+783.0~LK11+763.0) | 106861.512 | 27 | 29 | 106861.512 | 0 | 106861.512
5.2.2.33 | 1485 m (N-L, LK11+763.0~LK11+743.0) | 106861.512 | 27 | 29 | 106861.512 | 0 | 106861.512
5.2.2.34 | 1505 m (N-L, LK11+743.0~LK11+723.0) | 106861.512 | 28 | 29 | 106861.512 | 0 | 106861.512
5.2.2.35 | 1525 m (N-L, LK11+723.0~LK11+703.0) | 106861.512 | 28 | 29 | 106861.512 | 0 | 106861.512
5.2.2.36 | 1545 m (N-L, LK11+703.0~LK11+683.0) | 106861.512 | 28 | 30 | 0 | 106861.512 | 106861.512
5.2.2.37 | 1565 m (N-L, LK11+683.0~LK11+663.0) | 106861.512 | 28 | 30 | 0 | 106861.512 | 106861.512
5.2.2.38 | 1585 m (N-L, LK11+663.0~LK11+643.0) | 106861.512 | 28 | 30 | 0 | 106861.512 | 106861.512
5.2.2.39 | 1605 m | 106861.512 | 28 |  | 0 | 0 | 0
5.2.2.40 | 1625 m | 106861.512 | 28 |  | 0 | 0 | 0
5.2.2.41 | 1645 m | 106861.512 | 29 |  | 0 | 0 | 0
5.2.2.42 | 1665 m | 106861.512 | 29 |  | 0 | 0 | 0
5.2.2.43 | 1685 m | 106861.512 | 29 |  | 0 | 0 | 0
5.2.2.44 | 1705 m | 106861.512 | 29 |  | 0 | 0 | 0
5.2.2.45 | 1725 m | 106861.512 | 30 |  | 0 | 0 | 0
5.2.2.46 | 1745 m | 106861.512 | 30 |  | 0 | 0 | 0
5.2.2.47 | 1752 m | 37401.5292 | 31 |  | 0 | 0 | 0
5.2.3 | Construction of waterproofing and drainage & Construction of secondary lining / Konstrukcija hidroizolacije i drenaže & Konstrukcija sekundarne obloge
5.2.3.1 | 20 m | 153132.7688 | 21 |  | 0 | 0 | 0
5.2.3.2 | 40 m | 153132.7688 | 21 |  | 0 | 0 | 0
5.2.3.3 | 60 m | 153132.7688 | 21 |  | 0 | 0 | 0
5.2.3.4 | 80 m | 153132.7688 | 21 |  | 0 | 0 | 0
5.2.3.5 | 100 m | 153132.7688 | 21 |  | 0 | 0 | 0
5.2.3.6 | 120 m | 153132.7688 | 21 |  | 0 | 0 | 0
5.2.3.7 | 140 m | 153132.7688 | 21 |  | 0 | 0 | 0
5.2.3.8 | 160 m | 153132.7688 | 21 |  | 0 | 0 | 0
5.2.3.9 | 180 m | 153132.7688 | 21 |  | 0 | 0 | 0
5.2.3.10 | 200 m | 153132.7688 | 21 |  | 0 | 0 | 0
5.2.3.11 | 220 m | 153132.7688 | 22 |  | 0 | 0 | 0
5.2.3.12 | 240 m | 153132.7688 | 22 |  | 0 | 0 | 0
5.2.3.13 | 260 m | 153132.7688 | 22 |  | 0 | 0 | 0
5.2.3.14 | 280 m | 153132.7688 | 22 |  | 0 | 0 | 0
5.2.3.15 | 300 m | 153132.7688 | 22 |  | 0 | 0 | 0
5.2.3.16 | 320 m | 153132.7688 | 22 |  | 0 | 0 | 0
5.2.3.17 | 340 m | 153132.7688 | 22 |  | 0 | 0 | 0
5.2.3.18 | 360 m | 153132.7688 | 22 |  | 0 | 0 | 0
5.2.3.19 | 380 m | 153132.7688 | 23 |  | 0 | 0 | 0
5.2.3.20 | 400 m | 153132.7688 | 23 |  | 0 | 0 | 0
5.2.3.21 | 420 m | 153132.7688 | 23 |  | 0 | 0 | 0
5.2.3.22 | 440 m | 153132.7688 | 23 |  | 0 | 0 | 0
5.2.3.23 | 460 m | 153132.7688 | 23 |  | 0 | 0 | 0
5.2.3.24 | 480 m | 153132.7688 | 23 |  | 0 | 0 | 0
5.2.3.25 | 500 m | 153132.7688 | 23 |  | 0 | 0 | 0
5.2.3.26 | 520 m | 153132.7688 | 24 |  | 0 | 0 | 0
5.2.3.27 | 540 m | 153132.7688 | 24 |  | 0 | 0 | 0
5.2.3.28 | 560 m | 153132.7688 | 24 |  | 0 | 0 | 0
5.2.3.29 | 580 m | 153132.7688 | 24 |  | 0 | 0 | 0
5.2.3.30 | 600 m | 153132.7688 | 24 |  | 0 | 0 | 0
5.2.3.31 | 620 m | 153132.7688 | 24 |  | 0 | 0 | 0
5.2.3.32 | 640 m | 153132.7688 | 24 |  | 0 | 0 | 0
5.2.3.33 | 660 m | 153132.7688 | 24 |  | 0 | 0 | 0
5.2.3.34 | 680 m | 153132.7688 | 25 |  | 0 | 0 | 0
5.2.3.35 | 700 m | 153132.7688 | 25 |  | 0 | 0 | 0
5.2.3.36 | 720 m | 153132.7688 | 25 |  | 0 | 0 | 0
5.2.3.37 | 740 m | 153132.7688 | 25 |  | 0 | 0 | 0
5.2.3.38 | 760 m | 153132.7688 | 25 |  | 0 | 0 | 0
5.2.3.39 | 780 m | 153132.7688 | 25 |  | 0 | 0 | 0
5.2.3.40 | 800 m | 153132.7688 | 25 |  | 0 | 0 | 0
5.2.3.41 | 820 m | 153132.7688 | 26 |  | 0 | 0 | 0
5.2.3.42 | 840 m | 153132.7688 | 26 |  | 0 | 0 | 0
5.2.3.43 | 860 m | 153132.7688 | 26 |  | 0 | 0 | 0
5.2.3.44 | 880 m | 153132.7688 | 26 |  | 0 | 0 | 0
5.2.3.45 | 900 m | 153132.7688 | 26 |  | 0 | 0 | 0
5.2.3.46 | 920 m | 153132.7688 | 26 |  | 0 | 0 | 0
5.2.3.47 | 940 m | 153132.7688 | 26 |  | 0 | 0 | 0
5.2.3.48 | 960 m | 153132.7688 | 26 |  | 0 | 0 | 0
5.2.3.49 | 980 m | 153132.7688 | 27 |  | 0 | 0 | 0
5.2.3.50 | 1000 m | 153132.7688 | 27 |  | 0 | 0 | 0
5.2.3.51 | 1020 m | 153132.7688 | 27 |  | 0 | 0 | 0
5.2.3.52 | 1040 m | 153132.7688 | 27 |  | 0 | 0 | 0
5.2.3.53 | 1060 m | 153132.7688 | 27 |  | 0 | 0 | 0
5.2.3.54 | 1080 m | 153132.7688 | 27 |  | 0 | 0 | 0
5.2.3.55 | 1100 m | 153132.7688 | 27 |  | 0 | 0 | 0
5.2.3.56 | 1120 m | 153132.7688 | 28 |  | 0 | 0 | 0
5.2.3.57 | 1140 m | 153132.7688 | 28 |  | 0 | 0 | 0
5.2.3.58 | 1160 m | 153132.7688 | 28 |  | 0 | 0 | 0
5.2.3.59 | 1180 m | 153132.7688 | 28 |  | 0 | 0 | 0
5.2.3.60 | 1200 m | 153132.7688 | 28 |  | 0 | 0 | 0
5.2.3.61 | 1220 m | 153132.7688 | 28 |  | 0 | 0 | 0
5.2.3.62 | 1240 m | 153132.7688 | 28 |  | 0 | 0 | 0
5.2.3.63 | 1260 m | 153132.7688 | 28 |  | 0 | 0 | 0
5.2.3.64 | 1280 m | 153132.7688 | 29 |  | 0 | 0 | 0
5.2.3.65 | 1300 m | 153132.7688 | 29 |  | 0 | 0 | 0
5.2.3.66 | 1320 m | 153132.7688 | 29 |  | 0 | 0 | 0
5.2.3.67 | 1340 m | 153132.7688 | 29 |  | 0 | 0 | 0
5.2.3.68 | 1360 m | 153132.7688 | 29 |  | 0 | 0 | 0
5.2.3.69 | 1380 m | 153132.7688 | 29 |  | 0 | 0 | 0
5.2.3.70 | 1400 m | 153132.7688 | 29 |  | 0 | 0 | 0
5.2.3.71 | 1420 m | 153132.7688 | 30 |  | 0 | 0 | 0
5.2.3.72 | 1440 m | 153132.7688 | 30 |  | 0 | 0 | 0
5.2.3.73 | 1460 m | 153132.7688 | 30 |  | 0 | 0 | 0
5.2.3.74 | 1480 m | 153132.7688 | 30 |  | 0 | 0 | 0
5.2.3.75 | 1500 m | 153132.7688 | 30 |  | 0 | 0 | 0
5.2.3.76 | 1520 m | 153132.7688 | 30 |  | 0 | 0 | 0
5.2.3.77 | 1540 m | 153132.7688 | 30 |  | 0 | 0 | 0
5.2.3.78 | 1560 m | 153132.7688 | 31 |  | 0 | 0 | 0
5.2.3.79 | 1580 m | 153132.7688 | 31 |  | 0 | 0 | 0
5.2.3.80 | 1600 m | 153132.7688 | 31 |  | 0 | 0 | 0
5.2.3.81 | 1620 m | 153132.7688 | 31 |  | 0 | 0 | 0
5.2.3.82 | 1640 m | 153132.7688 | 31 |  | 0 | 0 | 0
5.2.3.83 | 1660 m | 153132.7688 | 31 |  | 0 | 0 | 0
5.2.3.84 | 1680 m | 153132.7688 | 31 |  | 0 | 0 | 0
5.2.3.85 | 1700 m | 153132.7688 | 31 |  | 0 | 0 | 0
5.2.3.86 | 1720 m | 153132.7688 | 32 |  | 0 | 0 | 0
5.2.3.87 | 1740 m | 153132.7688 | 32 |  | 0 | 0 | 0
5.2.3.88 | 1752 m | 91879.6613 | 33 |  | 0 | 0 | 0
5.2.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi I ploca, drenazni sistem)
5.2.4.1 | 200 m | 80000 | 23 |  | 0 | 0 | 0
5.2.4.2 | 400 m | 80000 | 24 |  | 0 | 0 | 0
5.2.4.3 | 600 m | 80000 | 26 |  | 0 | 0 | 0
5.2.4.4 | 800 m | 80000 | 27 |  | 0 | 0 | 0
5.2.4.5 | 1000 m | 80000 | 28 |  | 0 | 0 | 0
5.2.4.6 | 1200 m | 80000 | 29 |  | 0 | 0 | 0
5.2.4.7 | 1400 m | 80000 | 32 |  | 0 | 0 | 0
5.2.4.8 | 1600 m | 80000 | 33 |  | 0 | 0 | 0
5.2.4.9 | 1752 m | 60800 | 34 |  | 0 | 0 | 0
5.2.5 | Construction of pavement/ Izgradnja kolovoza
5.2.5.1 | Left tube/ Lijeva cijev
0-500 m
5.2.5.1.1 | Layer/ Sloj 1 | 36320.91 | 38 |  | 0 | 0 | 0
5.2.5.1.2 | Layer/ Sloj 2 | 36320.91 | 39 |  | 0 | 0 | 0
5.2.5.1.3 | Layer/ Sloj 3 | 40861.02 | 40 |  | 0 | 0 | 0
500-998.93 m
5.2.5.1.4 | Layer/ Sloj 1 | 36243.18 | 38 |  | 0 | 0 | 0
5.2.5.1.5 | Layer/ Sloj 2 | 36243.18 | 39 |  | 0 | 0 | 0
5.2.5.1.6 | Layer/ Sloj 3 | 40773.6 | 40 |  | 0 | 0 | 0
5.2.5.2 | Right tube/ Desna cijev
0-500 m
5.2.5.2.1 | Layer/ Sloj 1 | 36320.91 | 38 |  | 0 | 0 | 0
5.2.5.2.2 | Layer/ Sloj 2 | 36320.91 | 39 |  | 0 | 0 | 0
5.2.5.2.3 | Layer/ Sloj 3 | 40861.02 | 40 |  | 0 | 0 | 0
500-841.82 m
5.2.5.2.4 | Layer/ Sloj 1 | 24830.43 | 38 |  | 0 | 0 | 0
5.2.5.2.5 | Layer/ Sloj 2 | 24830.43 | 39 |  | 0 | 0 | 0
5.2.5.2.6 | Layer/ Sloj 3 | 27934.23 | 40 |  | 0 | 0 | 0
5.2.6 | Tunnel facilities/ Tunelski objekti
5.2.6.1 | Construction of Power Station/ Izgradnja elektro-stanice | 165282.22 | 43 |  | 0 | 0 | 0
5.2.6.2 | Construction of antifire reservoir/ Izgradnja protivpožarnog rezervoara | 86312.55 | 44 |  | 0 | 0 | 0
5.2.7 | Tunnel Equipment / Tunelska oprema
5.2.7.1 | Right tube/ Desna cijev
5.2.7.1.1 | 90% (Equipment installed/Oprema postavljena) | 843746.59 | 44 |  | 0 | 0 | 0
5.2.7.1.2 | 10% (Equipment tested/Oprema ispitana) | 93749.62 | 45 |  | 0 | 0 | 0
5.2.7.2 | Left tube/ Lijeva cijev
5.2.7.2.1 | 90% (Equipment installed/Oprema postavljena) | 997882.98 | 44 |  | 0 | 0 | 0
5.2.7.2.2 | 10% (Equipment tested/ Oprema ispitana) | 110875.88 | 45 |  | 0 | 0 | 0
| Sub Total / Suma stavke 5.2 | 26346166.79 |  |  | 7989758.9792 | 320584.5359 | 8310343.5151
Cost Center/ Troškovno mjesto 5.3 | Road Works/ Radovi na putevima (LK12+480.000—LK13+885.000, RK12+410.000—RK13+790.000)
Completion of/Završetak:
5.3.1 | Subgrade/ Posteljica
5.3.1.1 | Top soil removal/ Uklanjanje humusa
5.3.1.1.1 | 0 - 250 m (LK&RK) | 53021.2025 | 17 |  | 0 | 0 | 0
5.3.1.1.2 | 250 - 500 m (LK&RK) | 53021.2025 | 17 |  | 0 | 0 | 0
5.3.1.1.3 | 500 - 750 m (LK&RK) | 53021.2025 | 17 |  | 0 | 0 | 0
5.3.1.1.4 | 750 - 1000 m (LK&RK) | 53021.2025 | 17 |  | 0 | 0 | 0
5.3.1.1.5 | 1000 - 1250 m (LK&RK) | 53021.2025 | 17 |  | 0 | 0 | 0
5.3.1.1.6 | 1250 - 1405 m (LK); 1250 - 1380 m (RK) | 30222.0854 | 17 |  | 0 | 0 | 0
5.3.1.2 | Earthworks/ Zemljani radovi |  | 30
At every 250 m and 4m height /Na svakih 250m i visini od 4m
5.3.1.2.1 | 12410-12660, layers 1, 2, 3, 4, 5
5.3.1.2.1.1 | 12410-12660, layer 1 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.1.2 | 12410-12660, layer 2 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.1.3 | 12410-12660, layer 3 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.1.4 | 12410-12660, layer 4 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.1.5 | 12410-12660, layer 5 | 33253.5966 |  |  | 0 | 0 | 0
5.3.1.2.2 | 12660-12910, layers 6, 7, 8, 9, 10, 11
5.3.1.2.2.6 | 12660-12910, layer 6 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.2.7 | 12660-12910, layer 7 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.2.8 | 12660-12910, layer 8 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.2.9 | 12660-12910, layer 9 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.2.10 | 12660-12910, layer 10 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.2.11 | 12660-12910, layer 11 | 32166.8777 |  |  | 0 | 0 | 0
5.3.1.2.3 | 12910-13160, layers 12, 13, 14, 15, 16,17
5.3.1.2.3.12 | 12910-13160, layer 12 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.3.13 | 12910-13160, layer 13 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.3.14 | 12910-13160, layer 14 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.3.15 | 12910-13160, layer 15 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.3.16 | 12910-13160, layer 16 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.3.17 | 12910-13160, layer 17 | 106281.1027 |  |  | 0 | 0 | 0
5.3.1.2.4 | 13160-13410, layers 18, 19, 20, 21, 22, 23, 24
5.3.1.2.4.18 | 13160-13410, layer 18 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.4.19 | 13160-13410, layer 19 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.4.20 | 13160-13410, layer 20 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.4.21 | 13160-13410, layer 21 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.4.22 | 13160-13410, layer 22 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.4.23 | 13160-13410, layer 23 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.4.24 | 13160-13410, layer 24 | 31514.8464 |  |  | 0 | 0 | 0
5.3.1.2.5 | 13410-13660 layers 25, 26, 27, 28, 29, 30, 31, 32, 33, 34
5.3.1.2.5.25 | 13410-13660 layer 25 | 38035.1595 |  |  | 0 | 0 | 0
5.3.1.2.5.26 | 13410-13660 layer 26 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.5.27 | 13410-13660 layer 27 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.5.28 | 13410-13660 layer 28 | 86937.5073 |  | 30 | 0 | 86937.5073 | 86937.5073
5.3.1.2.5.29 | 13410-13660 layer 29 | 86937.5073 |  | 27 | 86937.5073 | 0 | 86937.5073
5.3.1.2.5.30 | 13410-13660 layer 30 | 86937.5073 |  | 27 | 86937.5073 | 0 | 86937.5073
5.3.1.2.5.31 | 13410-13660 layer 31 | 86937.5073 |  | 24 &28 | 86937.5073 | 0 | 86937.5073
5.3.1.2.5.32 | 13410-13660 layer 32 | 86937.5073 |  | 23 &28 | 86937.5073 | 0 | 86937.5073
5.3.1.2.5.33 | 13410-13660 layer 33 | 86937.5073 |  | 23& 28 | 86937.5073 | 0 | 86937.5073
5.3.1.2.5.34 | 13410-13660 layer 34 | 86937.5073 |  | 21& 27 | 86937.51 | -0.0026569 | 86937.5073
5.3.1.2.6 | 13660-13790 layers 35, 36, 37, 38, 39, 40, 41, 42, 43, 44, 45, 46, 47
5.3.1.2.6.35 | 13660-13790 layer 35 | 101282.1961 |  |  | 0 | 0 | 0
5.3.1.2.6.36 | 13660-13790 layer 36 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.6.37 | 13660-13790 layer 37 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.6.38 | 13660-13790 layer 38 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.6.39 | 13660-13790 layer 39 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.6.40 | 13660-13790 layer 40 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.6.41 | 13660-13790 layer 41 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.6.42 | 13660-13790 layer 42 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.6.43 | 13660-13790 layer 43 | 86937.5073 |  |  | 0 | 0 | 0
5.3.1.2.6.44 | 13660-13790 layer 44 | 86937.5073 |  | 29 | 86937.5073 | 0 | 86937.5073
5.3.1.2.6.45 | 13660-13790 layer 45 | 86937.5073 |  | 27 | 86937.51 | 0 | 86937.51
5.3.1.2.6.46 | 13660-13790 layer 46 | 86937.5073 |  | 27 | 86937.51 | 0 | 86937.51
5.3.1.2.6.47 | 13660-13790 layer 47 | 86937.5073 |  | 27 | 86937.51 | 0 | 86937.51
5.3.1.3 | Road Foundation/ Temelj puta
5.3.1.3.1 | 0 - 250 m right side/ desna strana | 21037.2015 | 32 |  | 0 | 0 | 0
5.3.1.3.2 | 0 - 250 m left side/ lijeva strana | 21037.2015 | 32 |  | 0 | 0 | 0
5.3.1.3.3 | 250 - 500 m right side/ desna strana | 21037.2015 | 33 |  | 0 | 0 | 0
5.3.1.3.4 | 250 - 500 m left side/ lijeva strana | 21037.2015 | 33 |  | 0 | 0 | 0
5.3.1.3.5 | 500 - 750 m right side/ desna strana | 21037.2015 | 34 |  | 0 | 0 | 0
5.3.1.3.6 | 500 - 750 m left side/ lijeva strana | 21037.2015 | 34 |  | 0 | 0 | 0
5.3.1.3.7 | 750 - 1000 m right side/ desna strana | 21037.2015 | 35 |  | 0 | 0 | 0
5.3.1.3.8 | 750 - 1000 m left side/ lijeva strana | 21037.2015 | 35 |  | 0 | 0 | 0
5.3.1.3.9 | 1000 - 1250 m right side/ desna strana | 21037.2015 | 36 |  | 0 | 0 | 0
5.3.1.3.10 | 1000 - 1250 m left side/ lijeva strana | 21037.2015 | 36 |  | 0 | 0 | 0
5.3.1.3.11 | 1250 - 1380 m, right side/ desna strana | 10939.3448 | 37 |  | 0 | 0 | 0
5.3.1.3.12 | 1250 - 1405 m, left side/ lijeva strana | 13043.0649 | 37 |  | 0 | 0 | 0
5.3.2 | Engineering structures/ Inženjerske konstrukcije
5.3.2.1 | Culvert/ Propust
5.3.2.1 | K12+470 (91m) | 22774.6853 | 25 |  | 0 | 0 | 0
5.3.2.2 | K13+528.9 (105m) | 26278.4831 | 25 |  | 0 | 0 | 0
5.3.2.3 | K13+760 (20m) | 5005.4253 | 25 |  | 0 | 0 | 0
5.3.3 | Water drainage/ Drenaža vode
5.3.3.1 | per one direction of 500m / Na 500m dužine u jednom pravcu |  | 38
5.3.3.1 | LK12+480.000 —LK13+885.000 (1405 m) |  |  |  | 0 | 0 | 0
5.3.3.1.1 | LK12+480.000 —LK12+980.000 (500 m) | 165445.07 |  |  | 0 | 0 | 0
5.3.3.1.2 | LK12+980.000 —LK13+480.000 (500 m) | 165445.07 |  |  | 0 | 0 | 0
5.3.3.1.3 | LK13+480.000 —LK12+885.000 (405 m) | 134010.5067 |  |  | 0 | 0 | 0
5.3.3.2 | RK12+410.000—RK13+790.000 (1380 m) |  |  |  | 0 | 0 | 0
5.3.3.2.1 | RK12+410.000—RK12+910.000 (500 m) | 165445.07 |  |  | 0 | 0 | 0
5.3.3.2.2 | RK12+910.000—RK13+410.000 (500 m) | 165445.07 |  |  | 0 | 0 | 0
5.3.3.2.3 | RK13+410.000—RK13+790.000 (380 m) | 125738.2532 |  |  | 0 | 0 | 0
5.3.4 | Pavement structure/ Kolovozna konstrukcija
5.3.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 0-500m | 55293.3485 | 36 |  | 0 | 0 | 0
5.3.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 0-500m | 55293.3485 | 36 |  | 0 | 0 | 0
5.3.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 500-1000m | 55293.3485 | 37 |  | 0 | 0 | 0
5.3.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 500-1000m | 55293.3485 | 37 |  | 0 | 0 | 0
5.3.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 1000-1335m | 42022.9449 | 38 |  | 0 | 0 | 0
5.3.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 1000-1335m | 44787.6123 | 38 |  | 0 | 0 | 0
5.3.4.7 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 0-500m | 55293.3485 | 39 |  | 0 | 0 | 0
5.3.4.8 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 0-500m | 55293.3485 | 39 |  | 0 | 0 | 0
5.3.4.9 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 500-1000m | 55293.3485 | 39 |  | 0 | 0 | 0
5.3.4.10 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 500-1000m | 55293.3485 | 39 |  | 0 | 0 | 0
5.3.4.11 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 1000-1335m | 42022.9449 | 40 |  | 0 | 0 | 0
5.3.4.12 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 1000-1335m | 44787.6123 | 40 |  | 0 | 0 | 0
5.3.4.13 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 0-500m | 61440.6983 | 41 |  | 0 | 0 | 0
5.3.4.14 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 0-500m | 61440.6983 | 41 |  | 0 | 0 | 0
5.3.4.15 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 500-1000m | 61440.6983 | 41 |  | 0 | 0 | 0
5.3.4.16 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 500-1000m | 61440.6983 | 41 |  | 0 | 0 | 0
5.3.4.17 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 1000-1335m | 46694.9307 | 42 |  | 0 | 0 | 0
5.3.4.18 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 1000-1335m | 49766.9656 | 42 |  | 0 | 0 | 0
5.3.5 | Overbridge/Nadvožnjak PRELJUBOVICA
Foundation concrete/ Temeljni beton
5.3.5.1 | A1 | 7915.2539 | 24 | 29 | 7915.2539 | 0 | 7915.2539
5.3.5.2 | P1 | 17096.44 | 25 |  | 0 | 0 | 0
5.3.5.3 | A2 | 7915.25 | 26 | 30 | 0 | 7915.25 | 7915.25
Abutments and Piers elevation/ Elevacija mosnih stubova
5.3.5.4 | A1 | 23183.4059 | 26 |  | 0 | 0 | 0
5.3.5.5 | P1 - stage 1 (6m) | 14698.2058 | 26 |  | 0 | 0 | 0
5.3.5.6 | P1 - stage 2 (4.6m) | 11268.6245 | 27 |  | 0 | 0 | 0
5.3.5.7 | A2 | 23183.4059 | 28 |  | 0 | 0 | 0
Bridge deck superstructure/ Gornji stroj mosne ploče
5.3.5.8 | A1-P1 | 82440.32 | 29 |  | 0 | 0 | 0
5.3.5.9 | P1-A2 | 82440.32 | 30 |  | 0 | 0 | 0
Bridge deck prestressing/ Prednaprezanje mosne ploče
5.3.5.10 | A1-P1 | 9160.04 | 30 |  | 0 | 0 | 0
5.3.5.11 | P1-A2 | 9160.04 | 31 |  | 0 | 0 | 0
Bridge Furniture/ Mosna estetika
5.3.5.12 | 56m | 250301.56 | 32 |  | 0 | 0 | 0
Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
5.3.5.13 | Asphalt layer/ Sloj asfalta 1 + waterproofing/ hidroizolacija | 12973.55 | 33 |  | 0 | 0 | 0
5.3.5.14 | Asphalt layer/ Sloj asfalta 2 + joints/ spojnice | 35656.39 | 34 |  | 0 | 0 | 0
5.3.6 | Deviation of Existing Road
5.3.6.1 | Preljubovica 1 | 215497.73 | 26 |  | 0 | 0 | 0
5.3.6.2 | Preljubovica 2 | 29939.4 | 27 |  | 0 | 0 | 0
5.3.6.3 | Preljubovica 3 | 44172.06 | 25 |  | 0 | 0 | 0
| Sub Total / Suma stavke 5.3 | 7247436.3242 |  |  | 877290.338 | 94852.7547 | 972143.0927
Cost Center/ Troškovno mjesto 5.4 | Construction of tunnel/ Izgradnja tunela Vilac LK 13+885.000 - LK 14+700.000, RK 13+790.000- RK 14+740.000
Completion of/Završetak:
5.4.1 | Portal construction/ Izgradnja portala
5.4.1.1 | 20% complete/završeno (portal 1) | 130865.64 | 17 | 23 | 130865.64 | 0 | 130865.64
5.4.1.2 | 40% complete/završeno (portal 2) | 130865.64 | 17 | 23 | 130865.64 | 0 | 130865.64
5.4.1.3 | 60% complete/završeno (portal 3) | 130865.64 | 18 |  | 0 | 0 | 0
5.4.1.4 | 80% complete/završeno (portal 4) | 130865.64 | 18 |  | 0 | 0 | 0
5.4.1.5 | 85% (portal 1 complete/završen) | 32716.41 | 39 |  | 0 | 0 | 0
5.4.1.6 | 90% (portal 2 complete/završen) | 32716.41 | 39 |  | 0 | 0 | 0
5.4.1.7 | 95% (portal 3 complete/završen) | 32716.41 | 40 |  | 0 | 0 | 0
5.4.1.8 | 100% (portal 4 complete/završen) | 32716.39 | 40 |  | 0 | 0 | 0
5.4.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
5.4.2.1 | 75 m (N-L, LK 14+688.0- LK14+613.0) | 391721.6 | 21 | 25 | 391721.6 | 0 | 391721.6
5.4.2.2 | 150 m (N-R, RK 14+728.0 - RK 14+653.0) | 391721.6 | 21 | 25 | 391721.6 | 0 | 391721.6
5.4.2.3 | 225 m (N-R, RK 14+653.0 - RK 14+578.0) | 391721.6 | 22 | 25 | 391721.6 | 0 | 391721.6
5.4.2.4 | 300 m | 391721.6 | 22 | 25 | 391721.6 | 0 | 391721.6
5.4.2.5 | 375 m (N-R, RK 14+578.0 - RK 14+503.0) | 391721.6 | 23 | 27 | 391721.6 | 0 | 391721.6
5.4.2.6 | 450 m (N-L, LK 14+538.0- LK14+463.0) | 391721.6 | 23 | 26 | 391721.6 | 0 | 391721.6
5.4.2.7 | 525 m (N-R, RK 14+503.0 - RK 14+428.0) | 391721.6 | 24 | 28 | 391721.6 | 0 | 391721.6
5.4.2.8 | 600 m (N-L, LK 14+463.0- LK14+388.0) | 391721.6 | 24 | 27 | 391721.6 | 0 | 391721.6
5.4.2.9 | 675 m (N-R, RK14+428.0-RK14+353.0) | 391721.6 | 25 | 30 | 0 | 391721.6 | 391721.6
5.4.2.10 | 750 m (N-L,LK14+388.0-LK14+313.0) | 391721.6 | 25 | 30 | 0 | 391721.6 | 391721.6
5.4.2.11 | 825 m (N-R, RK14+353.0-RK14+278.0) | 391721.6 | 26 | 29 | 391721.6 | 0 | 391721.6
5.4.2.12 | 900 m (N-L, LK 14+313.0- LK14+238.0) | 391721.6 | 26 | 28 | 391721.6 | 0 | 391721.6
5.4.2.13 | 920 m (N-R, RK14+278.0-RK14+258.0) | 109189.8015 | 26 | 29 | 109189.8015 | 0 | 109189.8015
5.4.2.14 | 940 m (N-R, RK14+258.0-RK14+238.0) | 109189.8015 | 27 | 29 | 109189.8015 | 0 | 109189.8015
5.4.2.15 | 960 m (N-R, RK14+238.0-RK14+218.0) | 109189.8015 | 27 | 29 | 109189.8015 | 0 | 109189.8015
5.4.2.16 | 980 m (N-R, RK14+218.0-RK14+198.0) | 109189.8015 | 27 | 29 | 109189.8015 | 0 | 109189.8015
5.4.2.17 | 1000 m (N-L, LK14+238.0-LK14+218.0) | 109189.8015 | 27 | 29 | 109189.8015 | 0 | 109189.8015
5.4.2.18 | 1020 m (N-L, LK14+218.0-LK14+198.0) | 109189.8015 | 27 | 29 | 109189.8015 | 0 | 109189.8015
5.4.2.19 | 1040 m (N-L, LK14+198.0-LK14+178.0) | 109189.8015 | 27 | 29 | 109189.8015 | 0 | 109189.8015
5.4.2.20 | 1060 m (N-L, LK14+178.0-LK14+158.0) | 109189.8015 | 27 | 29 | 109189.8015 | 0 | 109189.8015
5.4.2.21 | 1080 m(N-L, LK14+158.0-LK14+138.0) | 109189.8015 | 27 | 29 | 109189.8015 | 0 | 109189.8015
5.4.2.22 | 1100 m (N-L, LK14+138.0-LK14+118.0) | 109189.8015 | 27 | 29 | 109189.8015 | 0 | 109189.8015
5.4.2.23 | 1120 m (N-L, LK14+118.0-LK14+098.0) | 109189.8015 | 28 | 29 | 109189.8015 | 0 | 109189.8015
5.4.2.24 | 1140 m (N-L, LK14+098.0-LK14+078.0) | 109189.8015 | 28 | 29 | 109189.8015 | 0 | 109189.8015
5.4.2.25 | 1160 m (N-R, RK14+198.0~RK14+178.0) | 109189.8015 | 28 | 30 | 0 | 109189.8015 | 109189.8015
5.4.2.26 | 1180 m (N-R, RK14+178.0~RK14+158.0) | 109189.8015 | 28 | 30 | 0 | 109189.8015 | 109189.8015
5.4.2.27 | 1200 m (N-R, RK14+158.0~RK14+138.0) | 109189.8015 | 28 | 30 | 0 | 109189.8015 | 109189.8015
5.4.2.28 | 1220 m (N-R, RK14+138.0~RK14+118.0) | 109189.8015 | 28 | 30 | 0 | 109189.8015 | 109189.8015
5.4.2.29 | 1240 m (N-L,LK14+078.0~LK14+058.0) | 109189.8015 | 28 | 30 | 0 | 109189.8015 | 109189.8015
5.4.2.30 | 1260 m (N-L,LK14+058.0~LK14+038.0) | 109189.8015 | 28 | 30 | 0 | 109189.8015 | 109189.8015
5.4.2.31 | 1280 m (N-L,LK14+038.0~LK14+018.0) | 109189.8015 | 29 | 30 | 0 | 109189.8015 | 109189.8015
5.4.2.32 | 1300 m (N-L,LK14+018.0~LK13+998.0) | 109189.8015 | 29 | 30 | 0 | 109189.8015 | 109189.8015
5.4.2.33 | 1320 m (N-R, RK14+118.0~RK14+098.0) | 109189.8015 | 29 | 30 | 0 | 109189.8015 | 109189.8015
5.4.2.34 | 1340 m (N-R, RK14+098.0~RK14+078.0) | 109189.8015 | 29 | 30 | 0 | 109189.8015 | 109189.8015
5.4.2.35 | 1360 m (N-R, RK14+078.0~RK14+058.0) | 109189.8015 | 29 | 30 | 0 | 109189.8015 | 109189.8015
5.4.2.36 | 1380 m (N-R, RK14+058.0~RK14+038.0) | 109189.8015 | 29 | 30 | 0 | 109189.8015 | 109189.8015
5.4.2.37 | 1400 m | 109189.8015 | 29 |  | 0 | 0 | 0
5.4.2.38 | 1420 m | 109189.8015 | 30 |  | 0 | 0 | 0
5.4.2.39 | 1440 m | 109189.8015 | 30 |  | 0 | 0 | 0
5.4.2.40 | 1460 m | 109189.8015 | 30 |  | 0 | 0 | 0
5.4.2.41 | 1480 m | 109189.8015 | 30 |  | 0 | 0 | 0
5.4.2.42 | 1500 m | 109189.8015 | 30 |  | 0 | 0 | 0
5.4.2.43 | 1520 m | 109189.8015 | 30 |  | 0 | 0 | 0
5.4.2.44 | 1540 m | 109189.8015 | 30 |  | 0 | 0 | 0
5.4.2.45 | 1560 m | 109189.8015 | 31 |  | 0 | 0 | 0
5.4.2.46 | 1580 m | 109189.8015 | 31 |  | 0 | 0 | 0
5.4.2.47 | 1600 m | 109189.8015 | 31 |  | 0 | 0 | 0
5.4.2.48 | 1620 m | 109189.8015 | 31 |  | 0 | 0 | 0
5.4.2.49 | 1640 m | 109189.8015 | 31 |  | 0 | 0 | 0
5.4.2.50 | 1660 m | 109189.8015 | 31 |  | 0 | 0 | 0
5.4.2.51 | 1680 m | 109189.8015 | 31 |  | 0 | 0 | 0
5.4.2.52 | 1700 m | 109189.8015 | 32 |  | 0 | 0 | 0
5.4.2.53 | 1717 m | 92811.3312 | 32 |  | 0 | 0 | 0
5.4.3 | Construction of waterproofing and drainage & Construction of secondary lining / Konstrukcija hidroizolacije i drenaže & Konstrukcija sekundarne obloge
5.4.3.1 | 20 m | 93156.1531 | 21 |  | 0 | 0 | 0
5.4.3.2 | 40 m | 93156.1531 | 21 |  | 0 | 0 | 0
5.4.3.3 | 60 m | 93156.1531 | 21 |  | 0 | 0 | 0
5.4.3.4 | 80 m | 93156.1531 | 21 |  | 0 | 0 | 0
5.4.3.5 | 100 m | 93156.1531 | 21 |  | 0 | 0 | 0
5.4.3.6 | 120 m | 93156.1531 | 21 |  | 0 | 0 | 0
5.4.3.7 | 140 m | 93156.1531 | 21 |  | 0 | 0 | 0
5.4.3.8 | 160 m | 93156.1531 | 21 |  | 0 | 0 | 0
5.4.3.9 | 180 m | 93156.1531 | 21 |  | 0 | 0 | 0
5.4.3.10 | 200 m | 93156.1531 | 22 |  | 0 | 0 | 0
5.4.3.11 | 220 m | 93156.1531 | 22 |  | 0 | 0 | 0
5.4.3.12 | 240 m | 93156.1531 | 22 |  | 0 | 0 | 0
5.4.3.13 | 260 m | 93156.1531 | 22 |  | 0 | 0 | 0
5.4.3.14 | 280 m | 93156.1531 | 22 |  | 0 | 0 | 0
5.4.3.15 | 300 m | 93156.1531 | 22 |  | 0 | 0 | 0
5.4.3.16 | 320 m | 93156.1531 | 22 |  | 0 | 0 | 0
5.4.3.17 | 340 m | 93156.1531 | 22 |  | 0 | 0 | 0
5.4.3.18 | 360 m | 93156.1531 | 22 |  | 0 | 0 | 0
5.4.3.19 | 380 m | 93156.1531 | 23 |  | 0 | 0 | 0
5.4.3.20 | 400 m | 93156.1531 | 23 |  | 0 | 0 | 0
5.4.3.21 | 420 m | 93156.1531 | 23 |  | 0 | 0 | 0
5.4.3.22 | 440 m | 93156.1531 | 23 |  | 0 | 0 | 0
5.4.3.23 | 460 m | 93156.1531 | 23 |  | 0 | 0 | 0
5.4.3.24 | 480 m | 93156.1531 | 23 |  | 0 | 0 | 0
5.4.3.25 | 500 m | 93156.1531 | 23 |  | 0 | 0 | 0
5.4.3.26 | 520 m | 93156.1531 | 24 |  | 0 | 0 | 0
5.4.3.27 | 540 m | 93156.1531 | 24 |  | 0 | 0 | 0
5.4.3.28 | 560 m | 93156.1531 | 24 |  | 0 | 0 | 0
5.4.3.29 | 580 m | 93156.1531 | 24 |  | 0 | 0 | 0
5.4.3.30 | 600 m | 93156.1531 | 24 |  | 0 | 0 | 0
5.4.3.31 | 620 m | 93156.1531 | 24 |  | 0 | 0 | 0
5.4.3.32 | 640 m | 93156.1531 | 24 |  | 0 | 0 | 0
5.4.3.33 | 660 m | 93156.1531 | 24 |  | 0 | 0 | 0
5.4.3.34 | 680 m | 93156.1531 | 25 |  | 0 | 0 | 0
5.4.3.35 | 700 m | 93156.1531 | 25 |  | 0 | 0 | 0
5.4.3.36 | 720 m | 93156.1531 | 25 |  | 0 | 0 | 0
5.4.3.37 | 740 m | 93156.1531 | 25 |  | 0 | 0 | 0
5.4.3.38 | 760 m | 93156.1531 | 25 |  | 0 | 0 | 0
5.4.3.39 | 780 m | 93156.1531 | 25 |  | 0 | 0 | 0
5.4.3.40 | 800 m | 93156.1531 | 25 |  | 0 | 0 | 0
5.4.3.41 | 820 m | 93156.1531 | 25 |  | 0 | 0 | 0
5.4.3.42 | 840 m | 93156.1531 | 26 |  | 0 | 0 | 0
5.4.3.43 | 860 m | 93156.1531 | 26 |  | 0 | 0 | 0
5.4.3.44 | 880 m | 93156.1531 | 26 |  | 0 | 0 | 0
5.4.3.45 | 900 m | 93156.1531 | 26 |  | 0 | 0 | 0
5.4.3.46 | 920 m | 93156.1531 | 26 |  | 0 | 0 | 0
5.4.3.47 | 940 m | 93156.1531 | 26 |  | 0 | 0 | 0
5.4.3.48 | 960 m | 93156.1531 | 26 |  | 0 | 0 | 0
5.4.3.49 | 980 m | 93156.1531 | 27 |  | 0 | 0 | 0
5.4.3.50 | 1000 m | 93156.1531 | 27 |  | 0 | 0 | 0
5.4.3.51 | 1020 m | 93156.1531 | 27 |  | 0 | 0 | 0
5.4.3.52 | 1040 m | 93156.1531 | 27 |  | 0 | 0 | 0
5.4.3.53 | 1060 m | 93156.1531 | 27 |  | 0 | 0 | 0
5.4.3.54 | 1080 m | 93156.1531 | 27 |  | 0 | 0 | 0
5.4.3.55 | 1100 m | 93156.1531 | 27 |  | 0 | 0 | 0
5.4.3.56 | 1120 m | 93156.1531 | 28 |  | 0 | 0 | 0
5.4.3.57 | 1140 m | 93156.1531 | 28 |  | 0 | 0 | 0
5.4.3.58 | 1160 m | 93156.1531 | 28 |  | 0 | 0 | 0
5.4.3.59 | 1180 m | 93156.1531 | 28 |  | 0 | 0 | 0
5.4.3.60 | 1200 m | 93156.1531 | 28 |  | 0 | 0 | 0
5.4.3.61 | 1220 m | 93156.1531 | 28 |  | 0 | 0 | 0
5.4.3.62 | 1240 m | 93156.1531 | 28 |  | 0 | 0 | 0
5.4.3.63 | 1260 m | 93156.1531 | 28 |  | 0 | 0 | 0
5.4.3.64 | 1280 m | 93156.1531 | 29 |  | 0 | 0 | 0
5.4.3.65 | 1300 m | 93156.1531 | 29 |  | 0 | 0 | 0
5.4.3.66 | 1320 m | 93156.1531 | 29 |  | 0 | 0 | 0
5.4.3.67 | 1340 m | 93156.1531 | 29 |  | 0 | 0 | 0
5.4.3.68 | 1360 m | 93156.1531 | 29 |  | 0 | 0 | 0
5.4.3.69 | 1380 m | 93156.1531 | 29 |  | 0 | 0 | 0
5.4.3.70 | 1400 m | 93156.1531 | 29 |  | 0 | 0 | 0
5.4.3.71 | 1420 m | 93156.1531 | 29 |  | 0 | 0 | 0
5.4.3.72 | 1440 m | 93156.1531 | 30 |  | 0 | 0 | 0
5.4.3.73 | 1460 m | 93156.1531 | 30 |  | 0 | 0 | 0
5.4.3.74 | 1480 m | 93156.1531 | 30 |  | 0 | 0 | 0
5.4.3.75 | 1500 m | 93156.1531 | 30 |  | 0 | 0 | 0
5.4.3.76 | 1520 m | 93156.1531 | 30 |  | 0 | 0 | 0
5.4.3.77 | 1540 m | 93156.1531 | 30 |  | 0 | 0 | 0
5.4.3.78 | 1560 m | 93156.1531 | 30 |  | 0 | 0 | 0
5.4.3.79 | 1580 m | 93156.1531 | 31 |  | 0 | 0 | 0
5.4.3.80 | 1600 m | 93156.1531 | 31 |  | 0 | 0 | 0
5.4.3.81 | 1620 m | 93156.1531 | 31 |  | 0 | 0 | 0
5.4.3.82 | 1640 m | 93156.1531 | 31 |  | 0 | 0 | 0
5.4.3.83 | 1660 m | 93156.1531 | 31 |  | 0 | 0 | 0
5.4.3.84 | 1680 m | 93156.1531 | 31 |  | 0 | 0 | 0
5.4.3.85 | 1700 m | 93156.1531 | 31 |  | 0 | 0 | 0
5.4.3.86 | 1717 m | 79182.7301 | 32 |  | 0 | 0 | 0
5.4.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi i ploca, drenazni sistem)
5.4.4.1 | 200 m | 80000 | 24 |  | 0 | 0 | 0
5.4.4.2 | 400 m | 80000 | 25 |  | 0 | 0 | 0
5.4.4.3 | 600 m | 80000 | 26 |  | 0 | 0 | 0
5.4.4.4 | 800 m | 80000 | 27 |  | 0 | 0 | 0
5.4.4.5 | 1000 m | 80000 | 29 |  | 0 | 0 | 0
5.4.4.6 | 1200 m | 80000 | 30 |  | 0 | 0 | 0
5.4.4.7 | 1400 m | 80000 | 31 |  | 0 | 0 | 0
5.4.4.8 | 1600 m | 80000 | 32 |  | 0 | 0 | 0
5.4.4.9 | 1717 m | 46800 | 33 |  | 0 | 0 | 0
5.4.5 | Construction of pavement/ Izgradnja kolovoza
5.4.5.1 | Left tube/ Lijeva cijev
0-500 m
5.4.5.1.1 | Layer/ Sloj 1 | 36320.97 | 37 |  | 0 | 0 | 0
5.4.5.1.2 | Layer/ Sloj 2 | 36320.97 | 38 |  | 0 | 0 | 0
5.4.5.1.3 | Layer/ Sloj 3 | 40861.09 | 39 |  | 0 | 0 | 0
500-899 m
5.4.5.1.4 | Layer/ Sloj 1 | 28984.13 | 37 |  | 0 | 0 | 0
5.4.5.1.5 | Layer/ Sloj 2 | 28984.13 | 38 |  | 0 | 0 | 0
5.4.5.1.6 | Layer/ Sloj 3 | 32607.16 | 39 |  | 0 | 0 | 0
5.4.5.2 | Right tube/ Desna cijev
0-500 m
5.4.5.2.1 | Layer/ Sloj 1 | 36320.97 | 37 |  | 0 | 0 | 0
5.4.5.2.2 | Layer/ Sloj 2 | 36320.97 | 38 |  | 0 | 0 | 0
5.4.5.2.3 | Layer/ Sloj 3 | 40861.09 | 39 |  | 0 | 0 | 0
500-973 m
5.4.5.2.4 | Layer/ Sloj 1 | 34359.64 | 37 |  | 0 | 0 | 0
5.4.5.2.5 | Layer/ Sloj 2 | 34359.64 | 38 |  | 0 | 0 | 0
5.4.5.2.6 | Layer/ Sloj 3 | 38654.59 | 39 |  | 0 | 0 | 0
5.4.6 | Tunnel facilities/ Tunelski objekti
5.4.6.1 | Construction of Power Station/ Izgradnja elektro-stanice | 249149.36 | 42 |  | 0 | 0 | 0
5.4.6.2 | Construction of antifire reservoir/ Izgradnja protivpožarnog rezervoara | 86312.55 | 43 |  | 0 | 0 | 0
5.4.7 | Tunnel Equipment/ Tunelska oprema
5.4.7.1 | Right tube/ Desna cijev
5.4.7.1.1 | 90% (Equipment installed/Oprema postavljena) | 968857.29 | 43 |  | 0 | 0 | 0
5.4.7.1.2 | 10% (Equipment tested/Oprema ispitana) | 107650.81 | 44 |  | 0 | 0 | 0
5.4.7.2 | Left tube/ Lijeva cijev
5.4.7.2.1 | 90% (Equipment installed/Oprema postavljena) | 904800.61 | 43 |  | 0 | 0 | 0
5.4.7.2.2 | 10% (Equipment tested/Oprema ispitana) | 100533.4 | 44 |  | 0 | 0 | 0
| Sub Total / Suma stavke 5.4 | 21341905.88 |  |  | 5489224.8976 | 2093720.8176 | 7582945.7153
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 05 | 56934992.1642 |  |  | 14356274.2148 | 2509158.1082 | 16865432.323

## COST CENTER 06
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
| COST CENTER 06/TROŠKOVNI CENTAR 06 | rev Bridge Piers. Open Route
Cost Center No./ Troškovno mjesto Br. | 06 | Subsection/Podsekcija 2.2 (LK14+700.00-LK19+305, RK14+740-RK19+349.00)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost Center/ Troškovno mjesto 6.1 | Road Works/ Radovi na putevima (LK14+700.00—LK16+241, RK14+740.00—RK15+993.453)
Completion of/Završetak:
6.1.1 | Subgrade/ Posteljica
6.1.1.1 | Top soil removal/ Uklanjanje humusa
6.1.1.1.1 | 0 - 250 m (LK&RK) | 61627.8783 | 17 |  | 0 | 0 | 0
6.1.1.1.2 | 250 - 500 m (LK&RK) | 61627.8783 | 17 |  | 0 | 0 | 0
6.1.1.1.3 | 500 - 750 m (LK&RK) | 61627.8783 | 18 |  | 0 | 0 | 0
6.1.1.1.4 | 750 -1000 m (LK&RK) | 61627.8783 | 18 |  | 0 | 0 | 0
6.1.1.1.5 | 1000 -1250 m (LK&RK) | 61627.8783 | 19 |  | 0 | 0 | 0
6.1.1.1.6 | 1250 -1541.111 m (LK); 1250 - 1253.453 m (RK) | 36306.7087 | 19 |  | 0 | 0 | 0
6.1.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and 4m height /Na svakih 250m i visini od 4m |  | 29
6.1.1.2.1 | 14.740-14.990, layers 1,2,3,4,5,6
6.1.1.2.1.1 | 14.740-14.990, layer 1 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.1.2 | 14.740-14.990, layer 2 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.1.3 | 14.740-14.990, layer 3 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.1.4 | 14.740-14.990, layer 4 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.1.5 | 14.740-14.990, layer 5 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.1.6 | 14.740-14.990, layer 6 | 62116.2405 |  |  | 0 | 0 | 0
6.1.1.2.2 | 14.990-15.240, layers 7,8,9,10,11,12,13,14,15,16,17
6.1.1.2.2.7 | 14.990-15.240, layer 7 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.2.8 | 14.990-15.240, layer 8 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.2.9 | 14.990-15.240, layer 9 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.2.10 | 14.990-15.240, layer 10 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.2.11 | 14.990-15.240, layer 11 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.2.12 | 14.990-15.240, layer 12 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.2.13 | 14.990-15.240, layer 13 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.2.14 | 14.990-15.240, layer 14 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.2.15 | 14.990-15.240, layer 15 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.2.16 | 14.990-15.240, layer 16 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.2.17 | 14.990-15.240, layer 17 | 70559.2246 |  |  | 0 | 0 | 0
6.1.1.2.3 | 15.240-15.490, layers 18,19,20,21,22,23
6.1.1.2.3.18 | 15.240-15.490, layer 18 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.3.19 | 15.240-15.490, layer 19 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.3.20 | 15.240-15.490, layer 20 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.3.21 | 15.240-15.490, layer 21 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.3.22 | 15.240-15.490, layer 22 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.3.23 | 15.240-15.490, layer 23 | 77494.533 |  |  | 0 | 0 | 0
6.1.1.2.4 | 15.490-15.740, layers 24,25,26,27,28,29
6.1.1.2.4.24 | 15.490-15.740, layer 24 | 67242.338 |  |  | 0 | 0 | 0
6.1.1.2.4.25 | 15.490-15.740, layer 25 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.4.26 | 15.490-15.740, layer 26 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.4.27 | 15.490-15.740, layer 27 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.4.28 | 15.490-15.740, layer 28 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.4.29 | 15.490-15.740, layer 29 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.5 | 15.740-15.993,48, layers 30,31.32.33.34.35.36.37,38
6.1.1.2.5.30 | 15.740-15.993,48, layer 30 | 122724.8052 |  |  | 0 | 0 | 0
6.1.1.2.5.31 | 15.740-15.993,48, layer 31 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.5.32 | 15.740-15.993,48, layer 32 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.5.33 | 15.740-15.993,48, layer 33 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.5.34 | 15.740-15.993,48, layer 34 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.5.35 | 15.740-15.993,48, layer 35 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.5.36 | 15.740-15.993,48, layer 36 | 120614.0592 |  |  | 0 | 0 | 0
6.1.1.2.5.37 | 15.740-15.993,48, layer 37 | 120614.0592 |  |  | 120614.06 | 0 | 120614.06
6.1.1.2.5.38 | 15.740-15.993,48, layer 38 | 120614.0592 |  |  | 120614.06 | 0 | 120614.06
6.1.1.3 | Road Foundation/ Temelj puta
6.1.1.3.1 | 0 - 250 m right side/ desna strana | 24452.0701 | 31 |  | 0 | 0 | 0
6.1.1.3.2 | 0 - 250 m left side/ lijeva strana | 24452.0701 | 31 |  | 0 | 0 | 0
6.1.1.3.3 | 250 - 500 m right side/ desna strana | 24452.0701 | 31 |  | 0 | 0 | 0
6.1.1.3.4 | 250 - 500 m left side/ lijeva strana | 24452.0701 | 31 |  | 0 | 0 | 0
6.1.1.3.5 | 500 - 750 m right side/ desna strana | 24452.0701 | 32 |  | 0 | 0 | 0
6.1.1.3.6 | 500 - 750 m left side/ lijeva strana | 24452.0701 | 32 |  | 0 | 0 | 0
6.1.1.3.7 | 750 - 1000 m right side/ desna strana | 24452.0701 | 32 |  | 0 | 0 | 0
6.1.1.3.8 | 750 - 1000 m left side/ lijeva strana | 24452.0701 | 33 |  | 0 | 0 | 0
6.1.1.3.9 | 1000 - 1253.453 m right side/ desna strana | 24789.8021 | 33 |  | 0 | 0 | 0
6.1.1.3.10 | 1000 - 1250 m left side/ lijeva strana | 24452.0701 | 34 |  | 0 | 0 | 0
6.1.1.3.11 | 1250 - 1541.111 m left side/ lijeva strana | 28473.0663 | 34 |  | 0 | 0 | 0
6.1.2 | Engineering structures/ Inženjerske konstrukcije
6.1.2.1 | Culvert/ Propust
6.1.2.1.1 | K14+800 (60m) | 7766.1653 | 24 |  | 0 | 0 | 0
6.1.2.1.2 | K15+608.78 (57m) | 7377.857 | 24 |  | 0 | 0 | 0
6.1.2.1.3 | K15+789.94 (78m) | 10096.0149 | 24 |  | 0 | 0 | 0
6.1.2.1.4 | K0+308.53 (12m) | 1553.2331 | 24 |  | 0 | 0 | 0
6.1.3 | Water drainage/ Drenaža vode
| per one direction of 500m / Na 500m dužine u jednom pravcu |  | 36
6.1.3.1 | LK14+700.000—LK16+241.111 (1541.111 m)
6.1.3.1.1 | LK14+700.000—LK15+200 (500 m) | 223351.9589 |  |  | 0 | 0 | 0
6.1.3.1.2 | LK15+200.000—LK15+700 (500 m) | 223351.9589 |  |  | 0 | 0 | 0
6.1.3.1.3 | LK15+700.000—LK16+241.111 (541.111 m) | 241716.4037 |  |  | 0 | 0 | 0
6.1.3.2 | RK14+740.000—RK15+993.453 1253.453 m)
6.1.3.2.1 | RK14+740.000—RK15+240 (500 m) | 223351.9589 |  |  | 0 | 0 | 0
6.1.3.2.2 | RK15+240.000—RK15+740 (500 m) | 223351.9589 |  |  | 0 | 0 | 0
6.1.3.2.3 | RK15+740.000—RK15+993.453 (253.453 m) | 113218.4481 |  |  | 0 | 0 | 0
6.1.4 | Pavement structure/ Kolovozna konstrukcija
6.1.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 0-500m | 64268.8479 | 37 |  | 0 | 0 | 0
6.1.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 0-500m | 64268.8479 | 37 |  | 0 | 0 | 0
6.1.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 500-1000m | 64268.8479 | 37 |  | 0 | 0 | 0
6.1.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 500-1000m | 64268.8479 | 37 |  | 0 | 0 | 0
6.1.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 1000-1253.453m | 32578.2646 | 37 |  | 0 | 0 | 0
6.1.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 1000-1541.111m | 69553.1611 | 38 |  | 0 | 0 | 0
6.1.4.7 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 0-500m | 64268.8479 | 38 |  | 0 | 0 | 0
6.1.4.8 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 0-500m | 64268.8479 | 38 |  | 0 | 0 | 0
6.1.4.9 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 500-1000m | 64268.8479 | 38 |  | 0 | 0 | 0
6.1.4.10 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 500-1000m | 64268.8479 | 38 |  | 0 | 0 | 0
6.1.4.11 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 1000-1253.453m | 32578.2646 | 38 |  | 0 | 0 | 0
6.1.4.12 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 1000-1541.111m | 69553.1611 | 39 |  | 0 | 0 | 0
6.1.4.13 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 0-500m | 71414.0758 | 39 |  | 0 | 0 | 0
6.1.4.14 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 0-500m | 71414.0758 | 39 |  | 0 | 0 | 0
6.1.4.15 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 500-1000m | 71414.0758 | 39 |  | 0 | 0 | 0
6.1.4.16 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 500-1000m | 71414.0758 | 39 |  | 0 | 0 | 0
6.1.4.17 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 1000-1253.453m | 36200.2235 | 39 |  | 0 | 0 | 0
6.1.4.18 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 1000-1541.111m | 77285.8839
6.1.5 | Deviation of local roads
6.1.5.1 | Kisjelica 1 (K0+000.00 - K0+418.81, 418.81m) | 77961.1954 |  |  | 0 | 0 | 0
6.1.5.2 | Kisjelica 2 (K0+000.00 - K0+476.51,476.51m ) | 88702.011 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 6.1 | 7557533.9018 |  |  | 241228.12 | 0 | 241228.12
Cost Center/ Troškovno mjesto 6.2 | Construction of interchange/Izgradnja petlje (LK16+241.111—LK16+937.953 RK15+993.453—RK16+787.903)
6.2.1 | Completion of/Završetak:
6.2.1.1 | Subgrade/ Posteljica
6.2.1.1 | Top soil removal/ Uklanjanje humusa
6.2.1.1.1 | RK15+993.453—RK16+243.453 (Inc.0 - 250 m (LK&RK)) | 65329.0737 | 18 |  | 0 | 0 | 0
6.2.1.1.2 | RK16+243.453 - RK16+493.453 (Inc.250 - 500 m (LK&RK)) | 65329.0737 | 18 |  | 0 | 0 | 0
6.2.1.1.3 | RK16+493.453 - RK16+743.453 (Inc.500 - 696.842 m (LK); 500 - 750 m (RK)) | 58383.5479 | 19 |  | 0 | 0 | 0
6.2.1.1.4 | RK16+743.453 - RK16+787.903 (Inc.750 - 794.450 m (RK)) | 5807.7547 | 19 |  | 0 | 0 | 0
6.2.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and certain high /Na svakih 250m i određenoj visini |  | 33 |  | 0 | 0 | 0
6.2.1.2.1.1 | 15,993.453 - 16,243.453, layers 1,2,3,4,5,6,7,8,9
6.2.1.2.1.1.1 | 15,993.453,-,16,243.453, layer 1 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.1.2 | 15,993.453,-,16,243.453, layer 2 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.1.3 | 15,993.453,-,16,243.453, layer 3 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.1.4 | 15,993.453,-,16,243.453, layer 4 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.1.5 | 15,993.453,-,16,243.453, layer 5 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.1.6 | 15,993.453,-,16,243.453, layer 6 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.1.7 | 15,993.453,-,16,243.453, layer 7 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.1.8 | 15,993.453,-,16,243.453, layer 8 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.1.9 | 15,993.453,-,16,243.453, layer 9 | 44697.4355 |  |  | 0 | 0 | 0
6.2.1.2.1.2 | 16,243.453 - 16,493.453, layers 10,11,12,13,14
6.2.1.2.1.2.10 | 16,243.453 - 16,493.453, layer 10 | 47315.2896 |  |  | 0 | 0 | 0
6.2.1.2.1.2.11 | 16,243.453 - 16,493.453, layer 11 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.2.12 | 16,243.453 - 16,493.453, layer 12 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.2.13 | 16,243.453 - 16,493.453, layer 13 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.2.14 | 16,243.453 - 16,493.453, layer 14 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.3 | 16,493.453 - 16,787.903, layers 15,16,17,18,19,20,21
6.2.1.2.1.3.15 | 16,493.453 - 16,787.903, layers 15 | 34226.0189 |  |  | 0 | 0 | 0
6.2.1.2.1.3.16 | 16,493.453 - 16,787.903, layers 16 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.3.17 | 16,493.453 - 16,787.903, layers 17 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.3.18 | 16,493.453 - 16,787.903, layers 18 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.3.19 | 16,493.453 - 16,787.903, layers 19 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.3.20 | 16,493.453 - 16,787.903, layers 20 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.1.3.21 | 16,493.453 - 16,787.903, layers 21 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.2.1 | K0+000.00 - K0+250.000, layers 1,2,3,4,5,6
6.2.1.2.2.1.1 | K0+000.00 - K0+250.000, layer 1 | 30929.4619 |  |  | 0 | 0 | 0
6.2.1.2.2.1.2 | K0+000.00 - K0+250.000, layer 2 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.2.1.3 | K0+000.00 - K0+250.000, layer 3 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.2.1.4 | K0+000.00 - K0+250.000, layer 4 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.2.1.5 | K0+000.00 - K0+250.000, layer 5 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.2.1.6 | K0+000.00 - K0+250.000, layer 6 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.2.2 | K0+250.000 - K0+564.19, layers 7,8,9,10,11,12,13
6.2.1.2.2.2.7 | K0+250.000 - K0+564.19, layer 7 | 27051.1594 |  |  | 0 | 0 | 0
6.2.1.2.2.2.8 | K0+250.000 - K0+564.19, layer 8 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.2.2.9 | K0+250.000 - K0+564.19, layer 9 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.2.2.10 | K0+250.000 - K0+564.19, layer 10 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.2.2.11 | K0+250.000 - K0+564.19, layer 11 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.2.2.12 | K0+250.000 - K0+564.19, layer 12 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.2.2.13 | K0+250.000 - K0+564.19, layer 13 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.3.1 | 0+072.69 - 0+322.69. layers 1,2,3,4,5,6
6.2.1.2.3.1.1 | 0+072.69 - 0+322.69. layers 1 | 47897.035 |  |  | 0 | 0 | 0
6.2.1.2.3.1.2 | 0+072.69 - 0+322.69. layers 2 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.3.1.3 | 0+072.69 - 0+322.69. layers 3 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.3.1.4 | 0+072.69 - 0+322.69. layers 4 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.3.1.5 | 0+072.69 - 0+322.69. layers 5 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.3.1.6 | 0+072.69 - 0+322.69. layers 6 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.3.2 | 0+322.69.- 0+632.17, layers 7,8,9,10,11,12
6.2.1.2.3.2.7 | 0+322.69.- 0+632.17, layer 7 | 15804.0824 |  |  | 0 | 0 | 0
6.2.1.2.3.2.8 | 0+322.69.- 0+632.17, layer 8 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.3.2.9 | 0+322.69.- 0+632.17, layer 9 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.3.2.10 | 0+322.69.- 0+632.17, layer 10 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.3.2.11 | 0+322.69.- 0+632.17, layer 11 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.3.2.12 | 0+322.69.- 0+632.17, layer 12 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.4 | K0+172.36 - K0+452.03, layers1,2,3,4,5
6.2.1.2.4.1 | K0+172.36 - K0+452.03, layer 1 | 19488.4697 |  |  | 0 | 0 | 0
6.2.1.2.4.2 | K0+172.36 - K0+452.03, layer 2 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.4.3 | K0+172.36 - K0+452.03, layer 3 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.4.4 | K0+172.36 - K0+452.03, layer 4 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.4.5 | K0+172.36 - K0+452.03, layer 5 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.5 | K0+305.32 - K0+509.33, layers 1,2,3,4,5,6
6.2.1.2.5.1 | K0+305.32 - K0+509.33, layer 1 | 29087.2682 |  |  | 0 | 0 | 0
6.2.1.2.5.2 | K0+305.32 - K0+509.33, layer 2 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.5.3 | K0+305.32 - K0+509.33, layer 3 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.5.4 | K0+305.32 - K0+509.33, layer 4 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.5.5 | K0+305.32 - K0+509.33, layer 5 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.5.6 | K0+305.32 - K0+509.33, layer 6 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.6 | K0+092.98 - K0+293.13, layers 1,2,3,4,5,6,7
6.2.1.2.6.1 | K0+092.98 - K0+293.13, layer 1 | 11828.8224 |  |  | 0 | 0 | 0
6.2.1.2.6.2 | K0+092.98 - K0+293.13, layer 2 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.6.3 | K0+092.98 - K0+293.13, layer 3 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.6.4 | K0+092.98 - K0+293.13, layer 4 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.6.5 | K0+092.98 - K0+293.13, layer 5 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.6.6 | K0+092.98 - K0+293.13, layer 6 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.6.7 | K0+092.98 - K0+293.13, layer 7 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.7 | K0+127.57 - K0+273.76, layers 1,2,3,4,5
6.2.1.2.7.1 | K0+127.57 - K0+273.76, layers 1 | 19973.2575 |  |  | 0 | 0 | 0
6.2.1.2.7.2 | K0+127.57 - K0+273.76, layers 2 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.7.3 | K0+127.57 - K0+273.76, layers 3 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.7.4 | K0+127.57 - K0+273.76, layers 4 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.2.7.5 | K0+127.57 - K0+273.76, layers 5 | 38783.0243 |  |  | 0 | 0 | 0
6.2.1.3 | Road Foundation/ Temelj puta
6.2.1.3.1 | 0 - 250 m right side/ desna strana | 25920.591 | 34 |  | 0 | 0 | 0
6.2.1.3.2 | 0 - 250 m left side/ lijeva strana | 25920.591 | 34 |  | 0 | 0 | 0
6.2.1.3.3 | 250 - 500 m right side/ desna strana | 25920.591 | 35 |  | 0 | 0 | 0
6.2.1.3.4 | 250 - 500 m left side/ lijeva strana | 25920.591 | 35 |  | 0 | 0 | 0
6.2.1.3.5 | 500 - 750 m right side/ desna strana | 25920.591 | 36 |  | 0 | 0 | 0
6.2.1.3.6 | 500 - 696.842 m left side/ lijeva strana | 20409.0439 | 36 |  | 0 | 0 | 0
6.2.1.3.7 | 750 - 794.450 m right side/ desna strana | 4608.6811 | 37 |  | 0 | 0 | 0
6.2.2 | Engineering structures/ Inženjerske konstrukcije
6.2.2.1 | Culvert/ Propust
6.2.2.1.1 | KO+544.98 (11m) | 3828.8686 | 25 |  | 0 | 0 | 0
6.2.2.1.2 | K0+420 (44m) | 15315.4743 | 25 |  | 0 | 0 | 0
6.2.2.1.3 | K0+576.85 (22 m) | 7657.7371 | 25 |  | 0 | 0 | 0
6.2.3 | Water drainage/ Drenaža vode
| per one direction of 500m / Na 500m dužine u jednom pravcu |  | 37
6.2.3.1 | LK16+241.111—LK16+937.953 (732.842 m) |  |  |  | 0 | 0 | 0
6.2.3.1.1 | LK16+241.111—LK16+741.111 (500m) | 231185.0092 |  |  | 0 | 0 | 0
6.2.3.1.2 | LK16+741.111—LK16+937.953 (232.842m) | 107659.1598 |  |  | 0 | 0 | 0
6.2.3.2 | RK15+993.453—RK16+787.903 (794.450 m)
6.2.3.2.1 | RK15+993.453—RK16+493.453 (500m) | 231185.0092 |  |  | 0 | 0 | 0
6.2.3.2.2 | RK16+493.453—RK16+787.903 (294.450 m) | 136144.8519 |  |  | 0 | 0 | 0
6.2.4 | Pavement structure/ Kolovozna konstrukcija |  |  |  | 0 | 0 | 0
6.2.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 0-500m | 68128.6562 | 38 |  | 0 | 0 | 0
6.2.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 0-500m | 68128.6562 | 38 |  | 0 | 0 | 0
6.2.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 500-835m | 40120.9657 | 39 |  | 0 | 0 | 0
6.2.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 500-835m | 26821.1619 | 39 |  | 0 | 0 | 0
6.2.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 0-500m | 68128.6562 | 40 |  | 0 | 0 | 0
6.2.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 0-500m | 68128.6562 | 40 |  | 0 | 0 | 0
6.2.4.7 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 500-835m | 40120.9657 | 41 |  | 0 | 0 | 0
6.2.4.8 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 500-835m | 26821.1619 | 41 |  | 0 | 0 | 0
6.2.4.9 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 0-500m | 75703.0045 | 42 |  | 0 | 0 | 0
6.2.4.10 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 0-500m | 75703.0045 | 42 |  | 0 | 0 | 0
6.2.4.11 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 500-835m | 44581.4994
6.2.4.12 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 500-835m | 29803.0616
6.2.5 | Interchange bridge/ Mosna petlja
Completion of/Završetak:
| Foundation concrete/ Temeljni beton | [5 empty] | 0
6.2.5.1 | A1 | 23858.69 | 18 |  | 0 | 0 | 0
6.2.5.2 | P1 | 35136.74 | 19 |  | 0 | 0 | 0
6.2.5.3 | P2 | 35136.74 | 20 |  | 0 | 0 | 0
6.2.5.4 | P3 | 35136.74 | 21 |  | 0 | 0 | 0
6.2.5.5 | A2 | 23858.69 | 22 |  | 0 | 0 | 0
Abutments and Piers elevation/ Elevacija mosnih stubova
6.2.5.6 | A1 | 48944.34 | 20 |  | 0 | 0 | 0
6.2.5.7 | P1 stage 1 (4m) | 10098.1311 | 20 |  | 0 | 0 | 0
6.2.5.8 | P1 stage 2 (4m) | 10098.1311 | 20 |  | 0 | 0 | 0
6.2.5.9 | P1 stage 3 (4m) | 10098.1311 | 20 |  | 0 | 0 | 0
6.2.5.10 | P2 stage 1 (4m) | 10098.1311 | 21 |  | 0 | 0 | 0
6.2.5.11 | P2 stage 2 (4m) | 10098.1311 | 21 |  | 0 | 0 | 0
6.2.5.12 | P2 stage 3 (4m) | 10098.1311 | 21 |  | 0 | 0 | 0
6.2.5.13 | P2 stage 4 (4m) | 10098.1311 | 22 |  | 0 | 0 | 0
6.2.5.14 | P2 stage 5 (1.5m) | 3786.7992 | 22 |  | 0 | 0 | 0
6.2.5.15 | P3 stage 1 (4m) | 10098.1311 | 23 |  | 0 | 0 | 0
6.2.5.16 | P3 stage 2 (4m) | 10098.1311 | 23 |  | 0 | 0 | 0
6.2.5.17 | P3 stage 3 (4m) | 10098.1311 | 23 |  | 0 | 0 | 0
6.2.5.18 | P3 stage 4 (3.81m) | 9618.4699 | 23 |  | 0 | 0 | 0
6.2.5.19 | A2 | 48944.34 | 24 |  | 0 | 0 | 0
Bridge deck superstructure/ Gornji stroj mosne ploče
6.2.5.13 | A1-P1 | 141298.53 | 23 |  | 0 | 0 | 0
6.2.5.14 | P1-P2 | 179834.49 | 24 |  | 0 | 0 | 0
6.2.5.15 | P2-P3 | 179834.49 | 25 |  | 0 | 0 | 0
6.2.5.16 | P3-A2 | 141298.53 | 26 |  | 0 | 0 | 0
Bridge deck prestressing/ Prednaprezanje mosne ploče
6.2.5.17 | A1-P1 | 15699.84 | 24 |  | 0 | 0 | 0
6.2.5.18 | P1-P2 | 19981.61 | 25 |  | 0 | 0 | 0
6.2.5.19 | P2-P3 | 19981.61 | 26 |  | 0 | 0 | 0
6.2.5.20 | P3-A2 | 15699.82 | 27 |  | 0 | 0 | 0
| Bridge Furniture/ Mosna estetika |  |  |  | 0 | 0 | 0
6.2.5.21 | 50 m | 108241.11 | 29
6.2.5.22 | 100 m | 108241.11 | 30 |  | 0 | 0 | 0
Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
6.2.5.23 | Asphalt layer/Sloj asfalta 1 + waterproofing/hidroizolacija | 45200.48 | 30 |  | 0 | 0 | 0
6.2.5.24 | Asphalt layer/Sloj asfalta 2 + joints/Spojnice | 79177.5 | 30 |  | 0 | 0 | 0
| Sub Total / Suma stavke 6.2 | 5712241.38 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 6.3 | Road Works/Radovi na putevima (LK16+937.953—LK16+974.980 RK16+787.903—RK17+022.056)
Completion of/Završetak:
6.3.1 | Subgrade/ Posteljica
6.3.1.1 | Top soil removal/ Uklanjanje humusa
6.3.1.1.1 | 0 - 37.027 m (LK); 0 - 234.153 m (RK) | 30724.0394 | 18 |  | 0 | 0 | 0
6.3.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and 4m height /Na svakih 250m i visini od 4m |  | 33
6.3.1.2.1 | 16.787,90-17.022,06, layers 1,2,3,4,5,6,7,8,9,10,11
6.3.1.2.1.1 | 16.787,90-17.022,06, layer 1 | 38173.8743 |  |  | 0 | 0 | 0
6.3.1.2.1.2 | 16.787,90-17.022,06, layer 2 | 38173.8743 |  |  | 0 | 0 | 0
6.3.1.2.1.3 | 16.787,90-17.022,06, layer 3 | 38173.8743 |  |  | 0 | 0 | 0
6.3.1.2.1.4 | 16.787,90-17.022,06, layer 4 | 38173.8743 |  |  | 0 | 0 | 0
6.3.1.2.1.5 | 16.787,90-17.022,06, layer 5 | 38173.8743 |  |  | 0 | 0 | 0
6.3.1.2.1.6 | 16.787,90-17.022,06, layer 6 | 38173.8743 |  |  | 0 | 0 | 0
6.3.1.2.1.7 | 16.787,90-17.022,06, layer 7 | 38173.8743 |  |  | 0 | 0 | 0
6.3.1.2.1.8 | 16.787,90-17.022,06, layer 8 | 38173.8743 |  |  | 0 | 0 | 0
6.3.1.2.1.9 | 16.787,90-17.022,06, layer 9 | 38173.8743 |  |  | 0 | 0 | 0
6.3.1.2.1.10 | 16.787,90-17.022,06, layer 10 | 38173.8743 |  |  | 0 | 0 | 0
6.3.1.2.1.11 | 16.787,90-17.022,06, layer 11 | 24717.5836 |  |  | 0 | 0 | 0
6.3.1.3 | Road Foundation/ Temelj puta
6.3.1.3.1 | 0 - 234.153 m, right side/ desna strana | 21051.7791 | 34 |  | 0 | 0 | 0
6.3.1.3.2 | 0 - 37.027 m, left side/ lijeva strana | 3328.9525 | 34 |  | 0 | 0 | 0
6.3.2 | Engineering structures/ Inženjerske konstrukcije
6.3.2.1 | Concrete wall / Betonski zid |  | 32
80% for the concrete wall, the milestone is 50m lenth, no matter the hight+ 5% for the "after work" the whole lenth of each retaining wall + 5% for the "correction of the crown" the whole lenth of each retaining wall+10% for the "wall surface" the whole lenth of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
6.3.2.1.1 | Concrete wall/ Betonski zid LK16+964.58-LK16+970.58 (6m)
6.3.2.1.1.1 | Concrete wall/ Betonski zid LK16+964.58-LK16+970.58 - 80% | 14733.4297 |  |  | 0 | 0 | 0
6.3.2.1.1.2 | Concrete wall/ Betonski zid LK16+964.58-LK16+970.58- After work 5% | 920.8394 |  |  | 0 | 0 | 0
6.3.2.1.1.3 | Concrete wall/ Betonski zid LK16+964.58-LK16+970.58- Correction of the crown 5% | 920.8394 |  |  | 0 | 0 | 0
6.3.2.1.1.4 | Concrete wall/ Betonski zid LK16+964.58-LK16+970.58- Wall surface 10% | 1841.6787 |  |  | 0 | 0 | 0
6.3.2.1.2 | Concrete wall/ Betonski zid RK17+008.83--RK17+018.3 (9.47m)
6.3.2.1.2.1 | Concrete wall/ Betonski zid RK17+008.83--RK17+018.3 - 80% | 23254.2631 |  |  | 0 | 0 | 0
6.3.2.1.2.2 | Concrete wall/ Betonski zid RK17+008.83--RK17+018.3- After work 5% | 1453.3914 |  |  | 0 | 0 | 0
6.3.2.1.2.3 | Concrete wall/ Betonski zid RK17+008.83--RK17+018.3- Correction of the crown 5% | 1453.3914 |  |  | 0 | 0 | 0
6.3.2.1.2.4 | Concrete wall/ Betonski zid RK17+008.83--RK17+018.3- Wall surface 10% | 2906.7829 |  |  | 0 | 0 | 0
6.3.2.2 | Culvert/ Propust
6.3.2.2.1 | K16+806.23 (43m) | 13738.4327 | 32 |  | 0 | 0 | 0
6.3.3 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
6.3.3.1 | LK16+937.953—LK16+974.980 (37.027 m) | 15203.7874 | 38 |  | 0 | 0 | 0
6.3.3.2 | RK16+787.903—RK17+022.056 (234.153 m) | 96146.3913 | 38 |  | 0 | 0 | 0
6.3.4 | Pavement structure/ Kolovozna konstrukcija
6.3.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana | 27665.8296 | 39 |  | 0 | 0 | 0
6.3.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana | 4374.8433 | 39 |  | 0 | 0 | 0
6.3.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana | 27665.8296 | 40 |  | 0 | 0 | 0
6.3.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana | 4374.8433 | 40 |  | 0 | 0 | 0
6.3.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana | 30741.6392 | 41 |  | 0 | 0 | 0
6.3.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana | 4861.2261 | 41 |  | 0 | 0 | 0
| Sub Total / Suma stavka 6.3 | 733818.5359 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 6.4 | Construction of bridge/Izgradnja mosta Djuricev Laz (LK16+974.980—LK17+325.673 RK17+022.056—RK17+347.268)
6.4.1 | Completion of/Završetak:
Left bridge/ Lijevi most
Foundation concrete/ Temeljni beton
6.4.1.1 | A1 | 53232.04 | 19 |  | 0 | 0 | 0
6.4.1.2 | P1 | 24602.54 | 21 |  | 0 | 0 | 0
6.4.1.3 | P2 | 24602.54 | 22 |  | 0 | 0 | 0
6.4.1.4 | P3 | 24602.54 | 22 |  | 0 | 0 | 0
6.4.1.5 | P4 | 24602.54 | 23 |  | 0 | 0 | 0
6.4.1.6 | P5 | 24602.54 | 23 |  | 0 | 0 | 0
6.4.1.7 | P6 | 24602.54 | 24 |  | 0 | 0 | 0
6.4.1.8 | P7 | 24602.54 | 24 |  | 0 | 0 | 0
6.4.1.9 | P8 | 24602.54 | 25 | 30 | 0 | 24602.54 | 24602.54
6.4.1.10 | P9 | 24602.54 | 25 |  | 0 | 0 | 0
6.4.1.11 | P10 | 24602.54 | 26 |  | 0 | 0 | 0
6.4.1.12 | P11 | 24602.54 | 26 |  | 0 | 0 | 0
6.4.1.13 | P12 | 24602.54 | 27 |  | 0 | 0 | 0
6.4.1.14 | A2 | 53232.04 | 27 |  | 0 | 0 | 0
6.4.2 | Abutments and Piers elevation/ Elevacija mosnih stubova
6.4.2.1 | A1 | 58960.29 | 20 |  | 0 | 0 | 0
6.4.2.2 | P1 stage 1 (5.5m) | 10797.5665 | 19 |  | 0 | 0 | 0
6.4.2.3 | P1 stage 2 (4m) | 7852.7756 | 19 |  | 0 | 0 | 0
6.4.2.4 | P1 stage 3 (4m) | 7852.7756 | 20 |  | 0 | 0 | 0
6.4.2.5 | P1 stage 4 (2.4m) | 4711.6654 | 20 |  | 0 | 0 | 0
6.4.2.6 | P1 stage 5 (1m) | 1963.1939 | 20 |  | 0 | 0 | 0
6.4.2.7 | P2 stage 1 (4.5m) | 8834.3726 | 20 |  | 0 | 0 | 0
6.4.2.8 | P2 stage 2 (4m) | 7852.7756 | 20 |  | 0 | 0 | 0
6.4.2.9 | P2 stage 3 (4m) | 7852.7756 | 20 |  | 0 | 0 | 0
6.4.2.10 | P2 stage 4 (4m) | 7852.7756 | 21 |  | 0 | 0 | 0
6.4.2.11 | P2 stage 5 (4m) | 7852.7756 | 21 |  | 0 | 0 | 0
6.4.2.12 | P2 stage 6 (4m) | 7852.7756 | 21 |  | 0 | 0 | 0
6.4.2.13 | P2 stage 7 (2.4m) | 4711.6654 | 21 |  | 0 | 0 | 0
6.4.2.14 | P3 stage 1 (4.5m) | 8834.3726 | 19 |  | 0 | 0 | 0
6.4.2.15 | P3 stage 2 (4m) | 7852.7756 | 19 |  | 0 | 0 | 0
6.4.2.16 | P3 stage 3 (4m) | 7852.7756 | 20 |  | 0 | 0 | 0
6.4.2.17 | P3 stage 4 (4m) | 7852.7756 | 20 |  | 0 | 0 | 0
6.4.2.18 | P3 stage 5 (4m) | 7852.7756 | 21 |  | 0 | 0 | 0
6.4.2.19 | P3 stage 6 (3.9m) | 7656.4562 | 21 |  | 0 | 0 | 0
6.4.2.20 | P4 stage 1 (4.5m) | 8834.3726 | 20 |  | 0 | 0 | 0
6.4.2.21 | P4 stage 2 (4m) | 7852.7756 | 20 |  | 0 | 0 | 0
6.4.2.22 | P4 stage 3 (4m) | 7852.7756 | 21 |  | 0 | 0 | 0
6.4.2.23 | P4 stage 4 (4m) | 7852.7756 | 21 |  | 0 | 0 | 0
6.4.2.24 | P4 stage 5 (4m) | 7852.7756 | 22 |  | 0 | 0 | 0
6.4.2.25 | P4 stage 6 (2.9m) | 5693.2623 | 22 |  | 0 | 0 | 0
6.4.2.26 | P5 stage 1 (4.5m) | 8834.3726 | 21 |  | 0 | 0 | 0
6.4.2.27 | P5 stage 2 (4m) | 7852.7756 | 21 |  | 0 | 0 | 0
6.4.2.28 | P5 stage 3 (4m) | 7852.7756 | 22 |  | 0 | 0 | 0
6.4.2.29 | P5 stage 4 (4m) | 7852.7756 | 22 |  | 0 | 0 | 0
6.4.2.30 | P5 stage 5 (4m) | 7852.7756 | 22 |  | 0 | 0 | 0
6.4.2.31 | P5 stage 6 (4m) | 7852.7756 | 23 |  | 0 | 0 | 0
6.4.2.32 | P5 stage 7 (2.9m) | 5693.2623 | 23 |  | 0 | 0 | 0
6.4.2.33 | P6 stage 1 (4.5m) | 8834.3726 | 23 |  | 0 | 0 | 0
6.4.2.34 | P6 stage 2 (4m) | 7852.7756 | 21 |  | 0 | 0 | 0
6.4.2.35 | P6 stage 3 (4m) | 7852.7756 | 21 |  | 0 | 0 | 0
6.4.2.36 | P6 stage 4 (4m) | 7852.7756 | 22 |  | 0 | 0 | 0
6.4.2.37 | P6 stage 5 (4m) | 7852.7756 | 22 |  | 0 | 0 | 0
6.4.2.38 | P6 stage 6 (4m) | 7852.7756 | 23 |  | 0 | 0 | 0
6.4.2.39 | P6 stage 7 (4m) | 7852.7756 | 23 |  | 0 | 0 | 0
6.4.2.40 | P6 stage 8 (4.4m) | 8638.0532 | 24 |  | 0 | 0 | 0
6.4.2.41 | P7 stage 1 (5.5m) | 10797.5665 | 24 |  | 0 | 0 | 0
6.4.2.42 | P7 stage 2 (4m) | 7852.7756 | 22 |  | 0 | 0 | 0
6.4.2.43 | P7 stage 3 (4m) | 7852.7756 | 22 |  | 0 | 0 | 0
6.4.2.44 | P7 stage 4 (4m) | 7852.7756 | 23 |  | 0 | 0 | 0
6.4.2.45 | P7 stage 5 (4m) | 7852.7756 | 23 |  | 0 | 0 | 0
6.4.2.46 | P7 stage 6 (4m) | 7852.7756 | 24 |  | 0 | 0 | 0
6.4.2.47 | P7 stage 7 (4m) | 7852.7756 | 24 |  | 0 | 0 | 0
6.4.2.48 | P7 stage 8 (3.4m) | 6674.8593 | 25 |  | 0 | 0 | 0
6.4.2.49 | P8 stage 1 (4.5m) | 8834.3726 | 25 |  | 0 | 0 | 0
6.4.2.50 | P8 stage 2 (4m) | 7852.7756 | 23 |  | 0 | 0 | 0
6.4.2.51 | P8 stage 3 (4m) | 7852.7756 | 23 |  | 0 | 0 | 0
6.4.2.52 | P8 stage 4 (4m) | 7852.7756 | 24 |  | 0 | 0 | 0
6.4.2.53 | P8 stage 5 (4m) | 7852.7756 | 24 |  | 0 | 0 | 0
6.4.2.54 | P8 stage 6 (4m) | 7852.7756 | 25 |  | 0 | 0 | 0
6.4.2.55 | P8 stage 7 (3.4m) | 6674.8593 | 25 |  | 0 | 0 | 0
6.4.2.56 | P9 stage 1 (4.5m) | 8834.3726 | 25 |  | 0 | 0 | 0
6.4.2.57 | P9 stage 2 (4m) | 7852.7756 | 25 |  | 0 | 0 | 0
6.4.2.58 | P9 stage 3 (4m) | 7852.7756 | 25 |  | 0 | 0 | 0
6.4.2.59 | P9 stage 4 (4m) | 7852.7756 | 26 |  | 0 | 0 | 0
6.4.2.60 | P9 stage 5 (4m) | 7852.7756 | 26 |  | 0 | 0 | 0
6.4.2.61 | P9 stage 6 (4m) | 7852.7756 | 27 |  | 0 | 0 | 0
6.4.2.62 | P9 stage 7 (4m) | 7852.7756 | 27 |  | 0 | 0 | 0
6.4.2.63 | P9 stage 8 (2.4m) | 4711.6654 | 27 |  | 0 | 0 | 0
6.4.2.64 | P10 stage 1 (4.5m) | 8834.3726 | 24 |  | 0 | 0 | 0
6.4.2.65 | P10 stage 2 (4m) | 7852.7756 | 24 |  | 0 | 0 | 0
6.4.2.66 | P10 stage 3 (4m) | 7852.7756 | 25 |  | 0 | 0 | 0
6.4.2.67 | P10 stage 4 (4m) | 7852.7756 | 25 |  | 0 | 0 | 0
6.4.2.68 | P10 stage 5 (4m) | 7852.7756 | 26 |  | 0 | 0 | 0
6.4.2.69 | P10 stage 6 (4m) | 7852.7756 | 26 |  | 0 | 0 | 0
6.4.2.70 | P10 stage 7 (4m) | 7852.7756 | 27 |  | 0 | 0 | 0
6.4.2.71 | P10 stage 8 (2.4m) | 4711.6654 | 27 |  | 0 | 0 | 0
6.4.2.72 | P11 stage 1 (4.5m) | 8834.3726 | 25 |  | 0 | 0 | 0
6.4.2.73 | P11 stage 2 (4m) | 7852.7756 | 25 |  | 0 | 0 | 0
6.4.2.74 | P11 stage 3 (4m) | 7852.7756 | 26 |  | 0 | 0 | 0
6.4.2.75 | P11 stage 4 (4m) | 7852.7756 | 26 |  | 0 | 0 | 0
6.4.2.76 | P11 stage 5 (4m) | 7852.7756 | 27 |  | 0 | 0 | 0
6.4.2.77 | P11 stage 6 (4.9m) | 9619.6501 | 27 |  | 0 | 0 | 0
6.4.2.78 | P12 stage 1 (4.5m) | 8834.3726 | 26 |  | 0 | 0 | 0
6.4.2.79 | P12 stage 2 (4m) | 7852.7756 | 26 |  | 0 | 0 | 0
6.4.2.80 | P12 stage 3 (4m) | 7852.7756 | 27 |  | 0 | 0 | 0
6.4.2.81 | P12 stage 4 (2.4m) | 4711.6654 | 27 |  | 0 | 0 | 0
6.4.2.82 | A2 | 58960.29 | 27 |  | 0 | 0 | 0
6.4.3 | Bridge deck superstructure/ Gornji stroj mosne ploče
6.4.3.1 | A1-P1 | 114506.77 | 23 |  | 0 | 0 | 0
6.4.3.2 | P1-P2 | 145735.88 | 24 |  | 0 | 0 | 0
6.4.3.3 | P2-P3 | 145735.88 | 25 |  | 0 | 0 | 0
6.4.3.4 | P3-P4 | 145735.88 | 26 |  | 0 | 0 | 0
6.4.3.5 | P4-P5 | 145735.88 | 27 |  | 0 | 0 | 0
6.4.3.6 | P5-P6 | 145735.88 | 28 |  | 0 | 0 | 0
6.4.3.7 | P6-P7 | 145735.88 | 29 |  | 0 | 0 | 0
6.4.3.8 | P7-P8 | 145735.88 | 30 |  | 0 | 0 | 0
6.4.3.9 | P8-P9 | 145735.88 | 32 |  | 0 | 0 | 0
6.4.3.10 | P9-P10 | 145735.88 | 33 |  | 0 | 0 | 0
6.4.3.11 | P10-P11 | 145735.88 | 34 |  | 0 | 0 | 0
6.4.3.12 | P11-P12 | 145735.88 | 35
6.4.3.13 | P12-A2 | 114506.77 | 36 |  | 0 | 0 | 0
6.4.4 | Bridge deck prestressing/ Prednaprezanje mosne ploče
6.4.4.1 | A1-P1 | 12722.97 | 23 |  | 0 | 0 | 0
6.4.4.2 | P1-P2 | 16192.88 | 24 |  | 0 | 0 | 0
6.4.4.3 | P2-P3 | 16192.88 | 25 |  | 0 | 0 | 0
6.4.4.4 | P3-P4 | 16192.88 | 26 |  | 0 | 0 | 0
6.4.4.5 | P4-P5 | 16192.88 | 27 |  | 0 | 0 | 0
6.4.4.6 | P5-P6 | 16192.88 | 28 |  | 0 | 0 | 0
6.4.4.7 | P6-P7 | 16192.88 | 29 |  | 0 | 0 | 0
6.4.4.8 | P7-P8 | 16192.88 | 30 |  | 0 | 0 | 0
6.4.4.9 | P8-P9 | 16192.88 | 32 |  | 0 | 0 | 0
6.4.4.10 | P9-P10 | 16192.88 | 33 |  | 0 | 0 | 0
6.4.4.11 | P10-P11 | 16192.88 | 34 |  | 0 | 0 | 0
6.4.4.12 | P11-P12 | 16192.88 | 35
6.4.4.13 | P12-A2 | 12722.97 | 36 |  | 0 | 0 | 0
6.4.5 | Bridge Furniture/ Mosna estetika
6.4.5.1 | 50 m | 54382.58 | 37 |  | 0 | 0 | 0
6.4.5.2 | 100 m | 54382.58 | 38 |  | 0 | 0 | 0
6.4.5.3 | 150 m | 54382.58 | 38 |  | 0 | 0 | 0
6.4.5.4 | 200 m | 54382.58 | 39 |  | 0 | 0 | 0
6.4.5.5 | 250 m | 54382.58 | 39 |  | 0 | 0 | 0
6.4.5.6 | 300 m | 54382.58 | 40
6.4.5.7 | 352 m | 56557.77 | 40 |  | 0 | 0 | 0
6.4.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
6.4.6.1 | Asphalt layer/Sloj asfalta 1 + waterproofing/hidroizolacija | 132327.31 | 39
6.4.6.2 | Asphalt layer/Sloj asfalta 2 + joints/Spojnice | 99730.53 | 40
Right Bridge/ Desni most
6.4.7 | Foundation concrete/ Temeljni beton
6.4.7.1 | A1 | 49110.85 | 19 |  | 0 | 0 | 0
6.4.7.2 | P1 | 23993.84 | 21 |  | 0 | 0 | 0
6.4.7.3 | P2 | 23993.84 | 22 |  | 0 | 0 | 0
6.4.7.4 | P3 | 23993.84 | 23 |  | 0 | 0 | 0
6.4.7.5 | P4 | 23993.84 | 23 |  | 0 | 0 | 0
6.4.7.6 | P5 | 23993.84 | 24 |  | 0 | 0 | 0
6.4.7.7 | P6 | 23993.84 | 24 |  | 0 | 0 | 0
6.4.7.8 | P7 | 23993.84 | 25 |  | 0 | 0 | 0
6.4.7.9 | P8 | 23993.84 | 25 |  | 0 | 0 | 0
6.4.7.10 | P9 | 23993.84 | 26 |  | 0 | 0 | 0
6.4.7.11 | P10 | 23993.84 | 26 |  | 0 | 0 | 0
6.4.7.12 | P11 | 23993.84 | 27
6.4.7.13 | A2 | 49110.85 | 27 |  | 0 | 0 | 0
6.4.8 | Abutments and Piers elevation/ Elevacija mosnih stubova
6.4.8.1 | A1 | 44297.31 | 20 |  | 0 | 0 | 0
6.4.8.2 | P1 stage 1 (4.5m) | 9941.3028 | 21 |  | 0 | 0 | 0
6.4.8.3 | P1 stage 2 (4m) | 8836.7136 | 21 |  | 0 | 0 | 0
6.4.8.4 | P1 stage 3 (4.9m) | 10824.9741 | 22 |  | 0 | 0 | 0
6.4.8.5 | P1 stage 4 (1m) | 2209.1784 | 22 |  | 0 | 0 | 0
6.4.8.6 | P2 stage 1 (4.5m) | 9941.3028 | 21 |  | 0 | 0 | 0
6.4.8.7 | P2 stage 2 (4m) | 8836.7136 | 21 |  | 0 | 0 | 0
6.4.8.8 | P2 stage 3 (4m) | 8836.7136 | 22 |  | 0 | 0 | 0
6.4.8.9 | P2 stage 4 (4m) | 8836.7136 | 22 |  | 0 | 0 | 0
6.4.8.10 | P2 stage 5 (4m) | 8836.7136 | 23 |  | 0 | 0 | 0
6.4.8.11 | P3 stage 1 (5.8m) | 12813.2347 | 21 |  | 0 | 0 | 0
6.4.8.12 | P3 stage 2 (4m) | 8836.7136 | 21 |  | 0 | 0 | 0
6.4.8.13 | P3 stage 3 (4m) | 8836.7136 | 22 |  | 0 | 0 | 0
6.4.8.14 | P3 stage 4 (3.1m) | 6848.453 | 22 |  | 0 | 0 | 0
6.4.8.15 | P4 stage 1 (3.8m) | 8394.8779 | 23 |  | 0 | 0 | 0
6.4.8.16 | P4 stage 2 (4m) | 8836.7136 | 23 |  | 0 | 0 | 0
6.4.8.17 | P4 stage 3 (4m) | 8836.7136 | 24 |  | 0 | 0 | 0
6.4.8.18 | P4 stage 4 (4.1m) | 9057.6314 | 24 |  | 0 | 0 | 0
6.4.8.19 | P5 stage 1 (4.5m) | 9941.3028 | 23 |  | 0 | 0 | 0
6.4.8.20 | P5 stage 2 (4m) | 8836.7136 | 23 |  | 0 | 0 | 0
6.4.8.21 | P5 stage 3 (4m) | 8836.7136 | 24 |  | 0 | 0 | 0
6.4.8.22 | P5 stage 4 (4m) | 8836.7136 | 24 |  | 0 | 0 | 0
6.4.8.23 | P5 stage 5 (4.4m) | 9720.3849 | 25 |  | 0 | 0 | 0
6.4.8.24 | P6 stage 1 (4.5m) | 9941.3028 | 24 |  | 0 | 0 | 0
6.4.8.25 | P6 stage 2 (4m) | 8836.7136 | 24 |  | 0 | 0 | 0
6.4.8.26 | P6 stage 3 (4m) | 8836.7136 | 25 |  | 0 | 0 | 0
6.4.8.27 | P6 stage 4 (4m) | 8836.7136 | 25 |  | 0 | 0 | 0
6.4.8.28 | P6 stage 5 (4m) | 8836.7136 | 26 |  | 0 | 0 | 0
6.4.8.29 | P6 stage 6 (2.9m) | 6406.6173 | 26 |  | 0 | 0 | 0
6.4.8.30 | P7 stage 1 (4.5m) | 9941.3028 | 25 |  | 0 | 0 | 0
6.4.8.31 | P7 stage 2 (4m) | 8836.7136 | 25 |  | 0 | 0 | 0
6.4.8.32 | P7 stage 3 (4m) | 8836.7136 | 26 |  | 0 | 0 | 0
6.4.8.33 | P7 stage 4 (4m) | 8836.7136 | 26 |  | 0 | 0 | 0
6.4.8.34 | P7 stage 5 (4m) | 8836.7136 | 27 |  | 0 | 0 | 0
6.4.8.35 | P7 stage 6 (2.4m) | 5302.0281 | 27 |  | 0 | 0 | 0
6.4.8.36 | P8 stage 1 (4.5m) | 9941.3028 | 26 |  | 0 | 0 | 0
6.4.8.37 | P8 stage 2 (4m) | 8836.7136 | 26 |  | 0 | 0 | 0
6.4.8.38 | P8 stage 3 (4m) | 8836.7136 | 27 |  | 0 | 0 | 0
6.4.8.39 | P8 stage 4 (4m) | 8836.7136 | 27 |  | 0 | 0 | 0
6.4.8.40 | P8 stage 5 (2.9m) | 6406.6173 | 28 |  | 0 | 0 | 0
6.4.8.41 | P8 stage 6 (2.5m) | 5522.946 | 28 |  | 0 | 0 | 0
6.4.8.42 | P9 stage 1 (4.5m) | 9941.3028 | 27 |  | 0 | 0 | 0
6.4.8.43 | P9 stage 2 (4m) | 8836.7136 | 27 |  | 0 | 0 | 0
6.4.8.44 | P9 stage 3 (4m) | 8836.7136 | 28 |  | 0 | 0 | 0
6.4.8.45 | P9 stage 4 (4m) | 8836.7136 | 28 |  | 0 | 0 | 0
6.4.8.46 | P9 stage 5 (4m) | 8836.7136 | 29 |  | 0 | 0 | 0
6.4.8.47 | P9 stage 6 (4.4) | 9720.3849 | 29 |  | 0 | 0 | 0
6.4.8.48 | P10 stage 1 (4.5m) | 9941.3028 | 28 |  | 0 | 0 | 0
6.4.8.49 | P10 stage 2 (4m) | 8836.7136 | 28 |  | 0 | 0 | 0
6.4.8.50 | P10 stage 3 (4m) | 8836.7136 | 29 |  | 0 | 0 | 0
6.4.8.51 | P10 stage 4 (4m) | 8836.7136 | 29 |  | 0 | 0 | 0
6.4.8.52 | P10 stage 5 (3.4m) | 7511.2065 | 30 |  | 0 | 0 | 0
6.4.8.53 | P10 stage 6 (2.5m) | 5522.946 | 30 |  | 0 | 0 | 0
6.4.8.54 | P11 stage 1 (4.5m) | 9941.3028 | 29 |  | 0 | 0 | 0
6.4.8.55 | P11 stage 2 (4m) | 8836.7136 | 29 |  | 0 | 0 | 0
6.4.8.56 | P11 stage 3 (4.4m) | 9720.3849 | 30 |  | 0 | 0 | 0
6.4.8.57 | P11 stage 4 (1m) | 2209.1784 | 30 |  | 0 | 0 | 0
6.4.8.58 | A2 | 44297.31 | 30 |  | 0 | 0 | 0
6.4.9 | Bridge deck superstructure/ Gornji stroj mosne ploče
6.4.9.1 | A1-P1 | 113717.91 | 22 |  | 0 | 0 | 0
6.4.9.2 | P1-P2 | 144731.89 | 24 |  | 0 | 0 | 0
6.4.9.3 | P2-P3 | 144731.89 | 26 |  | 0 | 0 | 0
6.4.9.4 | P3-P4 | 144731.89 | 28 |  | 0 | 0 | 0
6.4.9.5 | P4-P5 | 144731.89 | 29 |  | 0 | 0 | 0
6.4.9.6 | P5-P6 | 144731.89 | 30 |  | 0 | 0 | 0
6.4.9.7 | P6-P7 | 144731.89 | 31 |  | 0 | 0 | 0
6.4.9.8 | P7-P8 | 144731.89 | 32 |  | 0 | 0 | 0
6.4.9.9 | P8-P9 | 144731.89 | 33 |  | 0 | 0 | 0
6.4.9.10 | P9-P10 | 144731.89 | 34 |  | 0 | 0 | 0
6.4.9.11 | P10-P11 | 144731.89 | 35
6.4.9.12 | P11-A2 | 113717.91 | 36 |  | 0 | 0 | 0
6.4.10 | Bridge deck prestressing/ Prednaprezanje mosne ploče
6.4.10.1 | A1-P1 | 12635.32 | 22 |  | 0 | 0 | 0
6.4.10.2 | P1-P2 | 16081.32 | 24 |  | 0 | 0 | 0
6.4.10.3 | P2-P3 | 16081.32 | 26 |  | 0 | 0 | 0
6.4.10.4 | P3-P4 | 16081.32 | 28 |  | 0 | 0 | 0
6.4.10.5 | P4-P5 | 16081.32 | 29 |  | 0 | 0 | 0
6.4.10.6 | P5-P6 | 16081.32 | 30 |  | 0 | 0 | 0
6.4.10.7 | P6-P7 | 16081.32 | 31 |  | 0 | 0 | 0
6.4.10.8 | P7-P8 | 16081.32 | 32 |  | 0 | 0 | 0
6.4.10.9 | P8-P9 | 16081.32 | 33 |  | 0 | 0 | 0
6.4.10.10 | P9-P10 | 16081.32 | 34 |  | 0 | 0 | 0
6.4.10.11 | P10-P11 | 16081.32 | 35
6.4.10.12 | P11-A2 | 12635.34 | 36 |  | 0 | 0 | 0
6.4.11 | Bridge Furniture/ Mosna estetika
6.4.11.1 | 50 m | 51729.28 | 37 |  | 0 | 0 | 0
6.4.11.2 | 100 m | 51729.28 | 38 |  | 0 | 0 | 0
6.4.11.3 | 150 m | 51729.28 | 38 |  | 0 | 0 | 0
6.4.11.4 | 200 m | 51729.28 | 39 |  | 0 | 0 | 0
6.4.11.5 | 250 m | 51729.28 | 39 |  | 0 | 0 | 0
6.4.11.6 | 300 m | 51729.28 | 40
6.4.11.7 | 324 m | 24829.98 | 40 |  | 0 | 0 | 0
6.4.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
6.4.12.1 | Asphalt layer/Sloj asfalta 1 + waterproofing/hidroizolacija | 120961.77 | 39 |  | 0 | 0 | 0
6.4.12.2 | Asphalt layer/Sloj asfalta 2 + joints/Spojnice | 94041.42 | 40 |  | 0 | 0 | 0
| Sub Total / Suma stavke 6.4 | 7131612.39 |  |  | 0 | 24602.54 | 24602.54
Cost Center/ Troškovno mjesto 6.5 | Road Works/ Radovi na putevima (LK17+325.673 —LK17+895.654 RK17+347.268—RK17+946.301)
Completion of/Završetak:
6.5.1 | Subgrade/ Posteljica
6.5.1.1 | Top soil removal/ Uklanjanje humusa
6.5.1.1.1 | 0 - 250 m (LK&RK) | 56929.9019 | 17 |  | 0 | 0 | 0
6.5.1.1.2 | 250 - 500 m (LK&RK) | 56929.9019 | 18 |  | 0 | 0 | 0
6.5.1.1.3 | 500 - 569.981 m (LK)；500 - 599.033 m (RK) | 19243.9009 | 18 |  | 0 | 0 | 0
6.5.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and 4m height /Na svakih 250m i visini od 4m |  | 32
6.5.1.2.1 | 17347.27-17597.27, layers 1,2,3,4,5,6,7,8,9,10
6.5.1.2.1.1 | 17347.27-17597.27, layer 1 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.1.2 | 17347.27-17597.27, layer 2 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.1.3 | 17347.27-17597.27, layer 3 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.1.4 | 17347.27-17597.27, layer 4 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.1.5 | 17347.27-17597.27, layer 5 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.1.6 | 17347.27-17597.27, layer 6 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.1.7 | 17347.27-17597.27, layer 7 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.1.8 | 17347.27-17597.27, layer 8 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.1.9 | 17347.27-17597.27, layer 9 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.1.10 | 17347.27-17597.27, layer 10 | 57950.0706 |  |  | 0 | 0 | 0
6.5.1.2.2 | 17597.27-17847.27, layers 11,12,13,14,15,16,17,18,19,20,21,22
6.5.1.2.2.11 | 17597.27-17847.27, layer 11 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.2.12 | 17597.27-17847.27, layer 12 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.2.13 | 17597.27-17847.27, layer 13 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.2.14 | 17597.27-17847.27, layer 14 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.2.15 | 17597.27-17847.27, layer 15 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.2.16 | 17597.27-17847.27, layer 16 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.2.17 | 17597.27-17847.27, layer 17 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.2.18 | 17597.27-17847.27, layer 18 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.2.19 | 17597.27-17847.27, layer 19 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.2.20 | 17597.27-17847.27, layer 20 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.2.21 | 17597.27-17847.27, layer 21 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.2.22 | 17597.27-17847.27, layer 22 | 67240.9786 |  |  | 0 | 0 | 0
6.5.1.2.3 | 17847.27-17946.30, layers 23,24,25,26,27,28
6.5.1.2.3.23 | 17847.27-17946.30, layer 23 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.3.24 | 17847.27-17946.30, layer 24 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.3.25 | 17847.27-17946.30, layer 25 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.3.26 | 17847.27-17946.30, layer 26 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.3.27 | 17847.27-17946.30, layer 27 | 62989.2072 |  |  | 0 | 0 | 0
6.5.1.2.3.88 | 17847.27-17946.30, layer 28 | 60942.0579 |  |  | 0 | 0 | 0
6.5.1.3 | Road Foundation/ Temelj puta
6.5.1.3.1 | 0 - 250 m right side/ desna strana | 22588.0551 | 33 |  | 0 | 0 | 0
6.5.1.3.2 | 0 - 250 m left side/ lijeva strana | 22588.0551 | 34 |  | 0 | 0 | 0
6.5.1.3.3 | 250 - 500 m right side/ desna strana | 22588.0551 | 35 |  | 0 | 0 | 0
6.5.1.3.4 | 250 - 500 m left side/ lijeva strana | 22588.0551 | 36 |  | 0 | 0 | 0
6.5.1.3.5 | 500 - 599.033 m left side/ lijeva strana | 8947.8514 | 37 |  | 0 | 0 | 0
6.5.1.3.6 | 500 - 569.981 m right side/ desna strana | 6322.9387 | 37 |  | 0 | 0 | 0
6.5.2 | Engineering structures/ Inženjerske konstrukcije
6.5.2.1 | Concrete wall / Betonski zid |  | 29
80% for the concrete wall, the milestone is 50m lenth, no matter the hight+ 5% for the "after work" the whole lenth of each retaining wall + 5% for the "correction of the crown" the whole lenth of each retaining wall+10% for the "wall surface" the whole lenth of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
6.5.2.1.1 | Concrete wall/ Betonski zid LK17+330.07--K17+346.07 (16m)
6.5.2.1.1.1 | Concrete wall/ Betonski zid LK17+330.07--K17+346.07 - 90% | 124034.0489 |  |  | 0 | 0 | 0
6.5.2.1.1.2 | Concrete wall/ Betonski zid LK17+330.07--K17+346.07- After work 5% | 7752.1281 |  |  | 0 | 0 | 0
6.5.2.1.1.3 | Concrete wall/ Betonski zid LK17+330.07--K17+346.07- Correction of the crown 5% | 7752.1281 |  |  | 0 | 0 | 0
6.5.2.1.1.4 | Concrete wall/ Betonski zid LK17+330.07--K17+346.07- Wall surface 10% | 15504.2561 |  |  | 0 | 0 | 0
6.5.2.1.2 | Concrete wall/ Betonski zid RK17+351.00--RK17+359.00 (8m)
6.5.2.1.2.1 | Concrete wall/ Betonski zid RK17+351.00--RK17+359.00 - 80% | 62017.0244 |  |  | 0 | 0 | 0
6.5.2.1.2.2 | Concrete wall/Betonski zid RK17+351.00-RK17+359.00- After work 5% | 3876.064 |  |  | 0 | 0 | 0
6.5.2.1.2.3 | Concrete wall/Betonski zid RK17+351.00-RK17+359.00- Correction of the crown 5% | 3876.064 |  |  | 0 | 0 | 0
6.5.2.1.2.4 | Concrete wall/Betonski zid RK17+351.00-RK17+359.00- Wall surface 10% | 7752.1281 |  |  | 0 | 0 | 0
6.5.2.1.3 | Concrete wall/ Betonski zid LK17+879.25--LK17+891.25 (12m)
6.5.2.1.3.1 | Concrete wall/ Betonski zid LK17+879.25--LK17+891.25 - 80% | 93025.5366 |  | 29 | 93025.5366 | 0 | 93025.5366
6.5.2.1.3.2 | Concrete wall/Betonski zid LK17+879.25--LK17+891.25- After work 5% | 5814.096 |  |  | 0 | 0 | 0
6.5.2.1.3.3 | Concrete wall/Betonski zid LK17+879.25--LK17+891.25- Correction of the crown 5% | 5814.096 |  |  | 0 | 0 | 0
6.5.2.1.3.4 | Concrete wall/Betonski zid LK17+879.25--LK17+891.25- Wall surface 10% | 11628.1921 |  |  | 0 | 0 | 0
6.5.2.1.4 | Concrete wall/ Betonski zid RK17+928.00--RK17+940.00 (12m)
6.5.2.1.4.1 | Concrete wall/ Betonski zid RK17+928.00--RK17+940.00 - 80% | 93025.5366 |  |  | 0 | 0 | 0
6.5.2.1.4.2 | Concrete wall/Betonski zid RK17+928.00--RK17+940.00- After work 5% | 5814.096 |  |  | 0 | 0 | 0
6.5.2.1.4.3 | Concrete wall/Betonski zid RK17+928.00--RK17+940.00- Correction of the crown 5% | 5814.096 |  |  | 0 | 0 | 0
6.5.2.1.4.4 | Concrete wall/Betonski zid RK17+928.00--RK17+940.00- Wall surface 10% | 11628.1921 |  |  | 0 | 0 | 0
6.5.2.2 | Reinforced earth wall / Ojačani zemljani zid
The milestone is 2.25 m height of each leyer and no matter on the length / Reper je visina 2.25 m za svaki sloj, bez obzira na dužinu
6.5.2.1.1 | Reinforced soil retaining wall RK17+520.00--RK17+740.00 / Potporni zid od armirane zemlje
6.5.2.1.1.1 | Layer/Sloj 1 (0.0 -2.25 m height) | 66905.669 |  |  | 0 | 0 | 0
6.5.2.1.1.2 | Layer/Sloj 2 (2.25 -4.5 m height) | 66905.669 |  |  | 0 | 0 | 0
6.5.2.1.1.3 | Layer/Sloj 3 (4.5 -6.75 m height) | 66905.669 |  |  | 0 | 0 | 0
6.5.2.1.1.4 | Layer/Sloj 4 (6.75 -9.0 m height) | 66905.669 |  |  | 0 | 0 | 0
6.5.2.1.1.5 | Layer/Sloj 5 (9.0 -11.25 m height) | 66905.669 |  |  | 0 | 0 | 0
6.5.2.1.1.6 | Layer/Sloj 6 (11.25 -13.5 m height) | 66905.669 |  |  | 0 | 0 | 0
6.5.2.1.1.7 | Layer/Sloj 7 (13.5 -15.75 m height) | 66905.669 |  |  | 0 | 0 | 0
6.5.2.1.1.8 | Layer/Sloj 8 (15.75 -16.0 m height) | 7433.9632 |  |  | 0 | 0 | 0
6.5.2.3 | Culvert/ Propust
6.5.2.3.1 | K17+748 (35m) | 11092.2637 | 31 |  | 0 | 0 | 0
6.5.3 | Water drainage/ Drenaža vode
| per one direction of 500m / Na 500m dužine u jednom pravcu |  | 38
6.5.3.1 | LK17+325.673 —LK17+895.654 (569.981 m) | 235203.2738 |  |  | 0 | 0 | 0
6.5.3.2 | RK17+347.268—RK17+946.301 (599.033 m) | 247191.6129 |  |  | 0 | 0 | 0
6.5.4 | Pavement structure/ Kolovozna konstrukcija
6.5.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 0-500m | 59369.5474 | 37 |  | 0 | 0 | 0
6.5.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 0 - 500m | 59369.5474 | 37 |  | 0 | 0 | 0
6.5.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 500-599.033m | 11759.0888 | 38 |  | 0 | 0 | 0
6.5.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 500-569.981m | 8309.4806 | 38 |  | 0 | 0 | 0
6.5.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 0-500m | 59369.5474 | 39 |  | 0 | 0 | 0
6.5.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 0-500m | 59369.5474 | 39 |  | 0 | 0 | 0
6.5.4.7 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 500-599.033m | 11759.0888 | 40 |  | 0 | 0 | 0
6.5.4.8 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 500-569.981m | 8309.4806 | 40 |  | 0 | 0 | 0
6.5.4.9 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 0-500m | 65970.0865 | 41 |  | 0 | 0 | 0
6.5.4.10 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 0-500m | 65970.0865 | 41 |  | 0 | 0 | 0
6.5.4.11 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 500-599.033m | 13066.4311 | 42 |  | 0 | 0 | 0
6.5.4.12 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 500-569.981m | 9233.3052 | 42 |  | 0 | 0 | 0
6.5.5 | Deviation of local roads
6.5.5.1 | Ratkov Laz (K0+000.00 - K0+05219, 52.19m ) | 9702.1024 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 6.5 | 3875535.8209 |  |  | 93025.5366 | 0 | 93025.5366
Cost Center/ Troškovno mjesto 6.6 | Construction of bridge/ Izgradnja mosta Ratkov Laz (LK17+895.654—LK18+245.699 RK17+946.301—RK18+272.128)
Completion of/Završetak:
Left bridge/ Lijevi most
6.6.1 | Foundation concrete/ Temeljni beton
6.6.1.1 | A1 | 45097.22 | 19 | 29 | 45097.22 | 0 | 45097.22
6.6.1.2 | P1 | 23341.94 | 20 | 30 | 0 | 23341.94 | 23341.94
6.6.1.3 | P2 | 23341.94 | 21 | 30 | 0 | 23341.94 | 23341.94
6.6.1.4 | P3 | 23341.94 | 21 | 30 | 0 | 23341.94 | 23341.94
6.6.1.5 | P4 | 23341.94 | 21 | 30 | 0 | 23341.94 | 23341.94
6.6.1.6 | P5 | 23341.94 | 22 | 30 | 0 | 23341.94 | 23341.94
6.6.1.7 | P6 | 23341.94 | 22 | 30 | 0 | 23341.94 | 23341.94
6.6.1.8 | P7 | 23341.94 | 22 |  | 0 | 0 | 0
6.6.1.9 | P8 | 23341.94 | 23 |  | 0 | 0 | 0
6.6.1.10 | P9 | 23341.94 | 23 |  | 0 | 0 | 0
6.6.1.11 | P10 | 23341.94 | 23 |  | 0 | 0 | 0
6.6.1.12 | P11 | 23341.94 | 24 |  | 0 | 0 | 0
6.6.1.13 | P12 | 23341.94 | 24 |  | 0 | 0 | 0
6.6.1.14 | A2 | 45097.22 | 24 |  | 0 | 0 | 0
6.6.2 | Abutments and Piers elevation/ Elevacija mosnih stubova
6.6.2.1 | A1 | 58960.29 | 20 |  | 0 | 0 | 0
6.6.2.2 | P1 stage 1 (5.5m) | 10121.2035 | 21 |  | 0 | 0 | 0
6.6.2.3 | P1 stage 2 (4m) | 7360.8752 | 21 |  | 0 | 0 | 0
6.6.2.4 | P1 stage 3 (4m) | 7360.8752 | 21 |  | 0 | 0 | 0
6.6.2.5 | P1 stage 4 (3.5m) | 6440.7658 | 22 |  | 0 | 0 | 0
6.6.2.6 | P1 stage 5 (1m) | 1840.2188 | 22 |  | 0 | 0 | 0
6.6.2.7 | P2 stage 1 (3.9m) | 7176.8534 | 21 |  | 0 | 0 | 0
6.6.2.8 | P2 stage 2 (4m) | 7360.8752 | 21 |  | 0 | 0 | 0
6.6.2.9 | P2 stage 3 (4m) | 7360.8752 | 21 |  | 0 | 0 | 0
6.6.2.10 | P2 stage 4 (4m) | 7360.8752 | 21 |  | 0 | 0 | 0
6.6.2.11 | P2 stage 5 (4m) | 7360.8752 | 22 |  | 0 | 0 | 0
6.6.2.12 | P2 stage 6 (4m) | 7360.8752 | 22 |  | 0 | 0 | 0
6.6.2.13 | P2 stage 7 (3.6m) | 6624.7877 | 22 |  | 0 | 0 | 0
6.6.2.14 | P3 stage 1 (5.3m) | 9753.1597 | 21 |  | 0 | 0 | 0
6.6.2.15 | P3 stage 2 (4m) | 7360.8752 | 21 |  | 0 | 0 | 0
6.6.2.16 | P3 stage 3 (4m) | 7360.8752 | 22 |  | 0 | 0 | 0
6.6.2.17 | P3 stage 4 (4m) | 7360.8752 | 22 |  | 0 | 0 | 0
6.6.2.18 | P3 stage 5 (4m) | 7360.8752 | 23 |  | 0 | 0 | 0
6.6.2.19 | P3 stage 6 (3.9m) | 7176.8534 | 23 |  | 0 | 0 | 0
6.6.2.20 | P4 stage 1 (5.3m) | 9753.1597 | 23 |  | 0 | 0 | 0
6.6.2.21 | P4 stage 2 (4m) | 7360.8752 | 23 |  | 0 | 0 | 0
6.6.2.22 | P4 stage 3 (4m) | 7360.8752 | 23 |  | 0 | 0 | 0
6.6.2.23 | P4 stage 4 (4m) | 7360.8752 | 24 |  | 0 | 0 | 0
6.6.2.24 | P4 stage 5 (4m) | 7360.8752 | 24 |  | 0 | 0 | 0
6.6.2.25 | P4 stage 6 (4m) | 7360.8752 | 25 |  | 0 | 0 | 0
6.6.2.26 | P4 stage 7 (4m) | 7360.8752 | 25 |  | 0 | 0 | 0
6.6.2.27 | P4 stage 8 (4m) | 7360.8752 | 26 |  | 0 | 0 | 0
6.6.2.28 | P4 stage 9 (2m) | 3680.4376 | 26 |  | 0 | 0 | 0
6.6.2.29 | P5 stage 1 (3.9m) | 7176.8534 | 24 |  | 0 | 0 | 0
6.6.2.30 | P5 stage 2 (4m) | 7360.8752 | 24 |  | 0 | 0 | 0
6.6.2.31 | P5 stage 3 (4m) | 7360.8752 | 25 |  | 0 | 0 | 0
6.6.2.32 | P5 stage 4 (4m) | 7360.8752 | 25 |  | 0 | 0 | 0
6.6.2.33 | P5 stage 5 (4m) | 7360.8752 | 26 |  | 0 | 0 | 0
6.6.2.34 | P5 stage 6 (4m) | 7360.8752 | 26 |  | 0 | 0 | 0
6.6.2.35 | P5 stage 7 (4m) | 7360.8752 | 27 |  | 0 | 0 | 0
6.6.2.36 | P5 stage 8 (2.1m) | 3864.4595 | 27 |  | 0 | 0 | 0
6.6.2.37 | P6 stage 1 (5.3m) | 9753.1597 | 24 |  | 0 | 0 | 0
6.6.2.38 | P6 stage 2 (4m) | 7360.8752 | 24 |  | 0 | 0 | 0
6.6.2.39 | P6 stage 3 (4m) | 7360.8752 | 25 |  | 0 | 0 | 0
6.6.2.40 | P6 stage 4 (4m) | 7360.8752 | 25 |  | 0 | 0 | 0
6.6.2.41 | P6 stage 5 (4m) | 7360.8752 | 26 |  | 0 | 0 | 0
6.6.2.42 | P6 stage 6 (4m) | 7360.8752 | 26 |  | 0 | 0 | 0
6.6.2.43 | P6 stage 7 (4m) | 7360.8752 | 27 |  | 0 | 0 | 0
6.6.2.44 | P6 stage 8 (2.3m) | 4232.5033 | 27 |  | 0 | 0 | 0
6.6.2.45 | P7 stage 1 (5.3m) | 9753.1597 | 24 |  | 0 | 0 | 0
6.6.2.46 | P7 stage 2 (4m) | 7360.8752 | 24 |  | 0 | 0 | 0
6.6.2.47 | P7 stage 3 (4m) | 7360.8752 | 25 |  | 0 | 0 | 0
6.6.2.48 | P7 stage 4 (4m) | 7360.8752 | 25 |  | 0 | 0 | 0
6.6.2.49 | P7 stage 5 (4m) | 7360.8752 | 26 |  | 0 | 0 | 0
6.6.2.50 | P7 stage 6 (4m) | 7360.8752 | 26 |  | 0 | 0 | 0
6.6.2.51 | P7 stage 7 (4m) | 7360.8752 | 27 |  | 0 | 0 | 0
6.6.2.52 | P7 stage 8 (2.1m) | 3864.4595 | 27 |  | 0 | 0 | 0
6.6.2.53 | P7 stage 9 (2.5m) | 4600.547 | 27 |  | 0 | 0 | 0
6.6.2.54 | P8 stage 1 (3.9m) | 7176.8534 | 27 |  | 0 | 0 | 0
6.6.2.55 | P8 stage 2 (4m) | 7360.8752 | 27 |  | 0 | 0 | 0
6.6.2.56 | P8 stage 3 (4m) | 7360.8752 | 27 |  | 0 | 0 | 0
6.6.2.57 | P8 stage 4 (4m) | 7360.8752 | 28 |  | 0 | 0 | 0
6.6.2.58 | P8 stage 5 (2.5m) | 4600.547 | 28 |  | 0 | 0 | 0
6.6.2.59 | P9 stage 1 (5.3m) | 9753.1597 | 28 |  | 0 | 0 | 0
6.6.2.60 | P9 stage 2 (4m) | 7360.8752 | 28 |  | 0 | 0 | 0
6.6.2.61 | P9 stage 3 (4m) | 7360.8752 | 29 |  | 0 | 0 | 0
6.6.2.62 | P9 stage 4 (2.6m) | 4784.5689 | 29 |  | 0 | 0 | 0
6.6.2.63 | P9 stage 5 (2.5m) | 4600.547 | 29 |  | 0 | 0 | 0
6.6.2.64 | P10 stage 1 (3.9m) | 7176.8534 | 29 |  | 0 | 0 | 0
6.6.2.65 | P10 stage 2 (4m) | 7360.8752 | 29 |  | 0 | 0 | 0
6.6.2.66 | P10 stage 3 (4m) | 7360.8752 | 29 |  | 0 | 0 | 0
6.6.2.67 | P10 stage 4 (4m) | 7360.8752 | 30 |  | 0 | 0 | 0
6.6.2.68 | P10 stage 5 (4m) | 7360.8752 | 30 |  | 0 | 0 | 0
6.6.2.69 | P10 stage 6 (4m) | 7360.8752 | 30 |  | 0 | 0 | 0
6.6.2.70 | P10 stage 7 (4.5m) | 8280.9847 | 30 |  | 0 | 0 | 0
6.6.2.71 | P11 stage 1 (3.9m) | 7176.8534 | 28 |  | 0 | 0 | 0
6.6.2.72 | P11 stage 2 (4m) | 7360.8752 | 28 |  | 0 | 0 | 0
6.6.2.73 | P11 stage 3 (4m) | 7360.8752 | 29 |  | 0 | 0 | 0
6.6.2.74 | P11 stage 4 (4m) | 7360.8752 | 29 |  | 0 | 0 | 0
6.6.2.75 | P11 stage 5 (4m) | 7360.8752 | 30 |  | 0 | 0 | 0
6.6.2.76 | P11 stage 6 (4m) | 7360.8752 | 30 |  | 0 | 0 | 0
6.6.2.77 | P12 stage 1 (3.9m) | 7176.8534 | 29 |  | 0 | 0 | 0
6.6.2.78 | P12 stage 2 (4m) | 7360.8752 | 29 |  | 0 | 0 | 0
6.6.2.79 | P12 stage 3 (4m) | 7360.8752 | 30 |  | 0 | 0 | 0
6.6.2.80 | P12 stage 4 (2.7m) | 4968.5908 | 30 |  | 0 | 0 | 0
6.6.2.81 | P12 stage 5 (1m) | 1840.2188 | 30 |  | 0 | 0 | 0
6.6.2.82 | A2 | 58960.29 | 29 |  | 0 | 0 | 0
6.6.3 | Bridge deck superstructure/ Gornji stroj mosne ploče
6.6.3.1 | A1-P1 | 114506.77 | 24 |  | 0 | 0 | 0
6.6.3.2 | P1-P2 | 145735.88 | 25 |  | 0 | 0 | 0
6.6.3.3 | P2-P3 | 145735.88 | 26 |  | 0 | 0 | 0
6.6.3.4 | P3-P4 | 145735.88 | 27 |  | 0 | 0 | 0
6.6.3.5 | P4-P5 | 145735.88 | 28 |  | 0 | 0 | 0
6.6.3.6 | P5-P6 | 145735.88 | 29 |  | 0 | 0 | 0
6.6.3.7 | P6-P7 | 145735.88 | 30 |  | 0 | 0 | 0
6.6.3.8 | P7-P8 | 145735.88 | 31 |  | 0 | 0 | 0
6.6.3.9 | P8-P9 | 145735.88 | 32 |  | 0 | 0 | 0
6.6.3.10 | P9-P10 | 145735.88 | 33 |  | 0 | 0 | 0
6.6.3.11 | P10-P11 | 145735.88 | 34 |  | 0 | 0 | 0
6.6.3.12 | P11-P12 | 145735.88 | 35 |  | 0 | 0 | 0
6.6.3.13 | P12-A2 | 114506.77 | 36 |  | 0 | 0 | 0
6.6.4 | Bridge deck prestressing/ Prednaprezanje mosne ploče
6.6.4.1 | A1-P1 | 12722.97 | 24 |  | 0 | 0 | 0
6.6.4.2 | P1-P2 | 16192.88 | 25 |  | 0 | 0 | 0
6.6.4.3 | P2-P3 | 16192.88 | 26 |  | 0 | 0 | 0
6.6.4.4 | P3-P4 | 16192.88 | 27 |  | 0 | 0 | 0
6.6.4.5 | P4-P5 | 16192.88 | 28 |  | 0 | 0 | 0
6.6.4.6 | P5-P6 | 16192.88 | 29 |  | 0 | 0 | 0
6.6.4.7 | P6-P7 | 16192.88 | 30 |  | 0 | 0 | 0
6.6.4.8 | P7-P8 | 16192.88 | 31 |  | 0 | 0 | 0
6.6.4.9 | P8-P9 | 16192.88 | 32 |  | 0 | 0 | 0
6.6.4.10 | P9-P10 | 16192.88 | 33 |  | 0 | 0 | 0
6.6.4.11 | P10-P11 | 16192.88 | 34 |  | 0 | 0 | 0
6.6.4.12 | P11-P12 | 16192.88 | 35 |  | 0 | 0 | 0
6.6.4.13 | P12-A2 | 12722.97 | 36 |  | 0 | 0 | 0
6.6.5 | Bridge Furniture/ Mosna estetika
6.6.5.1 | 50 m | 54382.58 | 37 |  | 0 | 0 | 0
6.6.5.2 | 100 m | 54382.58 | 37 |  | 0 | 0 | 0
6.6.5.3 | 150 m | 54382.58 | 38 |  | 0 | 0 | 0
6.6.5.4 | 200 m | 54382.58 | 38 |  | 0 | 0 | 0
6.6.5.5 | 250 m | 54382.58 | 39 |  | 0 | 0 | 0
6.6.5.6 | 300 m | 54382.58 | 39 |  | 0 | 0 | 0
6.6.5.7 | 350.045 m | 56557.75 | 40 |  | 0 | 0 | 0
6.6.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
6.6.6.1 | Asphalt layer/Sloj asfalta 1 + waterproofing/hidroizolacija | 132327.31 | 39 |  | 0 | 0 | 0
6.6.6.2 | Asphalt layer/Sloj asfalta 2 + joints/Spojnice | 90592.74 | 40 |  | 0 | 0 | 0
Right Bridge/ Desni most
6.6.7 | Foundation concrete/ Temeljni beton
6.6.7.1 | A1 | 45614.15 | 20 |  | 0 | 0 | 0
6.6.7.2 | P1 | 23241.32 | 21 |  | 0 | 0 | 0
6.6.7.3 | P2 | 23241.32 | 21 |  | 0 | 0 | 0
6.6.7.4 | P3 | 23241.32 | 21 |  | 0 | 0 | 0
6.6.7.5 | P4 | 23241.32 | 22 |  | 0 | 0 | 0
6.6.7.6 | P5 | 23241.32 | 22 |  | 0 | 0 | 0
6.6.7.7 | P6 | 23241.32 | 22 |  | 0 | 0 | 0
6.6.7.8 | P7 | 23241.32 | 23 |  | 0 | 0 | 0
6.6.7.9 | P8 | 23241.32 | 23 |  | 0 | 0 | 0
6.6.7.10 | P9 | 23241.32 | 23 |  | 0 | 0 | 0
6.6.7.11 | P10 | 23241.32 | 24 |  | 0 | 0 | 0
6.6.7.12 | P11 | 23241.32 | 24 |  | 0 | 0 | 0
6.6.7.13 | A2 | 45614.15 | 24 |  | 0 | 0 | 0
6.6.8 | Abutments and Piers elevation/ Elevacija mosnih stubova
6.6.8.1 | A1 | 58960.29 | 20 |  | 0 | 0 | 0
6.6.8.2 | P1 stage 1 (3.9m) | 7345.2251 | 21 |  | 0 | 0 | 0
6.6.8.3 | P1 stage 2 (4m) | 7533.5642 | 21 |  | 0 | 0 | 0
6.6.8.4 | P1 stage 3 (4m) | 7533.5642 | 22 |  | 0 | 0 | 0
6.6.8.5 | P1 stage 4 (4m) | 7533.5642 | 22 |  | 0 | 0 | 0
6.6.8.6 | P1 stage 5 (2.5m) | 4708.4776 | 23 |  | 0 | 0 | 0
6.6.8.7 | P1 stage 6 (1m) | 1883.3911 | 23 |  | 0 | 0 | 0
6.6.8.8 | P2 stage 1 (5.3m) | 9981.9726 | 21 |  | 0 | 0 | 0
6.6.8.9 | P2 stage 2 (4m) | 7533.5642 | 21 |  | 0 | 0 | 0
6.6.8.10 | P2 stage 3 (4m) | 7533.5642 | 22 |  | 0 | 0 | 0
6.6.8.11 | P2 stage 4 (4m) | 7533.5642 | 22 |  | 0 | 0 | 0
6.6.8.12 | P2 stage 5 (4m) | 7533.5642 | 23 |  | 0 | 0 | 0
6.6.8.13 | P2 stage 6 (2.1m) | 3955.1212 | 23 |  | 0 | 0 | 0
6.6.8.14 | P3 stage 1 (3.9m) | 7345.2251 | 23 |  | 0 | 0 | 0
6.6.8.15 | P3 stage 2 (4m) | 7533.5642 | 23 |  | 0 | 0 | 0
6.6.8.16 | P3 stage 3 (4m) | 7533.5642 | 24 |  | 0 | 0 | 0
6.6.8.17 | P3 stage 4 (4m) | 7533.5642 | 24 |  | 0 | 0 | 0
6.6.8.18 | P3 stage 5 (4m) | 7533.5642 | 25 |  | 0 | 0 | 0
6.6.8.19 | P3 stage 6 (4m) | 7533.5642 | 25 |  | 0 | 0 | 0
6.6.8.20 | P3 stage 7 (3.3m) | 6215.1905 | 26 |  | 0 | 0 | 0
6.6.8.21 | P3 stage 8 (2.5m) | 4708.4776 | 26 |  | 0 | 0 | 0
6.6.8.22 | P4 stage 1 (3.9m) | 7345.2251 | 24 |  | 0 | 0 | 0
6.6.8.23 | P4 stage 2 (4m) | 7533.5642 | 24 |  | 0 | 0 | 0
6.6.8.24 | P4 stage 3 (4m) | 7533.5642 | 25 |  | 0 | 0 | 0
6.6.8.25 | P4 stage 4 (4m) | 7533.5642 | 25 |  | 0 | 0 | 0
6.6.8.26 | P4 stage 5 (4m) | 7533.5642 | 25 |  | 0 | 0 | 0
6.6.8.27 | P4 stage 6 (4m) | 7533.5642 | 26 |  | 0 | 0 | 0
6.6.8.28 | P4 stage 7 (4.6m) | 8663.5989 | 26 |  | 0 | 0 | 0
6.6.8.29 | P5 stage 1 (3.9m) | 7345.2251 | 23 |  | 0 | 0 | 0
6.6.8.30 | P5 stage 2 (4m) | 7533.5642 | 23 |  | 0 | 0 | 0
6.6.8.31 | P5 stage 3 (4m) | 7533.5642 | 24 |  | 0 | 0 | 0
6.6.8.32 | P5 stage 4 (4m) | 7533.5642 | 24 |  | 0 | 0 | 0
6.6.8.33 | P5 stage 5 (4m) | 7533.5642 | 25 |  | 0 | 0 | 0
6.6.8.34 | P5 stage 6 (4m) | 7533.5642 | 25 |  | 0 | 0 | 0
6.6.8.35 | P5 stage 7 (4m) | 7533.5642 | 26 |  | 0 | 0 | 0
6.6.8.36 | P5 stage 8 (2.7m) | 5085.1559 | 26 |  | 0 | 0 | 0
6.6.8.37 | P6 stage 1 (5.3m) | 9981.9726 | 23 |  | 0 | 0 | 0
6.6.8.38 | P6 stage 2 (4m) | 7533.5642 | 23 |  | 0 | 0 | 0
6.6.8.39 | P6 stage 3 (4m) | 7533.5642 | 24 |  | 0 | 0 | 0
6.6.8.40 | P6 stage 4 (4m) | 7533.5642 | 24 |  | 0 | 0 | 0
6.6.8.41 | P6 stage 5 (4m) | 7533.5642 | 25 |  | 0 | 0 | 0
6.6.8.42 | P6 stage 6 (4m) | 7533.5642 | 25 |  | 0 | 0 | 0
6.6.8.43 | P6 stage 7 (4m) | 7533.5642 | 26 |  | 0 | 0 | 0
6.6.8.44 | P6 stage 8 (4m) | 7533.5642 | 26 |  | 0 | 0 | 0
6.6.8.45 | P6 stage 9 (2.1m) | 3955.1212 | 26 |  | 0 | 0 | 0
6.6.8.46 | P7 stage 1 (5.3m) | 9981.9726 | 27 |  | 0 | 0 | 0
6.6.8.47 | P7 stage 2 (4m) | 7533.5642 | 27 |  | 0 | 0 | 0
6.6.8.48 | P7 stage 3 (4m) | 7533.5642 | 27 |  | 0 | 0 | 0
6.6.8.49 | P7 stage 4 (4m) | 7533.5642 | 28 |  | 0 | 0 | 0
6.6.8.50 | P7 stage 5 (4m) | 7533.5642 | 28 |  | 0 | 0 | 0
6.6.8.51 | P7 stage 6 (2.4m) | 4520.1385 | 28 |  | 0 | 0 | 0
6.6.8.52 | P8 stage 1 (3.9m) | 7345.2251 | 28 |  | 0 | 0 | 0
6.6.8.53 | P8 stage 2 (4m) | 7533.5642 | 29 |  | 0 | 0 | 0
6.6.8.54 | P8 stage 3 (4.1m) | 7721.9033 | 29 |  | 0 | 0 | 0
6.6.8.55 | P9 stage 1 (5.3m) | 9981.9726 | 28 |  | 0 | 0 | 0
6.6.8.56 | P9 stage 2 (4m) | 7533.5642 | 28 |  | 0 | 0 | 0
6.6.8.57 | P9 stage 3 (4m) | 7533.5642 | 29 |  | 0 | 0 | 0
6.6.8.58 | P9 stage 4 (4m) | 7533.5642 | 29 |  | 0 | 0 | 0
6.6.8.59 | P9 stage 5 (4m) | 7533.5642 | 30 |  | 0 | 0 | 0
6.6.8.60 | P9 stage 6 (3.1m) | 5838.5123 | 30 |  | 0 | 0 | 0
6.6.8.61 | P10 stage 1 (5.3m) | 9981.9726 | 28 |  | 0 | 0 | 0
6.6.8.62 | P10 stage 2 (4m) | 7533.5642 | 28 |  | 0 | 0 | 0
6.6.8.63 | P10 stage 3 (4m) | 7533.5642 | 29 |  | 0 | 0 | 0
6.6.8.64 | P10 stage 4 (4m) | 7533.5642 | 29 |  | 0 | 0 | 0
6.6.8.65 | P10 stage 5 (4m) | 7533.5642 | 30 |  | 0 | 0 | 0
6.6.8.66 | P10 stage 6 (3.1m) | 5838.5123 | 30 |  | 0 | 0 | 0
6.6.8.67 | P11 stage 1 (2.9m) | 5461.8341 | 29 |  | 0 | 0 | 0
6.6.8.68 | P11 stage 2 (4m) | 7533.5642 | 29 |  | 0 | 0 | 0
6.6.8.69 | P11 stage 3 (4.5m) | 8475.2598 | 30 |  | 0 | 0 | 0
6.6.8.70 | P11 stage 4 (1m) | 1883.3911 | 30 |  | 0 | 0 | 0
6.6.8.71 | A2 | 58960.29 | 29 |  | 0 | 0 | 0
6.6.9 | Bridge deck superstructure/ Gornji stroj mosne ploče
6.6.9.1 | A1-P1 | 113717.91 | 25 |  | 0 | 0 | 0
6.6.9.2 | P1-P2 | 144731.89 | 26 |  | 0 | 0 | 0
6.6.9.3 | P2-P3 | 144731.89 | 27 |  | 0 | 0 | 0
6.6.9.4 | P3-P4 | 144731.89 | 28 |  | 0 | 0 | 0
6.6.9.5 | P4-P5 | 144731.89 | 29 |  | 0 | 0 | 0
6.6.9.6 | P5-P6 | 144731.89 | 30 |  | 0 | 0 | 0
6.6.9.7 | P6-P7 | 144731.89 | 31 |  | 0 | 0 | 0
6.6.9.8 | P7-P8 | 144731.89 | 32 |  | 0 | 0 | 0
6.6.9.9 | P8-P9 | 144731.89 | 33 |  | 0 | 0 | 0
6.6.9.10 | P9-P10 | 144731.89 | 34 |  | 0 | 0 | 0
6.6.9.11 | P10-P11 | 144731.89 | 35 |  | 0 | 0 | 0
6.6.9.12 | P11-A2 | 113717.91 | 36 |  | 0 | 0 | 0
6.6.10 | Bridge deck prestressing/ Prednaprezanje mosne ploče
6.6.10.1 | A1-P1 | 12635.32 | 25 |  | 0 | 0 | 0
6.6.10.2 | P1-P2 | 16081.32 | 26 |  | 0 | 0 | 0
6.6.10.3 | P2-P3 | 16081.32 | 27 |  | 0 | 0 | 0
6.6.10.4 | P3-P4 | 16081.32 | 28 |  | 0 | 0 | 0
6.6.10.5 | P4-P5 | 16081.32 | 29 |  | 0 | 0 | 0
6.6.10.6 | P5-P6 | 16081.32 | 30 |  | 0 | 0 | 0
6.6.10.7 | P6-P7 | 16081.32 | 31 |  | 0 | 0 | 0
6.6.10.8 | P7-P8 | 16081.32 | 32 |  | 0 | 0 | 0
6.6.10.9 | P8-P9 | 16081.32 | 33 |  | 0 | 0 | 0
6.6.10.10 | P9-P10 | 16081.32 | 34 |  | 0 | 0 | 0
6.6.10.11 | P10-P11 | 16081.32 | 35 |  | 0 | 0 | 0
6.6.10.12 | P11-A2 | 12635.34 | 36 |  | 0 | 0 | 0
6.6.11 | Bridge Furniture/ Mosna estetika
6.6.11.1 | 50 m | 54792.22 | 37 |  | 0 | 0 | 0
6.6.11.2 | 100 m | 54792.22 | 37 |  | 0 | 0 | 0
6.6.11.3 | 150 m | 54792.22 | 38 |  | 0 | 0 | 0
6.6.11.4 | 200 m | 54792.22 | 38 |  | 0 | 0 | 0
6.6.11.5 | 250 m | 54792.22 | 39 |  | 0 | 0 | 0
6.6.11.6 | 300 m | 54792.22 | 39 |  | 0 | 0 | 0
6.6.11.7 | 325.827 m | 26300.29 | 40 |  | 0 | 0 | 0
6.6.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
6.6.12.1 | Asphalt layer/Sloj asfalta 1 + waterproofing/hidroizolacija | 120961.77 | 39 |  | 0 | 0 | 0
6.6.12.2 | Asphalt layer/Sloj asfalta 2 + joints/Spojnice | 94041.42 | 40 |  | 0 | 0 | 0
| Sub Total / Suma stavke 6.6 | 7085868.1 |  |  | 45097.22 | 140051.64 | 185148.86
Cost Center/ Troškovno mjesto 6.7 | Road Works/ Radovi na putevima (LK18+245.699—LK18+551.474 RK18+272.128—RK18+642.024)
Completion of/Završetak:
6.7.1 | Subgrade/ Posteljica
6.7.1.1 | Top soil removal/ Uklanjanje humusa
6.7.1.1.1 | 0 - 250 m (LK&RK) | 56867.3913 | 17 |  | 0 | 0 | 0
6.7.1.1.2 | 250 - 305.775 m (LK)；250 - 369.896 m (RK) | 19979.903 | 18 |  | 0 | 0 | 0
6.7.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and 4m height /Na svakih 250m i visini od 4m |  | 32
6.7.1.2.1 | 18272.13-18522.13, layers1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16
6.7.1.2.1.1 | 18272.13-18522.13, layer 1 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.2 | 18272.13-18522.13, layer 2 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.3 | 18272.13-18522.13, layer 3 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.4 | 18272.13-18522.13, layer 4 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.5 | 18272.13-18522.13, layer 5 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.6 | 18272.13-18522.13, layer 6 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.7 | 18272.13-18522.13, layer 7 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.8 | 18272.13-18522.13, layer 8 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.9 | 18272.13-18522.13, layer 9 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.10 | 18272.13-18522.13, layer 10 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.11 | 18272.13-18522.13, layer 11 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.12 | 18272.13-18522.13, layer 12 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.13 | 18272.13-18522.13, layer 13 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.14 | 18272.13-18522.13, layer 14 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.15 | 18272.13-18522.13, layer 15 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.1.16 | 18272.13-18522.13, layer 16 | 17303.989 |  |  | 0 | 0 | 0
6.7.1.2.2 | 18522.13-18642,02, layers 11,12,13,14,15,16,17
6.7.1.2.2.17 | 18522.13-18642,02, layer 17 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.2.18 | 18522.13-18642,02, layer 18 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.2.19 | 18522.13-18642,02, layer 19 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.2.20 | 18522.13-18642,02, layer 20 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.2.21 | 18522.13-18642,02, layer 21 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.2.22 | 18522.13-18642,02, layer 22 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.2.23 | 18522.13-18642,02, layer 23 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.2.24 | 18522.13-18642,02, layer 24 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.2.25 | 18522.13-18642,02, layer 25 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.2.26 | 18522.13-18642,02, layer 26 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.2.27 | 18522.13-18642,02, layer 27 | 37414.0302 |  |  | 0 | 0 | 0
6.7.1.2.2.28 | 18522.13-18642,02, layer 28 | 26563.9615 |  |  | 0 | 0 | 0
6.7.1.3 | Road Foundation/ Temelj puta
6.7.1.3.1 | 0 - 250 m right side/ desna strana | 22563.2527 | 33 |  | 0 | 0 | 0
6.7.1.3.2 | 0 - 250 m left side/ lijeva strana | 22563.2527 | 34 |  | 0 | 0 | 0
6.7.1.3.3 | 250 - 369.896 m, right side/ desna strana | 10820.975 | 35 |  | 0 | 0 | 0
6.7.1.3.4 | 250 - 305.775 m, left side/ lijeva strana | 5033.8617 | 35 |  | 0 | 0 | 0
6.7.2 | Engineering structures/ Inženjerske konstrukcije
6.7.3 | Water drainage/ Drenaža vode
per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP)
6.7.3.1 | LK18+245.699—LK18+551.474 (305.805 m) | 126046.6101 | 39 |  | 0 | 0 | 0
6.7.3.2 | RK18+272.128—RK18+642.024 (369.896 m) | 152463.6186 | 39 |  | 0 | 0 | 0
6.7.4 | Pavement structure/ Kolovozna konstrukcija
6.7.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana | 43872.8913 | 39 |  | 0 | 0 | 0
6.7.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana | 36267.5815 | 39 |  | 0 | 0 | 0
6.7.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana | 43872.8913 | 40 |  | 0 | 0 | 0
6.7.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana | 36267.5815 | 40 |  | 0 | 0 | 0
6.7.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana | 48750.555 | 41 |  | 0 | 0 | 0
6.7.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana | 40299.7085 | 41 |  | 0 | 0 | 0
| Sub Total / Suma stavke 6.7 | 1682302.8105 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 6.8 | Construction of bridge/ Izgradnja mosta Lutovo (LK18+551.474 —LK18+763.474 RK18+642.024—RK18+770.024)
Completion of/Završetak:
Left bridge/ Lijevi most
6.8.1 | Foundation concrete/ Temeljni beton
6.8.1.1 | A1 | 37811.6922 | 25 |  | 0 | 0 | 0
6.8.1.2 | P1 | 16825.0094 | 25 |  | 0 | 0 | 0
6.8.1.3 | P2 | 16825.0094 | 26 |  | 0 | 0 | 0
6.8.1.4 | P3 | 16825.0094 | 26 |  | 0 | 0 | 0
6.8.1.5 | P4 | 16825.0094 | 27 |  | 0 | 0 | 0
6.8.1.6 | P5 | 16825.0094 | 27 |  | 0 | 0 | 0
6.8.1.7 | P6 | 16825.0094 | 28 |  | 0 | 0 | 0
6.8.1.8 | P7 | 16825.0094 | 28 |  | 0 | 0 | 0
6.8.1.9 | A2 | 37811.6922 | 29 |  | 0 | 0 | 0
6.8.2 | Abutments and Piers elevation/ Elevacija mosnih stubova
6.8.2.1 | A1 | 85429.13 | 31 |  | 0 | 0 | 0
6.8.2.2 | P1 stage 1 (4m) | 9960.8201 | 32 |  | 0 | 0 | 0
6.8.2.3 | P1 stage 2 (2.95m) | 7346.1048 | 32 |  | 0 | 0 | 0
6.8.2.4 | P1 stage 3 (1m) | 2490.205 | 32 |  | 0 | 0 | 0
6.8.2.5 | P2 stage 1 (4m) | 9960.8201 | 32 |  | 0 | 0 | 0
6.8.2.6 | P2 stage 2 (4.3m) | 10707.8816 | 32 |  | 0 | 0 | 0
6.8.2.7 | P2 stage 3 (4m) | 9960.8201 | 33 |  | 0 | 0 | 0
6.8.2.8 | P2 stage 4 (4m) | 9960.8201 | 33 |  | 0 | 0 | 0
6.8.2.9 | P2 stage 5 (3.5m) | 8715.7176 | 33 |  | 0 | 0 | 0
6.8.2.10 | P3 stage 1 (4.5m) | 11205.9226 | 32 |  | 0 | 0 | 0
6.8.2.11 | P3 stage 2 (4m) | 9960.8201 | 32 |  | 0 | 0 | 0
6.8.2.12 | P3 stage 3 (4m) | 9960.8201 | 33 |  | 0 | 0 | 0
6.8.2.13 | P3 stage 4 (4m) | 9960.8201 | 33 |  | 0 | 0 | 0
6.8.2.14 | P3 stage 5 (3m) | 7470.6151 | 34 |  | 0 | 0 | 0
6.8.2.15 | P3 stage 6 (2.5m) | 6225.5126 | 34 |  | 0 | 0 | 0
6.8.2.16 | P4 stage 1 (4.5m) | 11205.9226 | 31 |  | 0 | 0 | 0
6.8.2.17 | P4 stage 2 (4m) | 9960.8201 | 31 |  | 0 | 0 | 0
6.8.2.18 | P4 stage 3 (4m) | 9960.8201 | 32 |  | 0 | 0 | 0
6.8.2.19 | P4 stage 4 (4m) | 9960.8201 | 32 |  | 0 | 0 | 0
6.8.2.20 | P4 stage 5 (4m) | 9960.8201 | 33 |  | 0 | 0 | 0
6.8.2.21 | P4 stage 6 (4m) | 9960.8201 | 33 |  | 0 | 0 | 0
6.8.2.22 | P4 stage 7 (4m) | 9960.8201 | 34 |  | 0 | 0 | 0
6.8.2.23 | P4 stage 8 (3.6m) | 8964.7381 | 34 |  | 0 | 0 | 0
6.8.2.24 | P5 stage 1 (4.5m) | 11205.9226 | 33 |  | 0 | 0 | 0
6.8.2.25 | P5 stage 2 (4m) | 9960.8201 | 33 |  | 0 | 0 | 0
6.8.2.26 | P5 stage 3 (4m) | 9960.8201 | 33 |  | 0 | 0 | 0
6.8.2.27 | P5 stage 4 (4m) | 9960.8201 | 34 |  | 0 | 0 | 0
6.8.2.28 | P5 stage 5 (4m) | 9960.8201 | 34 |  | 0 | 0 | 0
6.8.2.29 | P5 stage 6 (4m) | 9960.8201 | 34 |  | 0 | 0 | 0
6.8.2.30 | P5 stage 7 (4m) | 9960.8201 | 35 |  | 0 | 0 | 0
6.8.2.31 | P5 stage 8 (3.6m) | 8964.7381 | 35 |  | 0 | 0 | 0
6.8.2.32 | P6 stage 1 (4.5m) | 11205.9226 | 34 |  | 0 | 0 | 0
6.8.2.33 | P6 stage 2 (4m) | 9960.8201 | 34 |  | 0 | 0 | 0
6.8.2.34 | P6 stage 3 (4m) | 9960.8201 | 35 |  | 0 | 0 | 0
6.8.2.35 | P6 stage 4 (4m) | 9960.8201 | 35 |  | 0 | 0 | 0
6.8.2.36 | P6 stage 5 (4m) | 9960.8201 | 36 |  | 0 | 0 | 0
6.8.2.37 | P6 stage 6 (4m) | 9960.8201 | 36 |  | 0 | 0 | 0
6.8.2.38 | P7 stage 1 (3.5m) | 8715.7176 | 35 |  | 0 | 0 | 0
6.8.2.39 | P7 stage 2 (4m) | 9960.8201 | 35 |  | 0 | 0 | 0
6.8.2.40 | P7 stage 3 (4m) | 9960.8201 | 36 |  | 0 | 0 | 0
6.8.2.41 | P7 stage 4 (2.4m) | 5976.4921 | 36 |  | 0 | 0 | 0
6.8.2.42 | P7 stage 5 (1m) | 2490.205 | 36 |  | 0 | 0 | 0
6.8.2.43 | A2 | 85429.13 | 35 |  | 0 | 0 | 0
6.8.3 | Bridge deck superstructure/ Gornji stroj mosne ploče
6.8.3.1 | A1-P1 | 90678.16 | 37 |  | 0 | 0 | 0
6.8.3.2 | P1-P2 | 115408.57 | 38 |  | 0 | 0 | 0
6.8.3.3 | P2-P3 | 115408.57 | 39 |  | 0 | 0 | 0
6.8.3.4 | P3-P4 | 115408.57 | 39 |  | 0 | 0 | 0
6.8.3.5 | P4-P5 | 115408.57 | 40 |  | 0 | 0 | 0
6.8.3.6 | P5-P6 | 115408.57 | 40 |  | 0 | 0 | 0
6.8.3.7 | P6-P7 | 115408.57 | 41 |  | 0 | 0 | 0
6.8.3.8 | P7-A2 | 90678.16 | 41 |  | 0 | 0 | 0
6.8.4 | Bridge deck prestressing/ Prednaprezanje mosne ploče
6.8.4.1 | A1-P1 | 10075.35 | 37 |  | 0 | 0 | 0
6.8.4.2 | P1-P2 | 12823.17 | 38 |  | 0 | 0 | 0
6.8.4.3 | P2-P3 | 12823.17 | 39 |  | 0 | 0 | 0
6.8.4.4 | P3-P4 | 12823.17 | 39 |  | 0 | 0 | 0
6.8.4.5 | P4-P5 | 12823.17 | 40 |  | 0 | 0 | 0
6.8.4.6 | P5-P6 | 12823.17 | 40 |  | 0 | 0 | 0
6.8.4.7 | P6-P7 | 12823.17 | 41 |  | 0 | 0 | 0
6.8.4.8 | P7-A2 | 10075.43 | 41 |  | 0 | 0 | 0
6.8.5 | Bridge Furniture/ Mosna estetika
6.8.5.1 | 50 m | 51627.66 | 41 |  | 0 | 0 | 0
6.8.5.2 | 100 m | 51627.66 | 41 |  | 0 | 0 | 0
6.8.5.3 | 150 m | 51627.66 | 42 |  | 0 | 0 | 0
6.8.5.4 | 212 m | 64018.31 | 42 |  | 0 | 0 | 0
6.8.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
6.8.6.1 | Asphalt layer/Sloj asfalta 1 + waterproofing/hidroizolacija | 64134.09 | 41 |  | 0 | 0 | 0
6.8.6.2 | Asphalt layer/Sloj asfalta 2 + joints/Spojnice | 74113.95 | 42 |  | 0 | 0 | 0
Right Bridge/ Desni most
6.8.7 | Foundation concrete/ Temeljni beton
6.8.7.1 | A1 | 36127.2709 | 25 |  | 0 | 0 | 0
6.8.7.2 | P1 | 24117.6145 | 26 |  | 0 | 0 | 0
6.8.7.3 | P2 | 24117.6145 | 27 |  | 0 | 0 | 0
6.8.7.4 | P3 | 24117.6145 | 28 |  | 0 | 0 | 0
6.8.7.5 | P4 | 24117.6145 | 29 |  | 0 | 0 | 0
6.8.7.6 | A2 | 36127.2709 | 29 |  | 0 | 0 | 0
6.8.8 | Abutments and Piers elevation/ Elevacija mosnih stubova
6.8.8.1 | A1 | 58960.29 | 30 |  | 0 | 0 | 0
6.8.8.2 | P1 stage 1 (4.5m) | 6034.9562 | 31 |  | 0 | 0 | 0
6.8.8.3 | P1 stage 2 (4m) | 5364.4055 | 31 |  | 0 | 0 | 0
6.8.8.4 | P1 stage 3 (4m) | 5364.4055 | 32 |  | 0 | 0 | 0
6.8.8.5 | P1 stage 4 (2m) | 2682.2027 | 32 |  | 0 | 0 | 0
6.8.8.6 | P1 stage 5 (3.3m) | 4425.6345 | 32 |  | 0 | 0 | 0
6.8.8.7 | P2 stage 1 (4.5m) | 6034.9562 | 32 |  | 0 | 0 | 0
6.8.8.8 | P2 stage 2 (4m) | 5364.4055 | 32 |  | 0 | 0 | 0
6.8.8.9 | P2 stage 3 (4m) | 5364.4055 | 32 |  | 0 | 0 | 0
6.8.8.10 | P2 stage 4 (4m) | 5364.4055 | 32 |  | 0 | 0 | 0
6.8.8.11 | P2 stage 5 (4m) | 5364.4055 | 33 |  | 0 | 0 | 0
6.8.8.12 | P2 stage 6 (4m) | 5364.4055 | 33 |  | 0 | 0 | 0
6.8.8.13 | P2 stage 7 (4m) | 5364.4055 | 33 |  | 0 | 0 | 0
6.8.8.14 | P2 stage 8 (2.4m) | 3218.6433 | 33 |  | 0 | 0 | 0
6.8.8.15 | P3 stage 1 (4.5m) | 6034.9562 | 34 |  | 0 | 0 | 0
6.8.8.16 | P3 stage 2 (4m) | 5364.4055 | 34 |  | 0 | 0 | 0
6.8.8.17 | P3 stage 3 (4m) | 5364.4055 | 34 |  | 0 | 0 | 0
6.8.8.18 | P3 stage 4 (4m) | 5364.4055 | 35 |  | 0 | 0 | 0
6.8.8.19 | P3 stage 5 (4m) | 5364.4055 | 35 |  | 0 | 0 | 0
6.8.8.20 | P3 stage 6 (4m) | 5364.4055 | 35 |  | 0 | 0 | 0
6.8.8.21 | P3 stage 7 (3.2m) | 4291.5244 | 35 |  | 0 | 0 | 0
6.8.8.22 | P4 stage 1 (4.5m) | 6034.9562 | 35 |  | 0 | 0 | 0
6.8.8.23 | P4 stage 2 (4m) | 5364.4055 | 35 |  | 0 | 0 | 0
6.8.8.24 | P4 stage 3 (4m) | 5364.4055 | 36 |  | 0 | 0 | 0
6.8.8.25 | P4 stage 4 (4m) | 5364.4055 | 36 |  | 0 | 0 | 0
6.8.8.26 | P4 stage 5 (1.8m) | 2413.9825 | 36 |  | 0 | 0 | 0
6.8.8.27 | A2 | 58960.29 | 36 |  | 0 | 0 | 0
6.8.9 | Bridge deck superstructure/ Gornji stroj mosne ploče
6.8.9.1 | A1-P1 | 123416.66 | 37 |  | 0 | 0 | 0
6.8.9.2 | P1-P2 | 157075.74 | 38 |  | 0 | 0 | 0
6.8.9.3 | P2-P3 | 157075.74 | 39 |  | 0 | 0 | 0
6.8.9.4 | P3-P4 | 157075.74 | 40 |  | 0 | 0 | 0
6.8.9.5 | P4-A2 | 123416.66 | 41 |  | 0 | 0 | 0
6.8.10 | Bridge deck prestressing/ Prednaprezanje mosne ploče
6.8.10.1 | A1-P1 | 13712.96 | 37 |  | 0 | 0 | 0
6.8.10.2 | P1-P2 | 17452.86 | 38 |  | 0 | 0 | 0
6.8.10.3 | P2-P3 | 17452.86 | 39 |  | 0 | 0 | 0
6.8.10.4 | P3-P4 | 17452.86 | 40 |  | 0 | 0 | 0
6.8.10.5 | P4-A2 | 13712.99 | 41 |  | 0 | 0 | 0
6.8.11 | Bridge Furniture/ Mosna estetika
6.8.11.1 | 50 m | 74247.51 | 41 |  | 0 | 0 | 0
6.8.11.2 | 100 m | 74247.51 | 42 |  | 0 | 0 | 0
6.8.11.3 | 128 m | 41578.57 | 42 |  | 0 | 0 | 0
6.8.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
6.8.12.1 | Asphalt layer/Sloj asfalta 1 + waterproofing/hidroizolacija | 52768.56 | 41 |  | 0 | 0 | 0
6.8.12.2 | Asphalt layer/Sloj asfalta 2 + joints/Spojnice | 71367.49 | 42 |  | 0 | 0 | 0
6.8.13 | Engineering structures/ Inženjerske konstrukcije
6.8.13.1 | Concrete wall/ Betonski zid
80% for the concrete wall, the milestone is 50m lenth, no matter the hight+ 5% for the "after work" the whole lenth of each retaining wall + 5% for the "correction of the crown" the whole lenth of each retaining wall+10% for the "wall surface" the whole lenth of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
6.8.13.1.1 | Concrete wall/ Betonski zid LK18+567.07-LK18+576.07 (9m)
6.8.13.1.1.1 | Concrete wall/ Betonski zid LK18+567.07-LK18+576.07 - 80% | 11360.7738 |  |  | 0 | 0 | 0
6.8.13.1.1.2 | Concrete wall/ Betonski zid LK18+567.07-LK18+576.07- After work 5% | 710.0484 |  |  | 0 | 0 | 0
6.8.13.1.1.3 | Concrete wall/ Betonski zid LK18+567.07-LK18+576.07- Correction of the crown 5% | 710.0484 |  |  | 0 | 0 | 0
6.8.13.1.1.4 | Concrete wall/ Betonski zid LK18+567.07-LK18+576.07- 10% Wall surface | 1420.0967 |  |  | 0 | 0 | 0
6.8.13.1.2 | Concrete wall/ Betonski zid RK18+583.00--RK18+635.00 (52m)
6.8.13.1.2.1 | Concrete wall/ Betonski zid RK18+583.00--RK18+633.00 (52m) - 80% | 65640.0262 |  |  | 0 | 0 | 0
6.8.13.1.2.2 | Concrete wall/ Betonski zid RK18+583-RK18+635 (52m) After work 5% | 4102.5016 |  |  | 0 | 0 | 0
6.8.13.1.2.3 | Concrete wall/ Betonski zid RK18+583-RK18+635 (52m) Correction of the crown 5% | 4102.5016 |  |  | 0 | 0 | 0
6.8.13.1.2.4 | Concrete wall/ Betonski zid RK18+583-RK18+635 (52m) 10% Wall surface | 8205.0033 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 6.8 | 3696130.11 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 6.9 | Road Works/ Radovi na putevima (LK18+763.474—LK19+305.000 RK18+770.024—RK19+349.000)
Completion of/Završetak:
6.9.1 | Subgrade/ Posteljica
6.9.1.1 | Top soil removal/ Uklanjanje humusa
6.9.1.1.1 | 0 - 250 m (LK&RK) | 56630.4907 | 19 |  | 0 | 0 | 0
6.9.1.1.2 | 250 - 500 m (LK&RK) | 56630.4907 | 19 |  | 0 | 0 | 0
6.9.1.1.3 | 500 - 541.526 m (LK);500 - 578.976 m (RK) | 13648.1748 | 20 |  | 0 | 0 | 0
6.9.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and 4m height /Na svakih 250m i visini od 4m |  | 34
6.9.1.2.1 | 18770,02-19020,02, layers 1,2,3,4,5,6,7,8,9,10,11
6.9.1.2.1.1 | 18770,02-19020,02, layer 1 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.1.2 | 18770,02-19020,02, layer 2 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.1.3 | 18770,02-19020,02, layer 3 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.1.4 | 18770,02-19020,02, layer 4 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.1.5 | 18770,02-19020,02, layer 5 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.1.6 | 18770,02-19020,02, layer 6 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.1.7 | 18770,02-19020,02, layer 7 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.1.8 | 18770,02-19020,02 layer 8 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.1.9 | 18770,02-19020,02, layer 9 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.1.10 | 18770,02-19020,02, layer 10 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.1.11 | 18770,02-19020,02, layer 11 | 39976.9924 |  | 30 | 0 | 39976.9924 | 39976.9924
6.9.1.2.2 | 19020,02-19270,02, layers 12,13,14,15,16,17,18,19,20,21,22,23,24,25
6.9.1.2.2.12 | 19020,02-19270,02, layer 12 | 38061.9269 |  |  | 0 | 0 | 0
6.9.1.2.2.13 | 19020,02-19270,02, layer 13 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.2.14 | 19020,02-19270,02, layer 14 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.2.15 | 19020,02-19270,02, layer 15 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.2.16 | 19020,02-19270,02, layer 16 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.2.17 | 19020,02-19270,02, layer 17 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.2.18 | 19020,02-19270,02, layer 18 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.2.19 | 19020,02-19270,02, layer 19 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.2.20 | 19020,02-19270,02, layer 20 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.2.21 | 19020,02-19270,02, layer 21 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.2.22 | 19020,02-19270,02, layer 22 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.2.23 | 19020,02-19270,02, layer 23 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.2.24 | 19020,02-19270,02, layer 24 | 47876.6376 |  | 30 | 0 | 47876.6376 | 47876.6376
6.9.1.2.2.25 | 19020,02-19270,02, layer 25 | 47876.6376 |  | 30 | 0 | 47876.6376 | 47876.6376
6.9.1.2.3 | 19270,02-19349, layers 26,27,28,29,30,31,32,33,34,35,36
6.9.1.2.3.26 | 19270,02-19349, layer 26 | 32915.1884 |  |  | 0 | 0 | 0
6.9.1.2.3.27 | 19270,02-19349, layer 27 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.3.28 | 19270,02-19349, layer 28 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.3.29 | 19270,02-19349, layer 29 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.3.30 | 19270,02-19349, layer 30 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.3.31 | 19270,02-19349, layer 31 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.3.32 | 19270,02-19349, layer 32 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.3.33 | 19270,02-19349, layer 33 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.3.34 | 19270,02-19349, layer 34 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.3.35 | 19270,02-19349, layer 35 | 47876.6376 |  |  | 0 | 0 | 0
6.9.1.2.3.36 | 19270,02-19349, layer 36 | 35907.4782 |  |  | 0 | 0 | 0
6.9.1.3 | Road Foundation/ Temelj puta
6.9.1.3.1 | 0 - 250 m right side/ desna strana | 22469.2567 | 35 |  | 0 | 0 | 0
6.9.1.3.2 | 0 - 250 m left side/ lijeva strana | 22469.2567 | 35 |  | 0 | 0 | 0
6.9.1.3.3 | 250 - 500 m right side/ desna strana | 22469.2567 | 36 |  | 0 | 0 | 0
6.9.1.3.4 | 250 - 500 m left side/ lijeva strana | 22469.2567 | 36 |  | 0 | 0 | 0
6.9.1.3.5 | 500 - 578.976 m right side/ desna strana | 7098.1281 | 37 |  | 0 | 0 | 0
6.9.1.3.6 | 500 - 541.526 m left side/ lijeva strana | 3732.2334 | 37 |  | 0 | 0 | 0
6.9.2 | Engineering structures/ Inženjerske konstrukcije
6.9.2.1 | Concrete wall / Betonski zid |  | 26
80% for the concrete wall, the milestone is 50m lenth, no matter the hight+ 5% for the "after work" the whole lenth of each retaining wall + 5% for the "correction of the crown" the whole lenth of each retaining wall+10% for the "wall surface" the whole lenth of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
6.9.2.1.1 | Concrete wall/ Betonski zid LK18+770.72 - LK18+800.88 (30.16m)
6.9.2.1.1.1 | Concrete wall/ Betonski zid LK18+770.72 - LK18+800.88 - 80% | 60430.8219 |  |  | 0 | 0 | 0
6.9.2.1.1.2 | Concrete wall/ Betonski zid LK18+770.72-LK18+800.88- After work 5% | 3776.9264 |  |  | 0 | 0 | 0
6.9.2.1.1.3 | Concrete wall/ Betonski zid LK18+770.72-LK18+800.88- Correction of the crown 5% | 3776.9264 |  |  | 0 | 0 | 0
6.9.2.1.1.4 | Concrete wall/ Betonski zid LK18+770.72-LK18+800.88- 10% Wall surface | 7553.8527 |  |  | 0 | 0 | 0
6.9.2.1.2 | Concrete wall/ Betonski zid RK18+777 - RK18+795 (18m)
6.9.2.1.2.1 | Concrete wall/ Betonski zid RK18+777 - RK18+795 - 80% | 36066.1404 |  |  | 0 | 0 | 0
6.9.2.1.2.2 | Concrete wall/ Betonski zid RK18+777 - RK18+795 - After work 5% | 2254.1338 |  |  | 0 | 0 | 0
6.9.2.1.2.3 | Concrete wall/ Betonski zid RK18+777 - RK18+795 - Correction of the crown 5% | 2254.1338 |  |  | 0 | 0 | 0
6.9.2.1.2.4 | Concrete wall/ Betonski zid RK18+777 - RK18+795 - 10% Wall surface | 4508.2675 |  |  | 0 | 0 | 0
6.9.2.1.3 | Concrete wall/ Betonski zid RK19+075 - RK19+202 (127m)
6.9.2.1.3.1 | Segment 1, RK19+075 - RK19+125 - 80% (50m) | 100183.7233 |  | 29 | 100183.7233 | 0 | 100183.7233
6.9.2.1.3.2 | Segment 2, RK19+125 - RK19+175 - 80% (50m) | 100183.7233 |  | 30 | 0 | 100183.7233 | 100183.7233
6.9.2.1.3.3 | Segment 3, RK19+175 - RK19+202 - 80% (27m) | 54099.2106 |  | 30 | 0 | 54099.2106 | 54099.2106
6.9.2.1.3.4 | Concrete wall/ Betonski zid RK19+075 - RK19+202 (127m) - After work 5% | 15904.1661 |  |  | 0 | 0 | 0
6.9.2.1.3.5 | Concrete wall/ Betonski zid RK19+075 - RK19+202 (127m) - Correction of the crown 5% | 15904.1661 |  |  | 0 | 0 | 0
6.9.2.1.3.6 | Concrete wall/ Betonski zid RK19+075 - RK19+202 (127m) - 10% Wall surface | 31808.3321 |  |  | 0 | 0 | 0
6.9.2.1.4 | Concrete wall/ Betonski zid RK19+220--RK19+290 (70m),
6.9.2.1.4.1 | Segment 1, RK19+220 - RK19+270 - 80% (50m) | 100183.7233 |  |  | 0 | 0 | 0
6.9.2.1.4.2 | Segment 2, RK19+270 - RK19+290 - 80% (20m) | 40073.4893 |  |  | 0 | 0 | 0
6.9.2.1.4.3 | Concrete wall/ Betonski zid RK19+220 - RK19+290 - After work 5% | 8766.0758 |  |  | 0 | 0 | 0
6.9.2.1.4.4 | Concrete wall/ Betonski zid RK19+220 - RK19+290 - Correction of the crown 5% | 8766.0758 |  |  | 0 | 0 | 0
6.9.2.1.4.5 | Concrete wall/ Betonski zid RK19+220 - RK19+290 - 10% Wall surface | 17532.1516 |  |  | 0 | 0 | 0
6.9.2.2 | Culvert/ Propust
6.9.2.2.1 | K19+114.6 (111m) | 36898.3519 |  |  | 0 | 0 | 0
6.9.3 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
6.9.3.1 | LK18+763.474 —LK19+305.000 (541.526 m) | 222286.0365 |  |  | 0 | 0 | 0
6.9.3.2 | RK18+770.024—RK19+349.000 (578.976 m) | 237658.5432 |  |  | 0 | 0 | 0
6.9.4 | Pavement structure/ Kolovozna konstrukcija
6.9.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 0-500m | 59057.3062 | 37 |  | 0 | 0 | 0
6.9.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 0-500m | 59057.3062 | 37 |  | 0 | 0 | 0
6.9.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 500-578.976m | 9328.2196 | 38 |  | 0 | 0 | 0
6.9.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 500-541.526 m | 4904.8274 | 38 |  | 0 | 0 | 0
6.9.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 0-500m | 59057.3062 | 39 |  | 0 | 0 | 0
6.9.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 0-500m | 59057.3062 | 39 |  | 0 | 0 | 0
6.9.4.7 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 500-578.976m | 9328.2196 | 40 |  | 0 | 0 | 0
6.9.4.8 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 500-541.526 m | 4904.8274 | 40 |  | 0 | 0 | 0
6.9.4.9 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 0-500m | 65623.1285 | 41 |  | 0 | 0 | 0
6.9.4.10 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 0-500m | 65623.1285 | 41 |  | 0 | 0 | 0
6.9.4.11 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 500-578.976m | 10365.3044 | 42 |  | 0 | 0 | 0
6.9.4.12 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 500-541.526 m | 5450.1321 | 42 |  | 0 | 0 | 0
| Sub Total / Suma stavke 6.9 | 3429156.518 |  |  | 100183.7233 | 290013.2015 | 390196.9248
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 06 | 40904199.567 |  |  | 479534.5999 | 454667.3815 | 934201.9814

## COST CENTER 07
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
COST CENTER 07/TROŠKOVNI CENTAR 07 rev Tunnel and Open Route
Cost Center No./ Troškovno mjesto Br. | 07 | Subsection/Podsekcija 2.3 (LK19+305.00-LK22+730.00, RK19+349.00-RK22+735.00)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost Center/ Troškovno mjesto 7.1 | Road Works/ Radovi na putevima (LK19+305.000—LK19+655.919, RK19+349.000—RK19+719.643)
Completion of/Završetak:
7.1.1 | Subgrade/ Posteljica
7.1.1.1 | Top soil removal/ Uklanjanje humusa
7.1.1.1.1 | 0 - 250 m (LK&RK) | 58650.2869 | 17
7.1.1.1.2 | 250 - 350.919 m (LK); 250 - 370.643 m (RK) | 25989.3497 | 17
7.1.1.2 | Earthworks/ Zemljani radovi |  | 36
At every 250 m and 4m height /Na svakih 250m i visini od 4m
7.1.1.2.1 | 19349-19599, layers 1,2,3,4,5,6,7,8,9,10,11
7.1.1.2.1.1 | 19349-19599, layer 1 | 20218.38 |  |  | 0 | 0 | 0
7.1.1.2.1.2 | 19349-19599, layer 2 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.1.3 | 19349-19599, layer 3 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.1.4 | 19349-19599, layer 4 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.1.5 | 19349-19599, layer 5 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.1.6 | 19349-19599, layer 6 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.1.7 | 19349-19599, layer 7 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.1.8 | 19349-19599, layer 8 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.1.9 | 19349-19599, layer 9 | 50545.95 |  | 30 | 0 | 50545.95 | 50545.95
7.1.1.2.1.10 | 19349-19599, layer 10 | 50545.95 |  | 27 | 50545.95 | 0 | 50545.95
7.1.1.2.1.11 | 19349-19599, layer 11 | 50545.95 |  | 27 | 50545.95 | 0 | 50545.95
7.1.1.2.2 | 19599-19719,64,, layers 12, 13, 14, 15, 16, 17, 18, 19, 20, 21
7.1.1.2.2.12 | 19599-19719,64,92, layer 12 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.2.13 | 19599-19719,64,92, layer 13 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.2.14 | 19599-19719,64,92, layer 14 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.2.15 | 19599-19719,64,92, layer 15 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.2.16 | 19599-19719,64,92, layer 16 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.2.17 | 19599-19719,64,92, layer 17 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.2.18 | 19599-19719,64,92, layer 18 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.2.19 | 19599-19719,64,92, layer 19 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.2.20 | 19599-19719,64,92, layer 20 | 50545.95 |  |  | 0 | 0 | 0
7.1.1.2.2.21 | 19599-19719,64,92, layer 21 | 41953.1389 |  |  | 0 | 0 | 0
7.1.1.3 | Road Foundation/ Temelj puta
7.1.1.3.1 | 0 - 250 m, right side/ desna strana | 23270.6557 | 37 |  | 0 | 0 | 0
7.1.1.3.2 | 0 - 250 m, left side/ lijeva strana | 23270.6557 | 37 |  | 0 | 0 | 0
7.1.1.3.3 | 250 - 370.643 m, right side/ desna strana | 11229.7669 | 37 |  | 0 | 0 | 0
7.1.1.3.4 | 250 - 350.919 m, left side/ lijeva strana | 9393.8052 | 37 |  | 0 | 0 | 0
7.1.2 | Water drainage/ Drenaža vode
per one direction of 500m /Na 500m dužine u jednom pravcu
7.1.2.1 | LK19+305.000—LK19+655.919 | 139967.0597 | 39 |  | 0 | 0 | 0
7.1.2.2 | RK19+349.000—RK19+719.643 | 147834.1466 | 39 |  | 0 | 0 | 0
7.1.3 | Pavement structure/ Kolovozna konstrukcija
7.1.3.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana | 45339.7556 | 40 |  | 0 | 0 | 0
7.1.3.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana | 42926.9721 | 40 |  | 0 | 0 | 0
7.1.3.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana | 45339.7556 | 41 |  | 0 | 0 | 0
7.1.3.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana | 42926.9721 | 41 |  | 0 | 0 | 0
7.1.3.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana | 50380.5004 | 42 |  | 0 | 0 | 0
7.1.3.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana | 47699.4705 | 42 |  | 0 | 0 | 0
7.1.4 | Deviation of local Road/
7.1.4.1 | Gusici | 97174.8 |  |  | 0 | 0 | 0
7.1.5 | Culvert / Propust
7.1.5.1 | K19+387 (112m) | 18950 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 7.1 | 1852888.5217 |  |  | 101091.9 | 50545.95 | 151637.85
Cost Center/ Troškovno mjesto 7.2 | Construction of tunnel/ Izgradnja tunela Vjeternik (LK 19+655.919- LK 22+649.920, RK 19+719.643- RK 22+571.640)
Completion of/Završetak:
7.2.1 | Portal construction/ Izgradnja portala
7.2.1.1 | 20% complete/ završeno (portal 1) | 110970.57 | 16 | 19 | 110970.57 | 0 | 110970.57
7.2.1.2 | 40% complete/ završeno (portal 2) | 110970.57 | 16 |  | 0 | 0 | 0
7.2.1.3 | 60% complete/ završeno (portal 3) | 110970.57 | 16 | 28 | 110970.57 | 0 | 110970.57
7.2.1.4 | 80% complete/ završeno (portal 4) | 110970.57 | 16 | 28 | 110970.57 | 0 | 110970.57
7.2.1.5 | 85% (portal 1 complete/ završen) | 27742.6425 | 43 |  | 0 | 0 | 0
7.2.1.6 | 90% (portal 2 complete/ završen) | 27742.6425 | 43 |  | 0 | 0 | 0
7.2.1.7 | 95% (portal 3 complete/ završen) | 27742.6425 | 44 |  | 0 | 0 | 0
7.2.1.8 | 100% (portal 4 complete/ završen) | 27742.6325 | 44 |  | 0 | 0 | 0
7.2.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
7.2.2.1 | 40 m(S-R,RK 19+731.6- RK 19+771.6) | 212868.27 | 17 | 21 | 212868.27 | 0 | 212868.27
7.2.2.2 | 80 m(S-L,LK 19+667.9- LK 19+707.9) | 212868.27 | 17 | 21 | 212868.27 | 0 | 212868.27
7.2.2.3 | 120 m(S-R,RK 19+771.6- RK 19+811.6) | 212868.27 | 17 | 21 | 212868.27 | 0 | 212868.27
7.2.2.4 | 160 m(S-L,LK 19+707.9- LK 19+747.9) | 212868.27 | 17 | 21 | 212868.27 | 0 | 212868.27
7.2.2.5 | 200 m(N-R,RK 22+517.84- RK 22+476.64) | 212868.27 | 19 | 21 | 212868.27 | 0 | 212868.27
7.2.2.6 | 240 m(N-L, LK 22+683.00- LK22+643.00) | 212868.27 | 19 | 21 | 212868.27 | 0 | 212868.27
7.2.2.7 | 280 m(N-R, RK 22+559.64- RK 22+517.64) | 212868.27 | 19 | 21 | 212868.27 | 0 | 212868.27
7.2.2.8 | 320 m(N-L, LK 22+643.00- RK 22+602.02) | 212868.27 | 19 | 21 | 212868.27 | 0 | 212868.27
7.2.2.9 | 360 m (S-R, RK 19+811.6 - RK 19+851.6) | 212868.27 | 19 | 22 | 212868.27 | 0 | 212868.27
7.2.2.10 | 400 m (S-L, RK 19+747.9 - RK 19+787.9) | 212868.27 | 19 | 23 | 212868.27 | 0 | 212868.27
7.2.2.11 | 440 m (N-R, RK 22+476.84 - RK 22+439.00) | 212868.27 | 19 | 24 | 212868.27 | 0 | 212868.27
7.2.2.12 | 480 m (N-L, LK 22+602.20- LK 22+563.50) | 212868.27 | 19 | 24 | 212868.27 | 0 | 212868.27
7.2.2.13 | 520 m (N-R, RK 22+439.00 - RK 22+398.00) | 212868.27 | 19 | 25 | 212868.27 | 0 | 212868.27
7.2.2.14 | 560 m (N-L, LK 22+563.50- LK 22+522.80) | 212868.27 | 20 | 24 | 212868.27 | 0 | 212868.27
7.2.2.15 | 600 m (S-R, RK 19+851.8 - RK 19+861.6) | 212868.27 | 20 | 24 | 212868.27 | 0 | 212868.27
7.2.2.16 | 640 m (S-R, RK 19+891.6 - RK 19+931.6) | 212868.27 | 20 | 24 | 212868.27 | 0 | 212868.27
7.2.2.17 | 680 m (S-R, RK 19+931.6 - RK 19+971.6) | 212868.27 | 20 | 25 | 212868.27 | 0 | 212868.27
7.2.2.18 | 720 m (S-L, LK 19+867.9 - LK19+907.9) | 212868.27 | 20 | 25 | 212868.27 | 0 | 212868.27
7.2.2.19 | 760 m (S-L, LK 19+787.9 - LK19+827.9) | 212868.27 | 20 | 24 | 212868.27 | 0 | 212868.27
7.2.2.20 | 800 m (S-L, LK 19+827.90 - LK19+867.9) | 212868.27 | 20 | 25 | 212868.27 | 0 | 212868.27
7.2.2.21 | 840 m (N-R, RK 22+398.80 - RK 22+359.30) | 212868.27 | 20 | 25 | 212868.27 | 0 | 212868.27
7.2.2.22 | 880 m (N-L, LK 22+522.80- LK 22+481.50) | 212868.27 | 21 | 25 | 212868.27 | 0 | 212868.27
7.2.2.23 | 920 m (N-R, RK 22+359.30 - RK 22+319.70) | 212868.27 | 21 | 25 | 212868.27 | 0 | 212868.27
7.2.2.24 | 960 m (N-L, LK 22+481.50 - LK 22+439.50) | 212868.27 | 21 | 25 | 212868.27 | 0 | 212868.27
7.2.2.25 | 1000 m (S-L, LK 19+907.90 - LK19+947.9) | 212868.27 | 21 | 25 | 212868.27 | 0 | 212868.27
7.2.2.26 | 1040 m (S-L, LK 19+971.6 - LK20+011.60) | 212868.27 | 21 | 25 | 212868.27 | 0 | 212868.27
7.2.2.27 | 1080 m (N-L, LK 22+439.50- LK 22+400.30) | 212868.27 | 21 | 25 | 212868.27 | 0 | 212868.27
7.2.2.28 | 1120 m (N-R, RK 22+319.70 - RK 22+280.20) | 212868.27 | 22 | 25 | 212868.27 | 0 | 212868.27
7.2.2.29 | 1160 m (S-R, RK 20011.60 - RK 20051.60) | 212868.27 | 22 | 26 | 212868.27 | 0 | 212868.27
7.2.2.30 | 1200 m (S-L, LK 19+947.9 - LK19+987.90) | 212868.27 | 22 | 26 | 212868.27 | 0 | 212868.27
7.2.2.31 | 1240 m (S-R, RK 20.051.60- RK 20.091.60) | 212868.27 | 22 | 26 | 212868.27 | 0 | 212868.27
7.2.2.32 | 1280 m (S-L, LK 19+987.90- LK 20+027.90) | 212868.27 | 22 | 27 | 212868.27 | 0 | 212868.27
7.2.2.33 | 1320 m (S-R, RK 20.091.60- RK 20.131.60) | 212868.27 | 22 | 27 | 212868.27 | 0 | 212868.27
7.2.2.34 | 1360 m (S-L, LK 20+027.90- LK 20+067.90) | 212868.27 | 23 | 27 | 212868.27 | 0 | 212868.27
7.2.2.35 | 1400 m (N-R, RK 22+280.20 - RK 22+240.6) | 212868.27 | 23 | 26 | 212868.27 | 0 | 212868.27
7.2.2.36 | 1440 m | 212868.27 | 23 | 26 | 212868.27 | 0 | 212868.27
7.2.2.37 | 1480 m (N-R, RK 22+240.60 - RK 22+198.50) | 212868.27 | 23 | 26 | 212868.27 | 0 | 212868.27
7.2.2.38 | 1520 m (N-L, LK 22+359.00- LK 22+320.7) | 212868.27 | 23 | 27 | 212868.27 | 0 | 212868.27
7.2.2.39 | 1560 m (N-R, RK 22+198.50 - RK 22+159.1) | 212868.27 | 23 | 27 | 212868.27 | 0 | 212868.27
7.2.2.40 | 1600 m (N-L, LK 22+320.70- LK 22+280.1) | 212868.27 | 24 | 27 | 212868.27 | 0 | 212868.27
7.2.2.41 | 1640 m (N-R, RK 22+159.1 - RK 22+118.70) | 212868.27 | 24 | 27 | 212868.27 | 0 | 212868.27
7.2.2.42 | 1680 m (N-L, LK 22+280.1- LK 22+241.70) | 212868.27 | 24 | 27 | 212868.27 | 0 | 212868.27
7.2.2.43 | 1720 m (N-R, RK 22+118.70 - RK 22+077.70) | 212868.27 | 24 | 27 | 212868.27 | 0 | 212868.27
7.2.2.44 | 1760 m | 212868.27 | 24 |  | 0 | 0 | 0
7.2.2.45 | 1800 m (S-R, RK 20.131.60- RK 20.171.60) | 212868.27 | 24 | 28 | 212868.27 | 0 | 212868.27
7.2.2.46 | 1840 m (S-L, LK 20+067.90- LK 20+107.90) | 212868.27 | 24 | 28 | 212868.27 | 0 | 212868.27
7.2.2.47 | 1880 m (S-R, RK 20.171.60- RK 20.211.60) | 212868.27 | 25 | 28 | 212868.27 | 0 | 212868.27
7.2.2.48 | 1920 m (S-L, LK 20+107.90- LK 20+147.90) | 212868.27 | 25 | 28 | 212868.27 | 0 | 212868.27
7.2.2.49 | 1960 m (N-R, RK 22+077.10 - RK 22+035.50) | 212868.27 | 25 | 28 | 212868.27 | 0 | 212868.27
7.2.2.50 | 2000 m (N-R, RK 22+035.5 - RK 21+994.90) | 212868.27 | 25 | 28 | 212868.27 | 0 | 212868.27
7.2.2.51 | 2040 m (S-R, RK 20.211.60- RK 20.251.60) | 212868.27 | 25 | 28 | 212868.27 | 0 | 212868.27
7.2.2.52 | 2060 m (S-R, RK20+251.6~RK20+271.6) | 108073.6043 | 25 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.53 | 2080 m (S-R, RK20+271.6~RK20+291.7) | 108073.6043 | 25 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.54 | 2100 m S-R, RK20+291.6~RK20+311.6 | 108073.6043 | 25 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.55 | 2120 m S-R, RK20+311.6~RK20+331.7 | 108073.6043 | 25 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.56 | 2140 m S-L, LK20+147.9~LK20+167.9 | 108073.6043 | 25 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.57 | 2160 m S-L, LK20+167.9~LK20+187.9 | 108073.6043 | 26 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.58 | 2180 m S-L, LK20+187.9~LK20+207.9 | 108073.6043 | 26 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.59 | 2200 m S-L, LK20+207.9~LK20+227.9 | 108073.6043 | 26 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.60 | 2220 m S-L, LK20+227.9~LK20+247.9 | 108073.6043 | 26 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.61 | 2240 m S-L, LK20+247.9~LK20+267.9 | 108073.6043 | 26 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.62 | 2260 m N-R, RK21+999.6~RK21+979.6 | 108073.6043 | 26 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.63 | 2280 m N-R, RK21+979.6~RK21+959.6 | 108073.6043 | 26 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.64 | 2300 m N-R, RK21+959.6~RK21+939.6 | 108073.6043 | 26 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.65 | 2320 m N-R, RK21+939.6~RK21+919.6 | 108073.6043 | 26 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.66 | 2340 m S-R, RK20+331.6~RK20+351.6 | 108073.6043 | 26 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.67 | 2360 m S-R, RK20+351.6~RK20+371.7 | 108073.6043 | 26 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.68 | 2380 m S-R, RK20+371.6~RK20+391.6 | 108073.6043 | 26 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.69 | 2400 m S-R, RK20+391.6~RK20+411.6 | 108073.6043 | 27 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.70 | 2420 m S-L, LK20+267.9~LK20+287.9 | 108073.6043 | 27 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.71 | 2440 m S-L, LK20+287.9~LK20+307.9 | 108073.6043 | 27 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.72 | 2460 m S-R, RK20+411.6~RK20+431.7 | 108073.6043 | 27 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.73 | 2480 m S-R, RK20+431.6~RK20+451.8 | 108073.6043 | 27 | 29 | 108073.6043 | 0 | 108073.6043
7.2.2.74 | 2500 m | 108073.6043 | 27 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.75 | 2520 m | 108073.6043 | 27 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.76 | 2540 m | 108073.6043 | 27 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.77 | 2560 m | 108073.6043 | 27 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.78 | 2580 m | 108073.6043 | 27 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.79 | 2600 m | 108073.6043 | 27 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.80 | 2620 m | 108073.6043 | 27 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.81 | 2640 m | 108073.6043 | 27 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.82 | 2660 m | 108073.6043 | 27 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.83 | 2680 m | 108073.6043 | 28 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.84 | 2700 m | 108073.6043 | 28 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.85 | 2720 m | 108073.6043 | 28 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.86 | 2740 m | 108073.6043 | 28 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.87 | 2760 m | 108073.6043 | 28 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.88 | 2780 m | 108073.6043 | 28 |  | 0 | 0 | 0
7.2.2.89 | 2800 m | 108073.6043 | 28 |  | 0 | 0 | 0
7.2.2.90 | 2820 m | 108073.6043 | 28 |  | 0 | 0 | 0
7.2.2.91 | 2840 m | 108073.6043 | 28 |  | 0 | 0 | 0
7.2.2.92 | 2860 m | 108073.6043 | 28 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.93 | 2880 m | 108073.6043 | 28 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.94 | 2900 m | 108073.6043 | 28 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.95 | 2920 m | 108073.6043 | 28 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.96 | 2940 m | 108073.6043 | 28 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.97 | 2960 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.98 | 2980 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.99 | 3000 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.100 | 3020 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.101 | 3040 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.102 | 3060 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.103 | 3080 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.104 | 3100 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.105 | 3120 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.106 | 3140 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.107 | 3160 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.108 | 3180 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.109 | 3200 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.110 | 3220 m | 108073.6043 | 29 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.111 | 3240 m | 108073.6043 | 30 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.112 | 3260 m | 108073.6043 | 30 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.113 | 3280 m | 108073.6043 | 30 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.114 | 3300 m | 108073.6043 | 30 | 30 | 0 | 108073.6043 | 108073.6043
7.2.2.115 | 3320 m | 108073.6043 | 30 |  | 0 | 0 | 0
7.2.2.116 | 3340 m | 108073.6043 | 30 |  | 0 | 0 | 0
7.2.2.117 | 3360 m | 108073.6043 | 30 |  | 0 | 0 | 0
7.2.2.118 | 3380 m | 108073.6043 | 30 |  | 0 | 0 | 0
7.2.2.119 | 3400 m | 108073.6043 | 30 |  | 0 | 0 | 0
7.2.2.120 | 3420 m | 108073.6043 | 30 |  | 0 | 0 | 0
7.2.2.121 | 3440 m | 108073.6043 | 30 |  | 0 | 0 | 0
7.2.2.122 | 3460 m | 108073.6043 | 30 |  | 0 | 0 | 0
7.2.2.123 | 3480 m | 108073.6043 | 31 |  | 0 | 0 | 0
7.2.2.124 | 3500 m | 108073.6043 | 31 |  | 0 | 0 | 0
7.2.2.125 | 3520 m | 108073.6043 | 31 |  | 0 | 0 | 0
7.2.2.126 | 3540 m | 108073.6043 | 31 |  | 0 | 0 | 0
7.2.2.127 | 3560 m | 108073.6043 | 31 |  | 0 | 0 | 0
7.2.2.128 | 3580 m | 108073.6043 | 31 |  | 0 | 0 | 0
7.2.2.129 | 3600 m | 108073.6043 | 31 |  | 0 | 0 | 0
7.2.2.130 | 3620 m | 108073.6043 | 31 |  | 0 | 0 | 0
7.2.2.131 | 3640 m | 108073.6043 | 31 |  | 0 | 0 | 0
7.2.2.132 | 3660 m | 108073.6043 | 31 |  | 0 | 0 | 0
7.2.2.133 | 3680 m | 108073.6043 | 31 |  | 0 | 0 | 0
7.2.2.134 | 3700 m | 108073.6043 | 31 |  | 0 | 0 | 0
7.2.2.135 | 3720 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.136 | 3740 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.137 | 3760 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.138 | 3780 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.139 | 3800 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.140 | 3820 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.141 | 3840 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.142 | 3860 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.143 | 3880 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.144 | 3900 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.145 | 3920 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.146 | 3940 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.147 | 3960 m | 108073.6043 | 32 |  | 0 | 0 | 0
7.2.2.148 | 3980 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.149 | 4000 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.150 | 4020 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.151 | 4040 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.152 | 4060 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.153 | 4080 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.154 | 4100 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.155 | 4120 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.156 | 4140 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.157 | 4160 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.158 | 4180 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.159 | 4200 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.160 | 4220 m | 108073.6043 | 33 |  | 0 | 0 | 0
7.2.2.161 | 4240 m | 108073.6043 | 34 |  | 0 | 0 | 0
7.2.2.162 | 4260 m | 108073.6043 | 34 |  | 0 | 0 | 0
7.2.2.163 | 4280 m | 108073.6043 | 34 |  | 0 | 0 | 0
7.2.2.164 | 4300 m | 108073.6043 | 34 |  | 0 | 0 | 0
7.2.2.165 | 4320 m | 108073.6043 | 34 |  | 0 | 0 | 0
7.2.2.166 | 4340 m | 108073.6043 | 34 |  | 0 | 0 | 0
7.2.2.167 | 4360 m | 108073.6043 | 34 |  | 0 | 0 | 0
7.2.2.168 | 4380 m | 108073.6043 | 34 |  | 0 | 0 | 0
7.2.2.169 | 4400 m | 108073.6043 | 34 |  | 0 | 0 | 0
7.2.2.170 | 4420 m | 108073.6043 | 34 |  | 0 | 0 | 0
7.2.2.171 | 4440 m | 108073.6043 | 34 |  | 0 | 0 | 0
7.2.2.172 | 4460 m | 108073.6043 | 34 |  | 0 | 0 | 0
7.2.2.173 | 4480 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.174 | 4500 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.175 | 4520 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.176 | 4540 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.177 | 4560 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.178 | 4580 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.179 | 4600 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.180 | 4620 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.181 | 4640 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.182 | 4660 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.183 | 4680 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.184 | 4700 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.185 | 4720 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.186 | 4740 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.187 | 4760 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.188 | 4780 m | 108073.6043 | 35 |  | 0 | 0 | 0
7.2.2.189 | 4800 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.190 | 4820 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.191 | 4840 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.192 | 4860 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.193 | 4880 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.194 | 4900 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.195 | 4920 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.196 | 4940 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.197 | 4960 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.198 | 4980 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.199 | 5000 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.200 | 5020 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.201 | 5040 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.202 | 5060 m | 108073.6043 | 36 |  | 0 | 0 | 0
7.2.2.203 | 5080 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.204 | 5100 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.205 | 5120 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.206 | 5140 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.207 | 5160 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.208 | 5180 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.209 | 5200 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.210 | 5220 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.211 | 5240 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.212 | 5260 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.213 | 5280 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.214 | 5300 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.215 | 5320 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.216 | 5340 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.217 | 5360 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.218 | 5380 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.219 | 5400 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.220 | 5420 m | 108073.6043 | 37 |  | 0 | 0 | 0
7.2.2.221 | 5440 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.222 | 5460 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.223 | 5480 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.224 | 5500 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.225 | 5520 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.226 | 5540 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.227 | 5560 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.228 | 5580 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.229 | 5600 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.230 | 5620 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.231 | 5640 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.232 | 5660 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.233 | 5680 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.234 | 5700 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.235 | 5720 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.236 | 5740 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.237 | 5760 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.238 | 5780 m | 108073.6043 | 38 |  | 0 | 0 | 0
7.2.2.239 | 5800 m | 108073.6043 | 39 |  | 0 | 0 | 0
7.2.2.240 | 5820 m | 108073.6043 | 39 |  | 0 | 0 | 0
7.2.2.241 | 5840 m | 108073.6043 | 39 |  | 0 | 0 | 0
7.2.2.242 | 5843 m | 16211.0406 | 39 |  | 0 | 0 | 0
7.2.3 | Construction of waterproofing and drainage&Construction of secondary lining/ Konstrukcija hidroizolacije i drenaže&Konstrukcija sekundarne obloge
7.2.3.1 | 20 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.2 | 40 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.3 | 60 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.4 | 80 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.5 | 100 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.6 | 120 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.7 | 140 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.8 | 160 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.9 | 180 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.10 | 200 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.11 | 220 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.12 | 240 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.13 | 260 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.14 | 280 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.15 | 300 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.16 | 320 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.17 | 340 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.18 | 360 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.19 | 380 m | 82790.0074 | 19 |  | 0 | 0 | 0
7.2.3.20 | 400 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.21 | 420 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.22 | 440 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.23 | 460 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.24 | 480 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.25 | 500 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.26 | 520 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.27 | 540 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.28 | 560 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.29 | 580 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.30 | 600 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.31 | 620 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.32 | 640 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.33 | 660 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.34 | 680 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.35 | 700 m | 82790.0074 | 20 |  | 0 | 0 | 0
7.2.3.36 | 720 m | 82790.0074 | 21 |  | 0 | 0 | 0
7.2.3.37 | 740 m | 82790.0074 | 21 |  | 0 | 0 | 0
7.2.3.38 | 760 m | 82790.0074 | 21 |  | 0 | 0 | 0
7.2.3.39 | 780 m | 82790.0074 | 21 |  | 0 | 0 | 0
7.2.3.40 | 800 m | 82790.0074 | 21 |  | 0 | 0 | 0
7.2.3.41 | 820 m | 82790.0074 | 21 |  | 0 | 0 | 0
7.2.3.42 | 840 m | 82790.0074 | 21 |  | 0 | 0 | 0
7.2.3.43 | 860 m | 82790.0074 | 21 |  | 0 | 0 | 0
7.2.3.44 | 880 m | 82790.0074 | 21 |  | 0 | 0 | 0
7.2.3.45 | 900 m | 82790.0074 | 21 |  | 0 | 0 | 0
7.2.3.46 | 920 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.47 | 940 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.48 | 960 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.49 | 980 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.50 | 1000 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.51 | 1020 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.52 | 1040 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.53 | 1060 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.54 | 1080 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.55 | 1100 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.56 | 1120 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.57 | 1140 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.58 | 1160 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.59 | 1180 m | 82790.0074 | 22 |  | 0 | 0 | 0
7.2.3.60 | 1200 m | 82790.0074 | 23 |  | 0 | 0 | 0
7.2.3.61 | 1220 m | 82790.0074 | 23 |  | 0 | 0 | 0
7.2.3.62 | 1240 m | 82790.0074 | 23 |  | 0 | 0 | 0
7.2.3.63 | 1260 m | 82790.0074 | 23 |  | 0 | 0 | 0
7.2.3.64 | 1280 m | 82790.0074 | 23 |  | 0 | 0 | 0
7.2.3.65 | 1300 m | 82790.0074 | 23 |  | 0 | 0 | 0
7.2.3.66 | 1320 m | 82790.0074 | 23 |  | 0 | 0 | 0
7.2.3.67 | 1340 m | 82790.0074 | 23 |  | 0 | 0 | 0
7.2.3.68 | 1360 m | 82790.0074 | 23 |  | 0 | 0 | 0
7.2.3.69 | 1380 m | 82790.0074 | 23 |  | 0 | 0 | 0
7.2.3.70 | 1400 m | 82790.0074 | 23 |  | 0 | 0 | 0
7.2.3.71 | 1420 m | 82790.0074 | 23 |  | 0 | 0 | 0
7.2.3.72 | 1440 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.73 | 1460 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.74 | 1480 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.75 | 1500 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.76 | 1520 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.77 | 1540 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.78 | 1560 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.79 | 1580 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.80 | 1600 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.81 | 1620 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.82 | 1640 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.83 | 1660 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.84 | 1680 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.85 | 1700 m | 82790.0074 | 24 |  | 0 | 0 | 0
7.2.3.86 | 1720 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.87 | 1740 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.88 | 1760 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.89 | 1780 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.90 | 1800 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.91 | 1820 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.92 | 1840 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.93 | 1860 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.94 | 1880 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.95 | 1900 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.96 | 1920 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.97 | 1940 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.98 | 1960 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.99 | 1980 m | 82790.0074 | 25 |  | 0 | 0 | 0
7.2.3.100 | 2000 m | 82790.0074 | 26 |  | 0 | 0 | 0
7.2.3.101 | 2020 m | 82790.0074 | 26 |  | 0 | 0 | 0
7.2.3.102 | 2040 m | 82790.0074 | 26 |  | 0 | 0 | 0
7.2.3.103 | 2060 m | 82790.0074 | 26 |  | 0 | 0 | 0
7.2.3.104 | 2080 m | 82790.0074 | 26 |  | 0 | 0 | 0
7.2.3.105 | 2100 m | 82790.0074 | 26 |  | 0 | 0 | 0
7.2.3.106 | 2120 m | 82790.0074 | 26 |  | 0 | 0 | 0
7.2.3.107 | 2140 m | 82790.0074 | 26 |  | 0 | 0 | 0
7.2.3.108 | 2160 m | 82790.0074 | 26 |  | 0 | 0 | 0
7.2.3.109 | 2180 m | 82790.0074 | 26 |  | 0 | 0 | 0
7.2.3.110 | 2200 m | 82790.0074 | 26 |  | 0 | 0 | 0
7.2.3.111 | 2220 m | 82790.0074 | 26 |  | 0 | 0 | 0
7.2.3.112 | 2240 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.113 | 2260 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.114 | 2280 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.115 | 2300 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.116 | 2320 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.117 | 2340 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.118 | 2360 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.119 | 2380 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.120 | 2400 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.121 | 2420 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.122 | 2440 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.123 | 2460 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.124 | 2480 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.125 | 2500 m | 82790.0074 | 27 |  | 0 | 0 | 0
7.2.3.126 | 2520 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.127 | 2540 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.128 | 2560 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.129 | 2580 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.130 | 2600 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.131 | 2620 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.132 | 2640 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.133 | 2660 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.134 | 2680 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.135 | 2700 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.136 | 2720 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.137 | 2740 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.138 | 2760 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.139 | 2780 m | 82790.0074 | 28 |  | 0 | 0 | 0
7.2.3.140 | 2800 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.141 | 2820 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.142 | 2840 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.143 | 2860 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.144 | 2880 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.145 | 2900 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.146 | 2920 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.147 | 2940 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.148 | 2960 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.149 | 2980 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.150 | 3000 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.151 | 3020 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.152 | 3040 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.153 | 3060 m | 82790.0074 | 29 |  | 0 | 0 | 0
7.2.3.154 | 3080 m | 82790.0074 | 30 |  | 0 | 0 | 0
7.2.3.155 | 3100 m | 82790.0074 | 30 |  | 0 | 0 | 0
7.2.3.156 | 3120 m | 82790.0074 | 30 |  | 0 | 0 | 0
7.2.3.157 | 3140 m | 82790.0074 | 30 |  | 0 | 0 | 0
7.2.3.158 | 3160 m | 82790.0074 | 30 |  | 0 | 0 | 0
7.2.3.159 | 3180 m | 82790.0074 | 30 |  | 0 | 0 | 0
7.2.3.160 | 3200 m | 82790.0074 | 30 |  | 0 | 0 | 0
7.2.3.161 | 3220 m | 82790.0074 | 30 |  | 0 | 0 | 0
7.2.3.162 | 3240 m | 82790.0074 | 30 |  | 0 | 0 | 0
7.2.3.163 | 3260 m | 82790.0074 | 30 |  | 0 | 0 | 0
7.2.3.164 | 3280 m | 82790.0074 | 30 |  | 0 | 0 | 0
7.2.3.165 | 3300 m | 82790.0074 | 30 |  | 0 | 0 | 0
7.2.3.166 | 3320 m | 82790.0074 | 31 |  | 0 | 0 | 0
7.2.3.167 | 3340 m | 82790.0074 | 31 |  | 0 | 0 | 0
7.2.3.168 | 3360 m | 82790.0074 | 31 |  | 0 | 0 | 0
7.2.3.169 | 3380 m | 82790.0074 | 31 |  | 0 | 0 | 0
7.2.3.170 | 3400 m | 82790.0074 | 31 |  | 0 | 0 | 0
7.2.3.171 | 3420 m | 82790.0074 | 31 |  | 0 | 0 | 0
7.2.3.172 | 3440 m | 82790.0074 | 31 |  | 0 | 0 | 0
7.2.3.173 | 3460 m | 82790.0074 | 31 |  | 0 | 0 | 0
7.2.3.174 | 3480 m | 82790.0074 | 31 |  | 0 | 0 | 0
7.2.3.175 | 3500 m | 82790.0074 | 31 |  | 0 | 0 | 0
7.2.3.176 | 3520 m | 82790.0074 | 31 |  | 0 | 0 | 0
7.2.3.177 | 3540 m | 82790.0074 | 31 |  | 0 | 0 | 0
7.2.3.178 | 3560 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.179 | 3580 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.180 | 3600 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.181 | 3620 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.182 | 3640 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.183 | 3660 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.184 | 3680 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.185 | 3700 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.186 | 3720 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.187 | 3740 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.188 | 3760 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.189 | 3780 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.190 | 3800 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.191 | 3820 m | 82790.0074 | 32 |  | 0 | 0 | 0
7.2.3.192 | 3840 m | 82790.0074 | 33 |  | 0 | 0 | 0
7.2.3.193 | 3860 m | 82790.0074 | 33 |  | 0 | 0 | 0
7.2.3.194 | 3880 m | 82790.0074 | 33 |  | 0 | 0 | 0
7.2.3.195 | 3900 m | 82790.0074 | 33 |  | 0 | 0 | 0
7.2.3.196 | 3920 m | 82790.0074 | 33 |  | 0 | 0 | 0
7.2.3.197 | 3940 m | 82790.0074 | 33 |  | 0 | 0 | 0
7.2.3.198 | 3960 m | 82790.0074 | 33 |  | 0 | 0 | 0
7.2.3.199 | 3980 m | 82790.0074 | 33 |  | 0 | 0 | 0
7.2.3.200 | 4000 m | 82790.0074 | 33 |  | 0 | 0 | 0
7.2.3.201 | 4020 m | 82790.0074 | 33 |  | 0 | 0 | 0
7.2.3.202 | 4040 m | 82790.0074 | 33 |  | 0 | 0 | 0
7.2.3.203 | 4060 m | 82790.0074 | 33 |  | 0 | 0 | 0
7.2.3.204 | 4080 m | 82790.0074 | 34 |  | 0 | 0 | 0
7.2.3.205 | 4100 m | 82790.0074 | 34 |  | 0 | 0 | 0
7.2.3.206 | 4120 m | 82790.0074 | 34 |  | 0 | 0 | 0
7.2.3.207 | 4140 m | 82790.0074 | 34 |  | 0 | 0 | 0
7.2.3.208 | 4160 m | 82790.0074 | 34 |  | 0 | 0 | 0
7.2.3.209 | 4180 m | 82790.0074 | 34 |  | 0 | 0 | 0
7.2.3.210 | 4200 m | 82790.0074 | 34 |  | 0 | 0 | 0
7.2.3.211 | 4220 m | 82790.0074 | 34 |  | 0 | 0 | 0
7.2.3.212 | 4240 m | 82790.0074 | 34 |  | 0 | 0 | 0
7.2.3.213 | 4260 m | 82790.0074 | 34 |  | 0 | 0 | 0
7.2.3.214 | 4280 m | 82790.0074 | 34 |  | 0 | 0 | 0
7.2.3.215 | 4300 m | 82790.0074 | 34 |  | 0 | 0 | 0
7.2.3.216 | 4320 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.217 | 4340 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.218 | 4360 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.219 | 4380 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.220 | 4400 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.221 | 4420 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.222 | 4440 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.223 | 4460 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.224 | 4480 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.225 | 4500 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.226 | 4520 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.227 | 4540 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.228 | 4560 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.229 | 4580 m | 82790.0074 | 35 |  | 0 | 0 | 0
7.2.3.230 | 4600 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.231 | 4620 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.232 | 4640 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.233 | 4660 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.234 | 4680 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.235 | 4700 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.236 | 4720 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.237 | 4740 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.238 | 4760 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.239 | 4780 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.240 | 4800 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.241 | 4820 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.242 | 4840 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.243 | 4860 m | 82790.0074 | 36 |  | 0 | 0 | 0
7.2.3.244 | 4880 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.245 | 4900 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.246 | 4920 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.247 | 4940 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.248 | 4960 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.249 | 4980 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.250 | 5000 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.251 | 5020 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.252 | 5040 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.253 | 5060 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.254 | 5080 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.255 | 5100 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.256 | 5120 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.257 | 5140 m | 82790.0074 | 37 |  | 0 | 0 | 0
7.2.3.258 | 5160 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.259 | 5180 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.260 | 5200 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.261 | 5220 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.262 | 5240 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.263 | 5260 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.264 | 5280 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.265 | 5300 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.266 | 5320 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.267 | 5340 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.268 | 5360 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.269 | 5380 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.270 | 5400 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.271 | 5420 m | 82790.0074 | 38 |  | 0 | 0 | 0
7.2.3.272 | 5440 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.273 | 5460 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.274 | 5480 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.275 | 5500 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.276 | 5520 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.277 | 5540 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.278 | 5560 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.279 | 5580 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.280 | 5600 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.281 | 5620 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.282 | 5640 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.283 | 5660 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.284 | 5680 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.285 | 5700 m | 82790.0074 | 39 |  | 0 | 0 | 0
7.2.3.286 | 5720 m | 82790.0074 | 40 |  | 0 | 0 | 0
7.2.3.287 | 5740 m | 82790.0074 | 40 |  | 0 | 0 | 0
7.2.3.288 | 5760 m | 82790.0074 | 40 |  | 0 | 0 | 0
7.2.3.289 | 5780 m | 82790.0074 | 40 |  | 0 | 0 | 0
7.2.3.290 | 5800 m | 82790.0074 | 40 |  | 0 | 0 | 0
7.2.3.291 | 5820 m | 82790.0074 | 40 |  | 0 | 0 | 0
7.2.3.292 | 5840 m | 82790.0074 | 40 |  | 0 | 0 | 0
7.2.3.293 | 5843 m | 12418.5011 | 40 |  | 0 | 0 | 0
7.2.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi I ploca, drenazni sistem)
7.2.4.1 | 200 m | 80000 | 20 |  | 0 | 0 | 0
7.2.4.2 | 400 m | 80000 | 20 |  | 0 | 0 | 0
7.2.4.3 | 600 m | 80000 | 21 |  | 0 | 0 | 0
7.2.4.4 | 800 m | 80000 | 22 |  | 0 | 0 | 0
7.2.4.5 | 1000 m | 80000 | 23 |  | 0 | 0 | 0
7.2.4.6 | 1200 m | 80000 | 24 |  | 0 | 0 | 0
7.2.4.7 | 1400 m | 80000 | 25 |  | 0 | 0 | 0
7.2.4.8 | 1600 m | 80000 | 25 |  | 0 | 0 | 0
7.2.4.9 | 1800 m | 80000 | 26 |  | 0 | 0 | 0
7.2.4.10 | 2000 m | 80000 | 27 |  | 0 | 0 | 0
7.2.4.11 | 2200 m | 80000 | 28 |  | 0 | 0 | 0
7.2.4.12 | 2400 m | 80000 | 29 |  | 0 | 0 | 0
7.2.4.13 | 2600 m | 80000 | 30 |  | 0 | 0 | 0
7.2.4.14 | 2800 m | 80000 | 31 |  | 0 | 0 | 0
7.2.4.15 | 3000 m | 80000 | 31 |  | 0 | 0 | 0
7.2.4.16 | 3200 m | 80000 | 32 |  | 0 | 0 | 0
7.2.4.17 | 3400 m | 80000 | 33 |  | 0 | 0 | 0
7.2.4.18 | 3600 m | 80000 | 34 |  | 0 | 0 | 0
7.2.4.19 | 3800 m | 80000 | 34 |  | 0 | 0 | 0
7.2.4.20 | 4000 m | 80000 | 35 |  | 0 | 0 | 0
7.2.4.21 | 4200 m | 80000 | 36 |  | 0 | 0 | 0
7.2.4.22 | 4400 m | 80000 | 37 |  | 0 | 0 | 0
7.2.4.23 | 4600 m | 80000 | 37 |  | 0 | 0 | 0
7.2.4.24 | 4800 m | 80000 | 38 |  | 0 | 0 | 0
7.2.4.25 | 5000 m | 80000 | 39 |  | 0 | 0 | 0
7.2.4.26 | 5200 m | 80000 | 39 |  | 0 | 0 | 0
7.2.4.27 | 5400 m | 80000 | 40 |  | 0 | 0 | 0
7.2.4.28 | 5600 m | 80000 | 40 |  | 0 | 0 | 0
7.2.4.29 | 5800 m | 80000 | 41 |  | 0 | 0 | 0
7.2.4.30 | 5843 m | 17200 | 42 |  | 0 | 0 | 0
7.2.5 | Construction of pavement/ Izgradnja kolovoza
7.2.5.1 | Left tube/ Lijeva cijev
0-500 m
7.2.5.1.1 | Layer/ Sloj 1 | 36322.57 | 41 |  | 0 | 0 | 0
7.2.5.1.2 | Layer/ Sloj 2 | 36322.57 | 42 |  | 0 | 0 | 0
7.2.5.1.3 | Layer/ Sloj 3 | 40862.89 | 43 |  | 0 | 0 | 0
500-1000 m
7.2.5.1.4 | Layer/ Sloj 1 | 36322.57 | 41 |  | 0 | 0 | 0
7.2.5.1.5 | Layer/ Sloj 2 | 36322.57 | 42 |  | 0 | 0 | 0
7.2.5.1.6 | Layer/ Sloj 3 | 40862.89 | 43 |  | 0 | 0 | 0
1000-1500 m
7.2.5.1.7 | Layer/ Sloj 1 | 36322.57 | 41 |  | 0 | 0 | 0
7.2.5.1.8 | Layer/ Sloj 2 | 36322.57 | 42 |  | 0 | 0 | 0
7.2.5.1.9 | Layer/ Sloj 3 | 40862.89 | 43 |  | 0 | 0 | 0
1500-2000 m
7.2.5.1.10 | Layer/ Sloj 1 | 36322.57 | 41 |  | 0 | 0 | 0
7.2.5.1.11 | Layer/ Sloj 2 | 36322.57 | 42 |  | 0 | 0 | 0
7.2.5.1.12 | Layer/ Sloj 3 | 40862.89 | 43 |  | 0 | 0 | 0
2000-2500 m
7.2.5.1.13 | Layer/ Sloj 1 | 36322.57 | 41 |  | 0 | 0 | 0
7.2.5.1.14 | Layer/ Sloj 2 | 36322.57 | 42 |  | 0 | 0 | 0
7.2.5.1.15 | Layer/ Sloj 3 | 40862.89 | 43 |  | 0 | 0 | 0
2500-3039.001mm
7.2.5.1.16 | Layer/ Sloj 1 | 39377.3 | 41 |  | 0 | 0 | 0
7.2.5.1.17 | Layer/ Sloj 2 | 39377.3 | 42 |  | 0 | 0 | 0
7.2.5.1.18 | Layer/ Sloj 3 | 44299.47 | 43 |  | 0 | 0 | 0
7.2.5.2 | Right tube/ Desna cijev
0-500 m
7.2.5.2.1 | Layer/ Sloj 1 | 36322.57 | 41 |  | 0 | 0 | 0
7.2.5.2.2 | Layer/ Sloj 2 | 36322.57 | 42 |  | 0 | 0 | 0
7.2.5.2.3 | Layer/ Sloj 3 | 40862.89 | 43 |  | 0 | 0 | 0
500-1000 m
7.2.5.2.4 | Layer/ Sloj 1 | 36322.57 | 41 |  | 0 | 0 | 0
7.2.5.2.5 | Layer/ Sloj 2 | 36322.57 | 42 |  | 0 | 0 | 0
7.2.5.2.6 | Layer/ Sloj 3 | 40862.89 | 43 |  | 0 | 0 | 0
1000-1500 m
7.2.5.2.7 | Layer/ Sloj 1 | 36322.57 | 41 |  | 0 | 0 | 0
7.2.5.2.8 | Layer/ Sloj 2 | 36322.57 | 42 |  | 0 | 0 | 0
7.2.5.2.9 | Layer/ Sloj 3 | 40862.89 | 43 |  | 0 | 0 | 0
1500-2000 m
7.2.5.2.10 | Layer/ Sloj 1 | 36322.57 | 41 |  | 0 | 0 | 0
7.2.5.2.11 | Layer/ Sloj 2 | 36322.57 | 42 |  | 0 | 0 | 0
7.2.5.2.12 | Layer/ Sloj 3 | 40862.89 | 43 |  | 0 | 0 | 0
2000-2500 m
7.2.5.2.13 | Layer/ Sloj 1 | 36322.57 | 41 |  | 0 | 0 | 0
7.2.5.2.14 | Layer/ Sloj 2 | 36322.57 | 42 |  | 0 | 0 | 0
7.2.5.2.15 | Layer/ Sloj 3 | 40862.89 | 43 |  | 0 | 0 | 0
2500-2851.997 m
7.2.5.2.16 | Layer/ Sloj 1 | 29605.07 | 41 |  | 0 | 0 | 0
7.2.5.2.17 | Layer/ Sloj 2 | 29605.07 | 42 |  | 0 | 0 | 0
7.2.5.2.18 | Layer/ Sloj 3 | 33305.72 | 43 |  | 0 | 0 | 0
7.2.6 | Tunnel facilities/ Tunelski objekti
7.2.6.1 | Construction of Power Station/ Izgradnja elektro-stanice (1) | 165282.22 | 41 |  | 0 | 0 | 0
7.2.6.2 | Construction of Power Station/ Izgradnja elektro-stanice (2) | 165282.22 | 42 |  | 0 | 0 | 0
7.2.6.3 | Construction of antifire reservoir/ Izgradnja protivpožarnog rezervoara | 86312.55 | 43 |  | 0 | 0 | 0
7.2.7 | Tunnel Equipment/ Tunelska oprema
7.2.7.1 | Right tube/ Desna cijev
7.2.7.1.1 | 90% (Equipment installed/ Oprema postavljena) | 2909574.53 | 45 |  | 0 | 0 | 0
7.2.7.1.2 | 10% (Equipment tested/ Oprema ispitana) | 323286.06 | 46 |  | 0 | 0 | 0
7.2.7.2 | Left tube/ Lijeva cijev
7.2.7.2.1 | 90% (Equipment installed/ Oprema postavljena) | 3044694.09 | 45 |  | 0 | 0 | 0
7.2.7.2.2 | 10% (Equipment tested/ Oprema ispitana) | 338299.34 | 46 |  | 0 | 0 | 0
| Sub Total / Suma stavke 7.2 | 66869012.38 |  |  | 13353944.5049 | 3998723.3596 | 17352667.8644
Cost Center/ Troškovno mjesto 7.3 | Road Works/ Radovi na putevima (LK22+694.920—LK22+730.000, RK22+571.640—RK22+735.000)
Completion of/Završetak:
7.3.1 | Subgrade/ Posteljica
7.3.1.1 | Top soil removal/ Uklanjanje humusa
7.3.1.1.1 | RK22+571.640—RK22+735.000 (Inc.0 - 35.080 m (LK); 0 - 163.360 m (RK)) | 23277.1259 | 17 |  | 0 | 0 | 0
7.3.1.2 | Earthworks/ Zemljani radovi |  | 36
At every 250 m and 4m height /Na svakih 250m i visini od 4m
7.3.1.2.1 | 22+571.64 - 22+735.00, layers 1, 2, 3, 4, 5, 6
7.3.1.2.1.1 | 22+571.64 - 22+735.00, layer 1 | 53461.6399 |  |  | 0 | 0 | 0
7.3.1.2.1.2 | 22+571.64 - 22+735.00, layer 2 | 53461.6399 |  |  | 0 | 0 | 0
7.3.1.2.1.3 | 22+571.64 - 22+735.00, layer 3 | 53461.6399 |  |  | 0 | 0 | 0
7.3.1.2.1.4 | 22+571.64 - 22+735.00, layer 4 | 53461.6399 |  |  | 0 | 0 | 0
7.3.1.2.1.5 | 22+571.64 - 22+735.00, layer 5 | 53461.6399 |  |  | 0 | 0 | 0
7.3.1.2.1.6 | 22+571.64 - 22+735.00, layer 6 | 40630.8463 |  |  | 0 | 0 | 0
7.3.1.3 | Road Foundation/ Temelj puta
7.3.1.3.1 | 0 - 163.360 m, right side/ desna strana | 15205.9773 | 37 |  | 0 | 0 | 0
7.3.1.3.2 | 0 - 35.080 m, left side/ lijeva strana | 3265.35 | 37 |  | 0 | 0 | 0
7.3.2 | Water drainage/ Drenaža vode
per one direction of 500m /Na 500m dužine u jednom pravcu
7.3.2.1 | LK22+694.920—LK22+730.000 (35.080 m) | 14913.247 | 39 |  | 0 | 0 | 0
7.3.2.2 | RK22+571.640—RK22+735.000 (163.360 m) | 69447.7773 | 39 |  | 0 | 0 | 0
7.3.3 | Pavement structure/ Kolovozna konstrukcija
7.3.3.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana | 19983.3869 | 40 |  | 0 | 0 | 0
7.3.3.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana | 4291.2415 | 40 |  | 0 | 0 | 0
7.3.3.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana | 19983.3869 | 41 |  | 0 | 0 | 0
7.3.3.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana | 4291.2415 | 41 |  | 0 | 0 | 0
7.3.3.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana | 22205.0829 | 42 |  | 0 | 0 | 0
7.3.3.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana | 4768.3295 | 42 |  | 0 | 0 | 0
7.3.4 | Engineering structures/ Inženjerske konstrukcije
7.3.4.1 | Concrete wall / Betonski zid
80% for the concrete wall, the milestone is 50m lenth, no matter the hight+ 5% for the "after work" the whole lenth of each retaining wall + 5% for the "correction of the crown" the whole lenth of each retaining wall+10% for the "wall surface" the whole lenth of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
7.3.4.1.1 | Concrete wall/ Betonski zid RK22+564.64 ~ RK22+725 (160.36m) 80%, Layers 1,2,3,4,5
7.3.4.1.1.1 | Segment 1 RK22+564.64 ~ RK22+614.64 (50m) | 56460.464 |  |  | 0 | 0 | 0
7.3.4.1.1.2 | Segment 2 RK22+614.64 ~ RK22+664.64 (50m) | 56460.464 |  |  | 0 | 0 | 0
7.3.4.1.1.3 | Segment 3 RK22+664.64 ~ RK22+714.64 (50m) | 56460.464 |  |  | 0 | 0 | 0
7.3.4.1.1.4 | Segment 4 RK22+714.64 ~ RK22+725 (10.36m) | 11698.6081 |  |  | 0 | 0 | 0
7.3.4.1.1.5 | Concrete wall/ Betonski zid RK22+564.64 ~ RK22+725 - After work 5% | 11317.5 |  |  | 0 | 0 | 0
7.3.4.1.1.6 | Concrete wall/ Betonski zid RK22+564.64 ~ RK22+725 - Correction of the crown 5% | 11317.5 |  |  | 0 | 0 | 0
7.3.4.1.1.7 | Concrete wall/ Betonski zid RK22+564.64 ~ RK22+725 - 10% Wall surface | 22635 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 7.3 | 735921.1923 |  |  | 0 | 0 | 0
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 07 | 69457822.0941 |  |  | 13455036.4049 | 4049269.3096 | 17504305.7144

## COST CENTER 08
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
| COST CENTER 08/TROŠKOVNI CENTAR 08 | revised Bridge Piers
Cost Center No./ Troškovno mjesto Br. | 08 | Subsection/ Podsekcija 3.1 (LK22+730.000-LK24+778.000, RK22+735.000-RK24+915.000)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost Center/ Troškovno mjesto 8.1 | Road Works/Radovi na putevima (LK22+730.000—LK22+747.790, RK22+735.000—RK22+751.640)
Completion of/Završetak:
8.1.1 | Subgrade/ Posteljica
8.1.1.1 | Top soil removal/ Uklanjanje humusa
8.1.1.1.1 | 0 - 17.790 m (LK); 0 - 16.640 m (RK) | 21927.24 | 18 |  | 0 | 0 | 0
8.1.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and certain high (after MD approval)/Na svakih 250m i određenoj visini (nakon odobrenja GP) | 290081.12 | 35 |  | 0 | 0 | 0
8.1.1.3 | Road Foundation/ Temelj puta |  |  |  | 0 | 0 | 0
8.1.1.3.1 | 0 - 16.640 m, right side/ desna strana | 8700.06 | 36 |  | 0 | 0 | 0
8.1.1.3.2 | 0 - 17.790 m, left side/ lijeva strana | 8700.06 | 36 |  | 0 | 0 | 0
8.1.2 | Engineering structures/ Inženjerske konstrukcije
8.1.3 | Water drainage/ Drenaža vode
8.1.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 79468.78 | 40 |  | 0 | 0 | 0
8.1.4 | Pavement structure/ Kolovozna konstrukcija
8.1.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana | 11433.45 | 41 |  | 0 | 0 | 0
8.1.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana | 11433.45 | 41 |  | 0 | 0 | 0
8.1.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana | 11433.45 | 42 |  | 0 | 0 | 0
8.1.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana | 11433.45 | 42 |  | 0 | 0 | 0
8.1.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana | 12704.59 | 43 |  | 0 | 0 | 0
8.1.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana | 12704.59 | 43 |  | 0 | 0 | 0
| Sub Total / Suma stavke 8.1 | 480020.24 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 8.2 | Construction of bridge/ Izgradnja mosta Suvovara (LK 22+747.790 - LK 22+931.790, RK 22+751.640- RK 22+991.640)
Completion of/Završetak:
Left bridge/ Lijevi most
8.2.1 | Foundation concrete/ Temeljni beton
8.2.1.1 | A1 | 26933.62 | 19 |  | 0 | 0 | 0
8.2.1.2 | P1 | 22562.43 | 20 |  | 0 | 0 | 0
8.2.1.3 | P2 | 20055.5 | 21 |  | 0 | 0 | 0
8.2.1.4 | P3 | 27120.97 | 22 |  | 0 | 0 | 0
8.2.1.5 | P4 | 20055.5 | 23 |  | 0 | 0 | 0
8.2.1.6 | P5 | 20055.5 | 24 |  | 0 | 0 | 0
8.2.1.7 | P6 | 20055.5 | 25 |  | 0 | 0 | 0
8.2.1.8 | A2 | 26933.62 | 25 |  | 0 | 0 | 0
8.2.2 | Abutments and Piers elevation/ Elevacija mosnih stubova
8.2.2.1 | A1 | 19706.75 | 20 |  | 0 | 0 | 0
8.2.2.2 | P1 stage 1 (2.2m) | 2963.7382 | 20 |  | 0 | 0 | 0
8.2.2.3 | P1 stage 2 (2m) | 2694.3075 | 20 |  | 0 | 0 | 0
8.2.2.4 | P1 stage 3 (4.45m) | 5994.8341 | 20 |  | 0 | 0 | 0
8.2.2.5 | P1 stage 4 (3.2m) | 4310.892 | 20 |  | 0 | 0 | 0
8.2.2.6 | P2 stage 1 (2.2m) | 2963.7382 | 20 |  | 0 | 0 | 0
8.2.2.7 | P2 stage 2 (2m) | 2694.3075 | 20 |  | 0 | 0 | 0
8.2.2.8 | P2 stage 3 (5m) | 6735.7687 | 20 |  | 0 | 0 | 0
8.2.2.9 | P2 stage 4 (3.5m) | 4715.0381 | 20 |  | 0 | 0 | 0
8.2.2.10 | P2 stage 5 (3.2m) | 4310.892 | 21 |  | 0 | 0 | 0
8.2.2.11 | P3 stage 1 (2.2m) | 2963.7382 | 21 |  | 0 | 0 | 0
8.2.2.12 | P3 stage 2 (2m) | 2694.3075 | 21 |  | 0 | 0 | 0
8.2.2.13 | P3 stage 3 (5m) | 6735.7687 | 22 |  | 0 | 0 | 0
8.2.2.14 | P3 stage 4 (3.9m) | 5253.8996 | 22 |  | 0 | 0 | 0
8.2.2.15 | P3 stage 5 (3.2m) | 4310.892 | 22 |  | 0 | 0 | 0
8.2.2.16 | P4 stage 1 (2.2m) | 2963.7382 | 22 |  | 0 | 0 | 0
8.2.2.17 | P4 stage 2 (2m) | 2694.3075 | 22 |  | 0 | 0 | 0
8.2.2.18 | P4 stage 3 (5m) | 6735.7687 | 22 |  | 0 | 0 | 0
8.2.2.19 | P4 stage 4 (5m) | 6735.7687 | 23 |  | 0 | 0 | 0
8.2.2.20 | P4 stage 5 (2.05m) | 2761.6652 | 23 |  | 0 | 0 | 0
8.2.2.21 | P4 stage 6 (3.2m) | 4310.892 | 23 |  | 0 | 0 | 0
8.2.2.22 | P5 stage 1 (2.2m) | 2963.7382 | 23 |  | 0 | 0 | 0
8.2.2.23 | P5 stage 2 (2m) | 2694.3075 | 23 |  | 0 | 0 | 0
8.2.2.24 | P5 stage 3 (5m) | 6735.7687 | 23 |  | 0 | 0 | 0
8.2.2.25 | P5 stage 4 (3.9m) | 5253.8996 | 24 |  | 0 | 0 | 0
8.2.2.26 | P5 stage 5 (3.2m) | 4310.892 | 24 |  | 0 | 0 | 0
8.2.2.27 | P6 stage 1 (2.2m) | 2963.7382 | 24 |  | 0 | 0 | 0
8.2.2.28 | P6 stage 2 (2m) | 2694.3075 | 24 |  | 0 | 0 | 0
8.2.2.29 | P6 stage 3 (5m) | 6735.7687 | 25 |  | 0 | 0 | 0
8.2.2.30 | P6 stage 4 (3.35m) | 4512.965 | 25 |  | 0 | 0 | 0
8.2.2.31 | P6 stage 5 (3.2m) | 4310.892 | 25 |  | 0 | 0 | 0
8.2.2.32 | A2 | 19706.75 | 26 |  | 0 | 0 | 0
8.2.3 | Bridge deck superstructure/ Gornji stroj mosne ploče
8.2.3.1 | A1-P1 | 134336.02 | 22 |  | 0 | 0 | 0
8.2.3.2 | P1-P2 | 170973.12 | 23 |  | 0 | 0 | 0
8.2.3.3 | P2-P3 | 170973.12 | 24 |  | 0 | 0 | 0
8.2.3.4 | P3-P4 | 170973.12 | 25 |  | 0 | 0 | 0
8.2.3.5 | P4-P5 | 170973.12 | 26 |  | 0 | 0 | 0
8.2.3.6 | P5-P6 | 170973.12 | 27 |  | 0 | 0 | 0
8.2.3.7 | P6-A2 | 134336.02 | 28 |  | 0 | 0 | 0
8.2.4 | Bridge deck prestressing/ Prednaprezanje mosne ploče
8.2.4.1 | A1-P1 | 14926.22 | 26 |  | 0 | 0 | 0
8.2.4.2 | P1-P2 | 18997.01 | 26 |  | 0 | 0 | 0
8.2.4.3 | P2-P3 | 18997.01 | 27 |  | 0 | 0 | 0
8.2.4.4 | P3-P4 | 18997.01 | 27 |  | 0 | 0 | 0
8.2.4.5 | P4-P5 | 18997.01 | 28 |  | 0 | 0 | 0
8.2.4.6 | P5-P6 | 18997.01 | 28 |  | 0 | 0 | 0
8.2.4.7 | P6-A2 | 14926.22 | 28 |  | 0 | 0 | 0
8.2.5 | Bridge furniture/ Mosna estetika
8.2.5.1 | 50 m | 78575.03 | 26 |  | 0 | 0 | 0
8.2.5.2 | 100 m | 78575.03 | 27 |  | 0 | 0 | 0
8.2.5.3 | 150 m | 78575.03 | 28 |  | 0 | 0 | 0
8.2.5.4 | 184 m | 53431.03 | 28 |  | 0 | 0 | 0
8.2.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
8.2.6.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/ hidroizolacija | 72491 | 27 |  | 0 | 0 | 0
8.2.6.2 | Asphalt layer/ Sloj asfalta 2 + joints/ spojnice | 75584.9 | 28 |  | 0 | 0 | 0
Right bridge/ Desni most
8.2.7 | Foundation concrete/ Temeljni beton
8.2.7.1 | A1 | 26667.13 | 19 |  | 0 | 0 | 0
8.2.7.2 | P1 | 26668.05 | 20 |  | 0 | 0 | 0
8.2.7.3 | P2 | 21241.93 | 21 |  | 0 | 0 | 0
8.2.7.4 | P3 | 21241.93 | 22 |  | 0 | 0 | 0
8.2.7.5 | P4 | 22146.28 | 23 |  | 0 | 0 | 0
8.2.7.6 | P5 | 22146.28 | 23 |  | 0 | 0 | 0
8.2.7.7 | P6 | 21241.93 | 24 |  | 0 | 0 | 0
8.2.7.8 | P7 | 16720.16 | 24 |  | 0 | 0 | 0
8.2.7.9 | P8 | 18528.88 | 25 |  | 0 | 0 | 0
8.2.7.10 | A2 | 26667.13 | 25 |  | 0 | 0 | 0
8.2.8 | Abutments and Piers elevation/ Elevacija mosnih stubova
8.2.8.1 | A1 | 19841.06 | 19 |  | 0 | 0 | 0
8.2.8.2 | P1 stage 1 (1.2m) | 2141.0707 | 19 |  | 0 | 0 | 0
8.2.8.3 | P1 stage 2 (2m) | 3568.4511 | 19 |  | 0 | 0 | 0
8.2.8.4 | P1 stage 3 (2.8m) | 4995.8315 | 19 |  | 0 | 0 | 0
8.2.8.5 | P1 stage 4 (3.2m) | 5709.5218 | 19 |  | 0 | 0 | 0
8.2.8.6 | P2 stage 1 (1.2m) | 2141.0707 | 20 |  | 0 | 0 | 0
8.2.8.7 | P2 stage 2 (2m) | 3568.4511 | 20 |  | 0 | 0 | 0
8.2.8.8 | P2 stage 3 (5m) | 8921.1277 | 21 |  | 0 | 0 | 0
8.2.8.9 | P2 stage 4 (3.95m) | 7047.6909 | 21 |  | 0 | 0 | 0
8.2.8.10 | P2 stage 5 (3.2m) | 5709.5218 | 21 |  | 0 | 0 | 0
8.2.8.11 | P3 stage 1 (2.2m) | 3925.2962 | 20 |  | 0 | 0 | 0
8.2.8.12 | P3 stage 2 (2m) | 3568.4511 | 20 |  | 0 | 0 | 0
8.2.8.13 | P3 stage 3 (5m) | 8921.1277 | 21 |  | 0 | 0 | 0
8.2.8.14 | P3 stage 4 (3.95m) | 7047.6909 | 21 |  | 0 | 0 | 0
8.2.8.15 | P3 stage 5 (3.2m) | 5709.5218 | 21 |  | 0 | 0 | 0
8.2.8.16 | P4 stage 1 (2.2m) | 3925.2962 | 22 |  | 0 | 0 | 0
8.2.8.17 | P4 stage 2 (2m) | 3568.4511 | 22 |  | 0 | 0 | 0
8.2.8.18 | P4 stage 3 (5m) | 8921.1277 | 23 |  | 0 | 0 | 0
8.2.8.19 | P4 stage 4 (4m) | 7136.9022 | 23 |  | 0 | 0 | 0
8.2.8.20 | P4 stage 5 (3.2m) | 5709.5218 | 23 |  | 0 | 0 | 0
8.2.8.21 | P5 stage 1 (2.2m) | 3925.2962 | 24 |  | 0 | 0 | 0
8.2.8.22 | P5 stage 2 (2m) | 3568.4511 | 24 |  | 0 | 0 | 0
8.2.8.23 | P5 stage 3 (5m) | 8921.1277 | 24 |  | 0 | 0 | 0
8.2.8.24 | P5 stage 4 (5m) | 8921.1277 | 25 |  | 0 | 0 | 0
8.2.8.25 | P5 stage 5 (2.4m) | 4282.1413 | 25 |  | 0 | 0 | 0
8.2.8.26 | P5 stage 6 (3.2m) | 5709.5218 | 25 |  | 0 | 0 | 0
8.2.8.27 | P6 stage 1 (2.2m) | 3925.2962 | 23 |  | 0 | 0 | 0
8.2.8.28 | P6 stage 2 (2m) | 3568.4511 | 23 |  | 0 | 0 | 0
8.2.8.29 | P6 stage 3 (5m) | 8921.1277 | 24 |  | 0 | 0 | 0
8.2.8.30 | P6 stage 4 (5.15m) | 9188.7616 | 24 |  | 0 | 0 | 0
8.2.8.31 | P6 stage 5 (3.2m) | 5709.5218 | 24 |  | 0 | 0 | 0
8.2.8.32 | P7 stage 1 (2.2m) | 3925.2962 | 25 |  | 0 | 0 | 0
8.2.8.33 | P7 stage 2 (2m) | 3568.4511 | 25 |  | 0 | 0 | 0
8.2.8.34 | P7 stage 3 (5m) | 8921.1277 | 25 |  | 0 | 0 | 0
8.2.8.35 | P7 stage 4 (4.7m) | 8385.8601 | 26 |  | 0 | 0 | 0
8.2.8.36 | P7 stage 5 (3.2m) | 5709.5218 | 26 |  | 0 | 0 | 0
8.2.8.37 | P8 stage 1 (1.2m) | 2141.0707 | 26 |  | 0 | 0 | 0
8.2.8.38 | P8 stage 2 (2m) | 3568.4511 | 26 |  | 0 | 0 | 0
8.2.8.39 | P8 stage 3 (2.8m) | 4995.8315 | 26 |  | 0 | 0 | 0
8.2.8.40 | P8 stage 4 (3.2m) | 5709.5218 | 26 |  | 0 | 0 | 0
8.2.8.41 | A2 | 19841.06 | 25 |  | 0 | 0 | 0
8.2.9 | Bridge deck superstructure/ Gornji stroj mosne ploče
8.2.9.1 | A1-P1 | 133738.1 | 20 |  | 0 | 0 | 0
8.2.9.2 | P1-P2 | 170212.13 | 21 |  | 0 | 0 | 0
8.2.9.3 | P2-P3 | 170212.13 | 22 |  | 0 | 0 | 0
8.2.9.4 | P3-P4 | 170212.13 | 23 |  | 0 | 0 | 0
8.2.9.5 | P4-P5 | 170212.13 | 24 |  | 0 | 0 | 0
8.2.9.6 | P5-P6 | 170212.13 | 25 |  | 0 | 0 | 0
8.2.9.7 | P6-P7 | 170212.13 | 26 |  | 0 | 0 | 0
8.2.9.8 | P7-P8 | 170212.13 | 27 |  | 0 | 0 | 0
8.2.9.9 | P8-A2 | 133738.1 | 28 |  | 0 | 0 | 0
8.2.10 | Bridge deck prestressing/ Prednaprezanje mosne ploče
8.2.10.1 | A1-P1 | 14859.79 | 26 |  | 0 | 0 | 0
8.2.10.2 | P1-P2 | 18912.46 | 26 |  | 0 | 0 | 0
8.2.10.3 | P2-P3 | 18912.46 | 27 |  | 0 | 0 | 0
8.2.10.4 | P3-P4 | 18912.46 | 27 |  | 0 | 0 | 0
8.2.10.5 | P4-P5 | 18912.46 | 27 |  | 0 | 0 | 0
8.2.10.6 | P5-P6 | 18912.46 | 28 |  | 0 | 0 | 0
8.2.10.7 | P6-P7 | 18912.46 | 28 |  | 0 | 0 | 0
8.2.10.8 | P7-P8 | 18912.46 | 28 |  | 0 | 0 | 0
8.2.10.9 | P8-A2 | 14859.79 | 28 |  | 0 | 0 | 0
8.2.11 | Bridge furniture/ Mosna estetika
8.2.11.1 | 50 m | 60908.9 | 26 |  | 0 | 0 | 0
8.2.11.2 | 100 m | 60908.9 | 27 |  | 0 | 0 | 0
8.2.11.3 | 150 m | 60908.9 | 27 |  | 0 | 0 | 0
8.2.11.4 | 200 m | 60908.9 | 28 |  | 0 | 0 | 0
8.2.11.5 | 240 m | 48727.04 | 28 |  | 0 | 0 | 0
8.2.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
8.2.12.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/ hidroizolacija | 94553.47 | 27 |  | 0 | 0 | 0
8.2.12.2 | Asphalt layer/ Sloj asfalta 2 + joints/ spojnice | 77944.74 | 28 |  | 0 | 0 | 0
| Sub Total / Suma stavke 8.2 | 4602196.49 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 8.3 | Road Works/ Radovi na putevima (LK22+931.790—LK23+412.120, RK22+991.640—RK23+441.042)
Completion of/Završetak:
8.3.1 | Subgrade/ Posteljica
8.3.1.1 | Top soil removal/ Uklanjanje humusa
8.3.1.1.1 | 0 - 250 m (LK&RK) | 58310.92 | 20 |  | 0 | 0 | 0
8.3.1.1.2 | 250 - 480.330 m (LK); 250 - 449.402 m (RK) | 51515.37 | 21 |  | 0 | 0 | 0
8.3.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and certain high (after MD approval)/Na svakih 250m i određenoj visini (nakon odobrenja GP) | 1452920.39 | 36 |  | 0 | 0 | 0
8.3.1.3 | Road Foundation/ Temelj puta
8.3.1.3.1 | 0 - 250 m right side/ desna strana | 23434.5677 | 37 |  | 0 | 0 | 0
8.3.1.3.2 | 0 - 250 m left side/ lijeva strana | 23434.5677 | 37 |  | 0 | 0 | 0
8.3.1.3.3 | 250 - 449.402 m, right side/ desna strana | 18691.5987 | 38 |  | 0 | 0 | 0
8.3.1.3.4 | 250 - 480.330 m, left side/ lijeva strana | 21590.7359 | 38 |  | 0 | 0 | 0
8.3.2 | Engineering structures/ Inženjerske konstrukcije
8.3.2.1 | Concrete wall (it will be splitted after MD approval)/ Betonski zid (biće podijeljen nakon odobrenja GP) |  | 24
95% for the concrete wall, the milestone is 50m lenth, no matter the hight; 5% for the "after work" the whole lenth of each retaining wall / 95% za betonski zid, reper je 50 m dužine, bez obzira na visinu; 5% za "kasnije radove" čitava dužina potpornog
8.3.2.1.1 | Concrete wall/ Betonski zid LK22+933.790 ~ LK22+962.430 (28.64m)
8.3.2.1.1.1 | Concrete wall/ Betonski zid LK22+933.790 ~ LK22+962.430 95% | 163744.0178 |  |  | 0 | 0 | 0
8.3.2.1.1.2 | Concrete wall/ Betonski zid LK22+933.790 ~ LK22+962.430 After work 5% | 8618.1062 |  |  | 0 | 0 | 0
8.3.2.1.2 | Concrete wall/ Betonski zid LK22+940.0 ~ LK23+130.0 (190m) 95%, Layers 1,2,3,4
8.3.2.1.2.1 | Segment 1 LK22+940.0 ~ LK22+990.0 (50m) | 285865.9528 |  |  | 0 | 0 | 0
8.3.2.1.2.2 | Segment 2 LK22+990.0 ~ LK23+040.0 (50m) | 285865.9528 |  |  | 0 | 0 | 0
8.3.2.1.2.3 | Segment 3 LK23+040.0 ~ LK23+090.0 (50m) | 285865.9528 |  |  | 0 | 0 | 0
8.3.2.1.2.4 | Segment 4 LK23+090.0 ~ LK23+130.0 (40m) | 228692.7623 |  |  | 0 | 0 | 0
8.3.2.1.2.5 | Concrete wall/ Betonski zid LK22+940.0 ~ LK23+130.0 (190m) After work 5% | 57173.1906 |  |  | 0 | 0 | 0
8.3.2.1.3 | Concrete wall/ Betonski zid LK23+402.32 ~ LK23+407.32 (5m)
8.3.2.1.3.1 | Concrete wall/ Betonski zid LK23+402.32 ~ LK23+407.32 - 95% | 28586.5953 |  |  | 0 | 0 | 0
8.3.2.1.3.2 | Concrete wall/ Betonski zid LK23+402.32 ~ LK23+407.32 - After work 5% | 1504.5576 |  |  | 0 | 0 | 0
8.3.2.1.4 | Concrete wall/ Betonski zid RK22+994 ~ RK23+004 (10m)
8.3.2.1.4.1 | Concrete wall/ Betonski zid RK22+994 ~ RK23+004 - 95% | 57173.1906 |  |  | 0 | 0 | 0
8.3.2.1.4.2 | Concrete wall/ Betonski zid RK22+994 ~ RK23+004 - After work 5% | 3009.1153 |  |  | 0 | 0 | 0
8.3.2.1.5 | Concrete wall/ Betonski zid RK23+426.24~RK23+436.24 (10m)
8.3.2.1.5.1 | Concrete wall/ Betonski zid RK23+426.24~RK23+436.24 - 95% | 57173.1906 |  |  | 0 | 0 | 0
8.3.2.1.5.2 | Concrete wall/ Betonski zid RK23+426.24~RK23+436.24 - After work 5% | 3009.1153 |  |  | 0 | 0 | 0
8.3.2.2 | Culvert/ Propust | 15160.83 | 25 |  | 0 | 0 | 0
8.3.3 | Water drainage/ Drenaža vode
8.3.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 398032.81 | 37 |  | 0 | 0 | 0
8.3.4 | Pavement structure/ Kolovozna konstrukcija
8.3.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana | 55361.3756 | 38 |  | 0 | 0 | 0
8.3.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana | 59171.3644 | 38 |  | 0 | 0 | 0
8.3.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana | 55361.3756 | 39 |  | 0 | 0 | 0
8.3.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana | 59171.3644 | 39 |  | 0 | 0 | 0
8.3.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana | 61516.2938 | 40 |  | 0 | 0 | 0
8.3.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana | 65749.8662 | 40 |  | 0 | 0 | 0
| Sub Total / Suma stavke 8.3 | 3885705.13 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 8.4 | Construction of bridge/ Izgradnja mosta Krkor ( LK 23+412.12- LK 23+746.12, RK 23+441.042 - RK 23+731.042)
Completion of/Završetak:
Left bridge/ Lijevi most
8.4.1 | Foundation concrete/ Temeljni beton
8.4.1.1 | A1 | 75600.12 | 29 |  | 0 | 0 | 0
8.4.1.2 | P1 | 29300.02 | 29 |  | 0 | 0 | 0
8.4.1.3 | P2 | 29300.02 | 30 |  | 0 | 0 | 0
8.4.1.4 | P3 | 31400.51 | 30 |  | 0 | 0 | 0
8.4.1.5 | P4 | 25073.48 | 30 |  | 0 | 0 | 0
8.4.1.6 | P5 | 31202.56 | 31 |  | 0 | 0 | 0
8.4.1.7 | P6 | 29300.02 | 31 |  | 0 | 0 | 0
8.4.1.8 | P7 | 29300.02 | 31 |  | 0 | 0 | 0
8.4.1.9 | A2 | 75600.12 | 31 |  | 0 | 0 | 0
8.4.2 | Abutments and Piers elevation/ Elevacija mosnih stubova
8.4.2.1 | A1 | 161035.73 | 31 |  | 0 | 0 | 0
8.4.2.2 | P1 stage 1 (2.2m) | 6013.8627 | 31 |  | 0 | 0 | 0
8.4.2.3 | P1 stage 2 (2m) | 5467.1479 | 32 |  | 0 | 0 | 0
8.4.2.4 | P1 stage 3 (5m) | 13667.8699 | 32 |  | 0 | 0 | 0
8.4.2.5 | P1 stage 4 (5m) | 13667.8699 | 32 |  | 0 | 0 | 0
8.4.2.6 | P1 stage 5 (5m) | 13667.8699 | 32 |  | 0 | 0 | 0
8.4.2.7 | P1 stage 6 (5m) | 13667.8699 | 33 |  | 0 | 0 | 0
8.4.2.8 | P1 stage 7 (5m) | 13667.8699 | 33 |  | 0 | 0 | 0
8.4.2.9 | P1 stage 8 (4.4m) | 12027.7255 | 33 |  | 0 | 0 | 0
8.4.2.10 | P1 stage 9 (3.2m) | 8747.4367 | 33 |  | 0 | 0 | 0
8.4.2.11 | P2 stage 1 (2.2m) | 6013.8627 | 33 |  | 0 | 0 | 0
8.4.2.12 | P2 stage 2 (2m) | 5467.1479 | 33 |  | 0 | 0 | 0
8.4.2.13 | P2 stage 3 (5m) | 13667.8699 | 34 |  | 0 | 0 | 0
8.4.2.14 | P2 stage 4 (5m) | 13667.8699 | 34 |  | 0 | 0 | 0
8.4.2.15 | P2 stage 5 (5m) | 13667.8699 | 35 |  | 0 | 0 | 0
8.4.2.16 | P2 stage 6 (5m) | 13667.8699 | 35 |  | 0 | 0 | 0
8.4.2.17 | P2 stage 7 (5m) | 13667.8699 | 36 |  | 0 | 0 | 0
8.4.2.18 | P2 stage 8 (5m) | 13667.8699 | 36 |  | 0 | 0 | 0
8.4.2.19 | P2 stage 9 (3.8m) | 10387.5811 | 37 |  | 0 | 0 | 0
8.4.2.20 | P2 stage 10 (3.2m) | 8747.4367 | 37 |  | 0 | 0 | 0
8.4.2.21 | P3 stage 1 (2.2m) | 6013.8627 | 31 |  | 0 | 0 | 0
8.4.2.22 | P3 stage 2 (2m) | 5467.1479 | 31 |  | 0 | 0 | 0
8.4.2.23 | P3 stage 3 (5m) | 13667.8699 | 32 |  | 0 | 0 | 0
8.4.2.24 | P3 stage 4 (5m) | 13667.8699 | 32 |  | 0 | 0 | 0
8.4.2.25 | P3 stage 5 (5m) | 13667.8699 | 33 |  | 0 | 0 | 0
8.4.2.26 | P3 stage 6 (5m) | 13667.8699 | 33 |  | 0 | 0 | 0
8.4.2.27 | P3 stage 7 (5m) | 13667.8699 | 34 |  | 0 | 0 | 0
8.4.2.28 | P3 stage 8 (5m) | 13667.8699 | 34 |  | 0 | 0 | 0
8.4.2.29 | P3 stage 9 (3.8m) | 10387.5811 | 35 |  | 0 | 0 | 0
8.4.2.30 | P3 stage 10 (3.2m) | 8747.4367 | 35 |  | 0 | 0 | 0
8.4.2.31 | P4 stage 1 (2.2m) | 6013.8627 | 32 |  | 0 | 0 | 0
8.4.2.32 | P4 stage 2 (2m) | 5467.1479 | 32 |  | 0 | 0 | 0
8.4.2.33 | P4 stage 3 (5m) | 13667.8699 | 33 |  | 0 | 0 | 0
8.4.2.34 | P4 stage 4 (5m) | 13667.8699 | 33 |  | 0 | 0 | 0
8.4.2.35 | P4 stage 5 (5m) | 13667.8699 | 34 |  | 0 | 0 | 0
8.4.2.36 | P4 stage 6 (5m) | 13667.8699 | 34 |  | 0 | 0 | 0
8.4.2.37 | P4 stage 7 (5m) | 13667.8699 | 35 |  | 0 | 0 | 0
8.4.2.38 | P4 stage 8 (5m) | 13667.8699 | 35 |  | 0 | 0 | 0
8.4.2.39 | P4 stage 9 (3.8m) | 10387.5811 | 36 |  | 0 | 0 | 0
8.4.2.40 | P4 stage 10 (3.2m) | 8747.4367 | 36 |  | 0 | 0 | 0
8.4.2.41 | P5 stage 1 (2.2m) | 6013.8627 | 34 |  | 0 | 0 | 0
8.4.2.42 | P5 stage 2 (2m) | 5467.1479 | 34 |  | 0 | 0 | 0
8.4.2.43 | P5 stage 3 (5m) | 13667.8699 | 35 |  | 0 | 0 | 0
8.4.2.44 | P5 stage 4 (5m) | 13667.8699 | 35 |  | 0 | 0 | 0
8.4.2.45 | P5 stage 5 (3m) | 8200.7219 | 36 |  | 0 | 0 | 0
8.4.2.46 | P5 stage 6 (3.2m) | 8747.4367 | 36 |  | 0 | 0 | 0
8.4.2.47 | P6 stage 1 (2.2m) | 6013.8627 | 36 |  | 0 | 0 | 0
8.4.2.48 | P6 stage 2 (2m) | 5467.1479 | 36 |  | 0 | 0 | 0
8.4.2.49 | P6 stage 3 (5m) | 13667.8699 | 36 |  | 0 | 0 | 0
8.4.2.50 | P6 stage 4 (5.7m) | 15581.3716 | 37 |  | 0 | 0 | 0
8.4.2.51 | P6 stage 5 (3.2m) | 8747.4367 | 37 |  | 0 | 0 | 0
8.4.2.52 | P7 stage 1 (1.2m) | 3280.2888 | 37 |  | 0 | 0 | 0
8.4.2.53 | P7 stage 2 (2m) | 5467.1479 | 37 |  | 0 | 0 | 0
8.4.2.54 | P7 stage 3 (6.4m) | 17494.8734 | 38 |  | 0 | 0 | 0
8.4.2.55 | P7 stage 4 (3.2m) | 8747.4367 | 38 |  | 0 | 0 | 0
8.4.2.56 | A2 | 161035.73 | 38 |  | 0 | 0 | 0
8.4.3 | Bridge deck superstructure/ Gornji stroj mosne ploče
8.4.3.1 | A1-P1 | 165250.63 | 37 |  | 0 | 0 | 0
8.4.3.2 | P1-P2 | 207743.65 | 38 |  | 0 | 0 | 0
8.4.3.3 | P2-P3 | 207743.65 | 39 |  | 0 | 0 | 0
8.4.3.4 | P3-P4 | 207743.65 | 40 |  | 0 | 0 | 0
8.4.3.5 | P4-P5 | 207743.65 | 41 |  | 0 | 0 | 0
8.4.3.6 | P5-P6 | 207743.65 | 41 |  | 0 | 0 | 0
8.4.3.7 | P6-P7 | 207743.65 | 42 |  | 0 | 0 | 0
8.4.3.8 | P7-A2 | 165250.63 | 42 |  | 0 | 0 | 0
8.4.4 | Bridge deck prestressing/ Prednaprezanje mosne ploče
8.4.4.1 | A1-P1 | 18361.18 | 38 |  | 0 | 0 | 0
8.4.4.2 | P1-P2 | 23082.63 | 39 |  | 0 | 0 | 0
8.4.4.3 | P2-P3 | 23082.63 | 40 |  | 0 | 0 | 0
8.4.4.4 | P3-P4 | 23082.63 | 41 |  | 0 | 0 | 0
8.4.4.5 | P4-P5 | 23082.63 | 41 |  | 0 | 0 | 0
8.4.4.6 | P5-P6 | 23082.63 | 42 |  | 0 | 0 | 0
8.4.4.7 | P6-P7 | 23082.63 | 42 |  | 0 | 0 | 0
8.4.4.8 | P7-A2 | 18361.12 | 42 |  | 0 | 0 | 0
8.4.5 | Bridge furniture/ Mosna estetika
8.4.5.1 | 50 m | 38357.78 | 41 |  | 0 | 0 | 0
8.4.5.2 | 100 m | 38357.78 | 42 |  | 0 | 0 | 0
8.4.5.3 | 150 m | 38357.78 | 42 |  | 0 | 0 | 0
8.4.5.4 | 200 m | 38357.78 | 42 |  | 0 | 0 | 0
8.4.5.5 | 250 m | 38357.78 | 43 |  | 0 | 0 | 0
8.4.5.6 | 300 m | 38357.78 | 43 |  | 0 | 0 | 0
8.4.5.7 | 334 m | 26083.37 | 43 |  | 0 | 0 | 0
8.4.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
8.4.6.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/ hidroizolacija | 87370.4 | 42 |  | 0 | 0 | 0
8.4.6.2 | Asphalt layer/ Sloj asfalta 2 + joints/ spojnice | 21788.4 | 43 |  | 0 | 0 | 0
Right bridge/ Desni most
8.4.7 | Foundation concrete/ Temeljni beton
8.4.7.1 | A1 | 77737.94 | 29 |  | 0 | 0 | 0
8.4.7.2 | P1 | 33277.02 | 29 |  | 0 | 0 | 0
8.4.7.3 | P2 | 36855.41 | 30 |  | 0 | 0 | 0
8.4.7.4 | P3 | 33277.02 | 30 |  | 0 | 0 | 0
8.4.7.5 | P4 | 28476.8 | 30 |  | 0 | 0 | 0
8.4.7.6 | P5 | 35437.8 | 31 |  | 0 | 0 | 0
8.4.7.7 | P6 | 33277.01 | 31 |  | 0 | 0 | 0
8.4.7.8 | A2 | 77737.94 | 31 |  | 0 | 0 | 0
8.4.8 | Abutments and Piers elevation/ Elevacija mosnih stubova
8.4.8.1 | A1 | 161035.73 | 30 |  | 0 | 0 | 0
8.4.8.2 | P1 stage 1 (2.2m) | 6879.9501 | 30 |  | 0 | 0 | 0
8.4.8.3 | P1 stage 2 (2m) | 6254.5001 | 30 |  | 0 | 0 | 0
8.4.8.4 | P1 stage 3 (5m) | 15636.2502 | 31 |  | 0 | 0 | 0
8.4.8.5 | P1 stage 4 (5m) | 15636.2502 | 31 |  | 0 | 0 | 0
8.4.8.6 | P1 stage 5 (5m) | 15636.2502 | 32 |  | 0 | 0 | 0
8.4.8.7 | P1 stage 6 (5m) | 15636.2502 | 32 |  | 0 | 0 | 0
8.4.8.8 | P1 stage 7 (5m) | 15636.2502 | 33 |  | 0 | 0 | 0
8.4.8.9 | P1 stage 8 (3.3m) | 10319.9251 | 33 |  | 0 | 0 | 0
8.4.8.10 | P1 stage 9 (3.2m) | 10007.2001 | 33 |  | 0 | 0 | 0
8.4.8.11 | P2 stage 1 (2.2m) | 6879.9501 | 33 |  | 0 | 0 | 0
8.4.8.12 | P2 stage 2 (2m) | 6254.5001 | 33 |  | 0 | 0 | 0
8.4.8.13 | P2 stage 3 (5m) | 15636.2502 | 33 |  | 0 | 0 | 0
8.4.8.14 | P2 stage 4 (5m) | 15636.2502 | 34 |  | 0 | 0 | 0
8.4.8.15 | P2 stage 5 (5m) | 15636.2502 | 34 |  | 0 | 0 | 0
8.4.8.16 | P2 stage 6 (5m) | 15636.2502 | 34 |  | 0 | 0 | 0
8.4.8.17 | P2 stage 7 (5m) | 15636.2502 | 34 |  | 0 | 0 | 0
8.4.8.18 | P2 stage 8 (5m) | 15636.2502 | 35 |  | 0 | 0 | 0
8.4.8.19 | P2 stage 9 (5.2m) | 16261.7002 | 35 |  | 0 | 0 | 0
8.4.8.20 | P2 stage 10 (3.2m) | 10007.2001 | 35 |  | 0 | 0 | 0
8.4.8.21 | P3 stage 1 (2.2m) | 6879.9501 | 35 |  | 0 | 0 | 0
8.4.8.22 | P3 stage 2 (2m) | 6254.5001 | 35 |  | 0 | 0 | 0
8.4.8.23 | P3 stage 3 (5m) | 15636.2502 | 35 |  | 0 | 0 | 0
8.4.8.24 | P3 stage 4 (5m) | 15636.2502 | 36 |  | 0 | 0 | 0
8.4.8.25 | P3 stage 5 (5m) | 15636.2502 | 36 |  | 0 | 0 | 0
8.4.8.26 | P3 stage 6 (5m) | 15636.2502 | 36 |  | 0 | 0 | 0
8.4.8.27 | P3 stage 7 (5m) | 15636.2502 | 37 |  | 0 | 0 | 0
8.4.8.28 | P3 stage 8 (5m) | 15636.2502 | 37 |  | 0 | 0 | 0
8.4.8.29 | P3 stage 9 (5m) | 15636.2502 | 37 |  | 0 | 0 | 0
8.4.8.30 | P3 stage 10 (2.55m) | 7974.4876 | 37 |  | 0 | 0 | 0
8.4.8.31 | P3 stage 11 (3.2m) | 10007.2001 | 36 |  | 0 | 0 | 0
8.4.8.32 | P4 stage 1 (2.2m) | 6879.9501 | 36 |  | 0 | 0 | 0
8.4.8.33 | P4 stage 2 (2m) | 6254.5001 | 36 |  | 0 | 0 | 0
8.4.8.34 | P4 stage 3 (5m) | 15636.2502 | 36 |  | 0 | 0 | 0
8.4.8.35 | P4 stage 4 (5m) | 15636.2502 | 37 |  | 0 | 0 | 0
8.4.8.36 | P4 stage 5 (5m) | 15636.2502 | 37 |  | 0 | 0 | 0
8.4.8.37 | P4 stage 6 (5m) | 15636.2502 | 37 |  | 0 | 0 | 0
8.4.8.38 | P4 stage 7 (5.6m) | 17512.6002 | 37 |  | 0 | 0 | 0
8.4.8.39 | P4 stage 8 (3.2m) | 10007.2001 | 36 |  | 0 | 0 | 0
8.4.8.40 | P5 stage 1 (1.2m) | 3752.7 | 36 |  | 0 | 0 | 0
8.4.8.41 | P5 stage 2 (2m) | 6254.5001 | 36 |  | 0 | 0 | 0
8.4.8.42 | P5 stage 3 (5m) | 15636.2502 | 37 |  | 0 | 0 | 0
8.4.8.43 | P5 stage 4 (3.45) | 10789.0126 | 37 |  | 0 | 0 | 0
8.4.8.44 | P5 stage 5 (3.2m) | 10007.2001 | 37 |  | 0 | 0 | 0
8.4.8.45 | P6 stage 1 (1.2m) | 3752.7 | 37 |  | 0 | 0 | 0
8.4.8.46 | P6 stage 2 (2m) | 6254.5001 | 37 |  | 0 | 0 | 0
8.4.8.47 | P6 stage 3 (5m) | 15636.2502 | 38 |  | 0 | 0 | 0
8.4.8.48 | P6 stage 4 (2.55m) | 7974.4876 | 38 |  | 0 | 0 | 0
8.4.8.49 | P6 stage 5 (3.2m) | 10007.2001 | 38 |  | 0 | 0 | 0
8.4.8.50 | A2 | 161035.73 | 38 |  | 0 | 0 | 0
8.4.9 | Bridge deck superstructure/ Gornji stroj mosne ploče
8.4.9.1 | A1-P1 | 190323.14 | 37 |  | 0 | 0 | 0
8.4.9.2 | P1-P2 | 239263.37 | 38 |  | 0 | 0 | 0
8.4.9.3 | P2-P3 | 239263.37 | 39 |  | 0 | 0 | 0
8.4.9.4 | P3-P4 | 239263.37 | 40 |  | 0 | 0 | 0
8.4.9.5 | P4-P5 | 239263.37 | 41 |  | 0 | 0 | 0
8.4.9.6 | P5-P6 | 239263.37 | 42 |  | 0 | 0 | 0
8.4.9.7 | P6-A2 | 190323.14 | 42 |  | 0 | 0 | 0
8.4.10 | Bridge deck prestressing/ Prednaprezanje mosne ploče
8.4.10.1 | A1-P1 | 21147.02 | 38 |  | 0 | 0 | 0
8.4.10.2 | P1-P2 | 26584.82 | 39 |  | 0 | 0 | 0
8.4.10.3 | P2-P3 | 26584.82 | 40 |  | 0 | 0 | 0
8.4.10.4 | P3-P4 | 26584.82 | 41 |  | 0 | 0 | 0
8.4.10.5 | P4-P5 | 26584.82 | 42 |  | 0 | 0 | 0
8.4.10.6 | P5-P6 | 26584.82 | 42 |  | 0 | 0 | 0
8.4.10.7 | P6-A2 | 21147 | 42 |  | 0 | 0 | 0
8.4.11 | Bridge furniture/ Mosna estetika
8.4.11.1 | 50 m | 44177.59 | 41 |  | 0 | 0 | 0
8.4.11.2 | 100 m | 44177.59 | 42 |  | 0 | 0 | 0
8.4.11.3 | 150 m | 44177.59 | 42 |  | 0 | 0 | 0
8.4.11.4 | 200 m | 44177.59 | 43 |  | 0 | 0 | 0
8.4.11.5 | 250 m | 44177.59 | 43 |  | 0 | 0 | 0
8.4.11.6 | 290 m | 35342.01 | 43 |  | 0 | 0 | 0
8.4.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
8.4.12.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/ hidroizolacija | 87370.4 | 42 |  | 0 | 0 | 0
8.4.12.2 | Asphalt layer/ Sloj asfalta 2 + joints/ spojnice | 21788.4 | 43 |  | 0 | 0 | 0
| Sub Total / Suma stavke 8.4 | 6748832.06 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 8.5 | Road Works/ Radovi na putevima (LK23+746.12—LK23+752.474, RK23+731.042—RK23+806.016)
Completion of/Završetak:
8.5.1 | Subgrade/ Posteljica
8.5.1.1 | Top soil removal/ Uklanjanje humusa
8.5.1.1.1 | 0 - 6.354 m (LK); 0 - 74.974 m (RK) | 31097.22 | 24 |  | 0 | 0 | 0
8.5.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and certain high (after MD approval)/Na svakih 250m i određenoj visini (nakon odobrenja GP) | 411393.1 | 35 |  | 0 | 0 | 0
8.5.1.3 | Road Foundation/ Temelj puta
8.5.1.3.1 | 0 - 74.974 m, right side/ desna strana | 12338.43 | 36 |  | 0 | 0 | 0
8.5.1.3.2 | 0 - 6.354 m, left side/ lijeva strana | 12338.43 | 36 |  | 0 | 0 | 0
8.5.2 | Engineering structures/ Inženjerske konstrukcije
8.5.2.1 | Concrete wall / Betonski zid |  | 32
95% for the concrete wall, the milestone is 50m lenth, no matter the hight; 5% for the "after work" the whole lenth of each retaining wall / 95% za betonski zid, reper je 50 m dužine, bez obzira na visinu; 5% za "kasnije radove" čitava dužina potpornog
8.5.2.1.1 | Concrete wall/ Betonski zid RK23+735.842 ~ RK23+779.020 (43.18m)
8.5.2.1.1.1 | Concrete wall/ Betonski zid RK23+735.842 ~ RK23+779.020 - 95% | 237682.153 |  |  | 0 | 0 | 0
8.5.2.1.1.2 | Concrete wall/ Betonski zid RK23+735.842 ~ RK23+779.020 - After work 5% | 12509.587 |  |  | 0 | 0 | 0
8.5.3 | Water drainage/ Drenaža vode
8.5.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 112702.63 | 38 |  | 0 | 0 | 0
8.5.4 | Pavement structure/ Kolovozna konstrukcija
8.5.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana | 16214.92 | 37 |  | 0 | 0 | 0
8.5.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana | 16214.92 | 37 |  | 0 | 0 | 0
8.5.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana | 16214.92 | 38 |  | 0 | 0 | 0
8.5.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana | 16214.92 | 38 |  | 0 | 0 | 0
8.5.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana | 18017.65 | 39 |  | 0 | 0 | 0
8.5.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana | 18017.65 | 39 |  | 0 | 0 | 0
| Sub Total / Suma stavke 8.5 | 930956.53 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 8.6 | Construction of Verusa interchange/ Izgradnja petlje Veruša (LK 23+752.474- LK 24+762.820, RK 23+806.016- RK 24+892.257)
Completion of/Završetak:
8.6.1 | Subgrade/ Posteljica
8.6.1.1 | Top soil removal/ Uklanjanje humusa
8.6.1.1.1 | 0 - 250 m (LK&RK) | 49882.4876 | 22 |  | 0 | 0 | 0
8.6.1.1.2 | 250 - 500 m (LK&RK) | 49882.4876 | 22 |  | 0 | 0 | 0
8.6.1.1.3 | 500 - 750 m (LK&RK) | 49882.4876 | 23 |  | 0 | 0 | 0
8.6.1.1.4 | 750 - 1010.346 m (LK); 750 - 1000 m (RK) | 50914.656 | 23 |  | 0 | 0 | 0
8.6.1.1.5 | 1000 - 1086.241 m (RK) | 8603.8312 | 23 |  | 0 | 0 | 0
8.6.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and certain high (after MD approval)/Na svakih 250m i određenoj visini (nakon odobrenja GP) | 2767110.36 | 32 |  | 0 | 0 | 0
8.6.1.3 | Road Foundation/ Temelj puta
8.6.1.3.1 | 0 - 250 m right side/ desna strana | 19791.8546 | 33 |  | 0 | 0 | 0
8.6.1.3.2 | 0 - 250 m left side/ lijeva strana | 19791.8546 | 33 |  | 0 | 0 | 0
8.6.1.3.3 | 250 - 500 m right side/ desna strana | 19791.8546 | 34 |  | 0 | 0 | 0
8.6.1.3.4 | 250 - 500 m left side/ lijeva strana | 19791.8546 | 34 |  | 0 | 0 | 0
8.6.1.3.5 | 500 - 750 m right side/ desna strana | 19791.8546 | 35 |  | 0 | 0 | 0
8.6.1.3.6 | 500 - 750 m left side/ lijeva strana | 19791.8546 | 35 |  | 0 | 0 | 0
8.6.1.3.7 | 750 - 1000 m right side/ desna strana | 19791.8546 | 36 |  | 0 | 0 | 0
8.6.1.3.8 | 750 - 1010.346 m left side/ lijeva strana | 20610.9207 | 36 |  | 0 | 0 | 0
8.6.1.3.9 | 1000 - 1086.241 m right side/ desna strana | 6827.4773 | 36 |  | 0 | 0 | 0
8.6.2 | Engineering structures/ Inženjerske konstrukcije
8.6.2.1 | Concrete wall (it will be splitted after MD approval)/ Betonski zid (biće podijeljen nakon odobrenja GP) |  | 24
95% for the concrete wall, the milestone is 50m lenth, no matter the hight; 5% for the "after work" the whole lenth of each retaining wall / 95% za betonski zid, reper je 50 m dužine, bez obzira na visinu; 5% za "kasnije radove" čitava dužina potpornog
8.6.2.1.1 | Concrete wall/ Betonski zid LK23+750.920 - LK23+880.000 (129.08m) 95%, Layers 1,2,3
8.6.2.1.1.1 | Segment 1 LK23+750.920 ~ LK23+800.920 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.1.2 | Segment 2 LK23+800.920 ~ LK23+850.920 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.1.3 | Segment 3 LK23+850.920 ~ LK23+880.000 (29.08m) | 42598.6265 |  |  | 0 | 0 | 0
8.6.2.1.1.4 | Concrete wall/ Betonski zid LK23+750.920 - LK23+880.000 After work 5% | 9951.9125 |  |  | 0 | 0 | 0
8.6.2.1.2 | Concrete wall/ Betonski zid LK24+351.170 -LK24+399.250 (48.08m)
8.6.2.1.2.1 | Concrete wall/ Betonski zid LK24+351.170 - LK24+399.250 - 95%, | 70431.2917 |  |  | 0 | 0 | 0
8.6.2.1.2.2 | Concrete wall/ Betonski zid LK24+351.170 - LK24+399.250 - After work 5% | 3706.9101 |  |  | 0 | 0 | 0
8.6.2.1.3 | Concrete wall/ Betonski zid LK24+570 - LK24+787 (217m) 95%, Layers 1,2,3,4,5
8.6.2.1.3.1 | Segment1 LK24+570 - LK24+620 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.3.2 | Segment 2 LK24+620 - LK24+670 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.3.3 | Segment 3 LK24+670 - LK24+720 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.3.4 | Segment 4 LK24+720 - LK24+770 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.3.5 | Segment 5 LK24+770 - LK24+787 (17m) | 24902.911 |  |  | 0 | 0 | 0
8.6.2.1.3.6 | Concrete wall/ Betonski zid LK24+570 - LK24+787 After work 5% | 16730.4386 |  |  | 0 | 0 | 0
8.6.2.1.4 | Concrete wall/ Betonski zid RK24+434.05 - RK24+805.00 (370.95m) 95%, Layers 1,2,3,4,5,6,7,8
8.6.2.1.4.1 | Segment 1 RK24+434.05 - RK24+484.05 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.4.2 | Segment 2 RK24+484.05 - RK24+534.05 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.4.3 | Segment 3 RK24+534.05 - RK24+584.05 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.4.4 | Segment 4 RK24+584.05 - RK24+634.05 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.4.5 | Segment 5 RK24+634.05 - RK24+684.05 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.4.6 | Segment 6 RK24+684.05 - RK24+734.05 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.4.7 | Segment 7 RK24+734.05 - RK24+784.05 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.4.8 | Segment 8 RK24+784.05 - RK24+805.00 (20.95m) | 30689.1756 |  |  | 0 | 0 | 0
8.6.2.1.4.9 | Concrete wall/ Betonski zid RK24+434.05 - RK24+805.00 After work 5% | 28599.7982 |  |  | 0 | 0 | 0
8.6.2.1.5 | Concrete wall/ Betonski zid RK24+800.00 - RK24+922.00 (122m) 95%, Layers 1,2,3
8.6.2.1.5.1 | Segment 1 RK24+800.00 - RK24+850.00 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.5.2 | Segment 2 RK24+850.00 - RK24+900.00 (50m) | 73243.8558 |  |  | 0 | 0 | 0
8.6.2.1.5.3 | Segment 3 RK24+900.00 - RK24+922.00 (22m) | 32227.2965 |  |  | 0 | 0 | 0
8.6.2.1.5.4 | Concrete wall/ Betonski zid RK24+800.00 ~ RK24+800.00 - After work 5% | 9406.0531 |  |  | 0 | 0 | 0
8.6.2.2 | Reinforced earth wall / Ojačani zemljani zid
The milestone is 2.20 m height of each leyer and no matter on the length / Reper je visina 2.2m za svaki sloj, bez obzira na dužinu
8.6.2.2.1 | Reinforced soil retaining wall Ramp1: RK23+895-RK24+051 / Potporni zid od armirane zemlje
8.6.2.2.1.1 | Layer/Sloj 1 (0.0 -2.2 m height) | 223333.6386 |  |  | 0 | 0 | 0
8.6.2.2.1.2 | Layer/Sloj 2 (2.2 -4.4 m height) | 223333.6386 |  |  | 0 | 0 | 0
8.6.2.2.1.3 | Layer/Sloj 3 (4.4 -6.6 m height) | 223333.6386 |  |  | 0 | 0 | 0
8.6.2.2.1.4 | Layer/Sloj 4 (6.6 -8.8m height) | 223333.6386 |  |  | 0 | 0 | 0
8.6.2.2.1.5 | Layer/Sloj 5 (8.8 -11.0 m height) | 223333.6386 |  |  | 0 | 0 | 0
8.6.2.2.1.6 | Layer/Sloj 6 (11.0 -13.2 m height) | 223333.6386 |  |  | 0 | 0 | 0
8.6.2.2.1.7 | Layer/Sloj 7 (13.2 -15.4 m height) | 223333.6386 |  |  | 0 | 0 | 0
8.6.2.2.1.8 | Layer/Sloj 8 (15.4 -17.60 m height) | 223333.6386 |  |  | 0 | 0 | 0
8.6.2.2.1.9 | Layer/Sloj 8 (17.60 -18.19 m height) | 59894.0213 |  |  | 0 | 0 | 0
8.6.2.3 | Culvert (it will be splitted after MD approval)/ Propust (biće podijeljen nakon odobrenja GP) | 22487.6 | 20 |  | 0 | 0 | 0
8.6.3 | Water drainage/ Drenaža vode
8.6.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 758059.92 | 38 |  | 0 | 0 | 0
8.6.4 | Pavement structure/ Kolovozna konstrukcija
8.6.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 0-500m | 52020.126 | 36 |  | 0 | 0 | 0
8.6.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 0-500m | 52020.126 | 36 |  | 0 | 0 | 0
8.6.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 500-1000m | 52020.126 | 37 |  | 0 | 0 | 0
8.6.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana 500-1010.346m | 53096.5265 | 37 |  | 0 | 0 | 0
8.6.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana 500-1086.241m | 8972.5354 | 37 |  | 0 | 0 | 0
8.6.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 0-500m | 52020.126 | 38 |  | 0 | 0 | 0
8.6.4.7 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 0-500m | 52020.126 | 38 |  | 0 | 0 | 0
8.6.4.8 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 500-900m | 52020.126 | 39 |  | 0 | 0 | 0
8.6.4.9 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana 500-1010.346m | 53096.5265 | 39 |  | 0 | 0 | 0
8.6.4.10 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana 500-1086.241m | 8972.5354 | 39 |  | 0 | 0 | 0
8.6.4.11 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 0-500m | 57803.5803 | 40 |  | 0 | 0 | 0
8.6.4.12 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 0-500m | 57803.5803 | 40 |  | 0 | 0 | 0
8.6.4.13 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 500-900m | 57803.5803 | 40 |  | 0 | 0 | 0
8.6.4.14 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana 500-1010.346m | 58999.652 | 40 |  | 0 | 0 | 0
8.6.4.15 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana 500-1086.241m | 9970.0771 | 40 |  | 0 | 0 | 0
8.6.5 | Interchange bridges/ Mosne petlje
MV1 24+000
8.6.5.1 | Foundation concrete/ Temeljni beton
8.6.5.1.1 | A1 | 13921.67 | 20 |  | 0 | 0 | 0
8.6.5.1.2 | P1 | 19307.24 | 20 |  | 0 | 0 | 0
8.6.5.1.3 | P2 | 19307.24 | 20 |  | 0 | 0 | 0
8.6.5.1.4 | P3 | 19307.24 | 21 |  | 0 | 0 | 0
8.6.5.1.5 | P4 | 19307.24 | 22 |  | 0 | 0 | 0
8.6.5.1.6 | P5 | 19307.24 | 23 |  | 0 | 0 | 0
8.6.5.1.7 | P6 | 19307.24 | 24 |  | 0 | 0 | 0
8.6.5.1.8 | P7 | 19307.24 | 25 |  | 0 | 0 | 0
8.6.5.1.9 | A2 | 13921.67 | 26 |  | 0 | 0 | 0
8.6.5.2 | Abutments and Piers elevation/ Elevacija mosnih stubova
8.6.5.2.1 | A1 | 31058.58 | 20 |  | 0 | 0 | 0
8.6.5.2.2 | P1 stage 1 (5m) | 5685.4724 | 21 |  | 0 | 0 | 0
8.6.5.2.3 | P1 stage 2 (5.7m) | 6481.4385 | 22 |  | 0 | 0 | 0
8.6.5.2.4 | P2 stage 1 (5m) | 5685.4724 | 21 |  | 0 | 0 | 0
8.6.5.2.5 | P2 stage 2 (5m) | 5685.4724 | 22 |  | 0 | 0 | 0
8.6.5.2.6 | P2 stage 3 (6m) | 6822.5668 | 22 |  | 0 | 0 | 0
8.6.5.2.7 | P3 stage 1 (5m) | 5685.4724 | 22 |  | 0 | 0 | 0
8.6.5.2.8 | P3 stage 2 (5m) | 5685.4724 | 23 |  | 0 | 0 | 0
8.6.5.2.9 | P3 stage 3 (5m) | 5685.4724 | 23 |  | 0 | 0 | 0
8.6.5.2.10 | P3 stage 4 (6m) | 6822.5668 | 24 |  | 0 | 0 | 0
8.6.5.2.11 | P4 stage 1 (5m) | 5685.4724 | 23 |  | 0 | 0 | 0
8.6.5.2.12 | P4 stage 2 (5m) | 5685.4724 | 24 |  | 0 | 0 | 0
8.6.5.2.13 | P4 stage 3 (5m) | 5685.4724 | 25 |  | 0 | 0 | 0
8.6.5.2.14 | P4 stage 4 (8m) | 9096.7558 | 25 |  | 0 | 0 | 0
8.6.5.2.15 | P5 stage 1 (5m) | 5685.4724 | 24 |  | 0 | 0 | 0
8.6.5.2.16 | P5 stage 2 (5m) | 5685.4724 | 24 |  | 0 | 0 | 0
8.6.5.2.17 | P5 stage 3 (5m) | 5685.4724 | 25 |  | 0 | 0 | 0
8.6.5.2.18 | P5 stage 4 (6.8m) | 7732.2424 | 25 |  | 0 | 0 | 0
8.6.5.2.19 | P6 stage 1 (5m) | 5685.4724 | 25 |  | 0 | 0 | 0
8.6.5.2.20 | P6 stage 2 (6.7m) | 7618.533 | 26 |  | 0 | 0 | 0
8.6.5.2.21 | P7 stage 1 (5m) | 5685.4724 | 26 |  | 0 | 0 | 0
8.6.5.2.22 | P7 stage 2 (3m) | 3411.2834 | 26 |  | 0 | 0 | 0
8.6.5.2.23 | A2 | 31058.58 | 27 |  | 0 | 0 | 0
8.6.5.3 | Bridge deck superstructure/ Gornji stroj mosne ploče
8.6.5.3.1 | A1-P1 | 60524.3 | 23 |  | 0 | 0 | 0
8.6.5.3.2 | P1-P2 | 60524.3 | 24 |  | 0 | 0 | 0
8.6.5.3.3 | P2-P3 | 74934.85 | 25 |  | 0 | 0 | 0
8.6.5.3.4 | P3-P4 | 74934.85 | 26 |  | 0 | 0 | 0
8.6.5.3.5 | P4-P5 | 74934.85 | 27 |  | 0 | 0 | 0
8.6.5.3.6 | P5-P6 | 60524.3 | 28 |  | 0 | 0 | 0
8.6.5.3.7 | P6-P7 | 60524.3 | 29 |  | 0 | 0 | 0
8.6.5.3.8 | P7-A2 | 60524.3 | 30 |  | 0 | 0 | 0
8.6.5.4 | Bridge deck prestressing/ Prednaprezanje mosne ploče
8.6.5.4.1 | A1-P1 | 6724.92 | 24 |  | 0 | 0 | 0
8.6.5.4.2 | P1-P2 | 6724.92 | 25 |  | 0 | 0 | 0
8.6.5.4.3 | P2-P3 | 8326.09 | 26 |  | 0 | 0 | 0
8.6.5.4.4 | P3-P4 | 8326.09 | 27 |  | 0 | 0 | 0
8.6.5.4.5 | P4-P5 | 8326.09 | 28 |  | 0 | 0 | 0
8.6.5.4.6 | P5-P6 | 6724.92 | 29 |  | 0 | 0 | 0
8.6.5.4.7 | P6-P7 | 6724.92 | 30 |  | 0 | 0 | 0
8.6.5.4.8 | P7-A2 | 6724.95 | 30 |  | 0 | 0 | 0
8.6.5.5 | Bridge furniture/ Mosna estetika
8.6.5.5.1 | 50 m | 93093.21 | 29 |  | 0 | 0 | 0
8.6.5.5.2 | 100 m | 93093.21 | 29 |  | 0 | 0 | 0
8.6.5.5.3 | 150 m | 93093.21 | 30 |  | 0 | 0 | 0
8.6.5.5.4 | 183 m | 61441.57 | 30 |  | 0 | 0 | 0
8.6.5.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
8.6.5.6.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/ hidroizolacija | 38559.04 | 30 |  | 0 | 0 | 0
8.6.5.6.2 | Asphalt layer/ Sloj asfalta 2 + joints/ spojnice | 9615.84 | 30 |  | 0 | 0 | 0
MV2 24+000
8.6.5.7 | Foundation concrete/ Temeljni beton
8.6.5.7.1 | A1 | 16839.94 | 20 |  | 0 | 0 | 0
8.6.5.7.2 | P1 | 24231.77 | 21 |  | 0 | 0 | 0
8.6.5.7.3 | P2 | 24231.77 | 22 |  | 0 | 0 | 0
8.6.5.7.4 | P3 | 24231.77 | 23 |  | 0 | 0 | 0
8.6.5.7.5 | P4 | 24231.77 | 24 |  | 0 | 0 | 0
8.6.5.7.6 | P5 | 24231.77 | 25 |  | 0 | 0 | 0
8.6.5.7.7 | A2 | 16839.94 | 26 |  | 0 | 0 | 0
8.6.5.8 | Abutments and Piers elevation/ Elevacija mosnih stubova
8.6.5.8.1 | A1 | 74798.66 | 22 |  | 0 | 0 | 0
8.6.5.8.2 | P1 stage 1 (5m) | 10152.3363 | 22 |  | 0 | 0 | 0
8.6.5.8.3 | P1 stage 2 (6.6m) | 13401.0839 | 23 |  | 0 | 0 | 0
8.6.5.8.4 | P2 stage 1 (5m) | 10152.3363 | 23 |  | 0 | 0 | 0
8.6.5.8.5 | P2 stage 2 (5m) | 10152.3363 | 24 |  | 0 | 0 | 0
8.6.5.8.6 | P2 stage 3 (5m) | 10152.3363 | 25 |  | 0 | 0 | 0
8.6.5.8.7 | P2 stage 4 (7m) | 14213.2708 | 25 |  | 0 | 0 | 0
8.6.5.8.8 | P3 stage 1 (5m) | 10152.3363 | 24 |  | 0 | 0 | 0
8.6.5.8.9 | P3 stage 2 (5m) | 10152.3363 | 24 |  | 0 | 0 | 0
8.6.5.8.10 | P3 stage 3 (5m) | 10152.3363 | 25 |  | 0 | 0 | 0
8.6.5.8.11 | P3 stage 4 (5m) | 10152.3363 | 25 |  | 0 | 0 | 0
8.6.5.8.12 | P3 stage 5 (5m) | 10152.3363 | 26 |  | 0 | 0 | 0
8.6.5.8.13 | P3 stage 6 (5m) | 10152.3363 | 27 |  | 0 | 0 | 0
8.6.5.8.14 | P3 stage 7 (5m) | 10152.3363 | 28 |  | 0 | 0 | 0
8.6.5.8.15 | P3 stage 8 (3.5m) | 7106.6354 | 27 |  | 0 | 0 | 0
8.6.5.8.16 | P4 stage 1 (5m) | 10152.3363 | 25 |  | 0 | 0 | 0
8.6.5.8.17 | P4 stage 2 (5m) | 10152.3363 | 25 |  | 0 | 0 | 0
8.6.5.8.18 | P4 stage 3 (5m) | 10152.3363 | 26 |  | 0 | 0 | 0
8.6.5.8.19 | P4 stage 4 (5m) | 10152.3363 | 26 |  | 0 | 0 | 0
8.6.5.8.20 | P4 stage 5 (5m) | 10152.3363 | 27 |  | 0 | 0 | 0
8.6.5.8.21 | P4 stage 6 (5m) | 10152.3363 | 27 |  | 0 | 0 | 0
8.6.5.8.22 | P4 stage 7 (5m) | 10152.3363 | 28 |  | 0 | 0 | 0
8.6.5.8.23 | P4 stage 8 (3m) | 6091.4018 | 28 |  | 0 | 0 | 0
8.6.5.8.24 | P5 stage 1 (5m) | 10152.3363 | 26 |  | 0 | 0 | 0
8.6.5.8.25 | P5 stage 2 (5m) | 10152.3363 | 26 |  | 0 | 0 | 0
8.6.5.8.26 | P5 stage 3 (5m) | 10152.3363 | 27 |  | 0 | 0 | 0
8.6.5.8.27 | P5 stage 4 (6.2m) | 12588.897 | 27 |  | 0 | 0 | 0
8.6.5.8.28 | A2 | 74798.66 | 28 |  | 0 | 0 | 0
8.6.5.9 | Bridge deck superstructure/ Gornji stroj mosne ploče
8.6.5.9.1 | A1-P1 | 70427.95 | 23 |  | 0 | 0 | 0
8.6.5.9.2 | P1-P2 | 89635.58 | 24 |  | 0 | 0 | 0
8.6.5.9.3 | P2-P3 | 89635.58 | 25 |  | 0 | 0 | 0
8.6.5.9.4 | P3-P4 | 89635.58 | 26 |  | 0 | 0 | 0
8.6.5.9.5 | P4-P5 | 89635.58 | 27 |  | 0 | 0 | 0
8.6.5.9.6 | P5-A2 | 70427.95 | 28 |  | 0 | 0 | 0
8.6.5.10 | Bridge deck prestressing/ Prednaprezanje mosne ploče |  |  |  | 0 | 0 | 0
8.6.5.10.1 | A1-P1 | 7825.33 | 24 |  | 0 | 0 | 0
8.6.5.10.2 | P1-P2 | 9959.51 | 25 |  | 0 | 0 | 0
8.6.5.10.3 | P2-P3 | 9959.51 | 26 |  | 0 | 0 | 0
8.6.5.10.4 | P3-P4 | 9959.51 | 27 |  | 0 | 0 | 0
8.6.5.10.5 | P4-P5 | 9959.51 | 28 |  | 0 | 0 | 0
8.6.5.10.6 | P5-A2 | 7825.33 | 29 |  | 0 | 0 | 0
8.6.5.11 | Bridge furniture/ Mosna estetika
8.6.5.11.1 | 50 m | 103038.57 | 29 |  | 0 | 0 | 0
8.6.5.11.2 | 100 m | 103038.57 | 30 |  | 0 | 0 | 0
8.6.5.11.3 | 156 m | 115403.21 | 30 |  | 0 | 0 | 0
8.6.5.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
8.6.5.12.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/ hidroizolacija | 34786.96 | 30 |  | 0 | 0 | 0
8.6.5.12.2 | Asphalt layer/ Sloj asfalta 2 + joints/ spojnice | 8675.16 | 30 |  | 0 | 0 | 0
VERUSA-MATESEVO 24+000
8.6.5.13 | Foundation concrete/ Temeljni beton
8.6.5.13.1 | A1 | 12903.42 | 26 |  | 0 | 0 | 0
8.6.5.13.2 | P1 | 22901.49 | 26 |  | 0 | 0 | 0
8.6.5.13.3 | P2 | 22901.49 | 27 |  | 0 | 0 | 0
8.6.5.13.4 | P3 | 22901.49 | 27 |  | 0 | 0 | 0
8.6.5.13.5 | P4 | 22901.49 | 28 |  | 0 | 0 | 0
8.6.5.13.6 | P5 | 22901.49 | 28 |  | 0 | 0 | 0
8.6.5.13.7 | P6 | 22901.49 | 29 |  | 0 | 0 | 0
8.6.5.13.8 | P7 | 22901.49 | 29
8.6.5.13.9 | P8 | 22901.49 | 29
8.6.5.13.10 | A2 | 12903.42 | 29 |  | 0 | 0 | 0
8.6.5.14 | Abutments and Piers elevation/ Elevacija mosnih stubova
8.6.5.14.1 | A1 | 52009.61 | 27 |  | 0 | 0 | 0
8.6.5.14.2 | P1 stage 1 (5m) | 6594.1629 | 27 |  | 0 | 0 | 0
8.6.5.14.3 | P1 stage 2 (6.5m) | 8572.4118 | 28 |  | 0 | 0 | 0
8.6.5.14.4 | P2 stage 1 (5m) | 6594.1629 | 29 |  | 0 | 0 | 0
8.6.5.14.5 | P2 stage 2 (5m) | 6594.1629 | 29 |  | 0 | 0 | 0
8.6.5.14.6 | P2 stage 3 (5m) | 6594.1629 | 30 |  | 0 | 0 | 0
8.6.5.14.7 | P2 stage 4 (3m) | 3956.4978 | 30 |  | 0 | 0 | 0
8.6.5.14.8 | P3 stage 1 (5m) | 6594.1629 | 29 |  | 0 | 0 | 0
8.6.5.14.9 | P3 stage 2 (5m) | 6594.1629 | 29 |  | 0 | 0 | 0
8.6.5.14.10 | P3 stage 3 (5m) | 6594.1629 | 30 |  | 0 | 0 | 0
8.6.5.14.11 | P3 stage 4 (5m) | 6594.1629 | 30 |  | 0 | 0 | 0
8.6.5.14.12 | P4 stage 1 (5m) | 6594.1629 | 31 |  | 0 | 0 | 0
8.6.5.14.13 | P4 stage 2 (5m) | 6594.1629 | 31 |  | 0 | 0 | 0
8.6.5.14.14 | P4 stage 3 (5m) | 6594.1629 | 32 |  | 0 | 0 | 0
8.6.5.14.15 | P4 stage 4 (5m) | 6594.1629 | 33 |  | 0 | 0 | 0
8.6.5.14.16 | P4 stage 5 (3m) | 3956.4978 | 32 |  | 0 | 0 | 0
8.6.5.14.17 | P5 stage 1 (5m) | 6594.1629 | 31 |  | 0 | 0 | 0
8.6.5.14.18 | P5 stage 2 (5m) | 6594.1629 | 31 |  | 0 | 0 | 0
8.6.5.14.19 | P5 stage 3 (5m) | 6594.1629 | 32 |  | 0 | 0 | 0
8.6.5.14.20 | P5 stage 4 (5m) | 6594.1629 | 32 |  | 0 | 0 | 0
8.6.5.14.21 | P5 stage 5 (3m) | 3956.4978 | 32 |  | 0 | 0 | 0
8.6.5.14.22 | P6 stage 1 (5m) | 6594.1629 | 33 |  | 0 | 0 | 0
8.6.5.14.23 | P6 stage 2 (5m) | 6594.1629 | 33 |  | 0 | 0 | 0
8.6.5.14.24 | P6 stage 3 (5m) | 6594.1629 | 34 |  | 0 | 0 | 0
8.6.5.14.25 | P6 stage 4 (6m) | 7912.9955 | 34 |  | 0 | 0 | 0
8.6.5.14.26 | P7 stage 1 (5m) | 6594.1629 |  |  | 0 | 0 | 0
8.6.5.14.27 | P7 stage 2 (5m) | 6594.1629 |  |  | 0 | 0 | 0
8.6.5.14.28 | P7 stage 3 (5m) | 6594.1629 |  |  | 0 | 0 | 0
8.6.5.14.29 | P7 stage 4 (2.8m) | 3692.7312 |  |  | 0 | 0 | 0
8.6.5.14.30 | P8 stage 1 (5m) | 6594.1629 |  |  | 0 | 0 | 0
8.6.5.14.31 | P8 stage 2 (5m) | 6594.1629 |  |  | 0 | 0 | 0
8.6.5.14.32 | P8 stage 3 (3m) | 3956.4978 |  |  | 0 | 0 | 0
8.6.5.14.33 | A2 | 52009.61 | 35 |  | 0 | 0 | 0
8.6.5.15 | Bridge deck superstructure/ Gornji stroj mosne ploče
8.6.5.15.1 | A1-P1 | 34305.47 | 31 |  | 0 | 0 | 0
8.6.5.15.2 | P1-P2 | 42473.44 | 32 |  | 0 | 0 | 0
8.6.5.15.3 | P2-P3 | 42473.44 | 31 |  | 0 | 0 | 0
8.6.5.15.4 | P3-P4 | 42473.44 | 34 |  | 0 | 0 | 0
8.6.5.15.5 | P4-P5 | 42473.44 | 33 |  | 0 | 0 | 0
8.6.5.15.6 | P5-P6 | 42473.44 | 35 |  | 0 | 0 | 0
8.6.5.15.7 | P6-A2 | 34305.47 | 36 |  | 0 | 0 | 0
8.6.5.16 | Bridge deck prestressing/ Prednaprezanje mosne ploče
8.6.5.16.1 | A1-P1 | 3811.72 | 32 |  | 0 | 0 | 0
8.6.5.16.2 | P1-P2 | 4719.27 | 33 |  | 0 | 0 | 0
8.6.5.16.3 | P2-P3 | 4719.27 | 34 |  | 0 | 0 | 0
8.6.5.16.4 | P3-P4 | 4719.27 | 35 |  | 0 | 0 | 0
8.6.5.16.5 | P4-P5 | 4719.27 | 36 |  | 0 | 0 | 0
8.6.5.16.6 | P5-P6 | 4719.27 | 37 |  | 0 | 0 | 0
8.6.5.16.7 | P6-A2 | 3811.72 | 38 |  | 0 | 0 | 0
8.6.5.17 | Bridge furniture/ Mosna estetika
8.6.5.17.1 | 50 m | 88017.99 | 39 |  | 0 | 0 | 0
8.6.5.17.2 | 100 m | 88017.99 | 40 |  | 0 | 0 | 0
8.6.5.17.3 | 150 m | 88017.99 | 39 |  | 0 | 0 | 0
8.6.5.17.4 | 172 m | 38727.85 | 41 |  | 0 | 0 | 0
8.6.5.18 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
8.6.5.18.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/ hidroizolacija | 28544.05 | 41 |  | 0 | 0 | 0
8.6.5.18.2 | Asphalt layer/ Sloj asfalta 2 + joints/ spojnice | 5791.94 | 41 |  | 0 | 0 | 0
Viaduct/Vijadukt Podgorica Verusa
8.6.5.19 | Foundation concrete/ Temeljni beton
8.6.5.19.1 | A1 | 15164.27 | 25 |  | 0 | 0 | 0
8.6.5.19.2 | P1 | 24972.79 | 25 |  | 0 | 0 | 0
8.6.5.19.3 | P2 | 24972.79 | 26 |  | 0 | 0 | 0
8.6.5.19.4 | P3 | 24972.79 | 26 |  | 0 | 0 | 0
8.6.5.19.5 | P4 | 24972.79 | 27 |  | 0 | 0 | 0
8.6.5.19.6 | A2 | 15164.27 | 27 |  | 0 | 0 | 0
8.6.5.20 | Abutments and Piers elevation/ Elevacija mosnih stubova
8.6.5.20.1 | A1 | 24134.28 | 26 |  | 0 | 0 | 0
8.6.5.20.2 | P1 stage 1 (5m) | 3361.9964 | 26 |  | 0 | 0 | 0
8.6.5.20.3 | P1 stage 2 (5m) | 3361.9964 | 26 |  | 0 | 0 | 0
8.6.5.20.4 | P1 stage 3 (5m) | 3361.9964 | 27 |  | 0 | 0 | 0
8.6.5.20.5 | P1 stage 4 (3.7m) | 2487.8773 | 27 |  | 0 | 0 | 0
8.6.5.20.6 | P2 stage 1 (5m) | 3361.9964 | 27 |  | 0 | 0 | 0
8.6.5.20.7 | P2 stage 2 (5m) | 3361.9964 | 27 |  | 0 | 0 | 0
8.6.5.20.8 | P2 stage 3 (5m) | 3361.9964 | 28 |  | 0 | 0 | 0
8.6.5.20.9 | P2 stage 4 (5m) | 3361.9964 | 28 |  | 0 | 0 | 0
8.6.5.20.10 | P2 stage 5 (5m) | 3361.9964 | 29 |  | 0 | 0 | 0
8.6.5.20.11 | P2 stage 6 (5m) | 3361.9964 | 29 |  | 0 | 0 | 0
8.6.5.20.12 | P2 stage 7 (5m) | 3361.9964 | 30 |  | 0 | 0 | 0
8.6.5.20.13 | P2 stage 8 (2.4m) | 1613.7583 | 30 |  | 0 | 0 | 0
8.6.5.20.14 | P3 stage 1 (5m) | 3361.9964 | 28 |  | 0 | 0 | 0
8.6.5.20.15 | P3 stage 2 (5m) | 3361.9964 | 28 |  | 0 | 0 | 0
8.6.5.20.16 | P3 stage 3 (5m) | 3361.9964 | 28 |  | 0 | 0 | 0
8.6.5.20.17 | P3 stage 4 (5m) | 3361.9964 | 29 |  | 0 | 0 | 0
8.6.5.20.18 | P3 stage 5 (5m) | 3361.9964 | 29 |  | 0 | 0 | 0
8.6.5.20.19 | P3 stage 6 (5m) | 3361.9964 | 30 |  | 0 | 0 | 0
8.6.5.20.20 | P3 stage 7 (5m) | 3361.9964 | 30 |  | 0 | 0 | 0
8.6.5.20.21 | P3 stage 8 (1.7m) | 1143.0788 | 30 |  | 0 | 0 | 0
8.6.5.20.22 | P4 stage 1 (5m) | 3361.9964 | 30 |  | 0 | 0 | 0
8.6.5.20.23 | P4 stage 2 (5m) | 3361.9964 | 31 |  | 0 | 0 | 0
8.6.5.20.24 | P4 stage 3 (5m) | 3361.9964 | 32 |  | 0 | 0 | 0
8.6.5.20.25 | P4 stage 4 (3.7m) | 2487.8773 | 32 |  | 0 | 0 | 0
8.6.5.20.26 | A2 | 24134.28 | 32 |  | 0 | 0 | 0
8.6.5.21 | Bridge deck superstructure/ Gornji stroj mosne ploče
8.6.5.21.1 | A1-P1 | 104333.23 | 29 |  | 0 | 0 | 0
8.6.5.21.2 | P1-P2 | 132787.75 | 30 |  | 0 | 0 | 0
8.6.5.21.3 | P2-P3 | 132787.75 | 31 |  | 0 | 0 | 0
8.6.5.21.4 | P3-P4 | 132787.75 | 32 |  | 0 | 0 | 0
8.6.5.21.5 | P4-A2 | 104333.23 | 33 |  | 0 | 0 | 0
8.6.5.22 | Bridge deck prestressing/ Prednaprezanje mosne ploče
8.6.5.22.1 | A1-P1 | 11592.58 | 32 |  | 0 | 0 | 0
8.6.5.22.2 | P1-P2 | 14754.19 | 33 |  | 0 | 0 | 0
8.6.5.22.3 | P2-P3 | 14754.19 | 34 |  | 0 | 0 | 0
8.6.5.22.4 | P3-P4 | 14754.19 | 35 |  | 0 | 0 | 0
8.6.5.22.5 | P4-A2 | 11592.6 | 36 |  | 0 | 0 | 0
8.6.5.23 | Bridge furniture/ Mosna estetika
8.6.5.23.1 | 50 m | 105862.62 | 36 |  | 0 | 0 | 0
8.6.5.23.2 | 100 m | 105862.62 | 37 |  | 0 | 0 | 0
8.6.5.23.3 | 128 m | 59283.03 | 38 |  | 0 | 0 | 0
8.6.5.24 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
8.6.5.24.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/ hidroizolacija | 41654.08 | 38 |  | 0 | 0 | 0
8.6.5.24.2 | Asphalt layer/ Sloj asfalta 2 + joints/ spojnice | 10387.68 | 38 |  | 0 | 0 | 0
Viaduct/Vijadukt Verusa Podgorica
8.6.5.25 | Foundation concrete/ Temeljni beton
8.6.5.25.1 | A1 | 13027.59 | 27 |  | 0 | 0 | 0
8.6.5.25.2 | P1 | 24804.69 | 28 |  | 0 | 0 | 0
8.6.5.25.3 | P2 | 24804.69 | 29 |  | 0 | 0 | 0
8.6.5.25.4 | P3 | 24804.69 | 30 |  | 0 | 0 | 0
8.6.5.25.5 | P4 | 24804.69 | 31 |  | 0 | 0 | 0
8.6.5.25.6 | A2 | 13027.59 | 32 |  | 0 | 0 | 0
8.6.5.26 | Abutments and Piers elevation/ Elevacija mosnih stubova
8.6.5.26.1 | A1 | 39863.07 | 28 |  | 0 | 0 | 0
8.6.5.26.2 | P1 stage 1 (5m) | 3536.4837 | 29 |  | 0 | 0 | 0
8.6.5.26.3 | P1 stage 2 (5m) | 3536.4837 | 30 |  | 0 | 0 | 0
8.6.5.26.4 | P1 stage 3 (5m) | 3536.4837 | 30 |  | 0 | 0 | 0
8.6.5.26.5 | P1 stage 4 (5m) | 3536.4837 | 31 |  | 0 | 0 | 0
8.6.5.26.6 | P1 stage 5 (3.5m) | 2475.5386 | 31 |  | 0 | 0 | 0
8.6.5.26.7 | P2 stage 1 (5m) | 3536.4837 | 31 |  | 0 | 0 | 0
8.6.5.26.8 | P2 stage 2 (5m) | 3536.4837 | 31 |  | 0 | 0 | 0
8.6.5.26.9 | P2 stage 3 (5m) | 3536.4837 | 31 |  | 0 | 0 | 0
8.6.5.26.10 | P2 stage 4 (5m) | 3536.4837 | 32 |  | 0 | 0 | 0
8.6.5.26.11 | P2 stage 5 (5m) | 3536.4837 | 32 |  | 0 | 0 | 0
8.6.5.26.12 | P2 stage 6 (5m) | 3536.4837 | 32 |  | 0 | 0 | 0
8.6.5.26.13 | P2 stage 7 (5.5m) | 3890.1321 | 32 |  | 0 | 0 | 0
8.6.5.26.14 | P3 stage 1 (5m) | 3536.4837 | 32 |  | 0 | 0 | 0
8.6.5.26.15 | P3 stage 2 (5m) | 3536.4837 | 32 |  | 0 | 0 | 0
8.6.5.26.16 | P3 stage 3 (5m) | 3536.4837 | 32 |  | 0 | 0 | 0
8.6.5.26.17 | P3 stage 4 (5m) | 3536.4837 | 33 |  | 0 | 0 | 0
8.6.5.26.18 | P3 stage 5 (5m) | 3536.4837 | 32 |  | 0 | 0 | 0
8.6.5.26.19 | P3 stage 6 (4m) | 2829.187 | 33 |  | 0 | 0 | 0
8.6.5.26.20 | P4 stage 1 (5m) | 3536.4837 | 33 |  | 0 | 0 | 0
8.6.5.26.21 | P4 stage 2 (5m) | 3536.4837 | 34 |  | 0 | 0 | 0
8.6.5.26.22 | P4 stage 3 (6.5m) | 4597.4289 | 34 |  | 0 | 0 | 0
8.6.5.26.23 | A2 | 39863.07 | 34 |  | 0 | 0 | 0
8.6.5.27 | Bridge deck superstructure/ Gornji stroj mosne ploče
8.6.5.27.1 | A1-P1 | 106004.81 | 32 |  | 0 | 0 | 0
8.6.5.27.2 | P1-P2 | 123672.28 | 33 |  | 0 | 0 | 0
8.6.5.27.3 | P2-P3 | 123672.28 | 34 |  | 0 | 0 | 0
8.6.5.27.4 | P3-P4 | 123672.28 | 35 |  | 0 | 0 | 0
8.6.5.27.6 | P4-A2 | 106004.81 | 36 |  | 0 | 0 | 0
8.6.5.28 | Bridge deck prestressing/ Prednaprezanje mosne ploče
8.6.5.28.1 | A1-P1 | 11778.31 | 35 |  | 0 | 0 | 0
8.6.5.28.2 | P1-P2 | 13741.36 | 36 |  | 0 | 0 | 0
8.6.5.28.3 | P2-P3 | 13741.36 | 37 |  | 0 | 0 | 0
8.6.5.28.4 | P3-P4 | 13741.36 | 38 |  | 0 | 0 | 0
8.6.5.28.6 | P4-A2 | 11778.33 | 39 |  | 0 | 0 | 0
8.6.5.29 | Bridge furniture/ Mosna estetika
8.6.5.29.1 | 50 m | 102633.07 | 41 |  | 0 | 0 | 0
8.6.5.29.2 | 100 m | 102633.07 | 42 |  | 0 | 0 | 0
8.6.5.29.3 | 132 m | 65685.19 | 43 |  | 0 | 0 | 0
8.6.5.30 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
8.6.5.30.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/ hidroizolacija | 41654.08 | 43 |  | 0 | 0 | 0
| Asphalt layer/ Sloj asfalta 2 + joints/ spojnice | 10387.68 | 43 |  | 0 | 0 | 0
| Sub Total / Suma stavke 8.6 | 14291712.83 |  |  | 0 | 0 | 0
Cost Center/ 8.7 | Construction of bridge/ Izgradnja mosta Mistica (LK 24+173.92-LK24+345.92, RK 24+204.14-RK24+428.14)
Completion of/Završetak:
Left bridge/ Lijevi most
8.7.1 | Foundation concrete/ Temeljni beton
8.7.1.1 | A1 | 35094.56 | 26 |  | 0 | 0 | 0
8.7.1.2 | P1 | 22328.12 | 26 |  | 0 | 0 | 0
8.7.1.3 | P2 | 22328.12 | 27 |  | 0 | 0 | 0
8.7.1.4 | P3 | 22328.12 | 27 |  | 0 | 0 | 0
8.7.1.5 | P4 | 22328.12 | 27 |  | 0 | 0 | 0
8.7.1.6 | P5 | 22328.12 | 28 |  | 0 | 0 | 0
8.7.1.7 | P6 | 22328.12 | 28 |  | 0 | 0 | 0
8.7.1.8 | A2 | 35094.56 | 28 |  | 0 | 0 | 0
8.7.2 | Abutments and Piers elevation/ Elevacija mosnih stubova
8.7.2.1 | A1 | 52815.4 | 27 |  | 0 | 0 | 0
8.7.2.2 | P1 stage 1 (1.2m) | 3024.3508 | 27 |  | 0 | 0 | 0
8.7.2.3 | P1 stage 2 (2m) | 5040.5846 | 27 |  | 0 | 0 | 0
8.7.2.4 | P1 stage 3 (5.6m) | 14113.637 | 28 |  | 0 | 0 | 0
8.7.2.5 | P1 stage 4 (3.2m) | 8064.9354 | 28 |  | 0 | 0 | 0
8.7.2.6 | P2 stage 1 (2.2m) | 5544.6431 | 27 |  | 0 | 0 | 0
8.7.2.7 | P2 stage 2 (2m) | 5040.5846 | 27 |  | 0 | 0 | 0
8.7.2.8 | P2 stage 3 (5m) | 12601.4616 | 27 |  | 0 | 0 | 0
8.7.2.9 | P2 stage 4 (5.93m) | 14945.3335 | 28 |  | 0 | 0 | 0
8.7.2.10 | P2 stage 5 (3.2m) | 8064.9354 | 28 |  | 0 | 0 | 0
8.7.2.11 | P3 stage 1 (2.2m) | 5544.6431 | 27 |  | 0 | 0 | 0
8.7.2.12 | P3 stage 2 (2m) | 5040.5846 | 27 |  | 0 | 0 | 0
8.7.2.13 | P3 stage 3 (5m) | 12601.4616 | 28 |  | 0 | 0 | 0
8.7.2.14 | P3 stage 4 (5m) | 12601.4616 | 28 |  | 0 | 0 | 0
8.7.2.15 | P3 stage 5 (2.12m) | 5343.0197 | 28 |  | 0 | 0 | 0
8.7.2.16 | P3 stage 6 (3.2m) | 8064.9354 | 28 |  | 0 | 0 | 0
8.7.2.17 | P4 stage 1 (1.2m) | 3024.3508 | 28 |  | 0 | 0 | 0
8.7.2.18 | P4 stage 2 (2m) | 5040.5846 | 28 |  | 0 | 0 | 0
8.7.2.19 | P4 stage 3 (5m) | 12601.4616 | 28 |  | 0 | 0 | 0
8.7.2.20 | P4 stage 4 (5m) | 12601.4616 | 29 |  | 0 | 0 | 0
8.7.2.21 | P4 stage 5 (2.62m) | 6603.1659 | 29 |  | 0 | 0 | 0
8.7.2.22 | P4 stage 6 (3.2m) | 8064.9354 | 29 |  | 0 | 0 | 0
8.7.2.23 | P5 stage 1 (1.2m) | 3024.3508 | 30 |  | 0 | 0 | 0
8.7.2.24 | P5 stage 2 (2m) | 5040.5846 | 30 |  | 0 | 0 | 0
8.7.2.25 | P5 stage 3 (5m) | 12601.4616 | 30 |  | 0 | 0 | 0
8.7.2.26 | P5 stage 4 (5.92m) | 14920.1305 | 30 |  | 0 | 0 | 0
8.7.2.27 | P5 stage 5 (3.2m) | 8064.9354 | 30 |  | 0 | 0 | 0
8.7.2.28 | P6 stage 1 (2.2m) | 5544.6431 | 29 |  | 0 | 0 | 0
8.7.2.29 | P6 stage 2 (2m) | 5040.5846 | 29 |  | 0 | 0 | 0
8.7.2.30 | P6 stage 3 (3.7m) | 9325.0816 | 30 |  | 0 | 0 | 0
8.7.2.31 | P6 stage 4 (3.2m) | 8064.9354 | 30 |  | 0 | 0 | 0
8.7.2.32 | A2 | 52815.4 | 30 |  | 0 | 0 | 0
8.7.3 | Bridge deck superstructure/ Gornji stroj mosne ploče
8.7.3.1 | A1-P1 | 92923.31 | 30 |  | 0 | 0 | 0
8.7.3.2 | P1-P2 | 115047.91 | 31 |  | 0 | 0 | 0
8.7.3.3 | P2-P3 | 115047.91 | 32 |  | 0 | 0 | 0
8.7.3.4 | P3-P4 | 115047.91 | 33 |  | 0 | 0 | 0
8.7.3.5 | P4-P5 | 115047.91 | 34 |  | 0 | 0 | 0
8.7.3.6 | P5-P6 | 115047.91 | 35 |  | 0 | 0 | 0
8.7.3.7 | P6-A2 | 92923.31 | 36 |  | 0 | 0 | 0
8.7.4 | Bridge deck prestressing/ Prednaprezanje mosne ploče
8.7.4.1 | A1-P1 | 10324.81 | 31 |  | 0 | 0 | 0
8.7.4.2 | P1-P2 | 12783.1 | 32 |  | 0 | 0 | 0
8.7.4.3 | P2-P3 | 12783.1 | 33 |  | 0 | 0 | 0
8.7.4.4 | P3-P4 | 12783.1 | 34 |  | 0 | 0 | 0
8.7.4.5 | P4-P5 | 12783.1 | 35 |  | 0 | 0 | 0
8.7.4.6 | P5-P6 | 12783.1 | 36 |  | 0 | 0 | 0
8.7.4.7 | P6-A2 | 10324.81 | 36 |  | 0 | 0 | 0
8.7.5 | Bridge furniture/ Mosna estetika
8.7.5.1 | 50 m | 67907.17 | 34 |  | 0 | 0 | 0
8.7.5.2 | 100 m | 67907.17 | 35 |  | 0 | 0 | 0
8.7.5.3 | 150 m | 67907.17 | 36 |  | 0 | 0 | 0
8.7.5.4 | 172 m | 29879.21 | 37 |  | 0 | 0 | 0
8.7.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
8.7.6.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/ hidroizolacija | 70628.69 | 36 |  | 0 | 0 | 0
8.7.6.2 | Asphalt layer/ Sloj asfalta 2 + joints/ spojnice | 17067.31 | 37 |  | 0 | 0 | 0
Right bridge/ Desni most
8.7.7 | Foundation concrete/ Temeljni beton
8.7.7.1 | A1 | 28029.07 | 26 |  | 0 | 0 | 0
8.7.7.2 | P1 | 22887.35 | 26 |  | 0 | 0 | 0
8.7.7.3 | P2 | 22887.35 | 26 |  | 0 | 0 | 0
8.7.7.4 | P3 | 22887.35 | 27 |  | 0 | 0 | 0
8.7.7.5 | P4 | 22887.35 | 27 |  | 0 | 0 | 0
8.7.7.6 | P5 | 22887.35 | 27 |  | 0 | 0 | 0
8.7.7.7 | P6 | 22887.35 | 28 |  | 0 | 0 | 0
8.7.7.8 | P7 | 22887.35 | 28 |  | 0 | 0 | 0
8.7.7.9 | P8 | 22887.35 | 28 |  | 0 | 0 | 0
8.7.7.10 | A2 | 28029.07 | 28 |  | 0 | 0 | 0
8.7.8 | Abutments and Piers elevation/ Elevacija mosnih stubova
8.7.8.1 | A1 | 31099.65 | 26 |  | 0 | 0 | 0
8.7.8.2 | P1 stage 1 (1.2m) | 2804.1096 | 26 |  | 0 | 0 | 0
8.7.8.3 | P1 stage 2 (2m) | 4673.516 | 26 |  | 0 | 0 | 0
8.7.8.4 | P1 stage 3 (5.6m) | 13085.8447 | 27 |  | 0 | 0 | 0
8.7.8.5 | P1 stage 4 (3.2m) | 7477.6255 | 27 |  | 0 | 0 | 0
8.7.8.6 | P2 stage 1 (2.2m) | 5140.8675 | 27 |  | 0 | 0 | 0
8.7.8.7 | P2 stage 2 (2m) | 4673.516 | 27 |  | 0 | 0 | 0
8.7.8.8 | P2 stage 3 (5m) | 11683.7899 | 27 |  | 0 | 0 | 0
8.7.8.9 | P2 stage 4 (6.46m) | 15095.4565 | 28 |  | 0 | 0 | 0
8.7.8.10 | P2 stage 5 (3.2m) | 7477.6255 | 28 |  | 0 | 0 | 0
8.7.8.11 | P3 stage 1 (2.2m) | 5140.8675 | 27 |  | 0 | 0 | 0
8.7.8.12 | P3 stage 2 (2m) | 4673.516 | 27 |  | 0 | 0 | 0
8.7.8.13 | P3 stage 3 (5m) | 11683.7899 | 28 |  | 0 | 0 | 0
8.7.8.14 | P3 stage 4 (5m) | 11683.7899 | 28 |  | 0 | 0 | 0
8.7.8.15 | P3 stage 5 (4.28m) | 10001.3241 | 29 |  | 0 | 0 | 0
8.7.8.16 | P3 stage 6 (3.2m) | 7477.6255 | 29 |  | 0 | 0 | 0
8.7.8.17 | P4 stage 1 (2.2m) | 5140.8675 | 27 |  | 0 | 0 | 0
8.7.8.18 | P4 stage 2 (2m) | 4673.516 | 27 |  | 0 | 0 | 0
8.7.8.19 | P4 stage 3 (5m) | 11683.7899 | 28 |  | 0 | 0 | 0
8.7.8.20 | P4 stage 4 (5m) | 11683.7899 | 28 |  | 0 | 0 | 0
8.7.8.21 | P4 stage 5 (4.28m) | 10001.3241 | 29 |  | 0 | 0 | 0
8.7.8.22 | P4 stage 6 (3.2m) | 7477.6255 | 29 |  | 0 | 0 | 0
8.7.8.23 | P5 stage 1 (2.2m) | 5140.8675 | 28 |  | 0 | 0 | 0
8.7.8.24 | P5 stage 2 (2m) | 4673.516 | 28 |  | 0 | 0 | 0
8.7.8.25 | P5 stage 3 (5m) | 11683.7899 | 28 |  | 0 | 0 | 0
8.7.8.26 | P5 stage 4 (5m) | 11683.7899 | 29 |  | 0 | 0 | 0
8.7.8.27 | P5 stage 5 (2.98m) | 6963.5388 | 29 |  | 0 | 0 | 0
8.7.8.28 | P5 stage 6 (3.2m) | 7477.6255 | 29 |  | 0 | 0 | 0
8.7.8.29 | P6 stage 1 (2.2m) | 5140.8675 | 28 |  | 0 | 0 | 0
8.7.8.30 | P6 stage 2 (2m) | 4673.516 | 28 |  | 0 | 0 | 0
8.7.8.31 | P6 stage 3 (5m) | 11683.7899 | 29 |  | 0 | 0 | 0
8.7.8.32 | P6 stage 4 (4.68m) | 10936.0273 | 29 |  | 0 | 0 | 0
8.7.8.33 | P6 stage 5 (3.2m) | 7477.6255 | 29 |  | 0 | 0 | 0
8.7.8.34 | P7 stage 1 (1.2m) | 2804.1096 | 29 |  | 0 | 0 | 0
8.7.8.35 | P7 stage 2 (2m) | 4673.516 | 29 |  | 0 | 0 | 0
8.7.8.36 | P7 stage 3 (6.1m) | 14254.2236 | 30 |  | 0 | 0 | 0
8.7.8.37 | P7 stage 4 (3.2m) | 7477.6255 | 30 |  | 0 | 0 | 0
8.7.8.38 | P8 stage 1 (1.2m) | 2804.1096 | 29 |  | 0 | 0 | 0
8.7.8.39 | P8 stage 2 (2m) | 4673.516 | 29 |  | 0 | 0 | 0
8.7.8.40 | P8 stage 3 (5.15m) | 12034.3036 | 30 |  | 0 | 0 | 0
8.7.8.41 | P8 stage 4 (3.2m) | 7477.6255 | 30 |  | 0 | 0 | 0
8.7.8.59 | A2 | 31099.65 | 30 |  | 0 | 0 | 0
8.7.9 | Bridge deck superstructure/ Gornji stroj mosne ploče
8.7.9.1 | A1-P1 | 93492.1 | 29 |  | 0 | 0 | 0
8.7.9.2 | P1-P2 | 115752.12 | 30 |  | 0 | 0 | 0
8.7.9.3 | P2-P3 | 115752.12 | 31 |  | 0 | 0 | 0
8.7.9.4 | P3-P4 | 115752.12 | 32 |  | 0 | 0 | 0
8.7.9.5 | P4-P5 | 115752.12 | 33 |  | 0 | 0 | 0
8.7.9.6 | P5-P6 | 115752.12 | 34 |  | 0 | 0 | 0
8.7.9.7 | P6-P7 | 115752.12 | 35 |  | 0 | 0 | 0
8.7.9.8 | P7-P8 | 115752.12 | 36 |  | 0 | 0 | 0
8.7.9.9 | P8-A2 | 93492.1 | 36 |  | 0 | 0 | 0
8.7.10 | Bridge deck prestressing/ Prednaprezanje mosne ploče
8.7.10.1 | A1-P1 | 10388.01 | 30 |  | 0 | 0 | 0
8.7.10.2 | P1-P2 | 12861.35 | 31 |  | 0 | 0 | 0
8.7.10.3 | P2-P3 | 12861.35 | 32 |  | 0 | 0 | 0
8.7.10.4 | P3-P4 | 12861.35 | 33 |  | 0 | 0 | 0
8.7.10.5 | P4-P5 | 12861.35 | 34 |  | 0 | 0 | 0
8.7.10.6 | P5-P6 | 12861.35 | 35 |  | 0 | 0 | 0
8.7.10.7 | P6-P7 | 12861.35 | 35 |  | 0 | 0 | 0
8.7.10.8 | P7-P8 | 12861.35 | 36 |  | 0 | 0 | 0
8.7.10.9 | P8-A2 | 10388.01 | 36 |  | 0 | 0 | 0
8.7.11 | Bridge furniture/ Mosna estetika
8.7.11.1 | 50 m | 63478.17 | 33 |  | 0 | 0 | 0
8.7.11.2 | 100 m | 63478.17 | 34 |  | 0 | 0 | 0
8.7.11.3 | 150 m | 63478.17 | 35 |  | 0 | 0 | 0
8.7.11.4 | 200 m | 63478.17 | 36 |  | 0 | 0 | 0
8.7.11.5 | 224 m | 30469.52 | 37 |  | 0 | 0 | 0
8.7.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
8.7.12.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/ hidroizolacija | 91736.11 | 36 |  | 0 | 0 | 0
8.7.12.2 | Asphalt layer/ Sloj asfalta 2 + joints/ spojnice | 22167.89 | 37 |  | 0 | 0 | 0
| Sub Total / Suma stavke 8.7 | 3846801 |  |  | 0 | 0 | 0
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 08 | 34786224.28 |  |  | 0 | 0 | 0

## COST CENTER 09
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
COST CENTER 09/TROŠKOVNI CENTAR 09 rev Tunnel and Open Route
Cost center No./ Troškovno mjesto Br. | 09 | Subsection/ Podsekcija 3.2 (LK24+778.00-LK26+502.72,RK24+915.00-RK26+557.71)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost center/ Troškovno mjesto 9.1 | Construction of tunnel/ Izgradnja tunela Mrki Krs (LK 42+778000- LK 25+495.00, RK 24+915.000-RK 25+507.000)
Completion of/ Završetak:
9.1.1 | Portal construction/ Izgradnja portala
9.1.1.1 | 20% complete/ završeno (portal 1) | 81682.4726 | 17 |  | 0 | 0 | 0
9.1.1.2 | 40% complete/ završeno (portal 2) | 81682.4726 | 17 |  | 0 | 0 | 0
9.1.1.3 | 60% complete/ završeno (portal 3) | 81682.4726 | 18 |  | 0 | 0 | 0
9.1.1.4 | 80% complete/ završeno (portal 4) | 81682.4726 | 18 |  | 0 | 0 | 0
9.1.1.5 | 85% (portal 1 complete/ završen) | 20420.6181 | 40 |  | 0 | 0 | 0
9.1.1.6 | 90% (portal 2 complete/ završen) | 20420.6181 | 40 |  | 0 | 0 | 0
9.1.1.7 | 95% (portal 3 complete/ završen) | 20420.6181 | 40 |  | 0 | 0 | 0
9.1.1.8 | 100% (portal 4 complete/ završen) | 20420.6181 | 40 |  | 0 | 0 | 0
9.1.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
9.1.2.1 | 40 m (S-L, LK24+790 - LK24+830) | 310670.2272 | 19 | 27 | 310670.23 | 0 | 310670.23
9.1.2.2 | 80 m (S-L, LK24+830 - LK24+870) | 310670.2272 | 20 | 28 | 310670.23 | 0 | 310670.23
9.1.2.3 | 120 m (S-L, LK24+870 - LK24+910) | 310670.2272 | 20 | 28 | 310670.23 | 0 | 310670.23
9.1.2.4 | 160 m (S-R, RK24+927 - RK24+967) | 310670.2272 | 21 | 28 | 310670.23 | 0 | 310670.23
9.1.2.5 | 200 m (S-R, RK24+967 - RK25+007) | 310670.2272 | 21 | 28 | 310670.23 | 0 | 310670.23
9.1.2.6 | 220 m (S-L, LK24+910 - LK24+930) | 165876.2361 | 22 | 29 | 165876.2361 | 0 | 165876.2361
9.1.2.7 | 240 m (S-L, LK24+930 - LK24+950) | 165876.2361 | 22 | 29 | 165876.2361 | 0 | 165876.2361
9.1.2.8 | 260 m | 165876.2361 | 22 |  | 0 | 0 | 0
9.1.2.9 | 280 m | 165876.2361 | 22 |  | 0 | 0 | 0
9.1.2.10 | 300 m (S-R.RK25+007- RK25+027) | 165876.2361 | 22 | 29 | 165876.2361 | 0 | 165876.2361
9.1.2.11 | 320 m (S-R.RK25+027- RK25+047) | 165876.2361 | 23 | 29 | 165876.2361 | 0 | 165876.2361
9.1.2.12 | 340 m (S-R.RK25+047- RK25+067) | 165876.2361 | 23 | 29 | 165876.2361 | 0 | 165876.2361
9.1.2.13 | 360 m (S-R.RK25+067- RK25+087) | 165876.2361 | 23 | 29 | 165876.2361 | 0 | 165876.2361
9.1.2.14 | 380 m (S-R.RK25+087- RK25+107) | 165876.2361 | 23 | 29 | 165876.2361 | 0 | 165876.2361
9.1.2.15 | 400 m (S-R.RK25+107- RK25+127) | 165876.2361 | 24 | 29 | 165876.2361 | 0 | 165876.2361
9.1.2.16 | 420 m (S-R, RK25+127- RK25+147) | 165876.2361 | 24 | 29 | 165876.2361 | 0 | 165876.2361
9.1.2.17 | 440 m (S-R, RK25+147- RK25+167) | 165876.2361 | 24 | 29 | 165876.2361 | 0 | 165876.2361
9.1.2.18 | 460 m (S-L,LK24+990 - LK25+010) | 165876.2361 | 24 | 30 | 0 | 165876.2361 | 165876.2361
9.1.2.19 | 480 m (S-L,LK25+010 - LK25+030) | 165876.2361 | 25 | 30 | 0 | 165876.2361 | 165876.2361
9.1.2.20 | 500 m | 165876.2361 | 25 |  | 0 | 0 | 0
9.1.2.21 | 520 m | 165876.2361 | 25 |  | 0 | 0 | 0
9.1.2.22 | 540 m | 165876.2361 | 25 |  | 0 | 0 | 0
9.1.2.23 | 560 m | 165876.2361 | 26 |  | 0 | 0 | 0
9.1.2.24 | 580 m | 165876.2361 | 26 |  | 0 | 0 | 0
9.1.2.25 | 600 m (S-R,RK25+207- RK25+227) | 165876.2361 | 26 | 30 | 0 | 165876.2361 | 165876.2361
9.1.2.26 | 620 m (S-R,RK25+227 - RK25+247) | 165876.2361 | 26 | 30 | 0 | 165876.2361 | 165876.2361
9.1.2.27 | 640 m | 165876.2361 | 27 |  | 0 | 0 | 0
9.1.2.28 | 660 m | 165876.2361 | 27 |  | 0 | 0 | 0
9.1.2.29 | 680 m | 165876.2361 | 27 |  | 0 | 0 | 0
9.1.2.30 | 700 m | 165876.2361 | 27 |  | 0 | 0 | 0
9.1.2.31 | 720 m | 165876.2361 | 28 |  | 0 | 0 | 0
9.1.2.32 | 740 m | 165876.2361 | 28 |  | 0 | 0 | 0
9.1.2.33 | 760 m | 165876.2361 | 28 |  | 0 | 0 | 0
9.1.2.34 | 780 m | 165876.2361 | 28 |  | 0 | 0 | 0
9.1.2.35 | 800 m | 165876.2361 | 29 |  | 0 | 0 | 0
9.1.2.36 | 820 m | 165876.2361 | 29 |  | 0 | 0 | 0
9.1.2.37 | 840 m | 165876.2361 | 29 |  | 0 | 0 | 0
9.1.2.38 | 860 m | 165876.2361 | 29 |  | 0 | 0 | 0
9.1.2.39 | 880 m | 165876.2361 | 30 |  | 0 | 0 | 0
9.1.2.40 | 900 m | 165876.2361 | 30 |  | 0 | 0 | 0
9.1.2.41 | 920 m | 165876.2361 | 30 |  | 0 | 0 | 0
9.1.2.42 | 940 m | 165876.2361 | 30 |  | 0 | 0 | 0
9.1.2.43 | 960 m | 165876.2361 | 31 |  | 0 | 0 | 0
9.1.2.44 | 980 m | 165876.2361 | 31 |  | 0 | 0 | 0
9.1.2.45 | 1000 m | 165876.2361 | 31 |  | 0 | 0 | 0
9.1.2.46 | 1020 m | 165876.2361 | 31 |  | 0 | 0 | 0
9.1.2.47 | 1040 m | 165876.2361 | 32 |  | 0 | 0 | 0
9.1.2.48 | 1060 m | 165876.2361 | 32 |  | 0 | 0 | 0
9.1.2.49 | 1080 m | 165876.2361 | 32 |  | 0 | 0 | 0
9.1.2.50 | 1100 m | 165876.2361 | 32 |  | 0 | 0 | 0
9.1.2.51 | 1120 m | 165876.2361 | 33 |  | 0 | 0 | 0
9.1.2.52 | 1140 m | 165876.2361 | 33 |  | 0 | 0 | 0
9.1.2.53 | 1160 m | 165876.2361 | 33 |  | 0 | 0 | 0
9.1.2.54 | 1180 m | 165876.2361 | 33 |  | 0 | 0 | 0
9.1.2.55 | 1200 m | 165876.2361 | 34 |  | 0 | 0 | 0
9.1.2.56 | 1220 m | 165876.2361 | 34 |  | 0 | 0 | 0
9.1.2.57 | 1240 m | 165876.2361 | 34 |  | 0 | 0 | 0
9.1.2.58 | 1261 m | 174170.0479 | 34 |  | 0 | 0 | 0
9.1.3 | Construction of waterproofing and drainage & Construction of secondary lining/ Konstrukcija hidroizolacije i drenaže & Konstrukcija sekundarne obloge
9.1.3.1 | 20 m | 106134.4336 | 20 |  | 0 | 0 | 0
9.1.3.2 | 40 m | 106134.4336 | 20 |  | 0 | 0 | 0
9.1.3.3 | 60 m | 106134.4336 | 20 |  | 0 | 0 | 0
9.1.3.4 | 80 m | 106134.4336 | 21 |  | 0 | 0 | 0
9.1.3.5 | 100 m | 106134.4336 | 21 |  | 0 | 0 | 0
9.1.3.6 | 120 m | 106134.4336 | 21 |  | 0 | 0 | 0
9.1.3.7 | 140 m | 106134.4336 | 21 |  | 0 | 0 | 0
9.1.3.8 | 160 m | 106134.4336 | 22 |  | 0 | 0 | 0
9.1.3.9 | 180 m | 106134.4336 | 22 |  | 0 | 0 | 0
9.1.3.10 | 200 m | 106134.4336 | 22 |  | 0 | 0 | 0
9.1.3.11 | 220 m | 106134.4336 | 22 |  | 0 | 0 | 0
9.1.3.12 | 240 m | 106134.4336 | 23 |  | 0 | 0 | 0
9.1.3.13 | 260 m | 106134.4336 | 23 |  | 0 | 0 | 0
9.1.3.14 | 280 m | 106134.4336 | 23 |  | 0 | 0 | 0
9.1.3.15 | 300 m | 106134.4336 | 23 |  | 0 | 0 | 0
9.1.3.16 | 320 m | 106134.4336 | 24 |  | 0 | 0 | 0
9.1.3.17 | 340 m | 106134.4336 | 24 |  | 0 | 0 | 0
9.1.3.18 | 360 m | 106134.4336 | 24 |  | 0 | 0 | 0
9.1.3.19 | 380 m | 106134.4336 | 24 |  | 0 | 0 | 0
9.1.3.20 | 400 m | 106134.4336 | 25 |  | 0 | 0 | 0
9.1.3.21 | 420 m | 106134.4336 | 25 |  | 0 | 0 | 0
9.1.3.22 | 440 m | 106134.4336 | 25 |  | 0 | 0 | 0
9.1.3.23 | 460 m | 106134.4336 | 25 |  | 0 | 0 | 0
9.1.3.24 | 480 m | 106134.4336 | 26 |  | 0 | 0 | 0
9.1.3.25 | 500 m | 106134.4336 | 26 |  | 0 | 0 | 0
9.1.3.26 | 520 m | 106134.4336 | 26 |  | 0 | 0 | 0
9.1.3.27 | 540 m | 106134.4336 | 26 |  | 0 | 0 | 0
9.1.3.28 | 560 m | 106134.4336 | 27 |  | 0 | 0 | 0
9.1.3.29 | 580 m | 106134.4336 | 27 |  | 0 | 0 | 0
9.1.3.30 | 600 m | 106134.4336 | 27 |  | 0 | 0 | 0
9.1.3.31 | 620 m | 106134.4336 | 27 |  | 0 | 0 | 0
9.1.3.32 | 640 m | 106134.4336 | 28 |  | 0 | 0 | 0
9.1.3.33 | 660 m | 106134.4336 | 28 |  | 0 | 0 | 0
9.1.3.34 | 680 m | 106134.4336 | 28 |  | 0 | 0 | 0
9.1.3.35 | 700 m | 106134.4336 | 28 |  | 0 | 0 | 0
9.1.3.36 | 720 m | 106134.4336 | 29 |  | 0 | 0 | 0
9.1.3.37 | 740 m | 106134.4336 | 29 |  | 0 | 0 | 0
9.1.3.38 | 760 m | 106134.4336 | 29 |  | 0 | 0 | 0
9.1.3.39 | 780 m | 106134.4336 | 29 |  | 0 | 0 | 0
9.1.3.40 | 800 m | 106134.4336 | 30 |  | 0 | 0 | 0
9.1.3.41 | 820 m | 106134.4336 | 30 |  | 0 | 0 | 0
9.1.3.42 | 840 m | 106134.4336 | 30 |  | 0 | 0 | 0
9.1.3.43 | 860 m | 106134.4336 | 30 |  | 0 | 0 | 0
9.1.3.44 | 880 m | 106134.4336 | 31 |  | 0 | 0 | 0
9.1.3.45 | 900 m | 106134.4336 | 31 |  | 0 | 0 | 0
9.1.3.46 | 920 m | 106134.4336 | 31 |  | 0 | 0 | 0
9.1.3.47 | 940 m | 106134.4336 | 31 |  | 0 | 0 | 0
9.1.3.48 | 960 m | 106134.4336 | 32 |  | 0 | 0 | 0
9.1.3.49 | 980 m | 106134.4336 | 32 |  | 0 | 0 | 0
9.1.3.50 | 1000 m | 106134.4336 | 32 |  | 0 | 0 | 0
9.1.3.51 | 1020 m | 106134.4336 | 32 |  | 0 | 0 | 0
9.1.3.52 | 1040 m | 106134.4336 | 34 |  | 0 | 0 | 0
9.1.3.53 | 1060 m | 106134.4336 | 34 |  | 0 | 0 | 0
9.1.3.54 | 1080 m | 106134.4336 | 34 |  | 0 | 0 | 0
9.1.3.55 | 1100 m | 106134.4336 | 34 |  | 0 | 0 | 0
9.1.3.56 | 1120 m | 106134.4336 | 35 |  | 0 | 0 | 0
9.1.3.57 | 1140 m | 106134.4336 | 35 |  | 0 | 0 | 0
9.1.3.58 | 1160 m | 106134.4336 | 35 |  | 0 | 0 | 0
9.1.3.59 | 1180 m | 106134.4336 | 35 |  | 0 | 0 | 0
9.1.3.60 | 1200 m | 106134.4336 | 36 |  | 0 | 0 | 0
9.1.3.61 | 1220 m | 106134.4336 | 36 |  | 0 | 0 | 0
9.1.3.62 | 1240 m | 106134.4336 | 36 |  | 0 | 0 | 0
9.1.3.63 | 1261 m | 111441.15 | 36 |  | 0 | 0 | 0
9.1.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi I ploca, drenazni sistem)
9.1.4.1 | 200 m | 80000 | 25 |  | 0 | 0 | 0
9.1.4.2 | 400 m | 80000 | 27 |  | 0 | 0 | 0
9.1.4.3 | 600 m | 80000 | 29 |  | 0 | 0 | 0
9.1.4.4 | 800 m | 80000 | 32 |  | 0 | 0 | 0
9.1.4.5 | 1000 m | 80000 | 35 |  | 0 | 0 | 0
9.1.4.6 | 1200 m | 80000 | 38 |  | 0 | 0 | 0
9.1.4.7 | 1261 m | 24400 | 39 |  | 0 | 0 | 0
9.1.5 | Construction of pavement/ Izgradnja kolovoza
9.1.5.1 | Left tube/ Lijeva cijev
0-500 m
9.1.5.1.1 | Layer/ Sloj 1 | 39061.6541 | 38 |  | 0 | 0 | 0
9.1.5.1.2 | Layer/ Sloj 2 | 39061.6541 | 39 |  | 0 | 0 | 0
9.1.5.1.3 | Layer/ Sloj 3 | 43944.3703 | 39 |  | 0 | 0 | 0
500-837 m
9.1.5.1.4 | Layer/ Sloj 1 | 26327.56 | 38 |  | 0 | 0 | 0
9.1.5.1.5 | Layer/ Sloj 2 | 26327.56 | 39 |  | 0 | 0 | 0
9.1.5.1.6 | Layer/ Sloj 3 | 29618.4942 | 39 |  | 0 | 0 | 0
9.1.5.2 | Right tube/ Desna cijev
0-598 m
9.1.5.2.1 | Layer/ Sloj 1 | 46717.7428 | 38 |  | 0 | 0 | 0
9.1.5.2.2 | Layer/ Sloj 2 | 46717.7428 | 39 |  | 0 | 0 | 0
9.1.5.2.3 | Layer/ Sloj 3 | 52557.4647 | 39 |  | 0 | 0 | 0
9.1.6 | Tunnel facilities/ Tunelski objekti
9.1.6.1 | Construction of Power Station/ Izgradnja elektro-stanice | 269832.3429 | 41 |  | 0 | 0 | 0
9.1.6.2 | Construction of antifire reservoir/ Izgradnja protivpožarnog rezervoara | 93477.7339 | 41 |  | 0 | 0 | 0
9.1.7 | Tunnel Equipment/ Tunelska oprema
9.1.7.1 | Right tube/ Desna cijev | 0
9.1.7.1.1 | 90% (Equipment installed/Oprema postavljena) | 647132.204 | 41 |  | 0 | 0 | 0
9.1.7.1.2 | 10% (Equipment tested/Oprema ispitana) | 71903.5782 | 41 |  | 0 | 0 | 0
9.1.7.2 | Left tube/ Lijeva cijev | 0
9.1.7.2.1 | 90% (Equipment installed/Oprema postavljena) | 897367.4989 | 41 |  | 0 | 0 | 0
9.1.7.2.2 | 10% (Equipment tested/Oprema ispitana) | 99707.5035 | 41 |  | 0 | 0 | 0
| Sub Total / Suma stavke 9.1 | 20387428.962 |  |  | 3212113.5108 | 663504.9443 | 3875618.4551
Cost center/ Troškovno mjesto 9.2 | Road Works/Radovi na putevima (LK25+495.00—LK25+828.000, RK25+507.000—RK25+955.000)
Completion of/Završetak:
9.2.1 | Subgrade/ Posteljica
9.2.1.1 | Top soil removal/ Uklanjanje humusa
9.2.1.1.1 | RK25+507.000—RK25+757.000 (Inc.0 - 250 m (LK&RK)) | 45917.0551 | 23 |  | 0 | 0 | 0
9.2.1.1.2 | RK25+757.000—RK25+955.000 (Inc.250 - 333.000 m (LK); 250 - 448.000 m (RK)) | 25805.3849 | 24 |  | 0 | 0 | 0
9.2.1.2 | Earthworks/ Zemljani radovi |  | 35
At every 250 m and 4m height/Na svakih 250m i 4m visini
9.2.1.2.1.1 | RK25+507 - RK25+757 layers 1,2,3,4,5,6,7,8,9,10,11,12,13,14
9.2.1.2.1.1.1 | RK25+507 - RK25+757 layers 1 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.2 | RK25+507 - RK25+757 layers 2 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.3 | RK25+507 - RK25+757 layers 3 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.4 | RK25+507 - RK25+757 layers 4 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.5 | RK25+507 - RK25+757 layers 5 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.6 | RK25+507 - RK25+757 layers 6 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.7 | RK25+507 - RK25+757 layers 7 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.8 | RK25+507 - RK25+757 layers 8 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.9 | RK25+507 - RK25+757 layers 9 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.10 | RK25+507 - RK25+757 layers 10 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.11 | RK25+507 - RK25+757 layers 11 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.12 | RK25+507 - RK25+757 layers 12 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.13 | RK25+507 - RK25+757 layers 13 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.1.14 | RK25+507 - RK25+757 layers 14 | 10350.2197 |  |  | 0 | 0 | 0
9.2.1.2.1.2 | RK25+757 - RK25+955 Layers 15,16,17,18,19,20,21,22,23,24,25,26
9.2.1.2.1.2.15 | RK25+757 - RK25+955 Layers 15 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.2.16 | RK25+757 - RK25+955 Layers 16 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.2.17 | RK25+757 - RK25+955 Layers 17 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.2.18 | RK25+757 - RK25+955 Layers 18 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.2.19 | RK25+757 - RK25+955 Layers 19 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.2.20 | RK25+757 - RK25+955 Layers 20 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.2.21 | RK25+757 - RK25+955 Layers 21 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.2.22 | RK25+757 - RK25+955 Layers 22 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.2.23 | RK25+757 - RK25+955 Layers 23 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.2.24 | RK25+757 - RK25+955 Layers 24 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.2.25 | RK25+757 - RK25+955 Layers 25 | 38692.4102 |  |  | 0 | 0 | 0
9.2.1.2.1.2.26 | RK25+757 - RK25+955 Layers 26 | 9866.5646 |  |  | 0 | 0 | 0
9.2.1.3 | Road Foundation/ Temelj puta
9.2.1.3.1 | 0 - 250 m right side/ desna strana | 18218.4923 | 36 |  | 0 | 0 | 0
9.2.1.3.2 | 0 - 250 m left side/ lijeva strana | 18218.4923 | 36 |  | 0 | 0 | 0
9.2.1.3.3 | 250 - 448.000 m right side/ desna strana | 14429.0459 | 37 |  | 0 | 0 | 0
9.2.1.3.4 | 250 - 333.000 m left side/ lijeva strana | 6048.5394 | 37 |  | 0 | 0 | 0
9.2.2 | Engineering structures/ Inženjerske konstrukcije
9.2.2.1 | Concrete wall / Betonski zid
80% for the concrete wall, the milestone is 50m length, no matter the height+ 5% for the "after work" the whole length of each retaining wall + 5% for the "correction of the crown" the whole length of each retaining wall+10% for the "wall surface" the whole length of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
9.2.2.1.1 | Concrete wall/ Betonski zid LK25+486.000-LK25+534.64 (48.64m)
9.2.2.1.1.1 | Concrete wall/ Betonski zid LK25+486.000-LK25+534.64 - 80% | 44662.5097 |  |  | 0 | 0 | 0
9.2.2.1.1.2 | Concrete wall/ Betonski zidLK25+486.000-LK25+534.64 After work 5% | 2791.4069 |  |  | 0 | 0 | 0
9.2.2.1.1.3 | Concrete wall/ Betonski zidLK25+486.000-LK25+534.64 Correction of the crown 5% | 2791.4069 |  |  | 0 | 0 | 0
9.2.2.1.1.4 | Concrete wall/ Betonski zidLK25+486.000-LK25+534.64 10% Wall surface | 5582.8137 |  |  | 0 | 0 | 0
9.2.2.1.2 | Concrete wall/ Betonski zid LK25+538.38-LK25+601.34 (62.96m) 80%, Layers 1,2
9.2.2.1.2.1 | Segment 1 LK25+538.38 ~ LK25+588.38 (50m) | 45911.297 |  |  | 0 | 0 | 0
9.2.2.1.2.2 | Segment 2 LK25+588.38 ~ LK25+601.34 (12.96m) | 11900.2082 |  |  | 0 | 0 | 0
9.2.2.1.2.3 | Concrete wall/ Betonski zid LK25+538.38-LK25+601.34 After work 5% | 3613.2191 |  |  | 0 | 0 | 0
9.2.2.1.2.4 | Concrete wall/ Betonski zid LK25+538.38-LK25+601.34 Correction of the crown 5% | 3613.2191 |  |  | 0 | 0 | 0
9.2.2.1.2.5 | Concrete wall/ Betonski zid LK25+538.38-LK25+601.34 - 10% Wall surface | 7226.4381
9.2.2.1.3 | Concrete wall/ Betonski zid LK25+604.38-LK25+740.00 (135.62m) - 80%, Layers 1,2,3,4
9.2.2.1.3.1 | Segment 1 LK25+604.38 ~ LK25+654.38 (50m) | 45911.297 |  |  | 0 | 0 | 0
9.2.2.1.3.2 | Segment 2 LK25+654.38 ~ LK25+704.38 (50m) | 45911.297 |  |  | 0 | 0 | 0
9.2.2.1.3.3 | Segment 3 LK25+704.38 ~ LK25+740.00 (35.62m) | 32707.208 |  |  | 0 | 0 | 0
9.2.2.1.3.4 | Concrete wall/ Betonski zid LK25+604.38-LK25+740.00 - After work 5% | 7783.1126 |  |  | 0 | 0 | 0
9.2.2.1.3.5 | Concrete wall/ Betonski zid LK25+604.38-LK25+740.00 - Correction of the crown 5% | 7783.1126 |  |  | 0 | 0 | 0
9.2.2.1.3.6 | Concrete wall/ Betonski zid LK25+604.38-LK25+740.00 - 10% Wall surface | 15566.2252 |  |  | 0 | 0 | 0
9.2.2.1.4 | Concrete wall/ Betonski zid LK25+755-LK25+828 (73m) - 80%, Layers 1,2,3
9.2.2.1.4.1 | Segment 1 LK25+755 ~ LK25+805 (50m) | 45911.297 |  |  | 0 | 0 | 0
9.2.2.1.4.2 | Segment 2 LK25+805 ~ LK25+828 (23m) | 21119.1966 |  |  | 0 | 0 | 0
9.2.2.1.4.3 | Concrete wall/ Betonski zid LK25+755-LK25+828 - After work 5% | 4189.4059 |  |  | 0 | 0 | 0
9.2.2.1.4.4 | Concrete wall/ Betonski zid LK25+755-LK25+828 - Correction of the crown 5% | 4189.4059 |  |  | 0 | 0 | 0
9.2.2.1.4.5 | Concrete wall/ Betonski zid LK25+755-LK25+828 - 10% Wall surface | 8378.8117 |  |  | 0 | 0 | 0
9.2.2.1.5 | Concrete wall/ Betonski zid LK25+870-LK25+955 (85m) - 80%, Layers 1,2,3
9.2.2.1.5.1 | Segment 1 LK25+870 ~ LK25+920 (50m) | 45911.297 |  |  | 0 | 0 | 0
9.2.2.1.5.2 | Segment2 LK25+920 ~ LK25+955 (35m) | 32137.9079 |  |  | 0 | 0 | 0
9.2.2.1.5.3 | Concrete wall/ Betonski zid LK25+870-LK25+955 - After work 5% | 4878.0753 |  |  | 0 | 0 | 0
9.2.2.1.5.4 | Concrete wall/ Betonski zid LK25+870-LK25+955 - Correction of the crown 5% | 4878.0753 |  |  | 0 | 0 | 0
9.2.2.1.5.5 | Concrete wall/ Betonski zid LK25+870-LK25+955 - 10% Wall surface | 9756.1506 |  |  | 0 | 0 | 0
9.2.2.1.6 | Concrete wall/ Betonski zid RK25+874.044-RK25+909.95 (35.906m)
9.2.2.1.6.1 | Concrete wall/ Betonski zid RK25+874.044-RK25+909.95 - 80% | 32969.8206 |  |  | 0 | 0 | 0
9.2.2.1.6.2 | Concrete wall/ Betonski zid RK25+874.044-RK25+909.95 - After work 5% | 2060.6138 |  |  | 0 | 0 | 0
9.2.2.1.6.3 | Concrete wall/ Betonski zid RK25+874.044-RK25+909.95 - Correction of the crown 5% | 2060.6138 |  |  | 0 | 0 | 0
9.2.2.1.6.4 | Concrete wall/ Betonski zid RK25+874.044-RK25+909.95 - 10% Wall surface | 4121.2276 |  |  | 0 | 0 | 0
9.2.2.2 | Reinforced earth wall (it will be splitted after MD approval)/ Ojačani zemljani zid (biće podijeljen nakon odobrenja GP)
The milestone is 2.20 m height of each layer and no matter on the length / Reper je visina 2.2m za svaki sloj, bez obzira na dužinu
Reinforced soil retaining wall / Potporni zid od armirane zemlje RK25+523-RK25+865
| Layer/Sloj 1 (0.0 -2.2 m height) | 125714.0238 |  |  | 0 | 0 | 0
| Layer/Sloj 2 (2.2 -4.4 m height) | 125714.0238 |  |  | 0 | 0 | 0
| Layer/Sloj 3 (4.4 -6.6 m height) | 125714.0238 |  |  | 0 | 0 | 0
| Layer/Sloj 4 (6.6 -8.8m height) | 125714.0238 |  |  | 0 | 0 | 0
| Layer/Sloj 5 (8.8 -11.0 m height) | 125714.0238 |  |  | 0 | 0 | 0
| Layer/Sloj 6 (11.0 -13.2 m height) | 125714.0238 |  |  | 0 | 0 | 0
| Layer/Sloj 7 (13.2 -15.4 m height) | 125714.0238 |  |  | 0 | 0 | 0
| Layer/Sloj 8 (15.4 -17.6 m height) | 125714.0238 |  |  | 0 | 0 | 0
| Layer/Sloj 9 (17.6 -19.8 m height) | 125714.0238 |  |  | 0 | 0 | 0
| Layer/Sloj 10 (19.8 -22.0 m height) | 125714.0238 |  |  | 0 | 0 | 0
| Layer/Sloj 11 (22.0 -24.2 m height) | 125714.0238 |  |  | 0 | 0 | 0
| Layer/Sloj 12 (24.2 -26.4 m height) | 125714.0238 |  |  | 0 | 0 | 0
| Layer/Sloj 13 (26.4 -28.6 m height) | 125714.0238 |  |  | 0 | 0 | 0
9.2.2.3 | Culvert / Propust
9.2.2.3.1 | RK25+790.66 (62m) | 1250.2603 | 22 |  | 0 | 0 | 0
9.2.2.3.2 | RK25+644.85 (62m) | 1250.2603 | 22 |  | 0 | 0 | 0
9.2.2.3.3 | RK25+578.50 (60m) | 1209.9293 | 22 |  | 0 | 0 | 0
9.2.3 | Water drainage/ Drenaža vode
per one direction of 500m /Na 500m dužine u jednom pravcu
9.2.3.1 | LK25+495.000—LK25+828.000 (333 m) | 110830.8806 | 38 |  | 0 | 0 | 0
9.2.3.2 | RK25+507.000—RK25+955.000 (448 m) | 149105.8094 | 38 |  | 0 | 0 | 0
9.2.4 | Pavement structure/ Kolovozna konstrukcija
9.2.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana | 37398 | 39 |  | 0 | 0 | 0
9.2.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana | 37398 | 39 |  | 0 | 0 | 0
9.2.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana | 37398 | 40 |  | 0 | 0 | 0
9.2.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana | 37398 | 40 |  | 0 | 0 | 0
9.2.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana | 41555.8 | 41 |  | 0 | 0 | 0
9.2.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana | 41555.8 | 41 |  | 0 | 0 | 0
| Sub Total / Suma stavke 9.2 | 3714421.36 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 9.3 | Construction of tunnel/Izgradnja tunela Durilovac (LK25+828.000- LK 26+237.000, RK 25+955.000-RK 26+345.000)
Completion of/Završetak:
9.3.1 | Portal construction/ Izgradnja portala
9.3.1.1 | 20% complete/ završeno (portal 1) | 48116.72 | 25 |  | 0 | 0 | 0
9.3.1.2 | 40% complete/ završeno (portal 2) | 48116.72 | 25 |  | 0 | 0 | 0
9.3.1.3 | 60% complete/ završeno (portal 3) | 48116.72 | 26 |  | 0 | 0 | 0
9.3.1.4 | 80% complete/ završeno (portal 4) | 48116.72 | 26 |  | 0 | 0 | 0
9.3.1.5 | 85% (portal 1 complete/ završen) | 12029.18 | 31 |  | 0 | 0 | 0
9.3.1.6 | 90% (portal 2 complete/ završen) | 12029.18 | 31 |  | 0 | 0 | 0
9.3.1.7 | 95% (portal 3 complete/ završen) | 12029.18 | 31 |  | 0 | 0 | 0
9.3.1.8 | 100% (portal 4 complete/ završen) | 12029.19 | 31 |  | 0 | 0 | 0
9.3.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
9.3.2.1 | 20 m | 156674.162 | 27 |  | 0 | 0 | 0
9.3.2.2 | 40 m | 156674.162 | 27 |  | 0 | 0 | 0
9.3.2.3 | 60 m | 156674.162 | 27 |  | 0 | 0 | 0
9.3.2.4 | 80 m | 156674.162 | 27 |  | 0 | 0 | 0
9.3.2.5 | 100 m | 156674.162 | 28 |  | 0 | 0 | 0
9.3.2.6 | 120 m | 156674.162 | 28 |  | 0 | 0 | 0
9.3.2.7 | 140 m | 156674.162 | 28 |  | 0 | 0 | 0
9.3.2.8 | 160 m | 156674.162 | 28 |  | 0 | 0 | 0
9.3.2.9 | 180 m | 156674.162 | 29 |  | 0 | 0 | 0
9.3.2.10 | 200 m | 156674.162 | 29 |  | 0 | 0 | 0
9.3.2.11 | 220 m | 156674.162 | 29 |  | 0 | 0 | 0
9.3.2.12 | 240 m | 156674.162 | 29 |  | 0 | 0 | 0
9.3.2.13 | 260 m | 156674.162 | 30 |  | 0 | 0 | 0
9.3.2.14 | 280 m | 156674.162 | 30 |  | 0 | 0 | 0
9.3.2.15 | 300 m | 156674.162 | 30 |  | 0 | 0 | 0
9.3.2.16 | 320 m | 156674.162 | 30 |  | 0 | 0 | 0
9.3.2.17 | 340 m | 156674.162 | 31 |  | 0 | 0 | 0
9.3.2.18 | 360 m | 156674.162 | 31 |  | 0 | 0 | 0
9.3.2.19 | 380 m | 156674.162 | 31 |  | 0 | 0 | 0
9.3.2.20 | 400 m | 156674.162 | 31 |  | 0 | 0 | 0
9.3.2.21 | 420 m | 156674.162 | 32 |  | 0 | 0 | 0
9.3.2.22 | 440 m | 156674.162 | 32 |  | 0 | 0 | 0
9.3.2.23 | 460 m | 156674.162 | 32 |  | 0 | 0 | 0
9.3.2.24 | 480 m | 156674.162 | 32 |  | 0 | 0 | 0
9.3.2.25 | 500 m | 156674.162 | 33 |  | 0 | 0 | 0
9.3.2.26 | 520 m | 156674.162 | 33 |  | 0 | 0 | 0
9.3.2.27 | 540 m | 156674.162 | 33 |  | 0 | 0 | 0
9.3.2.28 | 560 m | 156674.162 | 33 |  | 0 | 0 | 0
9.3.2.29 | 580 m | 156674.162 | 34 |  | 0 | 0 | 0
9.3.2.30 | 600 m | 156674.162 | 34 |  | 0 | 0 | 0
9.3.2.31 | 620 m | 156674.162 | 34 |  | 0 | 0 | 0
9.3.2.32 | 640 m | 156674.162 | 34 |  | 0 | 0 | 0
9.3.2.33 | 660 m | 156674.162 | 35 |  | 0 | 0 | 0
9.3.2.34 | 680 m | 156674.162 | 35 |  | 0 | 0 | 0
9.3.2.35 | 700 m | 156674.162 | 36 |  | 0 | 0 | 0
9.3.2.36 | 720 m | 156674.162 | 36 |  | 0 | 0 | 0
9.3.2.37 | 740 m | 156674.162 | 36 |  | 0 | 0 | 0
9.3.2.38 | 760 m | 156674.162 | 36 |  | 0 | 0 | 0
9.3.2.39 | 780 m | 156674.162 | 36 |  | 0 | 0 | 0
9.3.2.40 | 800 m | 156674.162 | 36 |  | 0 | 0 | 0
9.3.2.41 | 820 m | 156674.162 | 37 |  | 0 | 0 | 0
9.3.2.42 | 840 m | 156674.162 | 37 |  | 0 | 0 | 0
9.3.2.43 | 860 m | 156674.162 | 37 |  | 0 | 0 | 0
9.3.2.44 | 869 m | 70503.3729 | 37 |  | 0 | 0 | 0
9.3.3 | Construction of waterproofing and drainage & Construction of secondary lining / Konstrukcija hidroizolacije i drenaže & Konstrukcija sekundarne obloge
9.3.3.1 | 20 m | 73424.551 | 28 |  | 0 | 0 | 0
9.3.3.2 | 40 m | 73424.551 | 28 |  | 0 | 0 | 0
9.3.3.3 | 60 m | 73424.551 | 28 |  | 0 | 0 | 0
9.3.3.4 | 80 m | 73424.551 | 28 |  | 0 | 0 | 0
9.3.3.5 | 100 m | 73424.551 | 29 |  | 0 | 0 | 0
9.3.3.6 | 120 m | 73424.551 | 29 |  | 0 | 0 | 0
9.3.3.7 | 140 m | 73424.551 | 29 |  | 0 | 0 | 0
9.3.3.8 | 160 m | 73424.551 | 29 |  | 0 | 0 | 0
9.3.3.9 | 180 m | 73424.551 | 30 |  | 0 | 0 | 0
9.3.3.10 | 200 m | 73424.551 | 30 |  | 0 | 0 | 0
9.3.3.11 | 220 m | 73424.551 | 30 |  | 0 | 0 | 0
9.3.3.12 | 240 m | 73424.551 | 30 |  | 0 | 0 | 0
9.3.3.13 | 260 m | 73424.551 | 31 |  | 0 | 0 | 0
9.3.3.14 | 280 m | 73424.551 | 31 |  | 0 | 0 | 0
9.3.3.15 | 300 m | 73424.551 | 31 |  | 0 | 0 | 0
9.3.3.16 | 320 m | 73424.551 | 31 |  | 0 | 0 | 0
9.3.3.17 | 340 m | 73424.551 | 32 |  | 0 | 0 | 0
9.3.3.18 | 360 m | 73424.551 | 32 |  | 0 | 0 | 0
9.3.3.19 | 380 m | 73424.551 | 32 |  | 0 | 0 | 0
9.3.3.20 | 400 m | 73424.551 | 32 |  | 0 | 0 | 0
9.3.3.21 | 420 m | 73424.551 | 33 |  | 0 | 0 | 0
9.3.3.22 | 440 m | 73424.551 | 33 |  | 0 | 0 | 0
9.3.3.23 | 460 m | 73424.551 | 33 |  | 0 | 0 | 0
9.3.3.24 | 480 m | 73424.551 | 33 |  | 0 | 0 | 0
9.3.3.25 | 500 m | 73424.551 | 34 |  | 0 | 0 | 0
9.3.3.26 | 520 m | 73424.551 | 34 |  | 0 | 0 | 0
9.3.3.27 | 540 m | 73424.551 | 34 |  | 0 | 0 | 0
9.3.3.28 | 560 m | 73424.551 | 34 |  | 0 | 0 | 0
9.3.3.29 | 580 m | 73424.551 | 35 |  | 0 | 0 | 0
9.3.3.30 | 600 m | 73424.551 | 35 |  | 0 | 0 | 0
9.3.3.31 | 620 m | 73424.551 | 36 |  | 0 | 0 | 0
9.3.3.32 | 640 m | 73424.551 | 36 |  | 0 | 0 | 0
9.3.3.33 | 660 m | 73424.551 | 36 |  | 0 | 0 | 0
9.3.3.34 | 680 m | 73424.551 | 36 |  | 0 | 0 | 0
9.3.3.35 | 700 m | 73424.551 | 36 |  | 0 | 0 | 0
9.3.3.36 | 720 m | 73424.551 | 36 |  | 0 | 0 | 0
9.3.3.37 | 740 m | 73424.551 | 37 |  | 0 | 0 | 0
9.3.3.38 | 760 m | 73424.551 | 37 |  | 0 | 0 | 0
9.3.3.39 | 780 m | 73424.551 | 37 |  | 0 | 0 | 0
9.3.3.40 | 800 m | 73424.551 | 37 |  | 0 | 0 | 0
9.3.3.41 | 820 m | 73424.551 | 37 |  | 0 | 0 | 0
9.3.3.42 | 840 m | 73424.551 | 38 |  | 0 | 0 | 0
9.3.3.43 | 860 m | 73424.551 | 38 |  | 0 | 0 | 0
9.3.3.44 | 869 m | 33041.0479 | 38 |  | 0 | 0 | 0
9.3.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi I ploca, drenazni sistem)
9.3.4.1 | 200 | 80000 | 31 |  | 0 | 0 | 0
9.3.4.2 | 400 | 80000 | 33 |  | 0 | 0 | 0
9.3.4.3 | 600 | 80000 | 36 |  | 0 | 0 | 0
9.3.4.4 | 800 | 80000 | 38 |  | 0 | 0 | 0
9.3.4.5 | 869 | 27600 | 39 |  | 0 | 0 | 0
9.3.5 | Construction of pavement/ Izgradnja kolovoza
9.3.5.1 | Left tube/ Lijeva cijev
0-548 m
9.3.5.1.1 | Layer/ Sloj 1 | 40204.28 | 38 |  | 0 | 0 | 0
9.3.5.1.2 | Layer/ Sloj 2 | 40204.28 | 38 |  | 0 | 0 | 0
9.3.5.1.3 | Layer/ Sloj 3 | 45229.81 | 38 |  | 0 | 0 | 0
9.3.5.2 | Right tube/ Desna cijev
0-475 m
9.3.5.2.1 | Layer/ Sloj 1 | 34848.6 | 38 |  | 0 | 0 | 0
9.3.5.2.2 | Layer/ Sloj 2 | 34848.6 | 38 |  | 0 | 0 | 0
9.3.5.2.3 | Layer/ Sloj 3 | 39204.68 | 38 |  | 0 | 0 | 0
9.3.6 | Tunnel facilities/ Tunelski objekti
9.3.6.1 | Construction of Power Station/ Izgradnja elektro-stanice | 249149.36 | 40 |  | 0 | 0 | 0
9.3.6.2 | Construction of antifire reservoir/ Izgradnja protivpožarnog rezervoara | 86312.55 | 40 |  | 0 | 0 | 0
9.3.7 | Tunnel Equipment/ Tunelska oprema
9.3.7.1 | Right tube/ Desna cijev
9.3.7.1.1 | 90% (Equipment installed/Oprema postavljena) | 483427.76 | 40 |  | 0 | 0 | 0
9.3.7.1.2 | 10% (Equipment tested/Oprema ispitana) | 53714.2 | 40 |  | 0 | 0 | 0
9.3.7.2 | Left tube/ Lijeva cijev
9.3.7.2.1 | 90% (Equipment installed/Oprema postavljena) | 550577.17 | 40 |  | 0 | 0 | 0
9.3.7.2.2 | 10% (Equipment tested/Oprema ispitana) | 61175.24 | 40 |  | 0 | 0 | 0
| Sub Total / Suma stavke 9.3 | 12304869.22 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 9.4 | Road Works/Radovi na putevima (LK26+327.40—LK26+387.920, RK26+345.000—RK26+393.143)
Completion of/Završetak:
9.4.1 | Subgrade/ Posteljica
9.4.1.1 | Top soil removal/ Uklanjanje humusa
9.4.1.1.1 | RK26+345.000—RK26+393.143 (Inc.0 - 60.920 m (LK); 0 - 48.143 m(RK)) | 8164.7 | 24 |  | 0 | 0 | 0
9.4.1.2 | Earthworks/ Zemljani radovi |  | 33
At every 250 m and 4m height/Na svakih 250m i 4m visini
9.4.1.2.1 | RK26+345 - RK26+393.143 Layers 1,2,3,4,5,6,7
9.4.1.2.1.1 | RK26+345 - RK26+393.143 Layer 1 | 15710.9629 |  |  | 0 | 0 | 0
9.4.1.2.1.2 | RK26+345 - RK26+393.143 Layer 2 | 15710.9629 |  |  | 0 | 0 | 0
9.4.1.2.1.3 | RK26+345 - RK26+393.143 Layer 3 | 15710.9629 |  |  | 0 | 0 | 0
9.4.1.2.1.4 | RK26+345 - RK26+393.143 Layer 4 | 15710.9629 |  |  | 0 | 0 | 0
9.4.1.2.1.5 | RK26+345 - RK26+393.143 Layer 5 | 15710.9629 |  |  | 0 | 0 | 0
9.4.1.2.1.6 | RK26+345 - RK26+393.143 Layer 6 | 15710.9629 |  |  | 0 | 0 | 0
9.4.1.2.1.7 | RK26+345 - RK26+393.143 Layer 7 | 13747.0925 |  |  | 0 | 0 | 0
9.4.1.3 | Road Foundation/ Temelj puta
9.4.1.3.1 | 0 - 48.143 m right side/ desna strana | 3239.51 | 34 |  | 0 | 0 | 0
9.4.1.3.2 | 0 - 60.920 m left side/ lijeva strana | 3239.5 | 34 |  | 0 | 0 | 0
9.4.2 | Engineering structures/ Inženjerske konstrukcije
9.4.2.1 | Concrete wall / Betonski zid |  | 20
80% for the concrete wall, the milestone is 50m length, no matter the height+ 5% for the "after work" the whole length of each retaining wall + 5% for the "correction of the crown" the whole length of each retaining wall+10% for the "wall surface" the whole length of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
9.4.2.1.1 | Concrete wall/ Betonski zid RK26+345-RK26+380 (35m)
9.4.2.1.1.1 | Concrete wall/ Betonski zid RK26+345-RK26+380 - 80% | 54007.112 |  |  | 0 | 0 | 0
9.4.2.1.1.2 | Concrete wall/ Betonski zid RK26+345-RK26+380 - After work 5% | 3375.4445 |  |  | 0 | 0 | 0
9.4.2.1.1.3 | Concrete wall/ Betonski zid RK26+345-RK26+380 - Correction of the crown 5% | 3375.4445 |  |  | 0 | 0 | 0
9.4.2.1.1.4 | Concrete wall/ Betonski zid RK26+345-RK26+380 - 10% Wall surface | 6750.889 |  |  | 0 | 0 | 0
9.4.3 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
9.4.3.1 | LK26+327.000—LK26+387.920 (60.920 m) | 16528.5613 | 35 |  | 0 | 0 | 0
9.4.3.2 | RK26+345.000—RK26+393.143 (48.143m) | 13061.9587 | 35 |  | 0 | 0 | 0
9.4.4 | Pavement structure/ Kolovozna konstrukcija
9.4.4.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana | 4756.042 | 36 |  | 0 | 0 | 0
9.4.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana | 3758.538 | 36 |  | 0 | 0 | 0
9.4.4.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana | 4756.042 | 37 |  | 0 | 0 | 0
9.4.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana | 3758.538 | 37 |  | 0 | 0 | 0
9.4.4.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana | 5284.8071 | 38 |  | 0 | 0 | 0
9.4.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana | 4176.4029 | 38 |  | 0 | 0 | 0
| Sub Total / Suma stavke 9.4 | 246246.36 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 9.5 | Construction of bridge/Izgradnja mosta Zagrade (LK 26.387.920- LK 26+487.920, RK 26+393.143- RK 26+539.143)
Completion of/Završetak:
Left bridge/ Lijevi most
9.5.1 | Foundation concrete/ Temeljni beton
9.5.1.1 | A1 | 20568.3468 | 25 |  | 0 | 0 | 0
9.5.1.2 | P1 | 12228.742 | 26 |  | 0 | 0 | 0
9.5.1.3 | P2 | 13860.0838 | 26 |  | 0 | 0 | 0
9.5.1.4 | P3 | 12228.742 | 27 |  | 0 | 0 | 0
9.5.1.5 | A2 | 20568.3468 | 27 |  | 0 | 0 | 0
9.5.2 | Abutments and Piers elevation/ Elevacija mosnih stubova
9.5.2.1 | A1 | 21316.73 | 26 |  | 0 | 0 | 0
9.5.2.2 | P1 stage 1 (2.2m) | 2673.1784 | 26 |  | 0 | 0 | 0
9.5.2.3 | P1 stage 2 (2m) | 2430.1622 | 26 |  | 0 | 0 | 0
9.5.2.4 | P1 stage 3 (3.355m) | 4076.597 | 27 |  | 0 | 0 | 0
9.5.2.5 | P1 stage 4 (3.2m) | 3888.2595 | 27 |  | 0 | 0 | 0
9.5.2.6 | P2 stage 1 (1.2m) | 1458.0973 | 27 |  | 0 | 0 | 0
9.5.2.7 | P2 stage 2 (2m) | 2430.1622 | 27 |  | 0 | 0 | 0
9.5.2.8 | P2 stage 3 (5m) | 6075.4054 | 27 |  | 0 | 0 | 0
9.5.2.9 | P2 stage 4 (6.255m) | 7600.3322 | 28 |  | 0 | 0 | 0
9.5.2.10 | P2 stage 5 (3.2m) | 3888.2595 | 28 |  | 0 | 0 | 0
9.5.2.11 | P3 stage 1 (1.2m) | 1458.0973 | 27 |  | 0 | 0 | 0
9.5.2.12 | P3 stage 2 (2m) | 2430.1622 | 27 |  | 0 | 0 | 0
9.5.2.13 | P3 stage 3 (5m) | 6075.4054 | 28 |  | 0 | 0 | 0
9.5.2.14 | P3 stage 4 (2.555m) | 3104.5322 | 28 |  | 0 | 0 | 0
9.5.2.15 | P3 stage 5 (3.2m) | 3888.2595 | 28 |  | 0 | 0 | 0
9.5.2.16 | A2 | 21316.73 | 28 |  | 0 | 0 | 0
9.5.3 | Bridge deck superstructure/ Gornji stroj mosne ploče
9.5.3.1 | A1-P1 | 84350.08 | 29 |  | 0 | 0 | 0
9.5.3.2 | P1-P2 | 107354.64 | 30 |  | 0 | 0 | 0
9.5.3.3 | P2-P3 | 107354.64 | 31 |  | 0 | 0 | 0
9.5.3.4 | P3-A2 | 84350.08 | 32 |  | 0 | 0 | 0
9.5.4 | Bridge deck prestressing/ Prednaprezanje mosne ploče
9.5.4.1 | A1-P1 | 9372.23 | 29 |  | 0 | 0 | 0
9.5.4.2 | P1-P2 | 11928.29 | 30 |  | 0 | 0 | 0
9.5.4.3 | P2-P3 | 11928.29 | 31 |  | 0 | 0 | 0
9.5.4.4 | P3-A2 | 9372.23 | 32 |  | 0 | 0 | 0
9.5.5 | Bridge furniture/ Mosna estetika
9.5.5.1 | 50 m | 78279.32 | 35 |  | 0 | 0 | 0
9.5.5.2 | 100 m | 78279.32 | 36 |  | 0 | 0 | 0
9.5.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
9.5.6.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/hidroizolacija | 20786.74 | 35 |  | 0 | 0 | 0
9.5.6.2 | Asphalt layer/ Sloj asfalta 2 + joints/spojnice | 5183.79 | 36 |  | 0 | 0 | 0
Right bridge/ Desni most
9.5.7 | Foundation concrete/ Temeljni beton
9.5.7.1 | A1 | 19244.6576 | 25 |  | 0 | 0 | 0
9.5.7.2 | P1 | 6956.94 | 25 |  | 0 | 0 | 0
9.5.7.3 | P2 | 13925.4232 | 26 |  | 0 | 0 | 0
9.5.7.4 | P3 | 12739.6978 | 26 |  | 0 | 0 | 0
9.5.7.5 | P4 | 15111.1392 | 27 |  | 0 | 0 | 0
9.5.7.6 | P5 | 12739.6978 | 27 |  | 0 | 0 | 0
9.5.7.7 | A2 | 19244.6576 | 27 |  | 0 | 0 | 0
9.5.8 | Abutments and Piers elevation/ Elevacija mosnih stubova
9.5.8.1 | A1 | 22225.79 | 26 |  | 0 | 0 | 0
9.5.8.2 | P1 stage 1 (1.2m) | 1485.297 | 26 |  | 0 | 0 | 0
9.5.8.3 | P1 stage 2 (2m) | 2475.495 | 26 |  | 0 | 0 | 0
9.5.8.4 | P1 stage 3 (5.3m) | 6560.0617 | 27 |  | 0 | 0 | 0
9.5.8.5 | P1 stage 4 (3.2m) | 3960.792 | 27 |  | 0 | 0 | 0
9.5.8.6 | P2 stage 1 (1.2m) | 1485.297 | 26 |  | 0 | 0 | 0
9.5.8.7 | P2 stage 2 (2m) | 2475.495 | 26 |  | 0 | 0 | 0
9.5.8.8 | P2 stage 3 (5m) | 6188.7375 | 28 |  | 0 | 0 | 0
9.5.8.9 | P2 stage 4 (3.243m) | 4014.0151 | 27 |  | 0 | 0 | 0
9.5.8.10 | P2 stage 5 (3.2m) | 3960.792 | 27 |  | 0 | 0 | 0
9.5.8.11 | P3 stage 1 (2.2m) | 2723.0445 | 26 |  | 0 | 0 | 0
9.5.8.12 | P3 stage 2 (2m) | 2475.495 | 26 |  | 0 | 0 | 0
9.5.8.13 | P3 stage 3 (5m) | 6188.7375 | 27 |  | 0 | 0 | 0
9.5.8.14 | P3 stage 4 (5m) | 6188.7375 | 27 |  | 0 | 0 | 0
9.5.8.15 | P3 stage 5 (3.643m) | 4509.1141 | 28 |  | 0 | 0 | 0
9.5.8.16 | P3 stage 6 (3.2m) | 3960.792 | 28 |  | 0 | 0 | 0
9.5.8.17 | P4 stage 1 (2.2m) | 2723.0445 | 27 |  | 0 | 0 | 0
9.5.8.18 | P4 stage 2 (2m) | 2475.495 | 27 |  | 0 | 0 | 0
9.5.8.19 | P4 stage 3 (5m) | 6188.7375 | 27 |  | 0 | 0 | 0
9.5.8.20 | P4 stage 4 (5m) | 6188.7375 | 27 |  | 0 | 0 | 0
9.5.8.21 | P4 stage 5 (6.543m) | 8098.5818 | 28 |  | 0 | 0 | 0
9.5.8.22 | P4 stage 6 (3.2m) | 3960.792 | 28 |  | 0 | 0 | 0
9.5.8.23 | P5 stage 1 (1.2m) | 1485.297 | 27 |  | 0 | 0 | 0
9.5.8.24 | P5 stage 2 (2m) | 2475.495 | 27 |  | 0 | 0 | 0
9.5.8.25 | P5 stage 3 (5m) | 6188.7375 | 27 |  | 0 | 0 | 0
9.5.8.26 | P5 stage 4 (4.143m) | 5127.9879 | 28 |  | 0 | 0 | 0
9.5.8.27 | P5 stage 5 (3.2m) | 3960.792 | 28 |  | 0 | 0 | 0
9.5.8.28 | A2 | 22225.79 | 28 |  | 0 | 0 | 0
9.5.9 | Bridge deck superstructure/ Gornji stroj mosne ploče
9.5.9.1 | A1-P1 | 79828.23 | 29 |  | 0 | 0 | 0
9.5.9.2 | P1-P2 | 98834.95 | 30 |  | 0 | 0 | 0
9.5.9.3 | P2-P3 | 98834.95 | 31 |  | 0 | 0 | 0
9.5.9.4 | P3-P4 | 98834.95 | 31 |  | 0 | 0 | 0
9.5.9.5 | P4-P5 | 98834.95 | 32 |  | 0 | 0 | 0
9.5.9.6 | P5-A2 | 79828.23 | 32 |  | 0 | 0 | 0
9.5.10 | Bridge deck prestressing/ Prednaprezanje mosne ploče
9.5.10.1 | A1-P1 | 8869.8 | 30 |  | 0 | 0 | 0
9.5.10.2 | P1-P2 | 10981.66 | 30 |  | 0 | 0 | 0
9.5.10.3 | P2-P3 | 10981.66 | 31 |  | 0 | 0 | 0
9.5.10.4 | P3-P4 | 10981.66 | 31 |  | 0 | 0 | 0
9.5.10.5 | P4-P5 | 10981.66 | 32 |  | 0 | 0 | 0
9.5.10.6 | P5-A2 | 8869.8 | 32 |  | 0 | 0 | 0
9.5.11 | Bridge furniture/ Mosna estetika
9.5.11.1 | 50 m | 65678.24 | 35 |  | 0 | 0 | 0
9.5.11.2 | 100 m | 65678.24 | 36 |  | 0 | 0 | 0
9.5.11.3 | 146 m | 60424 | 36 |  | 0 | 0 | 0
9.5.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
9.5.12.1 | Asphalt layer/ Sloj asfalta 1 + waterproofing/hidroizolacija | 43846.4 | 35 |  | 0 | 0 | 0
9.5.12.2 | Asphalt layer/ Sloj asfalta 2 + joints/spojnice | 10934.4 | 36 |  | 0 | 0 | 0
9.5.13 | Engineering structures/ Inženjerske konstrukcije
9.5.13.1 | Concrete wall / Betonski zid
80% for the concrete wall, the milestone is 50m length, no matter the height+ 5% for the "after work" the whole length of each retaining wall + 5% for the "correction of the crown" the whole length of each retaining wall+10% for the "wall surface" the whole length of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
9.5.13.1.1 | Concrete wall/ Betonski zid LK26+483.23-LK26+489.18 (5.95m)
9.5.13.1.1.1 | Concrete wall/ Betonski zid LK26+483.23-LK26+489.18 - 90% | 9161.696 |  |  | 0 | 0 | 0
9.5.13.1.1.2 | Concrete wall/ Betonski zid LK26+483.23-LK26+489.18 - After work 5% | 572.606 |  |  | 0 | 0 | 0
9.5.13.1.1.3 | Concrete wall/ Betonski zid LK26+483.23-LK26+489.18 - After work 5% | 572.606 |  |  | 0 | 0 | 0
9.5.13.1.1.4 | Concrete wall/ Betonski zid LK26+483.23-LK26+489.18 - 10% Wall surface | 1145.212 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 9.6 | 1908719.5746 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 9.6 | Road Works/Radovi na putevima (LK26+487.920—LK26+502.720, RK26+539.143—RK26+557.71)
Completion of/Završetak:
9.6.1 | Subgrade/ Posteljica
9.6.1.1 | Top soil removal/ Uklanjanje humusa
9.6.1.1.1 | RK26+539.143—RK26+557.710 (Inc. 0 - 14.800 m (LK); 0 - 18.567 m (RK)) | 4599.57 |  |  | 0 | 0 | 0
9.6.1.2 | Earthworks/ Zemljani radovi
At every 250 m and 4m height /Na svakih 250m i 4m visini
9.6.1.2.1 | RK26+539.143 - RK26+557.71 Layers 1,2,3,4
9.6.1.2.1.1 | RK26+539.143 - RK26+557.71 Layers 1 | 11828.969 |  |  | 0 | 0 | 0
9.6.1.2.1.2 | RK26+539.143 - RK26+557.71 Layers 2 | 11828.969 |  |  | 0 | 0 | 0
9.6.1.2.1.3 | RK26+539.143 - RK26+557.71 Layers 3 | 11828.969 |  |  | 0 | 0 | 0
9.6.1.2.1.4 | RK26+539.143 - RK26+557.71 Layers 4 | 6505.933 |  |  | 0 | 0 | 0
9.6.1.3 | Road Foundation/ Temelj puta
9.6.1.3.1 | 0 - 18.567 m right side/ desna strana | 1824.97 | 34 |  | 0 | 0 | 0
9.6.1.3.2 | 0 - 14.800 m left side/ lijeva strana | 1824.97 | 34 |  | 0 | 0 | 0
9.6.2 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
9.6.2.1 | LK26+487.920—LK26+502.720 (14.800 m) | 7393.9056 | 35 |  | 0 | 0 | 0
9.6.2.2 | RK26+539.143—RK26+557.710 (18.567 m) | 9275.8544 | 35 |  | 0 | 0 | 0
9.6.3 | Pavement structure/ Kolovozna konstrukcija
9.6.3.1 | Asphalt concrete layer/ Sloj asfaltnog betona 1 right side/ desna strana | 2669.0974 | 36 |  | 0 | 0 | 0
9.6.3.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana | 2127.5726 | 36 |  | 0 | 0 | 0
9.6.3.3 | Asphalt concrete layer/ Sloj asfaltnog betona 2 right side/ desna strana | 2669.0974 | 37 |  | 0 | 0 | 0
9.6.3.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana | 2127.5726 | 37 |  | 0 | 0 | 0
9.6.3.5 | Asphalt concrete layer/ Sloj asfaltnog betona 3 right side/ desna strana | 2965.84 | 38 |  | 0 | 0 | 0
9.6.3.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana | 2364.11 | 38 |  | 0 | 0 | 0
9.6.4 | Engineering structures/ Inženjerske konstrukcije
9.6.4.1 | Concrete wall / Betonski zid
80% for the concrete wall, the milestone is 50m length, no matter the height+ 5% for the "after work" the whole length of each retaining wall + 5% for the "correction of the crown" the whole length of each retaining wall+10% for the "wall surface" the whole length of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
9.6.4.1.1 | Concrete wall/ Betonski zid LK26+492.32-LK26+496.32 (4m)
9.6.4.1.1.1 | Concrete wall/ Betonski zid LK26+492.32-LK26+496.32 - 80% | 6033.92 |  |  | 0 | 0 | 0
9.6.4.1.1.2 | Concrete wall/ Betonski zid LK26+492.32-LK26+496.32 - After work 5% | 377.12 |  |  | 0 | 0 | 0
9.6.4.1.1.3 | Concrete wall/ Betonski zid LK26+492.32-LK26+496.32 - Correction of the crown 5% | 377.12 |  |  | 0 | 0 | 0
9.6.4.1.1.4 | Concrete wall/ Betonski zid LK26+492.32-LK26+496.32 - 10% Wall surface | 754.24 |  |  | 0 | 0 | 0
9.6.4.1.2 | Concrete wall/ Betonski zid RK26+543.543 -RK26+549.543 (6m)
9.6.4.1.2.1 | Concrete wall/ Betonski zid RK26+543.543 -RK26+549.543 - 80% | 9050.88 |  |  | 0 | 0 | 0
9.6.4.1.2.2 | Concrete wall/ Betonski zid RK26+543.543 -RK26+549.543 - After work 5% | 565.68 |  |  | 0 | 0 | 0
9.6.4.1.2.3 | Concrete wall/ Betonski zid RK26+543.543 -RK26+549.543 - Correction of the crown 5% | 565.68 |  |  | 0 | 0 | 0
9.6.4.1.2.4 | Concrete wall/ Betonski zid RK26+543.543 -RK26+549.543 - 10% Wall surface | 1131.36 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 9.6 | 100691.4 |  |  | 0 | 0 | 0
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 09 | 38662376.8766 |  |  | 3212113.5108 | 663504.9443 | 3875618.4551

## COST CENTER 10
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
| COST CENTER 10/TROŠKOVNI CENTAR 10 | rev Tunnels and Open Route
Cost center No./ Troškovno mjesto Br. | 10 | Subsection/Podsekcija 3.3 (LK26+502.72-LK29+317.00, RK26+557.71-RK29+350.00)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost center/ Troškovno mjesto 10.1 | Road Works/Radovi na putevima (LK 26+502.72- LK 26+512.921, RK26+557.71—RK26+724.643)
Completion of/Završetak:
10.1.1 | Subgrade/ Posteljica
10.1.1.1 | Top soil removal/ Uklanjanje humusa
10.1.1.1.1 | RK26+557.710—RK26+724.643 (Inc.0 - 10.201 m (LK); 0 - 166.933 m (RK)) | 18815.77 | 19 |  | 0 | 0 | 0
10.1.1.2 | Earthworks/ Zemljani radovi |  | 33
At every 250 m and 4m height /Na svakih 250m i 4m visini
10.1.1.2 | RK26+557.71 - RK26+724.643, Layers 1,2,3,4,5,6
10.1.1.2.1 | RK26+557.71 - RK26+724.643, Layer 1 | 46921.5212 |  |  | 0 | 0 | 0
10.1.1.2.2 | RK26+557.71 - RK26+724.643, Layer 2 | 46921.5212 |  |  | 0 | 0 | 0
10.1.1.2.3 | RK26+557.71 - RK26+724.643, Layer 3 | 46921.5212 |  |  | 0 | 0 | 0
10.1.1.2.4 | RK26+557.71 - RK26+724.643, Layer 4 | 46921.5212 |  |  | 0 | 0 | 0
10.1.1.2.5 | RK26+557.71 - RK26+724.643, Layer 5 | 46921.5212 |  |  | 0 | 0 | 0
10.1.1.2.6 | RK26+557.71 - RK26+724.643, Layer 6 | 14311.064 |  |  | 0 | 0 | 0
10.1.1.3 | Road Foundation/ Temelj puta
10.1.1.3.1 | 0 - 166.933 m right side/ desna strana | 14071.1832 | 35 |  | 0 | 0 | 0
10.1.1.3.2 | 0 - 10.201 m left side/ lijeva strana | 859.8668 | 35 |  | 0 | 0 | 0
10.1.2 | Engineering structures/ Inženjerske strukture
10.1.2.1 | Concrete wall / Betonski zid |  | 26
80% for the concrete wall, the milestone is 50m length, no matter the high+ 5% for the "after work" the whole length of each retaining wall + 5% for the "correction of the crown" the whole length of each retaining wall+10% for the "wall surface" the whole length of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
10.1.2.1.1 | Concrete wall/ Betonski zid RK26+543.543-RK26+670 (126.46m) 80%, Layers 1,2,3,4
10.1.2.1.1.1 | Segment 1 RK26+543.543 ~ RK26+593.543 (50m) | 207472.6247 |  |  | 0 | 0 | 0
10.1.2.1.1.2 | Segment 2 RK26+593.543 ~ RK26+643.543 (50m) | 207472.6247 |  |  | 0 | 0 | 0
10.1.2.1.1.3 | Segment 3 RK26+643.543 ~ RK26+670 (26.457m) | 109782.0646 |  |  | 0 | 0 | 0
10.1.2.1.1.4 | Concrete wall/ Betonski zid LK22+940.0 ~ LK23+130.0 (151.6m) After work 5% | 32795.4571 |  |  | 0 | 0 | 0
10.1.2.1.1.5 | Concrete wall/ Betonski zid LK22+940.0 ~ LK23+130.0 (151.6m) Correction of the crown 5% | 32795.4571 |  |  | 0 | 0 | 0
10.1.2.1.1.6 | Concrete wall/ Betonski zid LK22+940.0 ~ LK23+130.0 (151.6m) 10% Wall surface | 65590.9142 |  |  | 0 | 0 | 0
10.1.2.1.2 | Concrete wall/ Betonski zid RK26+580 - RK26+731.6(151.6m) 80%, Layers 1,2,3,4,5
10.1.2.1.2.1 | Segment 1 RK26+580 ~ RK26+630 (50m) | 207472.6247 |  |  | 0 | 0 | 0
10.1.2.1.2.2 | Segment 2 RK26+630 ~ RK26+680 (50m) | 207472.6247 |  |  | 0 | 0 | 0
10.1.2.1.2.3 | Segment 3 RK26+680 ~ RK26+731.6 (51.6m) | 214111.7487 |  |  | 0 | 0 | 0
10.1.2.1.2.4 | Concrete wall/ Betonski zid LK22+940.0 ~ LK23+130.0 (151.6m) After work 5% | 39316.0624 |  |  | 0 | 0 | 0
10.1.2.1.2.5 | Concrete wall/ Betonski zid LK22+940.0 ~ LK23+130.0 (151.6m) Correction of the crown 5% | 39316.0624 |  |  | 0 | 0 | 0
10.1.2.1.2.6 | Concrete wall/ Betonski zid LK22+940.0 ~ LK23+130.0 (151.6m) 10% Wall surface | 78632.1248 |  |  | 0 | 0 | 0
10.1.3 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
10.1.3.1 | LK26+502.720—LK26+512.921 (10.201m) | 3927.1305 |  |  | 0 | 0 | 0
10.1.3.2 | RK26+557.710—RK26+724.643 (166.933 m) | 64265.0395 |  |  | 0 | 0 | 0
10.1.4 | Pavement structure/ Kolovozna konstrukcija
10.1.4.1 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana | 18492.0701 | 40 |  | 0 | 0 | 0
10.1.4.2 | Asphalt concrete layer/ Sloj asfaltnog betona 1 left side/ lijeva strana | 1130.0199 | 40 |  | 0 | 0 | 0
10.1.4.3 | asphalt concrete layer/ sloj asfaltnog betona 2 right side/ desna strana | 18492.0701 | 40 |  | 0 | 0 | 0
10.1.4.4 | Asphalt concrete layer/ Sloj asfaltnog betona 2 left side/ lijeva strana | 1130.0199 | 40 |  | 0 | 0 | 0
10.1.4.5 | asphalt concrete layer/ sloj asfaltnog betona 3 right side/ desna strana | 20547.9676 | 41 |  | 0 | 0 | 0
10.1.4.6 | Asphalt concrete layer/ Sloj asfaltnog betona 3 left side/ lijeva strana | 1255.6524 | 41 |  | 0 | 0 | 0
| Sub Total / Suma stavke 10.1 | 1854135.85 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 10.2 | Construction of tunnel/Izgradnja tunela Kosman (LK 26+512.921 - LK 29+174.921 , RK 26+724.643- RK 29+231.643)
Completion of/Završeno:
10.2.1 | Portal construction/ Izgradnja portala
10.2.1.1 | 20% complete/ završeno (portal 1) | 43546.88 | 17 |  | 0 | 0 | 0
10.2.1.2 | 40% complete/ završeno (portal 2) | 43546.88 | 17 |  | 0 | 0 | 0
10.2.1.3 | 60% complete/ završeno (portal 3) | 43546.88 | 17 |  | 0 | 0 | 0
10.2.1.4 | 80% complete/ završeno (portal 4) | 43546.88 | 17 |  | 0 | 0 | 0
10.2.1.5 | 85% (portal 1 complete/ završen) | 10886.72 | 47 |  | 0 | 0 | 0
10.2.1.6 | 90% (portal 2 complete/ završen) | 10886.72 | 47 |  | 0 | 0 | 0
10.2.1.7 | 95% (portal 3 complete/ završen) | 10886.72 | 47 |  | 0 | 0 | 0
10.2.1.8 | 100% (portal 4 complete/ završen) | 10886.73 | 47 |  | 0 | 0 | 0
10.2.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
10.2.2.1 | 40 m (S-R, RK 26+736.6 - RK 26+776.6) | 269749.05 | 19 | 22 | 269749.05 | 0 | 269749.05
10.2.2.2 | 80 m (S-R, RK 26+776.6 - RK 26+816.6) | 269749.05 | 19 | 23 | 269749.05 | 0 | 269749.05
10.2.2.3 | 120 m (S-R, RK 26+816.6 - RK 26+856.6) | 269749.05 | 19 | 24 | 269749.05 | 0 | 269749.05
10.2.2.4 | 160 m (S-R, RK 26+856.6 - RK 26+896.14) | 269749.05 | 19 | 24 | 269749.05 | 0 | 269749.05
10.2.2.5 | 200 m (S-L, LK 26+524.9 - LK 26+564.9) | 269749.05 | 20 | 24 | 269749.05 | 0 | 269749.05
10.2.2.6 | 240 m (S-R, RK 26+896.6- RK 26+936.6) | 269749.05 | 20 | 24 | 269749.05 | 0 | 269749.05
10.2.2.7 | 280 m (S-R, RK 26+976.6- RK 27+016.6) | 269749.05 | 20 | 25 | 269749.05 | 0 | 269749.05
10.2.2.8 | 320 m (S-L, LK 25+564.9 - LK 26+604.9) | 269749.05 | 20 | 24 | 269749.05 | 0 | 269749.05
10.2.2.9 | 360 m (S-R, RK 26+936.6- RK 26+976.6) | 269749.05 | 20 | 25 | 269749.05 | 0 | 269749.05
10.2.2.10 | 400 m (N-L, LK 29+162.90 - LK 29+122.90) | 269749.05 | 21 | 25 | 269749.05 | 0 | 269749.05
10.2.2.11 | 440 m (N-R, RK 29+219.6- RK 29+179.6) | 269749.05 | 21 | 25 | 269749.05 | 0 | 269749.05
10.2.2.12 | 480 m (N-L, LK 29+122.90 - LK 29+082.90) | 269749.05 | 21 | 25 | 269749.05 | 0 | 269749.05
10.2.2.13 | 520 m (N-R, RK 29+179.6- RK 29+139.6) | 269749.05 | 21 | 25 | 269749.05 | 0 | 269749.05
10.2.2.14 | 560 m (S-R, RK 27+016.60- RK 27+056.6) | 269749.05 | 21 | 26 | 269749.05 | 0 | 269749.05
10.2.2.15 | 600 m (S-R, RK 27+056.60- RK 27+096.6) | 269749.05 | 22 | 26 | 269749.05 | 0 | 269749.05
10.2.2.16 | 640 m (S-L, LK 26+604.90 - LK 26+644.9) | 269749.05 | 22 | 26 | 269749.05 | 0 | 269749.05
10.2.2.17 | 680 m (N-L, LK 29+082.90 - LK 29+042.90) | 269749.05 | 22 | 26 | 269749.05 | 0 | 269749.05
10.2.2.18 | 720 m (N-R, RK 29+139.6- RK 29+099.6) | 269749.05 | 22 | 27 | 269749.05 | 0 | 269749.05
10.2.2.19 | 760 m (S-R, RK 27+096.60- RK 27+136.6) | 269749.05 | 22 | 26 | 269749.05 | 0 | 269749.05
10.2.2.20 | 800 m (S-R, RK 27+136.60- RK 27+176.6) | 269749.05 | 23 | 27 | 269749.05 | 0 | 269749.05
10.2.2.21 | 840 m (N-L, LK 29+042.90- LK 29+002.90) | 269749.05 | 23 | 27 | 269749.05 | 0 | 269749.05
10.2.2.22 | 880 m (S-R, RK 27+176.60- RK 27+216.6) | 269749.05 | 23 | 27 | 269749.05 | 0 | 269749.05
10.2.2.23 | 920 m (N-R, RK 29+099.6- RK 29+059.6) | 269749.05 | 23 | 27 | 269749.05 | 0 | 269749.05
10.2.2.24 | 960 m (S-R, RK 27+216.60- RK 27+256.6) | 269749.05 | 23 | 28 | 269749.05 | 0 | 269749.05
10.2.2.25 | 1000 m (S-L, LK 26+644.90 - LK 26+684.9) | 269749.05 | 24 | 28 | 269749.05 | 0 | 269749.05
10.2.2.26 | 1040 m (S-L, LK 26+684.90 - LK 26+724.9) | 269749.05 | 24 | 28 | 269749.05 | 0 | 269749.05
10.2.2.27 | 1080 m (S-L, LK 26+724.90 - LK 26+764.9) | 269749.05 | 24 | 28 | 269749.05 | 0 | 269749.05
10.2.2.28 | 1120 m (S-L, LK 26+767.90 - LK 26+804.9) | 269749.05 | 24 | 28 | 269749.05 | 0 | 269749.05
10.2.2.29 | 1160 m (N-R, RK 29+059.6- RK 29+019.6) | 269749.05 | 24 | 28 | 269749.05 | 0 | 269749.05
10.2.2.30 | 1200 m (N-R, RK 29+019.6- RK 28+979.6) | 269749.05 | 25 | 28 | 269749.05 | 0 | 269749.05
10.2.2.31 | 1240 m (N-R, RK 28+979.6- RK 28+939.6) | 269749.05 | 25 | 28 | 269749.05 | 0 | 269749.05
10.2.2.32 | 1280 m (N-R, RK 28+939.6- RK 28+899.6) | 269749.05 | 25 | 28 | 269749.05 | 0 | 269749.05
10.2.2.33 | 1320 m (N-L, LK 29+002.90- LK 28+962.90) | 269749.05 | 25 | 28 | 269749.05 | 0 | 269749.05
10.2.2.34 | 1360 m (N-L, LK 28+962.90- LK 28+922.90) | 269749.05 | 25 | 28 | 269749.05 | 0 | 269749.05
10.2.2.35 | 1400 m (N-L, LK 28+922.90- LK 28+882.90) | 269749.05 | 26 | 28 | 269749.05 | 0 | 269749.05
10.2.2.36 | 1440 m (N-L, LK 28+882.90- LK 28+842.90) | 269749.05 | 26 | 28 | 269749.05 | 0 | 269749.05
10.2.2.37 | 1460 m | 136635.4803 | 26 |  | 0 | 0 | 0
10.2.2.38 | 1480 m | 136635.4803 | 26 |  | 0 | 0 | 0
10.2.2.39 | 1500 m (S-L,LK26+844.9-LK26+864.9) | 136635.4803 | 26 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.40 | 1520 m (S-L,LK26+864.9-LK26+884.9) | 136635.4803 | 26 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.41 | 1540 m (S-L,LK26+884.9-LK26+904.9) | 136635.4803 | 26 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.42 | 1560 m (S-L,LK26+904.9-LK26+924.9) | 136635.4803 | 26 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.43 | 1580 m (S-L,LK26+924.9-LK26+944.9) | 136635.4803 | 26 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.44 | 1600 m (S-L,LK26+944.9-LK26+964.9) | 136635.4803 | 27 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.45 | 1620 m (S-R,RK27+256.6-RK27+276.6) | 136635.4803 | 27 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.46 | 1640 m (S-R,RK27+276.6-RK27+296.6) | 136635.4803 | 27 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.47 | 1660 m (S-R,RK27+296.6-RK27+316.6) | 136635.4803 | 27 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.48 | 1680 m (S-R,RK27+316.6-RK27+336.6) | 136635.4803 | 27 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.49 | 1700 m (S-R,RK27+336.6-RK27+356.6) | 136635.4803 | 27 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.50 | 1720 m (S-R,RK27+356.6-RK27+376.6) | 136635.4803 | 27 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.51 | 1740 m (N-L,LK28+842.9- LK28+822.9) | 136635.4803 | 27 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.52 | 1760 m (N-L,LK28+822.9- LK28+802.9) | 136635.4803 | 27 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.53 | 1780 m (N-L,LK28+802.9- LK28+782.9) | 136635.4803 | 27 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.54 | 1800 m (N-L,LK28+782.9- LK28+762.9) | 136635.4803 | 28 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.55 | 1820 m (N-L, LK28+762.9- LK28+742.9) | 136635.4803 | 28 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.56 | 1840 m (N-L, LK28+742.9- LK28+722.9) | 136635.4803 | 28 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.57 | 1860 m (N-R,RK28+899.6 - RK28+879.6) | 136635.4803 | 28 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.58 | 1880 m (N-R,RK28+879.6 - RK28+859.6) | 136635.4803 | 28 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.59 | 1900 m (N-R,RK28+859.6 - RK28+839.6) | 136635.4803 | 28 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.60 | 1920 m (N-R,RK28+839.6 - RK28+819.6) | 136635.4803 | 28 | 29 | 136635.4803 | 0 | 136635.4803
10.2.2.61 | 1940 m | 136635.4803 | 28 |  | 0 | 0 | 0
10.2.2.62 | 1960 m | 136635.4803 | 28 |  | 0 | 0 | 0
10.2.2.63 | 1980 m | 136635.4803 | 28 |  | 0 | 0 | 0
10.2.2.64 | 2000 m (S-L,LK26+964.9-LK26+984.9) | 136635.4803 | 29 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.65 | 2020 m (S-L,LK26+984.9-LK27+004.9) | 136635.4803 | 29 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.66 | 2040 m (S-L,LK27+004.9-LK27+024.9) | 136635.4803 | 29 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.67 | 2060 m (S-L,LK27+024.9-LK27+044.9) | 136635.4803 | 29 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.68 | 2080 m (S-L,LK27+044.9-LK27+064.9) | 136635.4803 | 29 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.69 | 2100 m (S-L,LK27+064.9-LK27+084.9) | 136635.4803 | 29 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.70 | 2120 m( S-L,LK27+084.9-LK27+104.9) | 136635.4803 | 29 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.71 | 2140 m (S-R,RK27+376.6-RK27+396.6) | 136635.4803 | 29 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.72 | 2160 m (S-R,RK27+396.6-RK27+416.6) | 136635.4803 | 29 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.73 | 2180 m (S-R,RK27+416.6-RK27+436.6) | 136635.4803 | 29 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.74 | 2200 m (S-R,RK27+436.6-RK27+456.6) | 136635.4803 | 30 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.75 | 2220 m (S-R,RK27+456.6-RK27+476.6) | 136635.4803 | 30 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.76 | 2240 m ( N-L,LK28+722.9-LK28+702.9) | 136635.4803 | 30 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.77 | 2260 m (N-L,LK28+702.9-LK28+682.9) | 136635.4803 | 30 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.78 | 2280 m (N-L,LK28+682.9-LK28+662.9) | 136635.4803 | 30 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.79 | 2300 m (N-L,LK28+662.9-LK28+642.9) | 136635.4803 | 30 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.80 | 2320 m (N-L,LK28+642.9-LK28+622.9) | 136635.4803 | 30 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.81 | 2340 m (N-R,RK28+759.6-RK28+739.6) | 136635.4803 | 30 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.82 | 2360 m (N-R,RK28+739.6-RK28+719.6) | 136635.4803 | 30 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.83 | 2380 m (N-R,RK28+719.6-RK28+699.60 | 136635.4803 | 30 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.84 | 2400 m (N-R,RK28+699.6-RK28+679.6) | 136635.4803 | 31 | 30 | 0 | 136635.4803 | 136635.4803
10.2.2.85 | 2420 m | 136635.4803 | 31 |  | 0 | 0 | 0
10.2.2.86 | 2440 m | 136635.4803 | 31 |  | 0 | 0 | 0
10.2.2.87 | 2460 m | 136635.4803 | 31 |  | 0 | 0 | 0
10.2.2.88 | 2480 m | 136635.4803 | 31 |  | 0 | 0 | 0
10.2.2.89 | 2500 m | 136635.4803 | 31 |  | 0 | 0 | 0
10.2.2.90 | 2520 m | 136635.4803 | 31 |  | 0 | 0 | 0
10.2.2.91 | 2540 m | 136635.4803 | 31 |  | 0 | 0 | 0
10.2.2.92 | 2560 m | 136635.4803 | 31 |  | 0 | 0 | 0
10.2.2.93 | 2580 m | 136635.4803 | 31 |  | 0 | 0 | 0
10.2.2.94 | 2600 m | 136635.4803 | 32 |  | 0 | 0 | 0
10.2.2.95 | 2620 m | 136635.4803 | 32 |  | 0 | 0 | 0
10.2.2.96 | 2640 m | 136635.4803 | 32 |  | 0 | 0 | 0
10.2.2.97 | 2660 m | 136635.4803 | 32 |  | 0 | 0 | 0
10.2.2.98 | 2680 m | 136635.4803 | 32 |  | 0 | 0 | 0
10.2.2.99 | 2700 m | 136635.4803 | 32 |  | 0 | 0 | 0
10.2.2.100 | 2720 m | 136635.4803 | 32 |  | 0 | 0 | 0
10.2.2.101 | 2740 m | 136635.4803 | 32 |  | 0 | 0 | 0
10.2.2.102 | 2760 m | 136635.4803 | 32 |  | 0 | 0 | 0
10.2.2.103 | 2780 m | 136635.4803 | 32 |  | 0 | 0 | 0
10.2.2.104 | 2800 m | 136635.4803 | 33 |  | 0 | 0 | 0
10.2.2.105 | 2820 m | 136635.4803 | 33 |  | 0 | 0 | 0
10.2.2.106 | 2840 m | 136635.4803 | 33 |  | 0 | 0 | 0
10.2.2.107 | 2860 m | 136635.4803 | 33 |  | 0 | 0 | 0
10.2.2.108 | 2880 m | 136635.4803 | 33 |  | 0 | 0 | 0
10.2.2.109 | 2900 m | 136635.4803 | 33 |  | 0 | 0 | 0
10.2.2.110 | 2920 m | 136635.4803 | 33 |  | 0 | 0 | 0
10.2.2.111 | 2940 m | 136635.4803 | 33 |  | 0 | 0 | 0
10.2.2.112 | 2960 m | 136635.4803 | 33 |  | 0 | 0 | 0
10.2.2.113 | 2980 m | 136635.4803 | 33 |  | 0 | 0 | 0
10.2.2.114 | 3000 m | 136635.4803 | 34 |  | 0 | 0 | 0
10.2.2.115 | 3020 m | 136635.4803 | 34 |  | 0 | 0 | 0
10.2.2.116 | 3040 m | 136635.4803 | 34 |  | 0 | 0 | 0
10.2.2.117 | 3060 m | 136635.4803 | 34 |  | 0 | 0 | 0
10.2.2.118 | 3080 m | 136635.4803 | 34 |  | 0 | 0 | 0
10.2.2.119 | 3100 m | 136635.4803 | 34 |  | 0 | 0 | 0
10.2.2.120 | 3120 m | 136635.4803 | 34 |  | 0 | 0 | 0
10.2.2.121 | 3140 m | 136635.4803 | 34 |  | 0 | 0 | 0
10.2.2.122 | 3160 m | 136635.4803 | 34 |  | 0 | 0 | 0
10.2.2.123 | 3180 m | 136635.4803 | 34 |  | 0 | 0 | 0
10.2.2.124 | 3200 m | 136635.4803 | 34 |  | 0 | 0 | 0
10.2.2.125 | 3220 m | 136635.4803 | 34 |  | 0 | 0 | 0
10.2.2.126 | 3240 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.127 | 3260 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.128 | 3280 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.129 | 3300 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.130 | 3320 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.131 | 3340 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.132 | 3360 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.133 | 3380 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.134 | 3400 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.135 | 3420 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.136 | 3440 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.137 | 3460 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.138 | 3480 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.139 | 3500 m | 136635.4803 | 35 |  | 0 | 0 | 0
10.2.2.140 | 3520 m | 136635.4803 | 36 |  | 0 | 0 | 0
10.2.2.141 | 3540 m | 136635.4803 | 36 |  | 0 | 0 | 0
10.2.2.142 | 3560 m | 136635.4803 | 36 |  | 0 | 0 | 0
10.2.2.143 | 3580 m | 136635.4803 | 36 |  | 0 | 0 | 0
10.2.2.144 | 3600 m | 136635.4803 | 36 |  | 0 | 0 | 0
10.2.2.145 | 3620 m | 136635.4803 | 36 |  | 0 | 0 | 0
10.2.2.146 | 3640 m | 136635.4803 | 36 |  | 0 | 0 | 0
10.2.2.147 | 3660 m | 136635.4803 | 36 |  | 0 | 0 | 0
10.2.2.148 | 3680 m | 136635.4803 | 36 |  | 0 | 0 | 0
10.2.2.149 | 3700 m | 136635.4803 | 36 |  | 0 | 0 | 0
10.2.2.150 | 3720 m | 136635.4803 | 36 |  | 0 | 0 | 0
10.2.2.151 | 3740 m | 136635.4803 | 36 |  | 0 | 0 | 0
10.2.2.152 | 3760 m | 136635.4803 | 37 |  | 0 | 0 | 0
10.2.2.153 | 3780 m | 136635.4803 | 37 |  | 0 | 0 | 0
10.2.2.154 | 3800 m | 136635.4803 | 37 |  | 0 | 0 | 0
10.2.2.155 | 3820 m | 136635.4803 | 37 |  | 0 | 0 | 0
10.2.2.156 | 3840 m | 136635.4803 | 37 |  | 0 | 0 | 0
10.2.2.157 | 3860 m | 136635.4803 | 37 |  | 0 | 0 | 0
10.2.2.158 | 3880 m | 136635.4803 | 37 |  | 0 | 0 | 0
10.2.2.159 | 3900 m | 136635.4803 | 37 |  | 0 | 0 | 0
10.2.2.160 | 3920 m | 136635.4803 | 37 |  | 0 | 0 | 0
10.2.2.161 | 3940 m | 136635.4803 | 37 |  | 0 | 0 | 0
10.2.2.162 | 3960 m | 136635.4803 | 37 |  | 0 | 0 | 0
10.2.2.163 | 3980 m | 136635.4803 | 37 |  | 0 | 0 | 0
10.2.2.164 | 4000 m | 136635.4803 | 38 |  | 0 | 0 | 0
10.2.2.165 | 4020 m | 136635.4803 | 38 |  | 0 | 0 | 0
10.2.2.166 | 4040 m | 136635.4803 | 38 |  | 0 | 0 | 0
10.2.2.167 | 4060 m | 136635.4803 | 38 |  | 0 | 0 | 0
10.2.2.168 | 4080 m | 136635.4803 | 38 |  | 0 | 0 | 0
10.2.2.169 | 4100 m | 136635.4803 | 38 |  | 0 | 0 | 0
10.2.2.170 | 4120 m | 136635.4803 | 38 |  | 0 | 0 | 0
10.2.2.171 | 4140 m | 136635.4803 | 38 |  | 0 | 0 | 0
10.2.2.172 | 4160 m | 136635.4803 | 38 |  | 0 | 0 | 0
10.2.2.173 | 4180 m | 136635.4803 | 38 |  | 0 | 0 | 0
10.2.2.174 | 4200 m | 136635.4803 | 38 |  | 0 | 0 | 0
10.2.2.175 | 4220 m | 136635.4803 | 38 |  | 0 | 0 | 0
10.2.2.176 | 4240 m | 136635.4803 | 39 |  | 0 | 0 | 0
10.2.2.177 | 4260 m | 136635.4803 | 39 |  | 0 | 0 | 0
10.2.2.178 | 4280 m | 136635.4803 | 39 |  | 0 | 0 | 0
10.2.2.179 | 4300 m | 136635.4803 | 39 |  | 0 | 0 | 0
10.2.2.180 | 4320 m | 136635.4803 | 39 |  | 0 | 0 | 0
10.2.2.181 | 4340 m | 136635.4803 | 39 |  | 0 | 0 | 0
10.2.2.182 | 4360 m | 136635.4803 | 39 |  | 0 | 0 | 0
10.2.2.183 | 4380 m | 136635.4803 | 39 |  | 0 | 0 | 0
10.2.2.184 | 4400 m | 136635.4803 | 39 |  | 0 | 0 | 0
10.2.2.185 | 4420 m | 136635.4803 | 39 |  | 0 | 0 | 0
10.2.2.186 | 4440 m | 136635.4803 | 39 |  | 0 | 0 | 0
10.2.2.187 | 4460 m | 136635.4803 | 39 |  | 0 | 0 | 0
10.2.2.188 | 4480 m | 136635.4803 | 40 |  | 0 | 0 | 0
10.2.2.189 | 4500 m | 136635.4803 | 40 |  | 0 | 0 | 0
10.2.2.190 | 4520 m | 136635.4803 | 40 |  | 0 | 0 | 0
10.2.2.191 | 4540 m | 136635.4803 | 40 |  | 0 | 0 | 0
10.2.2.192 | 4560 m | 136635.4803 | 40 |  | 0 | 0 | 0
10.2.2.193 | 4580 m | 136635.4803 | 40 |  | 0 | 0 | 0
10.2.2.194 | 4600 m | 136635.4803 | 40 |  | 0 | 0 | 0
10.2.2.195 | 4620 m | 136635.4803 | 40 |  | 0 | 0 | 0
10.2.2.196 | 4640 m | 136635.4803 | 40 |  | 0 | 0 | 0
10.2.2.197 | 4660 m | 136635.4803 | 40 |  | 0 | 0 | 0
10.2.2.198 | 4680 m | 136635.4803 | 40 |  | 0 | 0 | 0
10.2.2.199 | 4700 m | 136635.4803 | 40 |  | 0 | 0 | 0
10.2.2.200 | 4720 m | 136635.4803 | 41 |  | 0 | 0 | 0
10.2.2.201 | 4740 m | 136635.4803 | 41 |  | 0 | 0 | 0
10.2.2.202 | 4760 m | 136635.4803 | 41 |  | 0 | 0 | 0
10.2.2.203 | 4780 m | 136635.4803 | 41 |  | 0 | 0 | 0
10.2.2.204 | 4800 m | 136635.4803 | 41 |  | 0 | 0 | 0
10.2.2.205 | 4820 m | 136635.4803 | 41 |  | 0 | 0 | 0
10.2.2.206 | 4840 m | 136635.4803 | 41 |  | 0 | 0 | 0
10.2.2.207 | 4860 m | 136635.4803 | 41 |  | 0 | 0 | 0
10.2.2.208 | 4880 m | 136635.4803 | 41 |  | 0 | 0 | 0
10.2.2.209 | 4900 m | 136635.4803 | 41 |  | 0 | 0 | 0
10.2.2.210 | 4920 m | 136635.4803 | 41 |  | 0 | 0 | 0
10.2.2.211 | 4940 m | 136635.4803 | 41 |  | 0 | 0 | 0
10.2.2.212 | 4960 m | 136635.4803 | 42 |  | 0 | 0 | 0
10.2.2.213 | 4980 m | 136635.4803 | 42 |  | 0 | 0 | 0
10.2.2.214 | 5000 m | 136635.4803 | 42 |  | 0 | 0 | 0
10.2.2.215 | 5020 m | 136635.4803 | 42 |  | 0 | 0 | 0
10.2.2.216 | 5040 m | 136635.4803 | 42 |  | 0 | 0 | 0
10.2.2.217 | 5060 m | 136635.4803 | 42 |  | 0 | 0 | 0
10.2.2.218 | 5080 m | 136635.4803 | 42 |  | 0 | 0 | 0
10.2.2.219 | 5100 m | 136635.4803 | 42 |  | 0 | 0 | 0
10.2.2.220 | 5121 m | 143467.2543 | 42 |  | 0 | 0 | 0
10.2.3 | Construction of waterproofing and drainage & Construction of secondary lining / Konstrukcija hidroizolacije i drenaže & Konstrukcija sekundarne obloge
10.2.3.1 | 20 m | 53314.5092 | 20 |  | 0 | 0 | 0
10.2.3.2 | 40 m | 53314.5092 | 20 |  | 0 | 0 | 0
10.2.3.3 | 60 m | 53314.5092 | 20 |  | 0 | 0 | 0
10.2.3.4 | 80 m | 53314.5092 | 20 |  | 0 | 0 | 0
10.2.3.5 | 100 m | 53314.5092 | 20 |  | 0 | 0 | 0
10.2.3.6 | 120 m | 53314.5092 | 20 |  | 0 | 0 | 0
10.2.3.7 | 140 m | 53314.5092 | 20 |  | 0 | 0 | 0
10.2.3.8 | 160 m | 53314.5092 | 20 |  | 0 | 0 | 0
10.2.3.9 | 180 m | 53314.5092 | 20 |  | 0 | 0 | 0
10.2.3.10 | 200 m | 53314.5092 | 21 |  | 0 | 0 | 0
10.2.3.11 | 220 m | 53314.5092 | 21 |  | 0 | 0 | 0
10.2.3.12 | 240 m | 53314.5092 | 21 |  | 0 | 0 | 0
10.2.3.13 | 260 m | 53314.5092 | 21 |  | 0 | 0 | 0
10.2.3.14 | 280 m | 53314.5092 | 21 |  | 0 | 0 | 0
10.2.3.15 | 300 m | 53314.5092 | 21 |  | 0 | 0 | 0
10.2.3.16 | 320 m | 53314.5092 | 21 |  | 0 | 0 | 0
10.2.3.17 | 340 m | 53314.5092 | 21 |  | 0 | 0 | 0
10.2.3.18 | 360 m | 53314.5092 | 21 |  | 0 | 0 | 0
10.2.3.19 | 380 m | 53314.5092 | 21 |  | 0 | 0 | 0
10.2.3.20 | 400 m | 53314.5092 | 22 |  | 0 | 0 | 0
10.2.3.21 | 420 m | 53314.5092 | 22 |  | 0 | 0 | 0
10.2.3.22 | 440 m | 53314.5092 | 22 |  | 0 | 0 | 0
10.2.3.23 | 460 m | 53314.5092 | 22 |  | 0 | 0 | 0
10.2.3.24 | 480 m | 53314.5092 | 22 |  | 0 | 0 | 0
10.2.3.25 | 500 m | 53314.5092 | 22 |  | 0 | 0 | 0
10.2.3.26 | 520 m | 53314.5092 | 22 |  | 0 | 0 | 0
10.2.3.27 | 540 m | 53314.5092 | 22 |  | 0 | 0 | 0
10.2.3.28 | 560 m | 53314.5092 | 22 |  | 0 | 0 | 0
10.2.3.29 | 580 m | 53314.5092 | 22 |  | 0 | 0 | 0
10.2.3.30 | 600 m | 53314.5092 | 23 |  | 0 | 0 | 0
10.2.3.31 | 620 m | 53314.5092 | 23 |  | 0 | 0 | 0
10.2.3.32 | 640 m | 53314.5092 | 23 |  | 0 | 0 | 0
10.2.3.33 | 660 m | 53314.5092 | 23 |  | 0 | 0 | 0
10.2.3.34 | 680 m | 53314.5092 | 23 |  | 0 | 0 | 0
10.2.3.35 | 700 m | 53314.5092 | 23 |  | 0 | 0 | 0
10.2.3.36 | 720 m | 53314.5092 | 23 |  | 0 | 0 | 0
10.2.3.37 | 740 m | 53314.5092 | 23 |  | 0 | 0 | 0
10.2.3.38 | 760 m | 53314.5092 | 23 |  | 0 | 0 | 0
10.2.3.39 | 780 m | 53314.5092 | 23 |  | 0 | 0 | 0
10.2.3.40 | 800 m | 53314.5092 | 24 |  | 0 | 0 | 0
10.2.3.41 | 820 m | 53314.5092 | 24 |  | 0 | 0 | 0
10.2.3.42 | 840 m | 53314.5092 | 24 |  | 0 | 0 | 0
10.2.3.43 | 860 m | 53314.5092 | 24 |  | 0 | 0 | 0
10.2.3.44 | 880 m | 53314.5092 | 24 |  | 0 | 0 | 0
10.2.3.45 | 900 m | 53314.5092 | 24 |  | 0 | 0 | 0
10.2.3.46 | 920 m | 53314.5092 | 24 |  | 0 | 0 | 0
10.2.3.47 | 940 m | 53314.5092 | 24 |  | 0 | 0 | 0
10.2.3.48 | 960 m | 53314.5092 | 24 |  | 0 | 0 | 0
10.2.3.49 | 980 m | 53314.5092 | 24 |  | 0 | 0 | 0
10.2.3.50 | 1000 m | 53314.5092 | 25 |  | 0 | 0 | 0
10.2.3.51 | 1020 m | 53314.5092 | 25 |  | 0 | 0 | 0
10.2.3.52 | 1040 m | 53314.5092 | 25 |  | 0 | 0 | 0
10.2.3.53 | 1060 m | 53314.5092 | 25 |  | 0 | 0 | 0
10.2.3.54 | 1080 m | 53314.5092 | 25 |  | 0 | 0 | 0
10.2.3.55 | 1100 m | 53314.5092 | 25 |  | 0 | 0 | 0
10.2.3.56 | 1120 m | 53314.5092 | 25 |  | 0 | 0 | 0
10.2.3.57 | 1140 m | 53314.5092 | 25 |  | 0 | 0 | 0
10.2.3.58 | 1160 m | 53314.5092 | 25 |  | 0 | 0 | 0
10.2.3.59 | 1180 m | 53314.5092 | 25 |  | 0 | 0 | 0
10.2.3.60 | 1200 m | 53314.5092 | 26 |  | 0 | 0 | 0
10.2.3.61 | 1220 m | 53314.5092 | 26 |  | 0 | 0 | 0
10.2.3.62 | 1240 m | 53314.5092 | 26 |  | 0 | 0 | 0
10.2.3.63 | 1260 m | 53314.5092 | 26 |  | 0 | 0 | 0
10.2.3.64 | 1280 m | 53314.5092 | 26 |  | 0 | 0 | 0
10.2.3.65 | 1300 m | 53314.5092 | 26 |  | 0 | 0 | 0
10.2.3.66 | 1320 m | 53314.5092 | 26 |  | 0 | 0 | 0
10.2.3.67 | 1340 m | 53314.5092 | 26 |  | 0 | 0 | 0
10.2.3.68 | 1360 m | 53314.5092 | 26 |  | 0 | 0 | 0
10.2.3.69 | 1380 m | 53314.5092 | 26 |  | 0 | 0 | 0
10.2.3.70 | 1400 m | 53314.5092 | 27 |  | 0 | 0 | 0
10.2.3.71 | 1420 m | 53314.5092 | 27 |  | 0 | 0 | 0
10.2.3.72 | 1440 m | 53314.5092 | 27 |  | 0 | 0 | 0
10.2.3.73 | 1460 m | 53314.5092 | 27 |  | 0 | 0 | 0
10.2.3.74 | 1480 m | 53314.5092 | 27 |  | 0 | 0 | 0
10.2.3.75 | 1500 m | 53314.5092 | 27 |  | 0 | 0 | 0
10.2.3.76 | 1520 m | 53314.5092 | 27 |  | 0 | 0 | 0
10.2.3.77 | 1540 m | 53314.5092 | 27 |  | 0 | 0 | 0
10.2.3.78 | 1560 m | 53314.5092 | 27 |  | 0 | 0 | 0
10.2.3.79 | 1580 m | 53314.5092 | 27 |  | 0 | 0 | 0
10.2.3.80 | 1600 m | 53314.5092 | 28 |  | 0 | 0 | 0
10.2.3.81 | 1620 m | 53314.5092 | 28 |  | 0 | 0 | 0
10.2.3.82 | 1640 m | 53314.5092 | 28 |  | 0 | 0 | 0
10.2.3.83 | 1660 m | 53314.5092 | 28 |  | 0 | 0 | 0
10.2.3.84 | 1680 m | 53314.5092 | 28 |  | 0 | 0 | 0
10.2.3.85 | 1700 m | 53314.5092 | 28 |  | 0 | 0 | 0
10.2.3.86 | 1720 m | 53314.5092 | 28 |  | 0 | 0 | 0
10.2.3.87 | 1740 m | 53314.5092 | 28 |  | 0 | 0 | 0
10.2.3.88 | 1760 m | 53314.5092 | 28 |  | 0 | 0 | 0
10.2.3.89 | 1780 m | 53314.5092 | 28 |  | 0 | 0 | 0
10.2.3.90 | 1800 m | 53314.5092 | 29 |  | 0 | 0 | 0
10.2.3.91 | 1820 m | 53314.5092 | 29 |  | 0 | 0 | 0
10.2.3.92 | 1840 m | 53314.5092 | 29 |  | 0 | 0 | 0
10.2.3.93 | 1860 m | 53314.5092 | 29 |  | 0 | 0 | 0
10.2.3.94 | 1880 m | 53314.5092 | 29 |  | 0 | 0 | 0
10.2.3.95 | 1900 m | 53314.5092 | 29 |  | 0 | 0 | 0
10.2.3.96 | 1920 m | 53314.5092 | 29 |  | 0 | 0 | 0
10.2.3.97 | 1940 m | 53314.5092 | 29 |  | 0 | 0 | 0
10.2.3.98 | 1960 m | 53314.5092 | 29 |  | 0 | 0 | 0
10.2.3.99 | 1980 m | 53314.5092 | 29 |  | 0 | 0 | 0
10.2.3.100 | 2000 m | 53314.5092 | 30 |  | 0 | 0 | 0
10.2.3.101 | 2020 m | 53314.5092 | 30 |  | 0 | 0 | 0
10.2.3.102 | 2040 m | 53314.5092 | 30 |  | 0 | 0 | 0
10.2.3.103 | 2060 m | 53314.5092 | 30 |  | 0 | 0 | 0
10.2.3.104 | 2080 m | 53314.5092 | 30 |  | 0 | 0 | 0
10.2.3.105 | 2100 m | 53314.5092 | 30 |  | 0 | 0 | 0
10.2.3.106 | 2120 m | 53314.5092 | 30 |  | 0 | 0 | 0
10.2.3.107 | 2140 m | 53314.5092 | 30 |  | 0 | 0 | 0
10.2.3.108 | 2160 m | 53314.5092 | 30 |  | 0 | 0 | 0
10.2.3.109 | 2180 m | 53314.5092 | 30 |  | 0 | 0 | 0
10.2.3.110 | 2200 m | 53314.5092 | 31 |  | 0 | 0 | 0
10.2.3.111 | 2220 m | 53314.5092 | 31 |  | 0 | 0 | 0
10.2.3.112 | 2240m | 53314.5092 | 31 |  | 0 | 0 | 0
10.2.3.113 | 2260 m | 53314.5092 | 31 |  | 0 | 0 | 0
10.2.3.114 | 2280 m | 53314.5092 | 31 |  | 0 | 0 | 0
10.2.3.115 | 2300 m | 53314.5092 | 31 |  | 0 | 0 | 0
10.2.3.116 | 2320 m | 53314.5092 | 31 |  | 0 | 0 | 0
10.2.3.117 | 2340 m | 53314.5092 | 31 |  | 0 | 0 | 0
10.2.3.118 | 2360 m | 53314.5092 | 31 |  | 0 | 0 | 0
10.2.3.119 | 2380 m | 53314.5092 | 31 |  | 0 | 0 | 0
10.2.3.120 | 2400 m | 53314.5092 | 32 |  | 0 | 0 | 0
10.2.3.121 | 2420 m | 53314.5092 | 32 |  | 0 | 0 | 0
10.2.3.122 | 2440 m | 53314.5092 | 32 |  | 0 | 0 | 0
10.2.3.123 | 2460 m | 53314.5092 | 32 |  | 0 | 0 | 0
10.2.3.124 | 2480 m | 53314.5092 | 32 |  | 0 | 0 | 0
10.2.3.125 | 2500 m | 53314.5092 | 32 |  | 0 | 0 | 0
10.2.3.126 | 2520 m | 53314.5092 | 32 |  | 0 | 0 | 0
10.2.3.127 | 2540 m | 53314.5092 | 32 |  | 0 | 0 | 0
10.2.3.128 | 2560 m | 53314.5092 | 32 |  | 0 | 0 | 0
10.2.3.129 | 2580 m | 53314.5092 | 32 |  | 0 | 0 | 0
10.2.3.130 | 2600 m | 53314.5092 | 33 |  | 0 | 0 | 0
10.2.3.131 | 2620 m | 53314.5092 | 33 |  | 0 | 0 | 0
10.2.3.132 | 2640 m | 53314.5092 | 33 |  | 0 | 0 | 0
10.2.3.133 | 2660 m | 53314.5092 | 33 |  | 0 | 0 | 0
10.2.3.134 | 2680 m | 53314.5092 | 33 |  | 0 | 0 | 0
10.2.3.135 | 2700 m | 53314.5092 | 33 |  | 0 | 0 | 0
10.2.3.136 | 2720 m | 53314.5092 | 33 |  | 0 | 0 | 0
10.2.3.137 | 2740 m | 53314.5092 | 33 |  | 0 | 0 | 0
10.2.3.138 | 2760 m | 53314.5092 | 33 |  | 0 | 0 | 0
10.2.3.139 | 2780 m | 53314.5092 | 33 |  | 0 | 0 | 0
10.2.3.140 | 2800 m | 53314.5092 | 34 |  | 0 | 0 | 0
10.2.3.141 | 2820 m | 53314.5092 | 34 |  | 0 | 0 | 0
10.2.3.142 | 2840 m | 53314.5092 | 34 |  | 0 | 0 | 0
10.2.3.143 | 2860 m | 53314.5092 | 34 |  | 0 | 0 | 0
10.2.3.144 | 2880 m | 53314.5092 | 34 |  | 0 | 0 | 0
10.2.3.145 | 2900 m | 53314.5092 | 34 |  | 0 | 0 | 0
10.2.3.146 | 2920 m | 53314.5092 | 34 |  | 0 | 0 | 0
10.2.3.147 | 2940 m | 53314.5092 | 34 |  | 0 | 0 | 0
10.2.3.148 | 2960 m | 53314.5092 | 34 |  | 0 | 0 | 0
10.2.3.149 | 2980 m | 53314.5092 | 34 |  | 0 | 0 | 0
10.2.3.150 | 3000 m | 53314.5092 | 34 |  | 0 | 0 | 0
10.2.3.151 | 3020 m | 53314.5092 | 34 |  | 0 | 0 | 0
10.2.3.152 | 3040 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.153 | 3060 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.154 | 3080 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.155 | 3100 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.156 | 3120 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.157 | 3140 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.158 | 3160 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.159 | 3180 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.160 | 3200 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.161 | 3220 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.162 | 3240 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.163 | 3260 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.164 | 3280 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.165 | 3300 m | 53314.5092 | 35 |  | 0 | 0 | 0
10.2.3.166 | 3320 m | 53314.5092 | 36 |  | 0 | 0 | 0
10.2.3.167 | 3340 m | 53314.5092 | 36 |  | 0 | 0 | 0
10.2.3.168 | 3360 m | 53314.5092 | 36 |  | 0 | 0 | 0
10.2.3.169 | 3380 m | 53314.5092 | 36 |  | 0 | 0 | 0
10.2.3.170 | 3400 m | 53314.5092 | 36 |  | 0 | 0 | 0
10.2.3.171 | 3420 m | 53314.5092 | 36 |  | 0 | 0 | 0
10.2.3.172 | 3440 m | 53314.5092 | 36 |  | 0 | 0 | 0
10.2.3.173 | 3460 m | 53314.5092 | 36 |  | 0 | 0 | 0
10.2.3.174 | 3480 m | 53314.5092 | 36 |  | 0 | 0 | 0
10.2.3.175 | 3500 m | 53314.5092 | 36 |  | 0 | 0 | 0
10.2.3.176 | 3520 m | 53314.5092 | 36 |  | 0 | 0 | 0
10.2.3.177 | 3540 m | 53314.5092 | 36 |  | 0 | 0 | 0
10.2.3.178 | 3560 m | 53314.5092 | 37 |  | 0 | 0 | 0
10.2.3.179 | 3580 m | 53314.5092 | 37 |  | 0 | 0 | 0
10.2.3.180 | 3600 m | 53314.5092 | 37 |  | 0 | 0 | 0
10.2.3.181 | 3620 m | 53314.5092 | 37 |  | 0 | 0 | 0
10.2.3.182 | 3640 m | 53314.5092 | 37 |  | 0 | 0 | 0
10.2.3.183 | 3660 m | 53314.5092 | 37 |  | 0 | 0 | 0
10.2.3.184 | 3680 m | 53314.5092 | 37 |  | 0 | 0 | 0
10.2.3.185 | 3700 m | 53314.5092 | 37 |  | 0 | 0 | 0
10.2.3.186 | 3720 m | 53314.5092 | 37 |  | 0 | 0 | 0
10.2.3.187 | 3740 m | 53314.5092 | 37 |  | 0 | 0 | 0
10.2.3.188 | 3760 m | 53314.5092 | 37 |  | 0 | 0 | 0
10.2.3.189 | 3780 m | 53314.5092 | 37 |  | 0 | 0 | 0
10.2.3.190 | 3800 m | 53314.5092 | 38 |  | 0 | 0 | 0
10.2.3.191 | 3820 m | 53314.5092 | 38 |  | 0 | 0 | 0
10.2.3.192 | 3840 m | 53314.5092 | 38 |  | 0 | 0 | 0
10.2.3.193 | 3860 m | 53314.5092 | 38 |  | 0 | 0 | 0
10.2.3.194 | 3880 m | 53314.5092 | 38 |  | 0 | 0 | 0
10.2.3.195 | 3900 m | 53314.5092 | 38 |  | 0 | 0 | 0
10.2.3.196 | 3920 m | 53314.5092 | 38 |  | 0 | 0 | 0
10.2.3.197 | 3940 m | 53314.5092 | 38 |  | 0 | 0 | 0
10.2.3.198 | 3960 m | 53314.5092 | 38 |  | 0 | 0 | 0
10.2.3.199 | 3980 m | 53314.5092 | 38 |  | 0 | 0 | 0
10.2.3.200 | 4000 m | 53314.5092 | 38 |  | 0 | 0 | 0
10.2.3.201 | 4020 m | 53314.5092 | 38 |  | 0 | 0 | 0
10.2.3.202 | 4040 m | 53314.5092 | 39 |  | 0 | 0 | 0
10.2.3.203 | 4060 m | 53314.5092 | 39 |  | 0 | 0 | 0
10.2.3.204 | 4080 m | 53314.5092 | 39 |  | 0 | 0 | 0
10.2.3.205 | 4100 m | 53314.5092 | 39 |  | 0 | 0 | 0
10.2.3.206 | 4120 m | 53314.5092 | 39 |  | 0 | 0 | 0
10.2.3.207 | 4140 m | 53314.5092 | 39 |  | 0 | 0 | 0
10.2.3.208 | 4160 m | 53314.5092 | 39 |  | 0 | 0 | 0
10.2.3.209 | 4180 m | 53314.5092 | 39 |  | 0 | 0 | 0
10.2.3.210 | 4200 m | 53314.5092 | 39 |  | 0 | 0 | 0
10.2.3.211 | 4220 m | 53314.5092 | 39 |  | 0 | 0 | 0
10.2.3.212 | 4240 m | 53314.5092 | 39 |  | 0 | 0 | 0
10.2.3.213 | 4260 m | 53314.5092 | 39 |  | 0 | 0 | 0
10.2.3.214 | 4280 m | 53314.5092 | 40 |  | 0 | 0 | 0
10.2.3.215 | 4300 m | 53314.5092 | 40 |  | 0 | 0 | 0
10.2.3.216 | 4320 m | 53314.5092 | 40 |  | 0 | 0 | 0
10.2.3.217 | 4340 m | 53314.5092 | 40 |  | 0 | 0 | 0
10.2.3.218 | 4360 m | 53314.5092 | 40 |  | 0 | 0 | 0
10.2.3.219 | 4380 m | 53314.5092 | 40 |  | 0 | 0 | 0
10.2.3.220 | 4400 m | 53314.5092 | 40 |  | 0 | 0 | 0
10.2.3.221 | 4420 m | 53314.5092 | 40 |  | 0 | 0 | 0
10.2.3.222 | 4440 m | 53314.5092 | 40 |  | 0 | 0 | 0
10.2.3.223 | 4460 m | 53314.5092 | 40 |  | 0 | 0 | 0
10.2.3.224 | 4480 m | 53314.5092 | 40 |  | 0 | 0 | 0
10.2.3.225 | 4500 m | 53314.5092 | 40 |  | 0 | 0 | 0
10.2.3.226 | 4520 m | 53314.5092 | 41 |  | 0 | 0 | 0
10.2.3.227 | 4540 m | 53314.5092 | 41 |  | 0 | 0 | 0
10.2.3.228 | 4560 m | 53314.5092 | 41 |  | 0 | 0 | 0
10.2.3.229 | 4580 m | 53314.5092 | 41 |  | 0 | 0 | 0
10.2.3.230 | 4600 m | 53314.5092 | 41 |  | 0 | 0 | 0
10.2.3.231 | 4620 m | 53314.5092 | 41 |  | 0 | 0 | 0
10.2.3.232 | 4640 m | 53314.5092 | 41 |  | 0 | 0 | 0
10.2.3.233 | 4660 m | 53314.5092 | 41 |  | 0 | 0 | 0
10.2.3.234 | 4680 m | 53314.5092 | 41 |  | 0 | 0 | 0
10.2.3.235 | 4700 m | 53314.5092 | 41 |  | 0 | 0 | 0
10.2.3.236 | 4720 m | 53314.5092 | 41 |  | 0 | 0 | 0
10.2.3.237 | 4740 m | 53314.5092 | 41 |  | 0 | 0 | 0
10.2.3.238 | 4760 m | 53314.5092 | 42 |  | 0 | 0 | 0
10.2.3.239 | 4780 m | 53314.5092 | 42 |  | 0 | 0 | 0
10.2.3.240 | 4800 m | 53314.5092 | 42 |  | 0 | 0 | 0
10.2.3.241 | 4820 m | 53314.5092 | 42 |  | 0 | 0 | 0
10.2.3.242 | 4840 m | 53314.5092 | 42 |  | 0 | 0 | 0
10.2.3.243 | 4860 m | 53314.5092 | 42 |  | 0 | 0 | 0
10.2.3.244 | 4880 m | 53314.5092 | 42 |  | 0 | 0 | 0
10.2.3.245 | 4900 m | 53314.5092 | 42 |  | 0 | 0 | 0
10.2.3.246 | 4920 m | 53314.5092 | 42 |  | 0 | 0 | 0
10.2.3.247 | 4940 m | 53314.5092 | 43 |  | 0 | 0 | 0
10.2.3.248 | 4960 m | 53314.5092 | 43 |  | 0 | 0 | 0
10.2.3.249 | 4980 m | 53314.5092 | 43 |  | 0 | 0 | 0
10.2.3.250 | 5000 m | 53314.5092 | 43 |  | 0 | 0 | 0
10.2.3.251 | 5020 m | 53314.5092 | 43 |  | 0 | 0 | 0
10.2.3.252 | 5040 m | 53314.5092 | 43 |  | 0 | 0 | 0
10.2.3.253 | 5060 m | 53314.5092 | 43 |  | 0 | 0 | 0
10.2.3.254 | 5080 m | 53314.5092 | 43 |  | 0 | 0 | 0
10.2.3.255 | 5100 m | 53314.5092 | 43 |  | 0 | 0 | 0
10.2.3.256 | 5121 m | 55980.2347 | 43 |  | 0 | 0 | 0
10.2.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi I ploca, drenazni sistem)
10.2.4.1 | 200 m | 80000 | 22 |  | 0 | 0 | 0
10.2.4.2 | 400 m | 80000 | 23 |  | 0 | 0 | 0
10.2.4.3 | 600 m | 80000 | 24 |  | 0 | 0 | 0
10.2.4.4 | 800 m | 80000 | 25 |  | 0 | 0 | 0
10.2.4.5 | 1000 m | 80000 | 26 |  | 0 | 0 | 0
10.2.4.6 | 1200 m | 80000 | 27 |  | 0 | 0 | 0
10.2.4.7 | 1400 m | 80000 | 28 |  | 0 | 0 | 0
10.2.4.8 | 1600 m | 80000 | 29 |  | 0 | 0 | 0
10.2.4.9 | 1800 m | 80000 | 30 |  | 0 | 0 | 0
10.2.4.10 | 2000 m | 80000 | 31 |  | 0 | 0 | 0
10.2.4.11 | 2200 m | 80000 | 32 |  | 0 | 0 | 0
10.2.4.12 | 2400 m | 80000 | 33 |  | 0 | 0 | 0
10.2.4.13 | 2600 m | 80000 | 34 |  | 0 | 0 | 0
10.2.4.14 | 2800 m | 80000 | 35 |  | 0 | 0 | 0
10.2.4.15 | 3000 m | 80000 | 36 |  | 0 | 0 | 0
10.2.4.16 | 3200 m | 80000 | 37 |  | 0 | 0 | 0
10.2.4.17 | 3400 m | 80000 | 37 |  | 0 | 0 | 0
10.2.4.18 | 3600 m | 80000 | 38 |  | 0 | 0 | 0
10.2.4.19 | 3800 m | 80000 | 39 |  | 0 | 0 | 0
10.2.4.20 | 4000 m | 80000 | 40 |  | 0 | 0 | 0
10.2.4.21 | 4200 m | 80000 | 40 |  | 0 | 0 | 0
10.2.4.22 | 4400 m | 80000 | 41 |  | 0 | 0 | 0
10.2.4.23 | 4600 m | 80000 | 42 |  | 0 | 0 | 0
10.2.4.24 | 4800 m | 80000 | 43 |  | 0 | 0 | 0
10.2.4.25 | 5000 m | 80000 | 44 |  | 0 | 0 | 0
10.2.4.26 | 5121 m | 48400 | 44 |  | 0 | 0 | 0
10.2.5 | Construction of pavement/ Izgradnja kolovoza
10.2.5.1 | Left tube/ Lijeva cijev
0-500 m
10.2.5.1.1 | Layer/ Sloj 1 | 36326.48 | 44 |  | 0 | 0 | 0
10.2.5.1.2 | Layer/ Sloj 2 | 36326.48 | 45 |  | 0 | 0 | 0
10.2.5.1.3 | Layer/ Sloj 3 | 40867.29 | 45 |  | 0 | 0 | 0
500-1000 m
10.2.5.1.4 | Layer/ Sloj 1 | 36326.48 | 44 |  | 0 | 0 | 0
10.2.5.1.5 | Layer/ Sloj 2 | 36326.48 | 45 |  | 0 | 0 | 0
10.2.5.1.6 | Layer/ Sloj 3 | 40867.29 | 45 |  | 0 | 0 | 0
1000-1500 m
10.2.5.1.7 | Layer/ Sloj 1 | 36326.48 | 44 |  | 0 | 0 | 0
10.2.5.1.8 | Layer/ Sloj 2 | 36326.48 | 45 |  | 0 | 0 | 0
10.2.5.1.9 | Layer/ Sloj 3 | 40867.29 | 45 |  | 0 | 0 | 0
1500-2000 m
10.2.5.1.10 | Layer/ Sloj 1 | 36326.48 | 44 |  | 0 | 0 | 0
10.2.5.1.11 | Layer/ Sloj 2 | 36326.48 | 45 |  | 0 | 0 | 0
10.2.5.1.12 | Layer/ Sloj 3 | 40867.29 | 45 |  | 0 | 0 | 0
2000-2500 m
10.2.5.1.13 | Layer/ Sloj 1 | 36326.48 | 44 |  | 0 | 0 | 0
10.2.5.1.14 | Layer/ Sloj 2 | 36326.48 | 45 |  | 0 | 0 | 0
10.2.5.1.15 | Layer/ Sloj 3 | 40867.29 | 45 |  | 0 | 0 | 0
2500-2671.48 m
10.2.5.1.16 | Layer/ Sloj 1 | 12458.53 | 44 |  | 0 | 0 | 0
10.2.5.1.17 | Layer/ Sloj 2 | 12458.53 | 45 |  | 0 | 0 | 0
10.2.5.1.18 | Layer/ Sloj 3 | 14015.88 | 45 |  | 0 | 0 | 0
10.2.5.2 | Right tube/ Desna cijev
0-500 m
10.2.5.2.1 | Layer/ Sloj 1 | 36326.48 | 44 |  | 0 | 0 | 0
10.2.5.2.2 | Layer/ Sloj 2 | 36326.48 | 45 |  | 0 | 0 | 0
10.2.5.2.3 | Layer/ Sloj 3 | 40867.29 | 45 |  | 0 | 0 | 0
500-1000 m
10.2.5.2.4 | Layer/ Sloj 1 | 36326.48 | 44 |  | 0 | 0 | 0
10.2.5.2.5 | Layer/ Sloj 2 | 36326.48 | 45 |  | 0 | 0 | 0
10.2.5.2.6 | Layer/ Sloj 3 | 40867.29 | 45 |  | 0 | 0 | 0
1000-1500 m
10.2.5.2.7 | Layer/ Sloj 1 | 36326.48 | 44 |  | 0 | 0 | 0
10.2.5.2.8 | Layer/ Sloj 2 | 36326.48 | 45 |  | 0 | 0 | 0
10.2.5.2.9 | Layer/ Sloj 3 | 40867.29 | 45 |  | 0 | 0 | 0
1500-2000 m
10.2.5.2.10 | Layer/ Sloj 1 | 36326.48 | 44 |  | 0 | 0 | 0
10.2.5.2.11 | Layer/ Sloj 2 | 36326.48 | 45 |  | 0 | 0 | 0
10.2.5.2.12 | Layer/ Sloj 3 | 40867.29 | 45 |  | 0 | 0 | 0
2000-2545.58 m
10.2.5.2.13 | Layer/ Sloj 1 | 39638 | 44 |  | 0 | 0 | 0
10.2.5.2.14 | Layer/ Sloj 2 | 39638 | 45 |  | 0 | 0 | 0
10.2.5.2.15 | Layer/ Sloj 3 | 44592.78 | 45 |  | 0 | 0 | 0
10.2.6 | Tunnel facilities/ Tunelski objekti
10.2.6.1 | Construction of Power Station/ Izgradnja elektro-stanice (1) | 165282.22 | 47 |  | 0 | 0 | 0
10.2.6.2 | Construction of Power Station/ Izgradnja elektro-stanice (2) | 165282.22 | 47 |  | 0 | 0 | 0
10.2.6.3 | Construction of antifire reservoir/Izgradnja protivpožarnog rezervoara | 86312.55 | 48 |  | 0 | 0 | 0
10.2.7 | Tunnel Equipment/ Tunelska oprema
10.2.7.1 | Right tube/ Desna cijev
10.2.7.1.1 | 90% (Equipment installed/Oprema postavljena) | 2548254.82 | 48 |  | 0 | 0 | 0
10.2.7.1.2 | 10% (Equipment tested/Oprema ispitana) | 283139.42 | 48 |  | 0 | 0 | 0
10.2.7.2 | Left tube/ Lijeva cijev
10.2.7.2.1 | 90% (Equipment installed/Oprema postavljena) | 2673715.83 | 48 |  | 0 | 0 | 0
10.2.7.2.2 | 10% (Equipment tested/Oprema ispitana) | 297079.54 | 48 |  | 0 | 0 | 0
| Sub Total / Suma stavke 10.2 | 58179591.01 |  |  | 12716946.3667 | 2869345.0864 | 15586291.4531
Cost center/ Troškovno mjesto 10.3 | Road Works/Radovi na putevima (LK29+174.921—LK29+317.20 , RK29+231.643—RK29+350.00)
Completion of/Završetak:
10.3.1 | Subgrade/ Posteljica
10.3.1.1 | Top soil removal/ Uklanjanje humusa
10.3.1.1.1 | RK29+231.643—RK29+350.000 (Inc. 0 - 142.279 m (LK); 0 - 118.357 m (RK)) | 26599.11 | 19 |  | 0 | 0 | 0
10.3.1.2 | Earthworks/ Zemljani radovi |  | 37
At every 250 m and certain high / Na svakih 250m i određenoj visini
10.3.1.2.1 | RK29+231.64 - RK29+350.000, Layers 1,2,3,4,5,6
10.3.1.2.1.1 | RK29+231.64 - RK29+350.000, Layer 1 | 66081.9737 |  |  | 0 | 0 | 0
10.3.1.2.1.2 | RK29+231.64 - RK29+350.000, Layer 2 | 66081.9737 |  |  | 0 | 0 | 0
10.3.1.2.1.3 | RK29+231.64 - RK29+350.000, Layer 3 | 66081.9737 |  |  | 0 | 0 | 0
10.3.1.2.1.4 | RK29+231.64 - RK29+350.000, Layer 4 | 66081.9737 |  |  | 0 | 0 | 0
10.3.1.2.1.5 | RK29+231.64 - RK29+350.000, Layer 5 | 66081.9737 |  |  | 0 | 0 | 0
10.3.1.2.1.6 | RK29+231.64 - RK29+350.000, Layer 6 | 21476.6415 |  |  | 0 | 0 | 0
10.3.1.3 | Road Foundation/Temelj puta
10.3.1.3.1 | 0 - 118.357 m right side/ desna strana | 10553.72 | 38 |  | 0 | 0 | 0
10.3.1.3.2 | 0 - 142.279 m left side/ lijeva strana | 10553.72 | 38 |  | 0 | 0 | 0
10.3.2 | Engineering structures/ Inženjerske strukture |  | 34
10.3.2.1 | Concrete wall / Betonski zid
80% for the concrete wall, the milestone is 50m length, no matter the height+ 5% for the "after work" the whole length of each retaining wall + 5% for the "correction of the crown" the whole length of each retaining wall+10% for the "wall surface" the whole length of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
10.3.2.1.1 | Concrete wall/ Betonski zid RK 29+225.643 - RK 29+290 (64.357m) 80%, Layers 1,2
10.3.2.1.1.1 | Segment 1 RK 29+225.643 ~ RK 29+275.643 (50m) | 223880.6781 |  |  | 0 | 0 | 0
10.3.2.1.1.2 | Segment 2 RK 29+275.643 ~ RK 29+290 (14.357m) | 64285.0979 |  |  | 0 | 0 | 0
10.3.2.1.1.3 | Concrete wall/ Betonski zid RK 29+225.643 - RK 29+290 (64.357m) After work 5% | 18010.361 |  |  | 0 | 0 | 0
10.3.2.1.1.4 | Concrete wall/ Betonski zid RK 29+225.643 - RK 29+290 (64.357m) Correction of the crown 5% | 18010.361 |  |  | 0 | 0 | 0
10.3.2.1.1.5 | Concrete wall/ Betonski zid RK 29+225.643 - RK 29+290 (64.357m) - 10% Wall surface | 36020.722 |  |  | 0 | 0 | 0
10.3.2.2 | Culvert/ Propust | 17628.71 | 35 |  | 0 | 0 | 0
10.3.3 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
10.3.3.1 | LK29+174.921 —LK29+317.200 (142.279 m) | 52624.2712 | 38 |  | 0 | 0 | 0
10.3.3.2 | RK29+231.643—RK29+350.000 (118.357 m) | 43776.3188 | 38 |  | 0 | 0 | 0
10.3.4 | Pavement structure/ Kolovozna konstrukcija
10.3.4.1 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana | 12596.5042 | 39 |  | 0 | 0 | 0
10.3.4.2 | asphalt concrete layer/ sloj asfaltnog betona 1 left side/ lijeva strana | 15142.4758 | 39 |  | 0 | 0 | 0
10.3.4.3 | asphalt concrete layer/ sloj asfaltnog betona 2 right side/ desna strana | 12596.5042 | 40 |  | 0 | 0 | 0
10.3.4.4 | asphalt concrete layer/ sloj asfaltnog betona 2 left side/ lijeva strana | 15142.4758 | 40 |  | 0 | 0 | 0
10.3.4.5 | asphalt concrete layer/ sloj asfaltnog betona 3 right side/ desna strana | 13996.9472 | 41 |  | 0 | 0 | 0
10.3.4.6 | asphalt concrete layer/ sloj asfaltnog betona 3 left side/ lijeva strana | 16825.9728 | 41 |  | 0 | 0 | 0
| Sub Total / Suma stavke 10.3 | 960130.46 |  |  | 0 | 0 | 0
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 10 | 60993857.32 |  |  | 12716946.3667 | 2869345.0864 | 15586291.4531

## COST CENTER 11
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
COST CENTER 11/TROŠKOVNI CENTAR 11 rev Bridge,Tunnel and Open Route
Cost center No./ Troškovno mjesto Br. | 11 | Subsection/Podsekcija 3.4 (LK29+317.20-LK31+556.000, RK29+350.00- RK31+624.00)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost center/ Troškovno mjesto 11.1 | Road Works/Radovi na putevima LK29+317.200—LK29+489.000 RK29+350.000—RK29+710.000
Completion of/Završetak:
11.1.1 | Subgrade/ Posteljica
11.1.1.1 | Top soil removal/ Uklanjanje humusa
11.1.1.1 | RK29+350.000—RK29+600.000 (Inc.0 - 172 m (LK); 0 - 250 m (RK)) | 14836.6688 | 23 |  | 0 | 0 | 0
11.1.1.2 | RK29+600.000—RK29+710.000 (Inc. 250 - 360 m (RK)) | 3867.3781 | 23 |  | 0 | 0 | 0
11.1.1.2 | Earthworks/ Zemljani radovi |  | 37
At every 250 m and certain high /Na svakih 250m i određenoj visini
11.1.1.2.1 | RK29+350.00 - RK29+600.00, layers 1,2,3,4,5,6,7,8, 9,10
11.1.1.2.1.1 | RK29+350.00 - RK29+600.00, layer 1 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.1.2 | RK29+350.00 - RK29+600.00, layer 2 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.1.3 | RK29+350.00 - RK29+600.00, layer 3 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.1.4 | RK29+350.00 - RK29+600.00, layer 4 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.1.5 | RK29+350.00 - RK29+600.00, layer 5 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.1.6 | RK29+350.00 - RK29+600.00, layer 6 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.1.7 | RK29+350.00 - RK29+600.00, layer 7 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.1.8 | RK29+350.00 - RK29+600.00, layer 8 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.1.9 | RK29+350.00 - RK29+600.00, layer 9 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.1.10 | RK29+350.00 - RK29+600.00, layer 10 | 6715.4293 |  |  | 0 | 0 | 0
11.1.1.2.2 | RK29+600.00 - RK29+710.00, layers 11,12,13,14,15,16,17
11.1.1.2.2.11 | RK29+600.00 - RK29+710.00, layer 11 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.2.12 | RK29+600.00 - RK29+710.00, layer 12 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.2.13 | RK29+600.00 - RK29+710.00, layer 13 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.2.14 | RK29+600.00 - RK29+710.00, layer 14 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.2.15 | RK29+600.00 - RK29+710.00, layer 15 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.2.16 | RK29+600.00 - RK29+710.00, layer 16 | 15262.3394 |  |  | 0 | 0 | 0
11.1.1.2.2.17 | RK29+600.00 - RK29+710.00, layer 17 | 11790.1572 |  |  | 0 | 0 | 0
11.1.1.3 | Road Foundation/ Temelj puta | 14842.3969 | 38 |  | 0 | 0 | 0
11.1.2 | Engineering structures/ Inženjerske konstrukcije
11.1.2.1 | Concrete wall/ Betonski zid
80% for the concrete wall, the milestone is 50m length, no matter the height+ 5% for the "after work" the whole length of each retaining wall + 5% for the "correction of the crown" the whole length of each retaining wall+10% for the "wall surface" the whole length of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
11.1.2.1.1 | Concrete wall/ Betonski zid RK 29+490 - RK 29+575 (85m)
11.1.2.1.1.1 | Concrete wall/ Betonski zid RK 29+490 - RK 29+540 (50m) - 80% | 124554.9568 |  |  | 0 | 0 | 0
11.1.2.1.1.2 | Concrete wall/ Betonski zid RK 29+540 - RK 29+575 (35m) - 80% | 87188.4698 |  |  | 0 | 0 | 0
11.1.2.1.1.3 | Concrete wall/ Betonski zid RK 29+490 - RK 29+575 - After work 5% | 13233.9642 |  |  | 0 | 0 | 0
11.1.2.1.1.4 | Concrete wall/ Betonski zid RK 29+490 - RK 29+575 - Correction of the crown 5% | 13233.9642 |  |  | 0 | 0 | 0
11.1.2.1.1.5 | Concrete wall/ Betonski zid RK 29+490 - RK 29+575 - 10% Wall surface | 26467.9283 |  |  | 0 | 0 | 0
11.1.2.1.2 | Concrete wall/ Betonski zid RK29+570-RK29+665 (95m)
11.1.2.1.2.1 | Concrete wall/ Betonski zid RK29+570-RK29+620 (50m) - 80% | 124554.9568 |  |  | 0 | 0 | 0
11.1.2.1.2.2 | Concrete wall/ Betonski zid RK29+620-RK29+665 ( 45m) - 80% | 112099.4611 |  |  | 0 | 0 | 0
11.1.2.1.2.3 | Concrete wall/ Betonski zid RK RK29+570-RK29+665 - After work 5% | 14790.9011 |  |  | 0 | 0 | 0
11.1.2.1.2.4 | Concrete wall/ Betonski zid RK29+570-RK29+665 - Correction of the crown 5% | 14790.9011 |  |  | 0 | 0 | 0
11.1.2.1.2.5 | Concrete wall/ Betonski zid RK29+570-RK29+665 - 10% Wall surface | 29581.8022 |  |  | 0 | 0 | 0
11.1.2.2 | Reinforced earth wall/ Ojačani zemljani zid |  | 28
The milestone is 2.25 m height of each layer and no matter on the length / Reper je visina 2.25 m za svaki sloj, bez obzira na dužinu
11.1.2.2.1 | Reinforced soil retaining wall RK17+520.00--RK17+740.00 / Potporni zid od armirane zemlje
11.1.2.2.1.1 | Layer/Sloj 1 (0.0 -2.2 m height) | 8790.9729 |  |  | 0 | 0 | 0
11.1.2.2.1.2 | Layer/Sloj 2 (2.2 -4.4 m height) | 8790.9729 |  |  | 0 | 0 | 0
11.1.2.2.1.3 | Layer/Sloj 3 (4.4 -6.6 m height) | 8790.9729 |  |  | 0 | 0 | 0
11.1.2.2.1.4 | Layer/Sloj 4 (6.6 -8.8 m height) | 8790.9729 |  |  | 0 | 0 | 0
11.1.2.2.1.5 | Layer/Sloj 5 (8.8 -11.0 m height) | 8790.9729 |  |  | 0 | 0 | 0
11.1.2.2.1.6 | Layer/Sloj 6 (11.0 -13.2 m height) | 8790.9729 |  |  | 0 | 0 | 0
11.1.2.2.1.7 | Layer/Sloj 7 (13.2 -15.4 m height) | 8790.9729 |  |  | 0 | 0 | 0
11.1.2.2.1.8 | Layer/Sloj 8 (15.4 -17.6 m height) | 8790.9729 |  |  | 0 | 0 | 0
11.1.2.2.1.9 | Layer/Sloj 9 (17.6 -19.8 m height) | 8790.9729 |  |  | 0 | 0 | 0
11.1.2.2.1.10 | Layer/Sloj 10 (19.8 -22.0 m height) | 8790.9729 |  |  | 0 | 0 | 0
11.1.2.2.1.11 | Layer/Sloj 11 (22.0 -24.2 m height) | 8790.9729 |  |  | 0 | 0 | 0
11.1.2.2.1.12 | Layer/Sloj 12 (24.2 -25.67 m height) | 5873.9683 |  |  | 0 | 0 | 0
11.1.2.3 | Culvert/ Propust
11.1.2.3.1 | RK29+443.932 (78m) | 20184.0643 | 29 |  | 0 | 0 | 0
11.1.2.3.2 | RK29+697.798 (31m) | 8021.8717 | 29 |  | 0 | 0 | 0
11.1.3 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
11.1.3.1 | LK29+317.200—LK29+489.000 (172 m) | 21916.1863 | 38 |  | 0 | 0 | 0
11.1.3.2 | RK29+350.000—RK29+710.000 (360 m) | 45871.0876 | 38 |  | 0 | 0 | 0
11.1.4 | Pavement structure/ Kolovozna konstrukcija | 60685.3277 | 41-43 |  | 0 | 0 | 0
| Sub Total / Suma stavke 11.1 | 1100737.6343 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 11.3 | Bridge/Most Podovi LK29+489.000—LK29+661.000
Completion of/Završetak:
Left Bridge/ Lijevi most
11.3.1 | Foundation concrete/ Temeljni beton
11.3.1.1 | A1 | 36123.17
11.3.1.2 | P1 | 36123.17 |  |  | 0 | 0 | 0
11.3.1.3 | P2 | 36123.17 |  |  | 0 | 0 | 0
11.3.1.4 | P3 | 36123.17 |  |  | 0 | 0 | 0
11.3.1.5 | P4 | 36123.17 |  |  | 0 | 0 | 0
11.3.1.6 | P5 | 36123.17 |  |  | 0 | 0 | 0
11.3.1.7 | P6 | 36123.17 |  |  | 0 | 0 | 0
11.3.1.8 | A2 | 36123.17 |  |  | 0 | 0 | 0
11.3.2 | Abutments and Piers elevation/ Elevacija mosnih stubova
11.3.2.1 | A1 | 68559.156 |  |  | 0 | 0 | 0
11.3.2.2 | P1 stage 1 (1.2m) | 3525.1513 |  |  | 0 | 0 | 0
11.3.2.3 | P1 stage 2 (2m) | 5875.2521 |  |  | 0 | 0 | 0
11.3.2.4 | P1 stage 3 (4.6m) | 13513.0798 |  |  | 0 | 0 | 0
11.3.2.5 | P1 stage 4 (3.2m) | 9400.4033 |  |  | 0 | 0 | 0
11.3.2.6 | P2 stage 1 (1.2m) | 3525.1513 |  |  | 0 | 0 | 0
11.3.2.7 | P2 stage 2 (2m) | 5875.2521 |  |  | 0 | 0 | 0
11.3.2.8 | P2 stage 3 (5m) | 14688.1302 |  |  | 0 | 0 | 0
11.3.2.9 | P2 stage 4 (5m) | 14688.1302 |  |  | 0 | 0 | 0
11.3.2.10 | P2 stage 5 (3.766m) | 11063.0997 |  |  | 0 | 0 | 0
11.3.2.11 | P2 stage 6 (3.2m) | 9400.4033 |  |  | 0 | 0 | 0
11.3.2.12 | P3 stage 1 (1.2m) | 3525.1513 |  |  | 0 | 0 | 0
11.3.2.13 | P3 stage 2 (2m) | 5875.2521 |  |  | 0 | 0 | 0
11.3.2.14 | P3 stage 3 (5m) | 14688.1302 |  |  | 0 | 0 | 0
11.3.2.15 | P3 stage 4 (5m) | 14688.1302 |  |  | 0 | 0 | 0
11.3.2.16 | P3 stage 5 (5m) | 14688.1302 |  |  | 0 | 0 | 0
11.3.2.17 | P3 stage 6 (3.282m) | 9641.2887 |  |  | 0 | 0 | 0
11.3.2.18 | P3 stage 7 (3.2m) | 9400.4033 |  |  | 0 | 0 | 0
11.3.2.19 | P4 stage 1 (1.2m) | 3525.1513 |  |  | 0 | 0 | 0
11.3.2.20 | P4 stage 2 (2m) | 5875.2521 |  |  | 0 | 0 | 0
11.3.2.21 | P4 stage 3 (5m) | 14688.1302 |  |  | 0 | 0 | 0
11.3.2.22 | P4 stage 4 (5m) | 14688.1302 |  |  | 0 | 0 | 0
11.3.2.23 | P4 stage 5 (4.782m) | 13166.4399 |  |  | 0 | 0 | 0
11.3.2.24 | P4 stage 6 (3.2m) | 9400.4033 |  |  | 0 | 0 | 0
11.3.2.25 | P5 stage 1 (1.2m) | 3525.1513 |  |  | 0 | 0 | 0
11.3.2.26 | P5 stage 2 (2m) | 5875.2521 |  |  | 0 | 0 | 0
11.3.2.27 | P5 stage 3 (5m) | 14688.1302 |  |  | 0 | 0 | 0
11.3.2.28 | P5 stage 4 (5m) | 14688.1302 |  |  | 0 | 0 | 0
11.3.2.29 | P5 stage 5 (4.782m) | 14047.7278 |  |  | 0 | 0 | 0
11.3.2.30 | P5 stage 6 (3.2m) | 9400.4033 |  |  | 0 | 0 | 0
11.3.2.31 | P6 stage 1 (1.2m) | 3525.1513 |  |  | 0 | 0 | 0
11.3.2.32 | P6 stage 2 (2m) | 5875.2521 |  |  | 0 | 0 | 0
11.3.2.33 | P6 stage 3 (4.6m) | 13513.0798 |  |  | 0 | 0 | 0
11.3.2.34 | P6 stage 4 (3.2m) | 9400.4033 |  |  | 0 | 0 | 0
11.3.2.35 | A2 | 68559.156 |  |  | 0 | 0 | 0
11.3.3 | Spans/ Rasponi | 1349446.07 |  |  | 0 | 0 | 0
11.3.4 | Bridge Furniture/ Mosna estetika | 188987.17 |  |  | 0 | 0 | 0
11.3.5 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 144104.24 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 11.3 | 2428583.88 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 11.4 | Road Works/Radovi na putevima LK29+661.000—LK29+670.000
Completion of/Završetak:
11.4.1 | Subgrade/ Posteljica
11.4.1.1 | Top soil removal/ Uklanjanje humusa
11.4.1.1.1 | LK29+661.000—LK29+670.000 (Inc. 0 - 9 m (LK)) | 54.5956 |  |  | 0 | 0 | 0
11.4.1.2 | Earthworks/ Zemljani radovi
At every 250 m and certain high /Na svakih 250m i određenoj visini
11.4.1.2.1 | LK29+715.00 - LK29+724.00, layers 1,2,3,
11.4.1.2.1.1 | LK29+715.00 - LK29+724.00, layer 1 | 227.3043 |  |  | 0 | 0 | 0
11.4.1.2.1.2 | LK29+715.00 - LK29+724.00, layer 2 | 227.3043 |  |  | 0 | 0 | 0
11.4.1.2.1.3 | LK29+715.00 - LK29+724.00, layer 3 | 267.6508 |  |  | 0 | 0 | 0
11.4.1.3 | Road Foundation/ Temelj puta | 43.3238 |  |  | 0 | 0 | 0
11.4.2 | Water drainage/ Drenaža vode |  |  |  | 0 | 0 | 0
per one direction of 500m / Na 500m dužine u jednom pravcu
11.4.2.1 | LK29+661.000—LK29+670.000 (9 m) | 197.8656 |  |  | 0 | 0 | 0
11.4.3 | Pavement structure/ Kolovozna konstrukcija | 177.1356 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 11.4 | 1195.1797 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 11.5 | Road Works/Radovi na putevima LK29+670.000—LK29+683.000 RK29+710.000—RK29+722.000
Completion of/Završetak:
11.5.1 | Subgrade/ Posteljica
11.5.1.1 | Top soil removal/ Uklanjanje humusa | 145.5883 |  |  | 0 | 0 | 0
11.5.1.1.1 | RK29+710.000—RK29+722.000 (Inc.0 - 13 m (LK); 0 - 12 m (RK))
11.5.1.2 | Earthworks/ Zemljani radovi
At every 250 m and certain high /Na svakih 250m i određenoj visini
11.5.1.2.1 | LK29+710.00 - LK29+722.00, layers 1,2,3, | 629.9345 |  |  | 0 | 0 | 0
11.5.1.2.1.1 | LK29+710.00 - LK29+722.00, layer 1 | 629.9345 |  |  | 0 | 0 | 0
11.5.1.2.1.2 | LK29+710.00 - LK29+722.00, layer 2 | 666.1557 |  |  | 0 | 0 | 0
11.5.1.2.1.3 | LK29+710.00 - LK29+722.00, layer 3 | 115.53 |  |  | 0 | 0 | 0
11.5.1.3 | Road Foundation/ Temelj puta
11.5.2 | Water drainage/ Drenaža vode
| per one direction of 500m / Na 500m dužine u jednom pravcu | 274.3736 |  |  | 0 | 0 | 0
11.5.2.1 | LK29+670.000—LK29+683.000 | 253.2679 |  |  | 0 | 0 | 0
11.5.2.2 | RK29+710.000—RK29+722.000
11.5.3 | Pavement structure/ Kolovozna konstrukcija | 472.3615 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 11.5 | 3187.1459 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 11.2 | Construction of tunnel/Izgradnja tunela Mala Trava LK29+683.000—LK31+556.000 RK29+722.000—RK31+624.000
Completion of/Završetak:
11.2.1 | Portal construction/ Izgradnja portala
11.2.1.1 | 20% complete/ završeno (portal 1) | 36259.36 | 17 |  | 0 | 0 | 0
11.2.1.2 | 40% complete/ završeno (portal 2) | 36259.36 | 17 |  | 0 | 0 | 0
11.2.1.3 | 60% complete/ završeno (portal 3) | 36259.36 | 18 |  | 0 | 0 | 0
11.2.1.4 | 80% complete/ završeno (portal 4) | 36259.36 | 18 |  | 0 | 0 | 0
11.2.1.5 | 85% (portal 1 complete/ završen) | 9064.84 | 44 |  | 0 | 0 | 0
11.2.1.6 | 90% (portal 2 complete/ završen) | 9064.84 | 44 |  | 0 | 0 | 0
11.2.1.7 | 95% (portal 3 complete/ završen) | 9064.84 | 44 |  | 0 | 0 | 0
11.2.1.8 | 100% (portal 4 complete/ završen) | 9064.85 | 44 |  | 0 | 0 | 0
11.2.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
11.2.2.1 | 40 m (N-R, RK 31+612 - RK 31+772) | 254013.42 | 19 | 24 | 254013.42 | 0 | 254013.42
11.2.2.2 | 80 m (N-L, LK 31+544 - LK31+504) | 254013.42 | 19 | 24 | 254013.42 | 0 | 254013.42
11.2.2.3 | 120 m (N-R, RK 31+572 - RK 31+532) | 254013.42 | 19 | 24 | 254013.42 | 0 | 254013.42
11.2.2.4 | 160 m (N-R, RK 31+504 - RK 31+642) | 254013.42 | 19 | 24 | 254013.42 | 0 | 254013.42
11.2.2.5 | 200 m (N-R, RK31+520 - RK 31+492) | 254013.42 | 20 | 24 | 254013.42 | 0 | 254013.42
11.2.2.6 | 240 m (N-L, LK 31+460- LK 31+424) | 254013.42 | 20 | 24 | 254013.42 | 0 | 254013.42
11.2.2.7 | 280 m, (N-R, RK 31+492 - RK 31+452) | 254013.42 | 20 | 24 | 254013.42 | 0 | 254013.42
11.2.2.8 | 320 m (N-L, LK 31+464 - LK31+424) | 254013.42 | 20 | 24 | 254013.42 | 0 | 254013.42
11.2.2.9 | 360 m (N-L, LK 31+424- LK31+384) | 254013.42 | 21 | 25 | 254013.42 | 0 | 254013.42
11.2.2.10 | 400 m (S-L, LK 29+695.0- LK29+735.0) | 254013.42 | 21 | 25 | 254013.42 | 0 | 254013.42
11.2.2.11 | 440 m (S-R, RK 29+734.0- RK29+774.0) | 254013.42 | 21 | 25 | 254013.42 | 0 | 254013.42
11.2.2.12 | 480 m (S-L, LK 29+735- LK29+775.0) | 254013.42 | 21 | 25 | 254013.42 | 0 | 254013.42
11.2.2.13 | 520 m (S-R, RK 29+774.0- RK29+814.0) | 254013.42 | 22 | 25 | 254013.42 | 0 | 254013.42
11.2.2.14 | 560 m (S-R, RK 29+814.0- RK29+854.0) | 254013.42 | 22 | 25 | 254013.42 | 0 | 254013.42
11.2.2.15 | 600 m (N-R, RK 31+412- LK31+372) | 254013.42 | 22 | 25 | 254013.42 | 0 | 254013.42
11.2.2.16 | 640 m (N-L, LK 31+384- LK31+344) | 254013.42 | 22 | 25 | 254013.42 | 0 | 254013.42
11.2.2.17 | 680 m (S-L, LK 29+775- LK29+815.0) | 254013.42 | 23 | 26 | 254013.42 | 0 | 254013.42
11.2.2.18 | 720 m (S-R, RK 29+854.0- RK29+894.0) | 254013.42 | 23 | 26 | 254013.42 | 0 | 254013.42
11.2.2.19 | 760 m (S-L, LK 29+815- LK29+855.0) | 254013.42 | 23 | 26 | 254013.42 | 0 | 254013.42
11.2.2.20 | 800 m (S-R, RK 29+894.0- RK29+934.0) | 254013.42 | 23 | 28 | 254013.42 | 0 | 254013.42
11.2.2.21 | 840 m (N-R, RK 31+372.00- LK31+332.00) | 254013.42 | 24 | 26 | 254013.42 | 0 | 254013.42
11.2.2.22 | 880 m (N-R, RK 31+332.00- LK31+292.00) | 254013.42 | 24 | 26 | 254013.42 | 0 | 254013.42
11.2.2.23 | 920 m (N-L, LK 31+344.00- LK31+304.00) | 254013.42 | 24 | 26 | 254013.42 | 0 | 254013.42
11.2.2.24 | 960 m (N-L, LK 31+304.00- LK31+264.00) | 254013.42 | 24 | 26 | 254013.42 | 0 | 254013.42
11.2.2.25 | 1000 m (S-L, LK 29+855.0- LK29+895..0) | 254013.42 | 25 | 28 | 254013.42 | 0 | 254013.42
11.2.2.26 | 1040 m (S-R, RK 29+934.0- RK29+974.0) | 254013.42 | 25 | 27 | 254013.42 | 0 | 254013.42
11.2.2.27 | 1080 m (S-R, RK 29+894.0- RK29+934.0) | 254013.42 | 25 | 28 | 254013.42 | 0 | 254013.42
11.2.2.28 | 1120 m (S-R, RK 29+974.0- RK30+014.0) | 254013.42 | 25 | 27 | 254013.42 | 0 | 254013.42
11.2.2.29 | 1160 m (N-R, RK 31+292.00- LK31+252.00) | 254013.42 | 26 | 27 | 254013.42 | 0 | 254013.42
11.2.2.30 | 1200 m (N-L, LK 31+264.00- LK31+224.00) | 254013.42 | 26 | 27 | 254013.42 | 0 | 254013.42
11.2.2.31 | 1240 m (S-L, LK 29+935- LK29+975.0) | 254013.42 | 26 | 28 | 254013.42 | 0 | 254013.42
11.2.2.32 | 1280 m (S-L, LK 29+975- LK30+015.0) | 254013.42 | 26 | 28 | 254013.42 | 0 | 254013.42
11.2.2.33 | 1320 m (S-R, RK 30+014.0- RK30+054.0) | 254013.42 | 27 | 28 | 254013.42 | 0 | 254013.42
11.2.2.34 | 1360 m (S-R, RK 30+054.0- RK30+094.0) | 254013.42 | 27 | 28 | 254013.42 | 0 | 254013.42
11.2.2.35 | 1400 m (N-R, RK 31+252.00- LK31+212.00) | 254013.42 | 27 | 28 | 254013.42 | 0 | 254013.42
11.2.2.36 | 1440 m (N-L, LK 31+224.00- LK31+184.00) | 254013.42 | 27 | 28 | 254013.42 | 0 | 254013.42
11.2.2.37 | 1460 m (S-L,LK30+015- LK30+035) | 129616.818 | 28 | 29 | 129616.818 | 0 | 129616.818
11.2.2.38 | 1480 m (S-L,LK30+035- LK30+055) | 129616.818 | 28 | 29 | 129616.818 | 0 | 129616.818
11.2.2.39 | 1500 m (S-L,LK30+055 - LK30+075) | 129616.818 | 28 | 29 | 129616.818 | 0 | 129616.818
11.2.2.40 | 1520 m (S-L,LK30+075 - LK30+095) | 129616.818 | 28 | 29 | 129616.818 | 0 | 129616.818
11.2.2.41 | 1540 m (S-L,LK30+095 - LK30+115) | 129616.818 | 28 | 29 | 129616.818 | 0 | 129616.818
11.2.2.42 | 1560 m (S-L,LK30+115 - LK30+135) | 129616.818 | 28 | 29 | 129616.818 | 0 | 129616.818
11.2.2.43 | 1580 m (S-R,RK30+094 - RK30+114) | 129616.818 | 28 | 29 | 129616.818 | 0 | 129616.818
11.2.2.44 | 1600 m (S-R,RK30+114 - RK30+134) | 129616.818 | 28 | 29 | 129616.818 | 0 | 129616.818
11.2.2.45 | 1620 m (S-R,RK30+134 - RK30+154) | 129616.818 | 28 | 29 | 129616.818 | 0 | 129616.818
11.2.2.46 | 1640 m (S-R,RK30+154 - RK30+174) | 129616.818 | 29 | 29 | 129616.818 | 0 | 129616.818
11.2.2.47 | 1660 m (S-R,RK30+174 - RK30+194) | 129616.818 | 29 | 29 | 129616.818 | 0 | 129616.818
11.2.2.48 | 1680 m (N-L, LK31+064- LK31+044) | 129616.818 | 29 | 29 | 129616.818 | 0 | 129616.818
11.2.2.49 | 1700 m (N-L,LK31+184- LK31+164) | 129616.818 | 29 | 29 | 129616.818 | 0 | 129616.818
11.2.2.50 | 1720 m (N-L,LK31+164- LK31+144) | 129616.818 | 29 | 29 | 129616.818 | 0 | 129616.818
11.2.2.51 | 1740 m (N-L,LK31+144- LK31+124) | 129616.818 | 29 | 29 | 129616.818 | 0 | 129616.818
11.2.2.52 | 1760 m (N-L,LK31+124- LK31+104) | 129616.818 | 30 | 29 | 129616.818 | 0 | 129616.818
11.2.2.53 | 1780 m (N-L,LK31+104- LK31+084) | 129616.818 | 30 | 29 | 129616.818 | 0 | 129616.818
11.2.2.54 | 1800 m (N-L,LK31+084- LK31+064) | 129616.818 | 30 | 29 | 129616.818 | 0 | 129616.818
11.2.2.55 | 1820 m (N-R,RK31+212 - RK31+192) | 129616.818 | 30 | 29 | 129616.818 | 0 | 129616.818
11.2.2.56 | 1840 m (N-R,RK31+192 - RK31+172) | 129616.818 | 30 | 29 | 129616.818 | 0 | 129616.818
11.2.2.57 | 1860 m (N-R,RK31+172 - RK31+152) | 129616.818 | 30 | 29 | 129616.818 | 0 | 129616.818
11.2.2.58 | 1880 m (N-R,RK31+152 - RK31+132) | 129616.818 | 30 | 29 | 129616.818 | 0 | 129616.818
11.2.2.59 | 1900 m (N-R,RK31+132 - RK31+112) | 129616.818 | 30 | 29 | 129616.818 | 0 | 129616.818
11.2.2.60 | 1920 m (N-R,RK31+112 - RK31+092) | 129616.818 | 30 | 29 | 129616.818 | 0 | 129616.818
11.2.2.61 | 1940 m (N-R,RK31+092 - RK31+072) | 129616.818 | 30 | 29 | 129616.818 | 0 | 129616.818
11.2.2.62 | 1960 m (N-R,RK31+072 - RK31+052) | 129616.818 | 31 | 29 | 129616.818 | 0 | 129616.818
11.2.2.63 | 1980 m (S-L,LK30+135-LK30+155) | 129616.818 | 31 | 30 | 0 | 129616.818 | 129616.818
11.2.2.64 | 2000 m (S-L,LK30+155-LK30+175) | 129616.818 | 31 | 30 | 0 | 129616.818 | 129616.818
11.2.2.65 | 2020 m (S-L,LK30+175-LK30+195) | 129616.818 | 31 | 30 | 0 | 129616.818 | 129616.818
11.2.2.66 | 2040 m (S-L,LK30+195-LK30+215) | 129616.818 | 31 | 30 | 0 | 129616.818 | 129616.818
11.2.2.67 | 2060 m (S-R,RK30+194-RK30+214) | 129616.818 | 31 | 30 | 0 | 129616.818 | 129616.818
11.2.2.68 | 2080 m (S-R,RK30+214-RK30+234) | 129616.818 | 31 | 30 | 0 | 129616.818 | 129616.818
11.2.2.69 | 2100 m (S-R,RK30+234-RK30+254) | 129616.818 | 31 | 30 | 0 | 129616.818 | 129616.818
11.2.2.70 | 2120 m (S-R,RK30+254-RK30+274) | 129616.818 | 32 | 30 | 0 | 129616.818 | 129616.818
11.2.2.71 | 2140 m (N-L,LK31+044-LK31+024) | 129616.818 | 32 | 30 | 0 | 129616.818 | 129616.818
11.2.2.72 | 2160 m ( N-L,LK31+024-LK31+004) | 129616.818 | 32 | 30 | 0 | 129616.818 | 129616.818
11.2.2.73 | 2180 m (N-L,LK31+004-LK30+984) | 129616.818 | 32 | 30 | 0 | 129616.818 | 129616.818
11.2.2.74 | 2200 m (N-L,LK30+984-LK30+964) | 129616.818 | 32 | 30 | 0 | 129616.818 | 129616.818
11.2.2.75 | 2220 m (N-L,LK30+964-LK30+944) | 129616.818 | 32 | 30 | 0 | 129616.818 | 129616.818
11.2.2.76 | 2240 m (N-R,RK31+052-RK31+032) | 129616.818 | 32 | 30 | 0 | 129616.818 | 129616.818
11.2.2.77 | 2260 m(N-R,RK31+032-RK31+012) | 129616.818 | 32 | 30 | 0 | 129616.818 | 129616.818
11.2.2.78 | 2280 m (N-R,RK31+012-RK30+992) | 129616.818 | 33 | 30 | 0 | 129616.818 | 129616.818
11.2.2.79 | 2300 m (N-R,RK30+992-RK30+972) | 129616.818 | 33 | 30 | 0 | 129616.818 | 129616.818
11.2.2.80 | 2320 m (N-R,RK30+972-RK30+952) | 129616.818 | 33 | 30 | 0 | 129616.818 | 129616.818
11.2.2.81 | 2340 m | 129616.818 | 33 |  | 0 | 0 | 0
11.2.2.82 | 2360 m | 129616.818 | 33 |  | 0 | 0 | 0
11.2.2.83 | 2380 m | 129616.818 | 33 |  | 0 | 0 | 0
11.2.2.84 | 2400 m | 129616.818 | 33 |  | 0 | 0 | 0
11.2.2.85 | 2420 m | 129616.818 | 33 |  | 0 | 0 | 0
11.2.2.86 | 2440 m | 129616.818 | 34 |  | 0 | 0 | 0
11.2.2.87 | 2460 m | 129616.818 | 34 |  | 0 | 0 | 0
11.2.2.88 | 2480 m | 129616.818 | 34 |  | 0 | 0 | 0
11.2.2.89 | 2500 m | 129616.818 | 34 |  | 0 | 0 | 0
11.2.2.90 | 2520 m | 129616.818 | 34 |  | 0 | 0 | 0
11.2.2.91 | 2540 m | 129616.818 | 34 |  | 0 | 0 | 0
11.2.2.92 | 2560 m | 129616.818 | 34 |  | 0 | 0 | 0
11.2.2.93 | 2580 m | 129616.818 | 34 |  | 0 | 0 | 0
11.2.2.94 | 2600 m | 129616.818 | 35 |  | 0 | 0 | 0
11.2.2.95 | 2620 m | 129616.818 | 35 |  | 0 | 0 | 0
11.2.2.96 | 2640 m | 129616.818 | 35 |  | 0 | 0 | 0
11.2.2.97 | 2660 m | 129616.818 | 35 |  | 0 | 0 | 0
11.2.2.98 | 2680 m | 129616.818 | 35 |  | 0 | 0 | 0
11.2.2.99 | 2700 m | 129616.818 | 35 |  | 0 | 0 | 0
11.2.2.100 | 2720 m | 129616.818 | 35 |  | 0 | 0 | 0
11.2.2.101 | 2740 m | 129616.818 | 35 |  | 0 | 0 | 0
11.2.2.102 | 2760 m | 129616.818 | 36 |  | 0 | 0 | 0
11.2.2.103 | 2780 m | 129616.818 | 36 |  | 0 | 0 | 0
11.2.2.104 | 2800 m | 129616.818 | 36 |  | 0 | 0 | 0
11.2.2.105 | 2820 m | 129616.818 | 36 |  | 0 | 0 | 0
11.2.2.106 | 2840 m | 129616.818 | 36 |  | 0 | 0 | 0
11.2.2.107 | 2860 m | 129616.818 | 36 |  | 0 | 0 | 0
11.2.2.108 | 2880 m | 129616.818 | 36 |  | 0 | 0 | 0
11.2.2.109 | 2900 m | 129616.818 | 36 |  | 0 | 0 | 0
11.2.2.110 | 2920 m | 129616.818 | 37 |  | 0 | 0 | 0
11.2.2.111 | 2940 m | 129616.818 | 37 |  | 0 | 0 | 0
11.2.2.112 | 2960 m | 129616.818 | 37 |  | 0 | 0 | 0
11.2.2.113 | 2980 m | 129616.818 | 37 |  | 0 | 0 | 0
11.2.2.114 | 3000 m | 129616.818 | 37 |  | 0 | 0 | 0
11.2.2.115 | 3020 m | 129616.818 | 37 |  | 0 | 0 | 0
11.2.2.116 | 3040 m | 129616.818 | 37 |  | 0 | 0 | 0
11.2.2.117 | 3060 m | 129616.818 | 37 |  | 0 | 0 | 0
11.2.2.118 | 3080 m | 129616.818 | 38 |  | 0 | 0 | 0
11.2.2.119 | 3100 m | 129616.818 | 38 |  | 0 | 0 | 0
11.2.2.120 | 3120 m | 129616.818 | 38 |  | 0 | 0 | 0
11.2.2.121 | 3140 m | 129616.818 | 38 |  | 0 | 0 | 0
11.2.2.122 | 3160 m | 129616.818 | 38 |  | 0 | 0 | 0
11.2.2.123 | 3180 m | 129616.818 | 38 |  | 0 | 0 | 0
11.2.2.124 | 3200 m | 129616.818 | 38 |  | 0 | 0 | 0
11.2.2.125 | 3220 m | 129616.818 | 38 |  | 0 | 0 | 0
11.2.2.126 | 3240 m | 129616.818 | 39 |  | 0 | 0 | 0
11.2.2.127 | 3260 m | 129616.818 | 39 |  | 0 | 0 | 0
11.2.2.128 | 3280 m | 129616.818 | 39 |  | 0 | 0 | 0
11.2.2.129 | 3300 m | 129616.818 | 39 |  | 0 | 0 | 0
11.2.2.130 | 3320 m | 129616.818 | 39 |  | 0 | 0 | 0
11.2.2.131 | 3340 m | 129616.818 | 39 |  | 0 | 0 | 0
11.2.2.132 | 3360 m | 129616.818 | 39 |  | 0 | 0 | 0
11.2.2.133 | 3380 m | 129616.818 | 39 |  | 0 | 0 | 0
11.2.2.134 | 3400 m | 129616.818 | 40 |  | 0 | 0 | 0
11.2.2.135 | 3420 m | 129616.818 | 40 |  | 0 | 0 | 0
11.2.2.136 | 3440 m | 129616.818 | 40 |  | 0 | 0 | 0
11.2.2.137 | 3460 m | 129616.818 | 40 |  | 0 | 0 | 0
11.2.2.138 | 3480 m | 129616.818 | 40 |  | 0 | 0 | 0
11.2.2.139 | 3500 m | 129616.818 | 40 |  | 0 | 0 | 0
11.2.2.140 | 3520 m | 129616.818 | 40 |  | 0 | 0 | 0
11.2.2.141 | 3540 m | 129616.818 | 40 |  | 0 | 0 | 0
11.2.2.142 | 3560 m | 129616.818 | 40 |  | 0 | 0 | 0
11.2.2.143 | 3580 m | 129616.818 | 40 |  | 0 | 0 | 0
11.2.2.144 | 3600 m | 129616.818 | 41 |  | 0 | 0 | 0
11.2.2.145 | 3620 m | 129616.818 | 41 |  | 0 | 0 | 0
11.2.2.146 | 3640 m | 129616.818 | 41 |  | 0 | 0 | 0
11.2.2.147 | 3660 m | 129616.818 | 41 |  | 0 | 0 | 0
11.2.2.148 | 3680 m | 129616.818 | 41 |  | 0 | 0 | 0
11.2.2.149 | 3700 m | 129616.818 | 41 |  | 0 | 0 | 0
11.2.2.150 | 3720 m | 129616.818 | 41 |  | 0 | 0 | 0
11.2.2.151 | 3727 m | 45365.8863 | 41 |  | 0 | 0 | 0
11.2.3 | Construction of waterproofing and drainage & Construction of secondary lining / Konstrukcija hidroizolacije i drenaže & Konstrukcija sekundarne obloge
11.2.3.1 | 20 m | 72431.0336 | 20 |  | 0 | 0 | 0
11.2.3.2 | 40 m | 72431.0336 | 20 |  | 0 | 0 | 0
11.2.3.3 | 60 m | 72431.0336 | 20 |  | 0 | 0 | 0
11.2.3.4 | 80 m | 72431.0336 | 20 |  | 0 | 0 | 0
11.2.3.5 | 100 m | 72431.0336 | 20 |  | 0 | 0 | 0
11.2.3.6 | 120 m | 72431.0336 | 20 |  | 0 | 0 | 0
11.2.3.7 | 140 m | 72431.0336 | 20 |  | 0 | 0 | 0
11.2.3.8 | 160 m | 72431.0336 | 21 |  | 0 | 0 | 0
11.2.3.9 | 180 m | 72431.0336 | 21 |  | 0 | 0 | 0
11.2.3.10 | 200 m | 72431.0336 | 21 |  | 0 | 0 | 0
11.2.3.11 | 220 m | 72431.0336 | 21 |  | 0 | 0 | 0
11.2.3.12 | 240 m | 72431.0336 | 21 |  | 0 | 0 | 0
11.2.3.13 | 260 m | 72431.0336 | 21 |  | 0 | 0 | 0
11.2.3.14 | 280 m | 72431.0336 | 21 |  | 0 | 0 | 0
11.2.3.15 | 300 m | 72431.0336 | 21 |  | 0 | 0 | 0
11.2.3.16 | 320 m | 72431.0336 | 22 |  | 0 | 0 | 0
11.2.3.17 | 340 m | 72431.0336 | 22 |  | 0 | 0 | 0
11.2.3.18 | 360 m | 72431.0336 | 22 |  | 0 | 0 | 0
11.2.3.19 | 380 m | 72431.0336 | 22 |  | 0 | 0 | 0
11.2.3.20 | 400 m | 72431.0336 | 22 |  | 0 | 0 | 0
11.2.3.21 | 420 m | 72431.0336 | 22 |  | 0 | 0 | 0
11.2.3.22 | 440 m | 72431.0336 | 22 |  | 0 | 0 | 0
11.2.3.23 | 460 m | 72431.0336 | 22 |  | 0 | 0 | 0
11.2.3.24 | 480 m | 72431.0336 | 23 |  | 0 | 0 | 0
11.2.3.25 | 500 m | 72431.0336 | 23 |  | 0 | 0 | 0
11.2.3.26 | 520 m | 72431.0336 | 23 |  | 0 | 0 | 0
11.2.3.27 | 540 m | 72431.0336 | 23 |  | 0 | 0 | 0
11.2.3.28 | 560 m | 72431.0336 | 23 |  | 0 | 0 | 0
11.2.3.29 | 580 m | 72431.0336 | 23 |  | 0 | 0 | 0
11.2.3.30 | 600 m | 72431.0336 | 23 |  | 0 | 0 | 0
11.2.3.31 | 620 m | 72431.0336 | 23 |  | 0 | 0 | 0
11.2.3.32 | 640 m | 72431.0336 | 24 |  | 0 | 0 | 0
11.2.3.33 | 660 m | 72431.0336 | 24 |  | 0 | 0 | 0
11.2.3.34 | 680 m | 72431.0336 | 24 |  | 0 | 0 | 0
11.2.3.35 | 700 m | 72431.0336 | 24 |  | 0 | 0 | 0
11.2.3.36 | 720 m | 72431.0336 | 24 |  | 0 | 0 | 0
11.2.3.37 | 740 m | 72431.0336 | 24 |  | 0 | 0 | 0
11.2.3.38 | 760 m | 72431.0336 | 24 |  | 0 | 0 | 0
11.2.3.39 | 780 m | 72431.0336 | 24 |  | 0 | 0 | 0
11.2.3.40 | 800 m | 72431.0336 | 25 |  | 0 | 0 | 0
11.2.3.41 | 820 m | 72431.0336 | 25 |  | 0 | 0 | 0
11.2.3.42 | 840 m | 72431.0336 | 25 |  | 0 | 0 | 0
11.2.3.43 | 860 m | 72431.0336 | 25 |  | 0 | 0 | 0
11.2.3.44 | 880 m | 72431.0336 | 25 |  | 0 | 0 | 0
11.2.3.45 | 900 m | 72431.0336 | 25 |  | 0 | 0 | 0
11.2.3.46 | 920 m | 72431.0336 | 25 |  | 0 | 0 | 0
11.2.3.47 | 940 m | 72431.0336 | 25 |  | 0 | 0 | 0
11.2.3.48 | 960 m | 72431.0336 | 26 |  | 0 | 0 | 0
11.2.3.49 | 980 m | 72431.0336 | 26 |  | 0 | 0 | 0
11.2.3.50 | 1000 m | 72431.0336 | 26 |  | 0 | 0 | 0
11.2.3.51 | 1020 m | 72431.0336 | 26 |  | 0 | 0 | 0
11.2.3.52 | 1040 m | 72431.0336 | 26 |  | 0 | 0 | 0
11.2.3.53 | 1060 m | 72431.0336 | 26 |  | 0 | 0 | 0
11.2.3.54 | 1080 m | 72431.0336 | 26 |  | 0 | 0 | 0
11.2.3.55 | 1100 m | 72431.0336 | 26 |  | 0 | 0 | 0
11.2.3.56 | 1120 m | 72431.0336 | 27 |  | 0 | 0 | 0
11.2.3.57 | 1140 m | 72431.0336 | 27 |  | 0 | 0 | 0
11.2.3.58 | 1160 m | 72431.0336 | 27 |  | 0 | 0 | 0
11.2.3.59 | 1180 m | 72431.0336 | 27 |  | 0 | 0 | 0
11.2.3.60 | 1200 m | 72431.0336 | 27 |  | 0 | 0 | 0
11.2.3.61 | 1220 m | 72431.0336 | 27 |  | 0 | 0 | 0
11.2.3.62 | 1240 m | 72431.0336 | 27 |  | 0 | 0 | 0
11.2.3.63 | 1260 m | 72431.0336 | 27 |  | 0 | 0 | 0
11.2.3.64 | 1280 m | 72431.0336 | 28 |  | 0 | 0 | 0
11.2.3.65 | 1300 m | 72431.0336 | 28 |  | 0 | 0 | 0
11.2.3.66 | 1320 m | 72431.0336 | 28 |  | 0 | 0 | 0
11.2.3.67 | 1340 m | 72431.0336 | 28 |  | 0 | 0 | 0
11.2.3.68 | 1360 m | 72431.0336 | 28 |  | 0 | 0 | 0
11.2.3.69 | 1380 m | 72431.0336 | 28 |  | 0 | 0 | 0
11.2.3.70 | 1400 m | 72431.0336 | 28 |  | 0 | 0 | 0
11.2.3.71 | 1420 m | 72431.0336 | 28 |  | 0 | 0 | 0
11.2.3.72 | 1440 m | 72431.0336 | 29 |  | 0 | 0 | 0
11.2.3.73 | 1460 m | 72431.0336 | 29 |  | 0 | 0 | 0
11.2.3.74 | 1480 m | 72431.0336 | 29 |  | 0 | 0 | 0
11.2.3.75 | 1500 m | 72431.0336 | 29 |  | 0 | 0 | 0
11.2.3.76 | 1520 m | 72431.0336 | 29 |  | 0 | 0 | 0
11.2.3.77 | 1540 m | 72431.0336 | 29 |  | 0 | 0 | 0
11.2.3.78 | 1560 m | 72431.0336 | 29 |  | 0 | 0 | 0
11.2.3.79 | 1580 m | 72431.0336 | 29 |  | 0 | 0 | 0
11.2.3.80 | 1600 m | 72431.0336 | 30 |  | 0 | 0 | 0
11.2.3.81 | 1620 m | 72431.0336 | 30 |  | 0 | 0 | 0
11.2.3.82 | 1640 m | 72431.0336 | 30 |  | 0 | 0 | 0
11.2.3.83 | 1660 m | 72431.0336 | 30 |  | 0 | 0 | 0
11.2.3.84 | 1680 m | 72431.0336 | 30 |  | 0 | 0 | 0
11.2.3.85 | 1700 m | 72431.0336 | 30 |  | 0 | 0 | 0
11.2.3.86 | 1720 m | 72431.0336 | 30 |  | 0 | 0 | 0
11.2.3.87 | 1740 m | 72431.0336 | 30 |  | 0 | 0 | 0
11.2.3.88 | 1760 m | 72431.0336 | 31 |  | 0 | 0 | 0
11.2.3.89 | 1780 m | 72431.0336 | 31 |  | 0 | 0 | 0
11.2.3.90 | 1800 m | 72431.0336 | 31 |  | 0 | 0 | 0
11.2.3.91 | 1820 m | 72431.0336 | 31 |  | 0 | 0 | 0
11.2.3.92 | 1840 m | 72431.0336 | 31 |  | 0 | 0 | 0
11.2.3.93 | 1860 m | 72431.0336 | 31 |  | 0 | 0 | 0
11.2.3.94 | 1880 m | 72431.0336 | 31 |  | 0 | 0 | 0
11.2.3.95 | 1900 m | 72431.0336 | 31 |  | 0 | 0 | 0
11.2.3.96 | 1920 m | 72431.0336 | 32 |  | 0 | 0 | 0
11.2.3.97 | 1940 m | 72431.0336 | 32 |  | 0 | 0 | 0
11.2.3.98 | 1960 m | 72431.0336 | 32 |  | 0 | 0 | 0
11.2.3.99 | 1980 m | 72431.0336 | 32 |  | 0 | 0 | 0
11.2.3.100 | 2000 m | 72431.0336 | 32 |  | 0 | 0 | 0
11.2.3.101 | 2020 m | 72431.0336 | 32 |  | 0 | 0 | 0
11.2.3.102 | 2040 m | 72431.0336 | 32 |  | 0 | 0 | 0
11.2.3.103 | 2060 m | 72431.0336 | 32 |  | 0 | 0 | 0
11.2.3.104 | 2080 m | 72431.0336 | 33 |  | 0 | 0 | 0
11.2.3.105 | 2100 m | 72431.0336 | 33 |  | 0 | 0 | 0
11.2.3.106 | 2120 m | 72431.0336 | 33 |  | 0 | 0 | 0
11.2.3.107 | 2140 m | 72431.0336 | 33 |  | 0 | 0 | 0
11.2.3.108 | 2160 m | 72431.0336 | 33 |  | 0 | 0 | 0
11.2.3.109 | 2180 m | 72431.0336 | 33 |  | 0 | 0 | 0
11.2.3.110 | 2200 m | 72431.0336 | 33 |  | 0 | 0 | 0
11.2.3.111 | 2220 m | 72431.0336 | 33 |  | 0 | 0 | 0
11.2.3.112 | 2240 m | 72431.0336 | 34 |  | 0 | 0 | 0
11.2.3.113 | 2260 m | 72431.0336 | 34 |  | 0 | 0 | 0
11.2.3.114 | 2280 m | 72431.0336 | 34 |  | 0 | 0 | 0
11.2.3.115 | 2300 m | 72431.0336 | 34 |  | 0 | 0 | 0
11.2.3.116 | 2320 m | 72431.0336 | 34 |  | 0 | 0 | 0
11.2.3.117 | 2340 m | 72431.0336 | 34 |  | 0 | 0 | 0
11.2.3.118 | 2360 m | 72431.0336 | 34 |  | 0 | 0 | 0
11.2.3.119 | 2380 m | 72431.0336 | 34 |  | 0 | 0 | 0
11.2.3.120 | 2400 m | 72431.0336 | 35 |  | 0 | 0 | 0
11.2.3.121 | 2420 m | 72431.0336 | 35 |  | 0 | 0 | 0
11.2.3.122 | 2440 m | 72431.0336 | 35 |  | 0 | 0 | 0
11.2.3.123 | 2460 m | 72431.0336 | 35 |  | 0 | 0 | 0
11.2.3.124 | 2480 m | 72431.0336 | 35 |  | 0 | 0 | 0
11.2.3.125 | 2500 m | 72431.0336 | 35 |  | 0 | 0 | 0
11.2.3.126 | 2520 m | 72431.0336 | 35 |  | 0 | 0 | 0
11.2.3.127 | 2540 m | 72431.0336 | 35 |  | 0 | 0 | 0
11.2.3.128 | 2560 m | 72431.0336 | 36 |  | 0 | 0 | 0
11.2.3.129 | 2580 m | 72431.0336 | 36 |  | 0 | 0 | 0
11.2.3.130 | 2600 m | 72431.0336 | 36 |  | 0 | 0 | 0
11.2.3.131 | 2620 m | 72431.0336 | 36 |  | 0 | 0 | 0
11.2.3.132 | 2640 m | 72431.0336 | 36 |  | 0 | 0 | 0
11.2.3.133 | 2660 m | 72431.0336 | 36 |  | 0 | 0 | 0
11.2.3.134 | 2680 m | 72431.0336 | 36 |  | 0 | 0 | 0
11.2.3.135 | 2700 m | 72431.0336 | 36 |  | 0 | 0 | 0
11.2.3.136 | 2720 m | 72431.0336 | 37 |  | 0 | 0 | 0
11.2.3.137 | 2740 m | 72431.0336 | 37 |  | 0 | 0 | 0
11.2.3.138 | 2760 m | 72431.0336 | 37 |  | 0 | 0 | 0
11.2.3.139 | 2780 m | 72431.0336 | 37 |  | 0 | 0 | 0
11.2.3.140 | 2800 m | 72431.0336 | 37 |  | 0 | 0 | 0
11.2.3.141 | 2820 m | 72431.0336 | 37 |  | 0 | 0 | 0
11.2.3.142 | 2840 m | 72431.0336 | 37 |  | 0 | 0 | 0
11.2.3.143 | 2860 m | 72431.0336 | 37 |  | 0 | 0 | 0
11.2.3.144 | 2880 m | 72431.0336 | 38 |  | 0 | 0 | 0
11.2.3.145 | 2900 m | 72431.0336 | 38 |  | 0 | 0 | 0
11.2.3.146 | 2920 m | 72431.0336 | 38 |  | 0 | 0 | 0
11.2.3.147 | 2940 m | 72431.0336 | 38 |  | 0 | 0 | 0
11.2.3.148 | 2960 m | 72431.0336 | 38 |  | 0 | 0 | 0
11.2.3.149 | 2980 m | 72431.0336 | 38 |  | 0 | 0 | 0
11.2.3.150 | 3000 m | 72431.0336 | 38 |  | 0 | 0 | 0
11.2.3.151 | 3020 m | 72431.0336 | 38 |  | 0 | 0 | 0
11.2.3.152 | 3040 m | 72431.0336 | 39 |  | 0 | 0 | 0
11.2.3.153 | 3060 m | 72431.0336 | 39 |  | 0 | 0 | 0
11.2.3.154 | 3080 m | 72431.0336 | 39 |  | 0 | 0 | 0
11.2.3.155 | 3100 m | 72431.0336 | 39 |  | 0 | 0 | 0
11.2.3.156 | 3120 m | 72431.0336 | 39 |  | 0 | 0 | 0
11.2.3.157 | 3140 m | 72431.0336 | 39 |  | 0 | 0 | 0
11.2.3.158 | 3160 m | 72431.0336 | 39 |  | 0 | 0 | 0
11.2.3.159 | 3180 m | 72431.0336 | 39 |  | 0 | 0 | 0
11.2.3.160 | 3200 m | 72431.0336 | 41 |  | 0 | 0 | 0
11.2.3.161 | 3220 m | 72431.0336 | 41 |  | 0 | 0 | 0
11.2.3.162 | 3240 m | 72431.0336 | 41 |  | 0 | 0 | 0
11.2.3.163 | 3260 m | 72431.0336 | 41 |  | 0 | 0 | 0
11.2.3.164 | 3280 m | 72431.0336 | 41 |  | 0 | 0 | 0
11.2.3.165 | 3300 m | 72431.0336 | 41 |  | 0 | 0 | 0
11.2.3.166 | 3320 m | 72431.0336 | 41 |  | 0 | 0 | 0
11.2.3.167 | 3340 m | 72431.0336 | 41 |  | 0 | 0 | 0
11.2.3.168 | 3360 m | 72431.0336 | 41 |  | 0 | 0 | 0
11.2.3.169 | 3380 m | 72431.0336 | 41 |  | 0 | 0 | 0
11.2.3.170 | 3400 m | 72431.0336 | 40 |  | 0 | 0 | 0
11.2.3.171 | 3420 m | 72431.0336 | 40 |  | 0 | 0 | 0
11.2.3.172 | 3440 m | 72431.0336 | 40 |  | 0 | 0 | 0
11.2.3.173 | 3460 m | 72431.0336 | 40 |  | 0 | 0 | 0
11.2.3.174 | 3480 m | 72431.0336 | 40 |  | 0 | 0 | 0
11.2.3.175 | 3500 m | 72431.0336 | 40 |  | 0 | 0 | 0
11.2.3.176 | 3520 m | 72431.0336 | 40 |  | 0 | 0 | 0
11.2.3.177 | 3540 m | 72431.0336 | 40 |  | 0 | 0 | 0
11.2.3.178 | 3560 m | 72431.0336 | 40 |  | 0 | 0 | 0
11.2.3.179 | 3580 m | 72431.0336 | 40 |  | 0 | 0 | 0
11.2.3.180 | 3600 m | 72431.0336 | 42 |  | 0 | 0 | 0
11.2.3.181 | 3620 m | 72431.0336 | 42 |  | 0 | 0 | 0
11.2.3.182 | 3640 m | 72431.0336 | 42 |  | 0 | 0 | 0
11.2.3.183 | 3660 m | 72431.0336 | 42 |  | 0 | 0 | 0
11.2.3.184 | 3680 m | 72431.0336 | 42 |  | 0 | 0 | 0
11.2.3.185 | 3700 m | 72431.0336 | 42 |  | 0 | 0 | 0
11.2.3.186 | 3720 m | 72431.0336 | 42 |  | 0 | 0 | 0
11.2.3.187 | 3727 m | 25350.8618 | 42 |  | 0 | 0 | 0
11.2.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi I ploca, drenazni sistem)
11.2.4.1 | 200 m | 80000 | 24 |  | 0 | 0 | 0
11.2.4.2 | 400 m | 80000 | 25 |  | 0 | 0 | 0
11.2.4.3 | 600 m | 80000 | 26 |  | 0 | 0 | 0
11.2.4.4 | 800 m | 80000 | 27 |  | 0 | 0 | 0
11.2.4.5 | 1000 m | 80000 | 28 |  | 0 | 0 | 0
11.2.4.6 | 1200 m | 80000 | 29 |  | 0 | 0 | 0
11.2.4.7 | 1400 m | 80000 | 31 |  | 0 | 0 | 0
11.2.4.8 | 1600 m | 80000 | 32 |  | 0 | 0 | 0
11.2.4.9 | 1800 m | 80000 | 33 |  | 0 | 0 | 0
11.2.4.10 | 2000 m | 80000 | 34 |  | 0 | 0 | 0
11.2.4.11 | 2200 m | 80000 | 36 |  | 0 | 0 | 0
11.2.4.12 | 2400 m | 80000 | 37 |  | 0 | 0 | 0
11.2.4.13 | 2600 m | 80000 | 38 |  | 0 | 0 | 0
11.2.4.14 | 2800 m | 80000 | 39 |  | 0 | 0 | 0
11.2.4.15 | 3000 m | 80000 | 40 |  | 0 | 0 | 0
11.2.4.16 | 3200 m | 80000 | 41 |  | 0 | 0 | 0
11.2.4.17 | 3400 m | 80000 | 42 |  | 0 | 0 | 0
11.2.4.18 | 3600 m | 80000 | 45 |  | 0 | 0 | 0
11.2.4.19 | 3727 m | 50800 | 44 |  | 0 | 0 | 0
11.2.5 | Construction of pavement/ Izgradnja kolovoza
11.2.5.1 | Left tube/ Lijeva cijev
0-500 m
11.2.5.1.1 | Layer/ Sloj 1 | 36321.49 | 42 |  | 0 | 0 | 0
11.2.5.1.2 | Layer/ Sloj 2 | 36321.49 | 43 |  | 0 | 0 | 0
11.2.5.1.3 | Layer/ Sloj 3 | 40861.67 | 44 |  | 0 | 0 | 0
500-1000 m
11.2.5.1.4 | Layer/ Sloj 1 | 36321.49 | 42 |  | 0 | 0 | 0
11.2.5.1.5 | Layer/ Sloj 2 | 36321.49 | 43 |  | 0 | 0 | 0
11.2.5.1.6 | Layer/ Sloj 3 | 40861.67 | 44 |  | 0 | 0 | 0
1000-1500 m
11.2.5.1.7 | Layer/ Sloj 1 | 36321.49 | 42 |  | 0 | 0 | 0
11.2.5.1.8 | Layer/ Sloj 2 | 36321.49 | 43 |  | 0 | 0 | 0
11.2.5.1.9 | Layer/ Sloj 3 | 40861.67 | 44 |  | 0 | 0 | 0
1500-1883 m
11.2.5.1.10 | Layer/ Sloj 1 | 27822.26 | 42 |  | 0 | 0 | 0
11.2.5.1.11 | Layer/ Sloj 2 | 27822.26 | 43 |  | 0 | 0 | 0
11.2.5.1.12 | Layer/ Sloj 3 | 31300.04 | 44 |  | 0 | 0 | 0
11.2.5.2 | Right tube/ Desna cijev
0-500 m
11.2.5.2.1 | Layer/ Sloj 1 | 36321.49 | 42 |  | 0 | 0 | 0
11.2.5.2.2 | Layer/ Sloj 2 | 36321.49 | 43 |  | 0 | 0 | 0
11.2.5.2.3 | Layer/ Sloj 3 | 40861.67 | 44 |  | 0 | 0 | 0
500-1000 m
11.2.5.2.4 | Layer/ Sloj 1 | 36321.49 | 42 |  | 0 | 0 | 0
11.2.5.2.5 | Layer/ Sloj 2 | 36321.49 | 43 |  | 0 | 0 | 0
11.2.5.2.6 | Layer/ Sloj 3 | 40861.67 | 44 |  | 0 | 0 | 0
1000-1500 m
11.2.5.2.7 | Layer/ Sloj 1 | 36321.49 | 42 |  | 0 | 0 | 0
11.2.5.2.8 | Layer/ Sloj 2 | 36321.49 | 43 |  | 0 | 0 | 0
11.2.5.2.9 | Layer/ Sloj 3 | 40861.67 | 44 |  | 0 | 0 | 0
1500-1902 m
11.2.5.2.10 | Layer/ Sloj 1 | 29202.48 | 42 |  | 0 | 0 | 0
11.2.5.2.11 | Layer/ Sloj 2 | 29202.48 | 43 |  | 0 | 0 | 0
11.2.5.2.12 | Layer/ Sloj 3 | 32852.77 | 44 |  | 0 | 0 | 0
11.2.6 | Tunnel facilities/ Tunelski objekti
11.2.6.1 | Construction of Power Station/ Izgradnja elektro-stanice | 249149.36 | 41 |  | 0 | 0 | 0
11.2.6.2 | Construction of antifire reservoir/Izgradnja protivpožarnog rezervoara | 86312.55 | 42 |  | 0 | 0 | 0
11.2.7 | Tunnel Equipment/ Tunelska oprema
11.2.7.1 | Right tube/ Desna cijev
11.2.7.1.1 | 90% (Equipment installed/Oprema postavljena) | 1901682.7 | 43 |  | 0 | 0 | 0
11.2.7.1.2 | 10% (Equipment tested/Oprema ispitana) | 211298.08 | 45 |  | 0 | 0 | 0
11.2.7.2 | Left tube/ Lijeva cijev
11.2.7.2.1 | 90% (Equipment installed/Oprema postavljena) | 1886359.14 | 44 |  | 0 | 0 | 0
11.2.7.2.2 | 10% (Equipment tested/Oprema ispitana) | 209595.46 | 45 |  | 0 | 0 | 0
| Sub Total / Suma stavke 11.2 | 44539413.67 |  |  | 12514520.3884 | 2333102.7243 | 14847623.1127
| TOTAL COST CENTER / UKUPUNO TROSKOVNO MJESTO 11 | 48073117.51 |  |  | 12514520.3884 | 2333102.7243 | 14847623.1127

## COST CENTER 12
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
COST CENTER 12/TROŠKOVNI CENTAR 12
Cost center No./ Troškovno mjesto Br. | 12 | Subsection/Podsekcija 4.1 (LK31+556.000-LK35+425.00, RK31+624.000-RK35+480.00)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost center/ Troškovno mjesto 12.1 | Open Route/Otvorena trasa LK31+556.000 —LK31+587.000 RK31+624.000—RK31+658.000
Completion of/Završetak:
12.1.1 | Subgrade/ Posteljica
12.1.1.1 | Top soil removal/ Uklanjanje humusa | 5969.23 |  |  | 0 | 0 | 0
12.1.1.2 | Earthworks/ Zemljani radovi | 41160.93 |  |  | 0 | 0 | 0
12.1.1.3 | Road Foundation/ Temelj puta | 28704.24 |  |  | 0 | 0 | 0
12.1.2 | Water drainage/ Drenaža vode | 0 |  |  | 0 | 0 | 0
12.1.2.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 8339.73 |  |  | 0 | 0 | 0
12.1.3 | Pavement structure/ Kolovozna konstrukcija | 3669.49
| Sub Total / Suma stavke 12.1 | 87843.62 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.2 | BRIDGE/MOST ČESTOGAZ LK31+587.000—LK31+681.000 RK31+658.000—RK31+752.000
Completion of/Završetak:
Left Bridge/ Lijevi most
12.2.1 | Foundation concrete/ Temeljni beton | 273242.45 | 25 |  | 0 | 0 | 0
12.2.2 | Abutments and Piers elevation/ Elevacija mosnih stubova | 263519.1 | 25 |  | 0 | 0 | 0
12.2.3 | Bridge deck superstructure/Gornji stroj mosne ploče | 652634.49 | 26 |  | 0 | 0 | 0
12.2.5 | Bridge Furniture/ Mosna estetika | 148821.69 | 27 |  | 0 | 0 | 0
12.2.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 88878.63 | 27 |  | 0 | 0 | 0
Right Bridge/ Desni most
12.2.7 | Foundation concrete/ Temeljni beton | 263112.38 | 28 |  | 0 | 0 | 0
12.2.8 | Abutments and Piers elevation/ Elevacija mosnih stubova | 302624.57 | 30 |  | 0 | 0 | 0
12.2.9 | Bridge deck superstructure/Gornji stroj mosne ploče | 655772.06 | 31 |  | 0 | 0 | 0
12.2.11 | Bridge Furniture/ Mosna estetika | 151325.14 | 32 |  | 0 | 0 | 0
12.2.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 98393.6
| Sub Total / Suma stavke 12.2 | 2898324.11 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.3 | Road Works/ Radovi na putevima (LK31+681.000—LK32.201.200, RK31+752.000—RK32+231.500)
Completion of/Završetak:
12.3.1 | Subgrade/ Posteljica
12.3.1.1 | Top soil removal/ Uklanjanje humusa | 84183.66 | 23 |  | 0 | 0 | 0
12.3.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and certain high (after MD approval)/Na svakih 250m i određenoj visini (nakon odobrenja GP) | 1959154.4 | 37 |  | 0 | 0 | 0
12.3.1.3 | Road Foundation/ Temelj puta | 404814.21 | 38 |  | 0 | 0 | 0
12.3.2 | Engineering structures/ Inženjerske konstrukcije
12.3.2.1 | Concrete wall/ Betonski zid | 1418342.03 |  |  | 0 | 0 | 0
12.3.2.2 | Reinforced earth wall (it will be splitted after MD approval)/ Ojačani zemljani zid (podijeliće se nakon odobrenja GP) | 547235.86 | 33 |  | 0 | 0 | 0
12.3.2.3 | Culvert/ Propust | 0 |  |  | 0 | 0 | 0
12.3.3 | Water drainage/ Drenaža vode
12.3.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 117614.74 | 38 |  | 0 | 0 | 0
12.3.4 | Pavement structure/ Kolovozna konstrukcija | 51750.6 | 38 |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.3 | 4583095.5 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.4 | Construction of bridge/Izgradnja mosta Uvac 1 (LK 32.201.200- LK 32+489.20, RK 32+231.500- RK 32+579.500)
Completion of/Završetak:
Left Bridge/ Lijevi most
12.4.1 | Foundation piles/ Temeljni šipovi
12.4.1.1 | O2 | 105090.04 |  |  | 0 | 0 | 0
12.4.2 | Foundation concrete/ Temeljni beton
12.4.2.1 | A11 | 52074.2045 | 27 |  | 0 | 0 | 0
12.4.2.2 | P1 | 52074.2045 | 28 |  | 0 | 0 | 0
12.4.2.3 | P2 | 52074.2045 |  | 28 | 52074.2 | 0 | 52074.2
12.4.2.4 | P3 | 52074.2045 |  |  | 0 | 0 | 0
12.4.2.5 | P4 | 52074.2045 |  |  | 0 | 0 | 0
12.4.2.6 | P5 | 52074.2045 |  | 28 | 52074.2 | 0 | 52074.2
12.4.2.7 | P6 | 52074.2045 |  |  | 0 | 0 | 0
12.4.2.8 | P7 | 52074.2045 |  |  | 0 | 0 | 0
12.4.2.9 | P8 | 52074.2045 |  |  | 0 | 0 | 0
12.4.2.10 | P9 | 52074.2045 |  |  | 0 | 0 | 0
12.4.2.11 | A2 | 52074.2045 | 29 |  | 0 | 0 | 0
12.4.3 | Abutments and Piers elevation/ Elevacija mosnih stubova
12.4.3.1 | A1 | 92982.54 | 28 |  | 0 | 0 | 0
12.4.3.2 | P1 stage 1 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.3 | P1 stage 2 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.4 | P1 stage 3 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.5 | P1 stage 4 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.6 | P1 stage 5 (2.604m) | 4692.824 |  |  | 0 | 0 | 0
12.4.3.7 | P2 stage 1 (2.5m) | 4505.3994 |  | 29 | 4505.3994 | 0 | 4505.3994
12.4.3.8 | P2 stage 2 (5m) | 9010.7989 |  | 29 | 9010.7989 | 0 | 9010.7989
12.4.3.9 | P2 stage 3 (5m) | 9010.7989 |  | 29 | 9010.7989 | 0 | 9010.7989
12.4.3.10 | P2 stage 4 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.11 | P2 stage 5 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.12 | P2 stage 6 (1.804) | 3251.0962 |  |  | 0 | 0 | 0
12.4.3.13 | P3 stage 1 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.14 | P3 stage 2 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.15 | P3 stage 3 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.16 | P3 stage 4 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.17 | P3 stage 5 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.18 | P3 stage 6 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.19 | P3 stage 7 (4.307m) | 7761.9021 |  |  | 0 | 0 | 0
12.4.3.20 | P4 stage 1 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.21 | P4 stage 2 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.22 | P4 stage 3 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.23 | P4 stage 4 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.24 | P4 stage 5 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.25 | P4 stage 6 (4.004m) | 7215.8477 |  |  | 0 | 0 | 0
12.4.3.26 | P5 stage 1 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.27 | P5 stage 2 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.28 | P5 stage 3 (1.7m) | 3063.6716 |  |  | 0 | 0 | 0
12.4.3.29 | P6 stage 1 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.30 | P6 stage 2 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.31 | P6 stage 3 (1.8m) | 3243.8876 |  |  | 0 | 0 | 0
12.4.3.32 | P7 stage 1 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.33 | P7 stage 2 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.34 | P7 stage 3 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.35 | P7 stage 4 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.36 | P7 stage 5 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.37 | P7 stage 6 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.38 | P7 stage 7 (3.507m) | 6320.1743 |  |  | 0 | 0 | 0
12.4.3.39 | P8 stage 1 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.40 | P8 stage 2 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.41 | P8 stage 3 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.42 | P8 stage 4 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.43 | P8 stage 5 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.44 | P8 stage 6 (4.204m) | 7576.2797 |  |  | 0 | 0 | 0
12.4.3.45 | P9 stage 1 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.46 | P9 stage 2 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.47 | P9 stage 3 (5m) | 9010.7989 |  |  | 0 | 0 | 0
12.4.3.48 | P9 stage 4 (5.204m) | 9378.4395 |  |  | 0 | 0 | 0
12.4.3.49 | A2 | 92982.54 | 30 |  | 0 | 0 | 0
12.4.4 | Spans/ Rasponi
12.4.4.1 | A1-P1
12.4.4.1.1 | Bridge superstructure | 59889.5784 |  |  | 0 | 0 | 0
12.4.4.1.2 | Superstructure prestressing | 6654.3976 |  |  | 0 | 0 | 0
12.4.4.2 | P1-P2
12.4.4.2.1 | Bridge superstructure | 59889.5784 |  |  | 0 | 0 | 0
12.4.4.2.2 | Superstructure prestressing | 6654.3976 |  |  | 0 | 0 | 0
12.4.4.3 | P2-P3
12.4.4.3.1 | Bridge superstructure | 59889.5784 |  |  | 0 | 0 | 0
12.4.4.3.2 | Superstructure prestressing | 6654.3976 |  |  | 0 | 0 | 0
12.4.4.4 | P3-P4
12.4.4.4.1 | Bridge superstructure | 59889.5784 |  |  | 0 | 0 | 0
12.4.4.4.2 | Superstructure prestressing | 6654.3976 |  |  | 0 | 0 | 0
12.4.4.5 | P4-P5
12.4.4.5.1 | Bridge superstructure | 59889.5784 |  |  | 0 | 0 | 0
12.4.4.5.2 | Superstructure prestressing | 6654.3976 |  |  | 0 | 0 | 0
12.4.4.6 | P5-P6
12.4.4.6.1 | Bridge superstructure | 59889.5784 |  |  | 0 | 0 | 0
12.4.4.6.2 | Superstructure prestressing | 6654.3976 |  |  | 0 | 0 | 0
12.4.4.7 | P6-P7
12.4.4.7.1 | Bridge superstructure | 59889.5784 |  |  | 0 | 0 | 0
12.4.4.7.2 | Superstructure prestressing | 6654.3976 |  |  | 0 | 0 | 0
12.4.4.8 | P7-P8
12.4.4.8.1 | Bridge superstructure | 59889.5784 |  |  | 0 | 0 | 0
12.4.4.8.2 | Superstructure prestressing | 6654.3976 |  |  | 0 | 0 | 0
12.4.4.9 | P8-P9
12.4.4.9.1 | Bridge superstructure | 59889.5784 |  |  | 0 | 0 | 0
12.4.4.9.2 | Superstructure prestressing | 6654.3976 |  |  | 0 | 0 | 0
12.4.4.10 | P9-A2
12.4.4.10.1 | Bridge superstructure | 59889.5784 |  |  | 0 | 0 | 0
12.4.4.10.2 | Superstructure prestressing | 6654.3976 |  |  | 0 | 0 | 0
12.4.5 | Bridge Furniture/ Mosna estetika | 45355.98 |  |  | 0 | 0 | 0
12.4.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 120303.03 |  |  | 0 | 0 | 0
Right Bridge/ Desni most
12.4.7 | Foundation piles/ Temeljni šipovi
12.4.7.1 | A1 | 147006.295 |  |  | 0 | 0 | 0
12.4.7.2 | A2 | 147006.295 |  |  | 0 | 0 | 0
12.4.8 | Foundation concrete/ Temeljni beton
12.4.8.1 | A1 | 81240.09 | 25 |  | 0 | 0 | 0
12.4.8.2 | P1 | 54160.06 | 26 |  | 0 | 0 | 0
12.4.8.3 | P2 | 54160.06 | 27 |  | 0 | 0 | 0
12.4.8.4 | P3 | 54160.06 | 28 | 29 | 54160.06 | 0 | 54160.06
12.4.8.5 | P4 | 54160.06 |  | 29 | 54160.06 | 0 | 54160.06
12.4.8.6 | P5 | 54160.06 |  |  | 0 | 0 | 0
12.4.8.7 | P6 | 54160.06 |  | 28 | 54160.06 | 0 | 54160.06
12.4.8.8 | P7 | 54160.06 |  |  | 0 | 0 | 0
12.4.8.9 | P8 | 54160.06 |  |  | 0 | 0 | 0
12.4.8.10 | P9 | 54160.06 |  |  | 0 | 0 | 0
12.4.8.11 | P10 | 54160.06 |  |  | 0 | 0 | 0
12.4.8.12 | P11 | 54160.06 |  |  | 0 | 0 | 0
12.4.8.13 | A2 | 81240.09 | 30 |  | 0 | 0 | 0
12.4.9 | Abutments and Piers elevation/ Elevacija mosnih stubova
12.4.9.1 | A1 | 92982.54 | 26 |  | 0 | 0 | 0
12.4.9.2 | P1 stage 1 (5m) | 9326.7458 | 26 |  | 0 | 0 | 0
12.4.9.3 | P1 stage 2 (5m) | 9326.7458 | 26 |  | 0 | 0 | 0
12.4.9.4 | P1 stage 3 (2.1m) | 3917.2332 | 27 |  | 0 | 0 | 0
12.4.9.5 | P2 stage 1 (5m) | 9326.7458 | 27 |  | 0 | 0 | 0
12.4.9.6 | P2 stage 2 (5m) | 9326.7458 | 27 |  | 0 | 0 | 0
12.4.9.7 | P2 stage 3 (5m) | 9326.7458 | 28 |  | 0 | 0 | 0
12.4.9.8 | P2 stage 4 (2.8m) | 5222.9776 | 28 |  | 0 | 0 | 0
12.4.9.9 | P3 stage 1 (5m) | 9326.7458 | 28 |  | 0 | 0 | 0
12.4.9.10 | P3 stage 2 (5m) | 9326.7458 | 28 |  | 0 | 0 | 0
12.4.9.11 | P3 stage 3 (5m) | 9326.7458 | 28 |  | 0 | 0 | 0
12.4.9.12 | P3 stage 4 (5m) | 9326.7458 | 29 |  | 0 | 0 | 0
12.4.9.13 | P3 stage 5 (5m) | 9326.7458 | 29 |  | 0 | 0 | 0
12.4.9.14 | P3 stage 6 (2.097m) | 3911.6372 | 29 |  | 0 | 0 | 0
12.4.9.15 | P4 stage 1 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.16 | P4 stage 2 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.17 | P4 stage 3 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.18 | P4 stage 4 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.19 | P4 stage 5 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.20 | P4 stage 6 (6.097m) | 11373.0338 |  |  | 0 | 0 | 0
12.4.9.21 | P5 stage 1 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.22 | P5 stage 2 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.23 | P5 stage 3 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.24 | P5 stage 4 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.25 | P5 stage 5 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.26 | P5 stage 6 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.27 | P5 stage 7 (2.097m) | 3911.6372 |  |  | 0 | 0 | 0
12.4.9.28 | P6 stage 1 (5m) | 9326.7458 |  | 29 | 9326.7458 | 0 | 9326.7458
12.4.9.29 | P6 stage 2 (5m) | 9326.7458 |  | 29 | 9326.7458 | 0 | 9326.7458
12.4.9.30 | P6 stage 3 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.31 | P7 stage 1 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.32 | P7 stage 2 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.33 | P7 stage 3 (2.1m) | 3917.2332 |  |  | 0 | 0 | 0
12.4.9.34 | P8 stage 1 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.35 | P8 stage 2 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.36 | P8 stage 3 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.37 | P8 stage 4 (4.597m) | 8575.0101 |  |  | 0 | 0 | 0
12.4.9.38 | P9 stage 1 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.39 | P9 stage 2 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.40 | P9 stage 3 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.41 | P9 stage 4 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.42 | P9 stage 5 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.43 | P9 stage 6 (5.597m) | 10440.3592 |  |  | 0 | 0 | 0
12.4.9.44 | P10 stage 1 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.45 | P10 stage 2 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.46 | P10 stage 3 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.47 | P10 stage 4 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.48 | P10 stage 5 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.49 | P10 stage 6 (1.297m) | 2419.3579 |  |  | 0 | 0 | 0
12.4.9.50 | P11 stage 1 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.51 | P11 stage 2 (5m) | 9326.7458 |  |  | 0 | 0 | 0
12.4.9.52 | P11 stage 3 (2.1m) | 3917.2332 |  |  | 0 | 0 | 0
12.4.9.53 | A2 | 92982.54 | 30 |  | 0 | 0 | 0
12.4.10 | Spans/ Rasponi
12.4.10.1 | A1-P1
12.4.10.1.1 | Bridge superstructure | 60479.757 |  |  | 0 | 0 | 0
12.4.10.1.2 | Superstructure prestressing | 6719.973 |  |  | 0 | 0 | 0
12.4.10.2 | P1-P2
12.4.10.2.1 | Bridge superstructure | 60479.757 |  |  | 0 | 0 | 0
12.4.10.2.2 | Superstructure prestressing | 6719.973 |  |  | 0 | 0 | 0
12.4.10.3 | P2-P3
12.4.10.3.1 | Bridge superstructure | 60479.757 |  |  | 0 | 0 | 0
12.4.10.3.2 | Superstructure prestressing | 6719.973 |  |  | 0 | 0 | 0
12.4.10.4 | P3-P4
12.4.10.4.1 | Bridge superstructure | 60479.757 |  |  | 0 | 0 | 0
12.4.10.4.2 | Superstructure prestressing | 6719.973 |  |  | 0 | 0 | 0
12.4.10.5 | P4-P5
12.4.10.5.1 | Bridge superstructure | 60479.757 |  |  | 0 | 0 | 0
12.4.10.5.2 | Superstructure prestressing | 6719.973 |  |  | 0 | 0 | 0
12.4.10.6 | P5-P6
12.2.10.6.1 | Bridge superstructure | 60479.757 |  |  | 0 | 0 | 0
12.2.10.6.2 | Superstructure prestressing | 6719.973 |  |  | 0 | 0 | 0
12.4.10.7 | P6-P7
12.4.10.7.1 | Bridge superstructure | 60479.757 |  |  | 0 | 0 | 0
12.4.10.7.2 | Superstructure prestressing | 6719.973 |  |  | 0 | 0 | 0
12.4.10.8 | P7-P8
12.4.10.8.1 | Bridge superstructure | 60479.757 |  |  | 0 | 0 | 0
12.2.10.8.2 | Superstructure prestressing | 6719.973 |  |  | 0 | 0 | 0
12.4.10.9 | P8-P9
12.4.10.9.1 | Bridge superstructure | 60479.757 |  |  | 0 | 0 | 0
12.4.10.9.2 | Superstructure prestressing | 6719.973 |  |  | 0 | 0 | 0
12.4.10.10 | P9-P10
12.4.10.10.1 | Bridge superstructure | 60479.757 |  |  | 0 | 0 | 0
12.4.10.10.2 | Superstructure prestressing | 6719.973 |  |  | 0 | 0 | 0
12.4.10.11 | P10-P11
12.4.10.11.1 | Bridge superstructure | 60479.757 |  |  | 0 | 0 | 0
12.4.10.11.2 | Superstructure prestressing | 6719.973 |  |  | 0 | 0 | 0
12.4.10.12 | P12-A2
12.4.10.12.1 | Bridge superstructure | 60479.757 |  |  | 0 | 0 | 0
12.4.10.12.2 | Superstructure prestressing | 6719.973 |  |  | 0 | 0 | 0
12.4.11 | Bridge Furniture/ Mosna estetika | 51641.72 |  |  | 0 | 0 | 0
12.4.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 144767.31 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.4 | 4766405.81 |  |  | 307809.0687 | 0 | 307809.0687
Cost center/ Troškovno mjesto 12.5 | Road Works/Radovi na putevima (LK32+489.200—LK32+633.000, RK32+579.500—RK32+702.500)
Completion of/Završetak:
12.5.1 | Subgrade/ Posteljica
12.5.1.1 | Top soil removal/ Uklanjanje humusa | 21594.56 | 18 |  | 0 | 0 | 0
12.5.1.2 | Earthworks/ Zemljani radovi | 93066.08 | 18 |  | 0 | 0 | 0
12.5.1.3 | Road Foundation/ Temelj puta | 103841.81 | 35 |  | 0 | 0 | 0
12.5.2 | Engineering structures/ Inženjerske konstrukcije | 0 |  |  | 0 | 0 | 0
12.5.2.1 | Concrete wall/ Betonski zid | 1154123.07 |  |  | 0 | 0 | 0
12.5.3 | Water drainage/ Drenaža vode
12.5.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 30170.21 | 39 |  | 0 | 0 | 0
12.5.4 | Pavement structure/ Kolovozna konstrukcija | 13274.92 | 41 |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.5 | 1416070.65 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.6 | Construction of bridge/Izgradnja mosta Uvac 2 (LK 32+633.000- LK 32.793.00, RK 32.702.500-RK 32.862.500)
Completion of/Završeno:
Left bridge/ Lijevi most
12.6.1 | Foundation piles/ Temeljni sipovi | 398696.27 |  |  | 0 | 0 | 0
12.6.2 | Foundation concrete/ Temeljni beton | 280939.55 |  |  | 0 | 0 | 0
12.6.3 | Abutments and Piers elevation/ Elevacija mosnih stubova | 395293.91 |  |  | 0 | 0 | 0
12.6.4 | Spans/ Rasponi | 399122.15 |  |  | 0 | 0 | 0
12.6.5 | Bridge furniture/ Mosna estetika | 34187.18 |  |  | 0 | 0 | 0
12.6.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 68535.71 |  |  | 0 | 0 | 0
| Right bridge/ Desni most | 0
12.6.7 | Foundation piles/ Temeljni sipovi | 291051.91 |  |  | 0 | 0 | 0
12.6.8 | Foundation concrete/ Temeljni beton | 316525.68 |  |  | 0 | 0 | 0
12.6.9 | Abutments and Piers elevation/ Elevacija mosnih stubova | 317802.84 |  |  | 0 | 0 | 0
12.6.10 | Spans/ Rasponi | 399517.54 |  |  | 0 | 0 | 0
12.6.11 | Bridge furniture/ Mosna estetika | 31836.8 |  |  | 0 | 0 | 0
12.9.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 68535.71 |  |  | 0 | 0 | 0
12.6.13 | Engineering structures/Inženjerske konstrukcije | 0 |  |  | 0 | 0 | 0
12.6.13.1 | Reinforced earth wall (it will be splitted after MD approval)/ Ojačani zemljani zid (podijeliće se nakon odobrenja GP) | 56886.89 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.6 | 3058932.14 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.7 | Road Works/Radovi na putevima (LK32+793.000—LK32+820.000, RK32+862.500—RK32+885.000)
Completion of/Završetak:
12.7.1 | Subgrade/ Posteljica
12.7.1.1 | Top soil removal/ Uklanjanje humusa | 3950.22 | 19 |  | 0 | 0 | 0
12.7.1.2 | Earthworks/ Zemljani radovi | 46533.04 |  |  | 0 | 0 | 0
12.7.1.3 | Road Foundation/ Temelj puta | 18995.45 | 36 |  | 0 | 0 | 0
12.7.2 | Engineering structures/ Inženjerske konstrukcije
12.7.2.1 | Concrete wall/ Betonski zid | 149724.07 | 37 |  | 0 | 0 | 0
12.7.3 | Water drainage/ Drenaža vode
12.7.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 5518.94 | 37 |  | 0 | 0 | 0
12.7.4 | Pavement structure/ Kolovozna konstrukcija | 2428.34 | 38 |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.7 | 227150.06 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.8 | Construction of tunnel/Izgradnja tunela Vitanovice (LK 32+820.000- LK 32+950.000, RK 32+885.000- RK 33+035.000)
Completion of/Završetak:
12.8.1 | Portal construction/ Izgradnja portala | 535792.79 |  |  | 0 | 0 | 0
12.8.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade | 2716218.79 |  |  | 0 | 0 | 0
12.8.3 | Construction of waterproofing and drainage/ Konstrukcija hidroizolacije i drenaže | 1100901.17 |  |  | 0 | 0 | 0
12.8.4 | Construction of secondary lining/ Konstrukcija sekundarne obloge | 1556976.81 |  |  | 0 | 0 | 0
12.8.5 | Construction of pavement/ Izgradnja kolovoza
12.8.5.1 | Left tube/ Lijeva cijev | 31572.31 |  |  | 0 | 0 | 0
12.8.5.2 | Right tube/ Desna cijev | 36254.98 |  |  | 0 | 0 | 0
12.8.6 | Tunnel facilities/ Tunelski objekti
12.8.6.1 | Construction of Power Station/ Izgradnja elektro-stanice | 842710.55 |  |  | 0 | 0 | 0
12.8.6.2 | Construction of antifire reservoir/ Izgradnja protivpožarnog rezervoara | 281498.08 |  |  | 0 | 0 | 0
12.8.7 | Tunnel Equipment/ Tunelska oprema
12.8.6.1 | 90% (Equipment installed/Oprema postavljena) | 483817.698 | 39 |  | 0 | 0 | 0
12.8.6.2 | 10% (Equipment tested/Oprema ispitana) | 53757.522 | 39 |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.8 | 7639500.7 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.9 | Open Route/Otvorena trasa LK32+950.000—LK32+962.500 RK33+035.000—RK33+059.000
Completion of/Završetak:
12.9.1 | Subgrade/ Posteljica
12.9.1.1 | Top soil removal/ Uklanjanje humusa | 4213.57 | 19 |  | 0 | 0 | 0
12.9.1,2 | Earthworks/ Zemljani radovi | 19369.85 | 37 |  | 0 | 0 | 0
12.9.1.3 | Road Foundation/ Temelj puta | 20261.82
12.9.2 | Engineering structures/ Inženjerske konstrukcije
12.9.2.1 | Concrete wall/ Betonski zid | 91742.69 | 37 |  | 0 | 0 | 0
12.9.3 | Water drainage/ Drenaža vode
12.9.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 5886.87 | 39 |  | 0 | 0 | 0
12.9.4 | Pavement structure/ Kolovozna konstrukcija | 2590.23 | 40 |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.9 | 144065.03 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.10 | Construction of bridge/Izgradnja mosta Uvac 3 (LK 32+962.500-LK 33+108.500, RK 33+059.000-RK 33+153.00)
Completion of/Završeno:
Left bridge/ Lijevi most
12.10.1 | Foundation piles/ Temeljni sipovi | 284894.08 | 32-37 |  | 0 | 0 | 0
12.10.2 | Foundation concrete/ Temeljni beton | 286920.96 | 32-37 |  | 0 | 0 | 0
12.10.3 | Abutments and Piers elevation/ Elevacija mosnih stubova | 358450.4 | 39-41 |  | 0 | 0 | 0
12.10.4 | Spans/ Rasponi | 488652.68 | 41-42 |  | 0 | 0 | 0
12.10.5 | Bridge furniture/ Mosna estetika | 32206.86 | 42 |  | 0 | 0 | 0
12.10.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 81596.59 | 41-42 |  | 0 | 0 | 0
Right bridge/ Desni most
12.10.7 | Foundation piles/ Temeljni sipovi | 262331.45 | 32-37 |  | 0 | 0 | 0
12.10.8 | Foundation concrete/ Temeljni beton | 362755.3 | 32-37 |  | 0 | 0 | 0
12.10.9 | Abutments and Piers elevation/ Elevacija mosnih stubova | 262751.04 | 39-41 |  | 0 | 0 | 0
12.10.10 | Spans/ Rasponi | 278443.64 | 41-42 |  | 0 | 0 | 0
12.10.11 | Bridge furniture/ Mosna estetika | 12655.56 | 42 |  | 0 | 0 | 0
12.10.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 53862.81 | 41-42 |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.10 | 2765521.37 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.11 | Open Route/Otvorena trasa LK33+108.500—LK33+189.000 RK33+153.000—RK33+248.300
Completion of/Završetak:
12.11.1 | Subgrade/ Posteljica |  |  |  | 0 | 0 | 0
12.11.1.1 | Top soil removal/ Uklanjanje humusa | 16731.39 | 18 |  | 0 | 0 | 0
12.11.1.2 | Earthworks/ Zemljani radovi | 173057.5 | 38 |  | 0 | 0 | 0
12.11.1.3 | Road Foundation/ Temelj puta | 80456.3 | 39 |  | 0 | 0 | 0
12.11.2 | Engineering structures/ Inženjerske konstrukcije |  |  |  | 0 | 0 | 0
12.11.2.1 | Concrete wall/ Betonski zid | 575043.2 | 30 |  | 0 | 0 | 0
12.11.3 | Water drainage/ Drenaža vode |  |  |  | 0 | 0 | 0
12.11.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 23375.78 | 40 |  | 0 | 0 | 0
12.11.4 | Pavement structure/ Kolovozna konstrukcija | 10285.36 | 40-42 |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.11 | 878949.53 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.12 | Construction of bridge/Izgradnja mosta Uvac 4 (LK 33+189.000- LK33+283.00, LK 33+352.500-LK 34+062.500, RK 33+248.300-RK 34+138.300)
Completion of/Završetak:
Left Bridge-1/ Lijevi most
12.12.1 | Foundation piles/ Temeljni šipovi
12.12.1.1 | A1 | 240292.7433 |  |  | 0 | 0 | 0
12.12.1.2 | P1 | 80097.5811 |  |  | 0 | 0 | 0
12.12.1.3 | P2 | 80097.5811 |  |  | 0 | 0 | 0
12.12.1.4 | P3 | 80097.5811 |  |  | 0 | 0 | 0
12.12.1.5 | A2 | 240292.7433 |  |  | 0 | 0 | 0
12.12.2 | Foundation concrete/ Temeljni beton
12.12.2.1 | A1 | 60846.6 | 26 |  | 0 | 0 | 0
12.12.2.2 | P1 | 60846.6 | 27 |  | 0 | 0 | 0
12.12.2.3 | P2 | 60846.6 | 28 |  | 0 | 0 | 0
12.12.2.4 | P3 | 60846.6 |  |  | 0 | 0 | 0
12.12.2.5 | A2 | 60846.6 | 29 |  | 0 | 0 | 0
12.12.3 | Abutments and Piers elevation/ Elevacija mosnih stubova
12.12.3.1 | A1 | 41322.19 | 28 |  | 0 | 0 | 0
12.12.3.2 | P1 stage 1 (5m) | 12621.0309 | 30 |  | 0 | 0 | 0
12.12.3.3 | P1 stage 2 (5m) | 12621.0309 | 31 |  | 0 | 0 | 0
12.12.3.4 | P1 stage 3 (5m) | 12621.0309 | 32 |  | 0 | 0 | 0
12.12.3.5 | P1 stage 4 (2m) | 5048.4124 | 32 |  | 0 | 0 | 0
12.12.3.6 | P2 stage 1 (5m) | 12621.0309 | 34 |  | 0 | 0 | 0
12.12.3.7 | P2 stage 2 (5m) | 12621.0309 | 34 |  | 0 | 0 | 0
12.12.3.8 | P2 stage 3 (5m) | 12621.0309 | 35 |  | 0 | 0 | 0
12.12.3.9 | P2 stage 4 (5m) | 12621.0309 | 35 |  | 0 | 0 | 0
12.12.3.10 | P2 stage 5 (5m) | 12621.0309 | 36 |  | 0 | 0 | 0
12.12.3.11 | P2 stage 6 (6.5m) | 16407.3401 | 36 |  | 0 | 0 | 0
12.12.3.12 | P3 stage 1 (5m) | 12621.0309 |  |  | 0 | 0 | 0
12.12.3.13 | P3 stage 2 (5m) | 12621.0309 |  |  | 0 | 0 | 0
12.12.3.14 | P3 stage 3 (5m) | 12621.0309 |  |  | 0 | 0 | 0
12.12.3.15 | P3 stage 4 (4.5m) | 11358.9278 |  |  | 0 | 0 | 0
12.12.3.16 | A2 | 41322.19 | 36 |  | 0 | 0 | 0
12.12.4 | Spans/ Rasponi
12.12.4.1 | A1-P1
12.12.4.1.1 | Bridge superstructure | 63322.4182 |  |  | 0 | 0 | 0
12.12.4.1.2 | Superstructure prestressing | 7035.8242 |  |  | 0 | 0 | 0
12.12.4.2 | P1-P2
12.12.4.2.1 | Bridge superstructure | 63322.4182 |  |  | 0 | 0 | 0
12.12.4.2.2 | Superstructure prestressing | 7035.8242 |  |  | 0 | 0 | 0
12.12.4.3 | P2-P3
12.12.4.3.1 | Bridge superstructure | 63322.4182 |  |  | 0 | 0 | 0
12.12.4.3.2 | Superstructure prestressing | 7035.8242 |  |  | 0 | 0 | 0
12.12.4.4 | P3-A2
12.12.4.4.1 | Bridge superstructure | 63322.4182 |  |  | 0 | 0 | 0
12.12.4.4.2 | Superstructure prestressing | 7035.8242 |  |  | 0 | 0 | 0
12.12.5 | Bridge Furniture/ Mosna estetika | 28177.37 |  |  | 0 | 0 | 0
12.12.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 57062.85 |  |  | 0 | 0 | 0
Left Bridge-2/ Lijevi most
12.12.7 | Foundation piles/ Temeljni šipovi
12.12.7.1 | A1 | 191017.5857 |  |  | 0 | 0 | 0
12.12.7.2 | P1 | 152814.0686 |  | 30 | 0 | 152814.0686 | 152814.0686
12.12.7.3 | P2 | 152814.0686 |  | 30 | 0 | 152814.0686 | 152814.0686
12.12.7.4 | P3 | 152814.0686 |  |  | 0 | 0 | 0
12.12.7.5 | P4 | 152814.0686 |  |  | 0 | 0 | 0
12.12.7.6 | P5 | 152814.0686 |  | 30 | 0 | 152814.0686 | 152814.0686
12.12.7.7 | P6 | 152814.0686 |  | 30 | 0 | 152814.0686 | 152814.0686
12.12.7.8 | P7 | 152814.0686 |  | 30 | 0 | 152814.0686 | 152814.0686
12.12.7.9 | P8 | 152814.0686 |  | 29 | 152814.0686 | 0 | 152814.0686
12.12.7.10 | P9 | 152814.0686 |  | 30 | 0 | 152814.0686 | 152814.0686
12.12.7.11 | P10 | 152814.0686 |  | 30 | 0 | 152814.0686 | 152814.0686
12.12.7.12 | P11 | 152814.0686 |  |  | 0 | 0 | 0
12.12.7.13 | P12 | 152814.0686 |  |  | 0 | 0 | 0
12.12.7.14 | P13 | 152814.0686 |  |  | 0 | 0 | 0
12.12.7.15 | P14 | 152814.0686 |  |  | 0 | 0 | 0
12.12.7.16 | P15 | 152814.0686 |  |  | 0 | 0 | 0
12.12.7.17 | A2 | 191017.5857 |  |  | 0 | 0 | 0
12.12.8 | Foundation concrete/ Temeljni beton
12.12.8.1 | A1 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.2 | P1 | 59206.2676 |  | 30 | 0 | 59206.2676 | 59206.2676
12.12.8.3 | P2 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.4 | P3 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.5 | P4 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.6 | P5 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.7 | P6 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.8 | P7 | 59206.2676 |  | 30 | 0 | 59206.2676 | 59206.2676
12.12.8.9 | P8 | 59206.2676 |  | 29 | 59206.2676 | 0 | 59206.2676
12.12.8.10 | P9 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.11 | P10 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.12 | P11 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.13 | P12 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.14 | P13 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.15 | P14 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.16 | P15 | 59206.2676 |  |  | 0 | 0 | 0
12.12.8.17 | A2 | 59206.2676 |  |  | 0 | 0 | 0
12.12.9 | Abutments and Piers elevation/ Elevacija mosnih stubova
12.12.9.1 | A1 | 61774.6353 |  |  | 0 | 0 | 0
12.12.9.2 | P1 stage 1 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.3 | P1 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.4 | P1 stage 3 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.5 | P2 stage 1 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.6 | P2 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.7 | P2 stage 3 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.8 | P2 stage 4 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.9 | P2 stage 5 (6.5m) | 26769.0086 |  |  | 0 | 0 | 0
12.12.9.10 | P3 stage 1 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.11 | P3 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.12 | P3 stage 3 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.13 | P3 stage 4 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.14 | P3 stage 5 (4.2m) | 17296.8979 |  |  | 0 | 0 | 0
12.12.9.15 | P4 stage 1 (6m) | 24709.8541 |  |  | 0 | 0 | 0
12.12.9.16 | P4 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.17 | P4 stage 3 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.18 | P4 stage 4 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.19 | P4 stage 5 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.20 | P4 stage 6 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.21 | P4 stage 7 (2.5m) | 10295.7725 |  |  | 0 | 0 | 0
12.12.9.22 | P5 stage 1 (7.5m) | 30887.3176 |  |  | 0 | 0 | 0
12.12.9.23 | P5 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.24 | P5 stage 3 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.25 | P5 stage 4 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.26 | P5 stage 5 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.27 | P5 stage 6 (4.75m) | 19561.9678 |  |  | 0 | 0 | 0
12.12.9.28 | P5 stage 7 (2m) | 8236.618 |  |  | 0 | 0 | 0
12.12.9.29 | P6 stage 1 (6m) | 24709.8541 |  |  | 0 | 0 | 0
12.12.9.30 | P6 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.31 | P6 stage 3 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.32 | P6 stage 4 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.33 | P6 stage 5 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.34 | P6 stage 6 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.35 | P6 stage 7 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.36 | P6 stage 8 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.37 | P6 stage 9 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.38 | P6 stage 10 (4.5m) | 18532.3906 |  |  | 0 | 0 | 0
12.12.9.39 | P7 stage 1 (6m) | 24709.8541 |  |  | 0 | 0 | 0
12.12.9.40 | P7 stage 2 (6m) | 24709.8541 |  |  | 0 | 0 | 0
12.12.9.41 | P7 stage 3 (6m) | 24709.8541 |  |  | 0 | 0 | 0
12.12.9.42 | P7 stage 4 (6m) | 24709.8541 |  |  | 0 | 0 | 0
12.12.9.43 | P7 stage 5 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.44 | P7 stage 6 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.45 | P7 stage 7 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.46 | P7 stage 8 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.47 | P7 stage 9 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.48 | P7 stage 10 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.49 | P7 stage 11 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.50 | P7 stage 12 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.51 | S7 stage 13 | 0 |  |  | 0 | 0 | 0
12.12.9.52 | P8 stage 1 (6m) | 24709.8541 |  | 30 | 0 | 24709.8541 | 24709.8541
12.12.9.53 | P8 stage 2 (6m) | 24709.8541 |  | 30 | 0 | 24709.8541 | 24709.8541
12.12.9.54 | P8 stage 3 (6m) | 24709.8541 |  | 30 | 0 | 24709.8541 | 24709.8541
12.12.9.55 | P8 stage 4 (6m) | 24709.8541 |  | 30 | 0 | 24709.8541 | 24709.8541
12.12.9.56 | P8 stage 5 (6m) | 24709.8541 |  |  | 0 | 0 | 0
12.12.9.57 | P8 stage 6 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.58 | P8 stage 7 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.59 | P8 stage 8 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.60 | P8 stage 9 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.61 | P8 stage 10 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.62 | P8 stage 11 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.63 | P8 stage 12 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.64 | P9 stage 1 (7.5m) | 30887.3176 |  |  | 0 | 0 | 0
12.12.9.65 | P9 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.66 | P9 stage 3 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.67 | P9 stage 4 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.68 | P9 stage 5 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.69 | P9 stage 6 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.70 | P9 stage 7 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.71 | P9 stage 8 (4.5m) | 18532.3906 |  |  | 0 | 0 | 0
12.12.9.72 | P10 stage 1 (7.5m) | 30887.3176 |  |  | 0 | 0 | 0
12.12.9.73 | P10 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.74 | P10 stage 3 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.75 | P10 stage 4 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.76 | P10 stage 5 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.77 | P10 stage 6 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.78 | P10 stage 7 (4.7m) | 19356.0524 |  |  | 0 | 0 | 0
12.12.9.79 | P11 stage 1 (7.5m) | 30887.3176 |  |  | 0 | 0 | 0
12.12.9.80 | P11 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.81 | P11 stage 3 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.82 | P11 stage 4 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.83 | P11 stage 5 (3.75m) | 15443.6588 |  |  | 0 | 0 | 0
12.12.9.84 | P11 stage 6 (2m) | 8236.618 |  |  | 0 | 0 | 0
12.12.9.85 | P12 stage 1 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.86 | P12 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.87 | P12 stage 3 (4.5m) | 18532.3906 |  |  | 0 | 0 | 0
12.12.9.79 | P13 stage 1 (7.5m) | 30887.3176 |  |  | 0 | 0 | 0
12.12.9.80 | P13 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.81 | P13 stage 3 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.82 | P13 stage 4 (6m) | 24709.8541 |  |  | 0 | 0 | 0
12.12.9.83 | P14 stage 1 (7.5m) | 30887.3176 |  |  | 0 | 0 | 0
12.12.9.84 | P14 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.85 | P14 stage 3 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.86 | P14 stage 4 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.87 | P14 stage 5 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.79 | P14 stage 6 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.80 | P14 stage 7 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.81 | P14 stage 8 (6.3m) | 25945.3468 |  |  | 0 | 0 | 0
12.12.9.82 | P15 stage 1 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.83 | P15 stage 2 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.84 | P15 stage 3 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.85 | P15 stage 4 (5m) | 20591.5451 |  |  | 0 | 0 | 0
12.12.9.86 | P15 stage 5 (7.2m) | 29651.8249 |  |  | 0 | 0 | 0
12.12.9.87 | A2 | 61774.6353 |  |  | 0 | 0 | 0
12.12.10 | Spans/ Rasponi
12.12.10.1 | A1-P1
12.12.10.1.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.1.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.2 | P1-P2
12.12.10.2.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.2.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.3 | P2-P3
12.12.10.3.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.3.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.4 | P3-P4
12.12.10.4.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.4.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.5 | P4-P5
12.12.10.5.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.5.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.6 | P5-P6
12.12.10.6.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.6.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.7 | P6-P7
12.12.10.7.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.7.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.8 | P7-P8
12.12.10.8.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.8.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.9 | P8-P9
12.12.10.9.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.9.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.10 | P9-P10
12.12.10.10.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.10.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.11 | P10-P11
12.12.10.11.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.11.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.12 | P11-P12
12.12.10.12.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.12.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.13 | P12-P13
12.12.10.13.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.13.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.14 | P13-P14
12.12.10.14.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.14.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.15 | P14-P15
12.12.10.15.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.15.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.10.16 | P15-A2
12.12.10.16.1 | Bridge superstructure | 122120.577 |  |  | 0 | 0 | 0
12.12.10.16.2 | Superstructure prestressing | 13568.953 |  |  | 0 | 0 | 0
12.12.11 | Bridge Furniture/ Mosna estetika | 134579.8851 |  |  | 0 | 0 | 0
12.12.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 380953.63 |  |  | 0 | 0 | 0
Right Bridge/ Desni most
12.12.13 | Foundation piles/ Temeljni šipovi
12.12.13.1 | A1 | 182294.5855 |  |  | 0 | 0 | 0
12.12.13.2 | P1 | 121529.7237 |  |  | 0 | 0 | 0
12.12.13.3 | P2 | 121529.7237 |  |  | 0 | 0 | 0
12.12.13.4 | P3 | 121529.7237 |  |  | 0 | 0 | 0
12.12.13.5 | P4 | 121529.7237 |  |  | 0 | 0 | 0
12.12.13.6 | P5 | 121529.7237 |  |  | 0 | 0 | 0
12.12.13.7 | P6 | 121529.7237 |  | 30 | 0 | 121529.7237 | 121529.7237
12.12.13.8 | P7 | 121529.7237 |  | 28 | 121529.72 | 0 | 121529.72
12.12.13.9 | P8 | 121529.7237 |  | 28 | 121529.72 | 0 | 121529.72
12.12.13.10 | P9 | 121529.7237 |  | 30 | 0 | 121529.7237 | 121529.7237
12.12.13.11 | P10 | 121529.7237 |  | 30 | 0 | 121529.7237 | 121529.7237
12.12.13.12 | P11 | 121529.7237 |  | 28 | 121529.72 | 0 | 121529.72
12.12.13.13 | P12 | 121529.7237 |  |  | 0 | 0 | 0
12.12.13.14 | P13 | 121529.7237 |  |  | 0 | 0 | 0
12.12.13.15 | P14 | 121529.7237 |  | 30 | 0 | 121529.7237 | 121529.7237
12.12.13.16 | P15 | 121529.7237 |  |  | 0 | 0 | 0
12.12.13.17 | P16 | 121529.7237 |  |  | 0 | 0 | 0
12.12.13.18 | P17 | 121529.7237 |  |  | 0 | 0 | 0
12.12.13.19 | P18 | 121529.7237 |  |  | 0 | 0 | 0
12.12.13.20 | P19 | 121529.7237 |  |  | 0 | 0 | 0
12.12.13.21 | A2 | 151912.1546 |  |  | 0 | 0 | 0
12.12.14 | Foundation concrete/ Temeljni beton
12.12.14.1 | A1 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.2 | P1 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.3 | P2 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.4 | P3 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.5 | P4 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.6 | P5 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.7 | P6 | 42691.7276 |  | 30 | 0 | 42691.7276 | 42691.7276
12.12.14.8 | P7 | 42691.7276 |  | 28 | 42691.73 | 0 | 42691.73
12.12.14.9 | P8 | 42691.7276 |  | 28 | 42691.73 | 0 | 42691.73
12.12.14.10 | P9 | 42691.7276 |  | 30 | 0 | 42691.7276 | 42691.7276
12.12.14.11 | P10 | 42691.7276 |  | 30 | 0 | 42691.7276 | 42691.7276
12.12.14.12 | P11 | 42691.7276 |  | 29 | 42691.7276 | 0 | 42691.7276
12.12.14.13 | P12 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.14 | P13 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.15 | P14 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.16 | P15 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.17 | P16 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.18 | P17 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.19 | P18 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.20 | P19 | 42691.7276 |  |  | 0 | 0 | 0
12.12.14.21 | A2 | 42691.7276 |  |  | 0 | 0 | 0
12.12.15 | Abutments and Piers elevation/ Elevacija mosnih stubova
12.12.15.1 | A1 | 46744.9765 |  |  | 0 | 0 | 0
12.12.15.2 | P1 stage 1 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.3 | P1 stage 2 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.4 | P1 stage 3 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.5 | P1 stage 4 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.6 | P1 stage 5 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.7 | P1 stage 6 (3m) | 9348.9953 |  |  | 0 | 0 | 0
12.12.15.8 | P2 stage 1 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.9 | P2 stage 2 (4.5m) | 14023.493 |  |  | 0 | 0 | 0
12.12.15.10 | P3 stage 1 (4.5m) | 14023.493 |  |  | 0 | 0 | 0
12.12.15.11 | P4 stage 1 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.12 | P4 stage 2 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.13 | P4 stage 3 (2.5m) | 7790.8294 |  |  | 0 | 0 | 0
12.12.15.14 | P5 stage 1 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.15 | P5 stage 2 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.16 | P5 stage 3 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.17 | P5 stage 4 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.18 | P5 stage 5 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.19 | P6 stage 1 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.20 | P6 stage 2 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.21 | P6 stage 3 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.22 | P6 stage 4 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.23 | P6 stage 5 (6.5m) | 20256.1565 |  |  | 0 | 0 | 0
12.12.15.24 | P7 stage 1 (5m) | 15581.6588 |  | 28 | 15581.66 | 0 | 15581.66
12.12.15.25 | P7 stage 2 (5m) | 15581.6588 |  | 28 | 15581.66 | 0 | 15581.66
12.12.15.26 | P7 stage 3 (5m) | 15581.6588 |  | 28 | 15581.66 | 0 | 15581.66
12.12.15.27 | P7 stage 4 (5m) | 15581.6588 |  | 28 | 15581.66 | 0 | 15581.66
12.12.15.28 | P7 stage 5 (4.5m) | 14023.493 |  | 30 | 0 | 14023.493 | 14023.493
12.12.15.29 | P7 stage 6 (2m) | 6232.6635 |  |  | 0 | 0 | 0
12.12.15.30 | P8 stage 1 (5m) | 15581.6588 |  | 28 | 15581.66 | 0 | 15581.66
12.12.15.31 | P8 stage 2 (6m) | 18697.9906 |  | 28 | 18697.9906 | 0 | 18697.9906
12.12.15.32 | P8 stage 3 (5m) | 15581.6588 |  | 28 | 15581.66 | 0 | 15581.66
12.12.15.33 | P8 stage 4 (5m) | 15581.6588 |  | 30 | 0 | 15581.6588 | 15581.6588
12.12.15.34 | P8 stage 5 (5m) | 15581.6588 |  | 30 | 0 | 15581.6588 | 15581.6588
12.12.15.35 | P8 stage 6 (5m) | 15581.6588 |  | 30 | 0 | 15581.6588 | 15581.6588
12.12.15.36 | P8 stage 7 (5.5m) | 17139.8247 |  |  | 0 | 0 | 0
12.12.15.37 | P9 stage 1 (6m) | 18697.9906 |  | 30 | 0 | 18697.9906 | 18697.9906
12.12.15.38 | P9 stage 2 (5m) | 15581.6588 |  | 30 | 0 | 15581.6588 | 15581.6588
12.12.15.39 | P9 stage 3 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.40 | P9 stage 4 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.41 | P9 stage 5 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.42 | P9 stage 6 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.43 | P9 stage 7 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.44 | P9 stage 8 (4m) | 12465.3271 |  |  | 0 | 0 | 0
12.12.15.45 | P10 stage 1 (7.5m) | 23372.4883 |  | 30 | 0 | 23372.4883 | 23372.4883
12.12.15.46 | P10 stage 2 (5m) | 15581.6588 |  | 30 | 0 | 15581.6588 | 15581.6588
12.12.15.47 | P10 stage 3 (5m) | 15581.6588 |  | 30 | 0 | 15581.6588 | 15581.6588
12.12.15.48 | P10 stage 4 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.49 | P10 stage 5 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.50 | P10 stage 6 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.51 | P10 stage 7 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.52 | P10 stage 8 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.53 | P10 stage 9 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.54 | P10 stage 10 (6.5m) | 20256.1565 |  |  | 0 | 0 | 0
12.12.15.55 | P11 stage 1 (6m) | 18697.9906 |  | 30 | 0 | 18697.9906 | 18697.9906
12.12.15.56 | P11 stage 2 (6m) | 18697.9906 |  | 30 | 0 | 18697.9906 | 18697.9906
12.12.15.57 | P11 stage 3 (6m) | 18697.9906 |  | 30 | 0 | 18697.9906 | 18697.9906
12.12.15.58 | P11 stage 4 (6m) | 18697.9906 |  | 30 | 0 | 18697.9906 | 18697.9906
12.12.15.59 | P11 stage 5 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.60 | P11 stage 6 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.61 | P11 stage 7 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.62 | P11 stage 8 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.63 | P11 stage 9 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.64 | P11 stage 10 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.65 | P11 stage 11 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.66 | P12 stage 1 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.67 | P12 stage 2 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.68 | P12 stage 3 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.69 | P12 stage 4 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.70 | P12 stage 5 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.71 | P12 stage 6 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.72 | P12 stage 7 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.73 | P12 stage 8 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.74 | P12 stage 9 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.75 | P13 stage 1 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.76 | P13 stage 2 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.77 | P13 stage 3 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.78 | P13 stage 4 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.79 | P13 stage 5 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.80 | P13 stage 6 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.81 | P13 stage 7 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.82 | P13 stage 8 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.83 | P14 stage 1 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.84 | P14 stage 2 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.85 | P14 stage 3 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.86 | P14 stage 4 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.87 | P14 stage 5 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.88 | P14 stage 6 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.89 | P14 stage 7 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.90 | P14 stage 8 (4m) | 12465.3271 |  |  | 0 | 0 | 0
12.12.15.91 | P15 stage 1 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.92 | P15 stage 2 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.93 | P15 stage 3 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.94 | P15 stage 4 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.95 | P15 stage 5 (2m) | 6232.6635 |  |  | 0 | 0 | 0
12.12.15.96 | P16 stage 1 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.97 | P16 stage 2 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.98 | P16 stage 3 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.99 | P16 stage 4 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.100 | P16 stage 5 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.101 | P17 stage 1 (7.5m) | 23372.4883 |  |  | 0 | 0 | 0
12.12.15.102 | P17 stage 2 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.103 | P17 stage 3 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.104 | P17 stage 4 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.105 | P17 stage 5 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.106 | P17 stage 6 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.107 | P17 stage 7 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.108 | P18 stage 1 (7.5m) | 23372.4883 |  |  | 0 | 0 | 0
12.12.15.109 | P18 stage 2 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.110 | P18 stage 3 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.111 | P18 stage 4 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.112 | P18 stage 5 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.113 | P18 stage 6 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.114 | P18 stage 7 (5m) | 15581.6588 |  |  | 0 | 0 | 0
12.12.15.115 | P19 stage 1 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.116 | P19 stage 2 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.117 | P19 stage 3 (6m) | 18697.9906 |  |  | 0 | 0 | 0
12.12.15.118 | A2 | 46744.9765 |  |  | 0 | 0 | 0
12.12.16 | Spans/ Rasponi
12.12.16.1 | A1-P1
12.12.16.1.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.1.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.2 | P1-P2
12.12.16.2.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.2.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.3 | P2-P3
12.12.16.3.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.3.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.4 | P3-P4
12.12.16.4.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.4.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.5 | P4-P5
12.12.16.5.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.5.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.6 | P5-P6
12.12.16.6.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.6.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.7 | P6-P7
12.12.16.7.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.7.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.8 | P7-P8
12.12.16.8.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.8.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.9 | P8-P9
12.12.16.9.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.9.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.10 | P9-P10
12.12.16.10.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.10.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.11 | P10-P11
12.12.16.11.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.11.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.12 | P11-P12
12.12.16.12.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.12.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.13 | P12-P13
12.12.16.13.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.13.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.14 | P13-P14
12.12.16.14.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.14.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.15 | P14-P15
12.12.16.15.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.15.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.16 | P15-P16
12.12.16.16.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.16.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.17 | P16-P17
12.12.16.17.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.17.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.18 | P17-P18
12.12.16.18.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.18.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.19 | P18-P19
12.12.16.19.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.19.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.16.20 | P19-A2
12.12.16.20.1 | Bridge superstructure | 80685.0756 |  |  | 0 | 0 | 0
12.12.16.20.2 | Superstructure prestressing | 8965.0084 |  |  | 0 | 0 | 0
12.12.17 | Bridge Furniture/ Mosna estetika | 94084.73 |  |  | 0 | 0 | 0
12.12.18 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 304739.69 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.12 | 18005855.85 |  |  | 816872.6344 | 2125520.3966 | 2942393.031
Cost center/ Troškovno mjesto 12.13 | Open Route/Otvorena trasa LK33+283.000—LK33+352.500
Completion of/Završetak:
12.13.1 | Subgrade/ Posteljica
12.13.1.1 | Top soil removal/ Uklanjanje humusa | 12201.8 | 19 |  | 0 | 0 | 0
12.13.1.2 | Earthworks/ Zemljani radovi | 38563.15 | 38 |  | 0 | 0 | 0
12.13.1.3 | Road Foundation/ Temelj puta | 58674.84 | 41 |  | 0 | 0 | 0
12.13.2 | Engineering structures/ Inženjerske konstrukcije
12.13.2.1 | Concrete wall/ Betonski zid | 192659.65 | 28 |  | 0 | 0 | 0
12.13.3 | Water drainage/ Drenaža vode
12.13.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 17047.39 | 41 |  | 0 | 0 | 0
12.13.4 | Pavement structure/ Kolovozna konstrukcija | 7500.87 | 41-42 |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.13 | 326647.7 |  |  | 0 | 0 | 0
Cost Center/ Troškovno mjesto 12.14 | Open Route/Otvorena trasa LK34+062.500—LK34+078.000 RK34+138.300—RK34+148.000
Completion of/Završetak:
12.14.1 | Subgrade/ Posteljica
12.14.1.1 | Top soil removal/ Uklanjanje humusa | 1702.99 |  |  | 0 | 0 | 0
12.14.1.2 | Earthworks/ Zemljani radovi | 33271.75 |  |  | 0 | 0 | 0
12.14.1.3 | Road Foundation/ Temelj puta | 8189.15 |  |  | 0 | 0 | 0
12.14.2 | Engineering structures/ Inženjerske konstrukcije
12.14.2.1 | Concrete wall/ Betonski zid | 66788.68 |  |  | 0 | 0 | 0
12.14.3 | Water drainage/ Drenaža vode
12.13.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 2379.28 |  |  | 0 | 0 | 0
12.14.4 | Pavement structure/ Kolovozna konstrukcija | 1046.88 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.14 | 113378.73 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.15 | Construction of tunnel/Izgradnja tunela Zecka (LK 34+078.000-LK 34+768.000, RK 34+148.000- RK 34+815.000)
Completion of/Završetak:
12.15.1 | Portal construction/ Izgradnja portala | 431210.71 | 22-40 |  | 0 | 0 | 0
12.15.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade | 8842747.65 | 24-36 |  | 0 | 0 | 0
12.15.3 | Construction of waterproofing and drainage/ Konstrukcija hidroizolacije i drenaže | 1101822.32 | 26-37 |  | 0 | 0 | 0
12.15.4 | Construction of secondary lining/ Konstrukcija sekundarne obloge | 3886068.73 | 27-38 |  | 0 | 0 | 0
12.15.5 | Construction of pavement/ Izgradnja kolovoza
| Left | 22586.39 | 38-40 |  | 0 | 0 | 0
| Right | 29003.98 | 38-40 |  | 0 | 0 | 0
12.15.6 | Tunnel facilities/ Tunelski objekti
| Construction of Power Station/ Izgradnja elektro-stanice | 4084136.51 |  |  | 0 | 0 | 0
| Construction of antifire reservoir/ Izgradnja protivpožarnog rezervoara | 1364260.34 |  |  | 0 | 0 | 0
12.15.7 | Tunnel Equipment/ Tunelska oprema | 2605319.91 | 41 |  | 0 | 0 | 0
90% (Equipment installed/Oprema postavljena)
10% (Equipment tested/Oprema ispitana)
| Sub Total / Suma stavke 12.15 | 22367156.54 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.16 | Road Works/Radovi na putevima (LK34+768.000—LK34+810.500, RK34+815.000—RK34+841.500)
Completion of/Završetak:
12.16.1 | Subgrade/ Posteljica
12.16.1.1 | Top soil removal/ Uklanjanje humusa | 4652.49 | 19 |  | 0 | 0 | 0
12.16.1.2 | Earthworks/ Zemljani radovi | 32081.31 | 38 |  | 0 | 0 | 0
12.16.1.3 | Road Foundation/ Temelj puta | 22372.42 | 41 |  | 0 | 0 | 0
12.16.2 | Engineering structures/ Inženjerske konstrukcije
12.16.2.1 | Concrete wall/ Betonski zid | 73394.15 |  |  | 0 | 0 | 0
12.16.3 | Water drainage/ Drenaža vode
12.16.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 6500.08 | 27 |  | 0 | 0 | 0
12.16.4 | Pavement structure/ Kolovozna konstrukcija | 2860.04 | 41-43 |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.16 | 141860.49 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.17 | Construction of bridge/Izgradnja mosta Pajkov Vir (LK 34+810.500- LK 34+904.500, RK 34+841.500-RK 34+961.500)
Completion of/Završetak:
Left Bridge/ Lijevi most
12.17.1 | Foundation piles/ Temeljni šipovi | 468564.18 |  |  | 0 | 0 | 0
12.17.2 | Foundation concrete/ Temeljni beton | 284029.47 | 25-27 |  | 0 | 0 | 0
12.17.3 | Abutments and Piers elevation/ Elevacija mosnih stubova | 198500.04 | 25-30 |  | 0 | 0 | 0
12.17.4 | Spans/ Rasponi | 282090.66 | 27-32 |  | 0 | 0 | 0
12.17.5 | Bridge Furniture/ Mosna estetika | 27153.29 | 35-36 |  | 0 | 0 | 0
12.17.6 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 54066.27 | 36 |  | 0 | 0 | 0
Right Bridge/ Desni most
12.17.7 | Foundation piles/ Temeljni šipovi | 630422.46 |  |  | 0 | 0 | 0
12.17.8 | Foundation concrete/ Temeljni beton | 254018.16 | 25-27 |  | 0 | 0 | 0
12.17.9 | Abutments and Piers elevation/ Elevacija mosnih stubova | 348732.81 | 25-30 |  | 0 | 0 | 0
12.17.10 | Spans/ Rasponi | 407887.67 | 26-32 |  | 0 | 0 | 0
12.17.11 | Bridge Furniture/ Mosna estetika | 30050.16 | 35-36 |  | 0 | 0 | 0
12.17.12 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi | 67947.19 | 36 |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.17 | 3053462.36 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.18 | Road Works/ Radovi na putevima(LK34+904.500- LK 34+920.000, RK 34+961.500- RK 35+085.000)
Completion of/Završetak:
12.18.1 | Subgrade/ Posteljica
12.18.1.1 | Top soil removal/ Uklanjanje humusa | 21682.34 | 19 |  | 0 | 0 | 0
12.18.1.2 | Earthworks/ Zemljani radovi | 180659.16 | 38 |  | 0 | 0 | 0
12.18.1.3 | Road Foundation/ Temelj puta | 104263.93 | 41 |  | 0 | 0 | 0
12.18.2 | Engineering structures/ Inženjerske konstrukcije
12.18.2.1 | Concrete wall/ Betonski zid | 411007.26 |  |  | 0 | 0 | 0
12.18.3 | Water drainage/ Drenaža vode
12.18.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 30292.85 | 41 |  | 0 | 0 | 0
12.18.4 | Pavement structure/ Kolovozna konstrukcija | 13328.88 | 41-43 |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.18 | 761234.42 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.19 | Construction of tunnel/Izgradnja tunela Pajkov Vir (LK 34+920.000-LK 35+285.000, RK 35+085.000-RK 35+290.000)
Completion of/Završetak:
12.19.1 | Portal construction/ Izgradnja portala | 536094.74 | 31-42 |  | 0 | 0 | 0
12.19.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade | 4000256.8 | 34-39 |  | 0 | 0 | 0
12.19.3 | Construction of waterproofing and drainage/ Konstrukcija hidroizolacije i drenaže | 711292 | 36-40 |  | 0 | 0 | 0
12.19.4 | Construction of secondary lining/ Konstrukcija sekundarne obloge | 1951085.59 | 36-41 |  | 0 | 0 | 0
12.19.5 | Construction of pavement/ Izgradnja kolovoza
| Left | 88645.84 | 41-42 |  | 0 | 0 | 0
| Right | 49548.4 | 41-42 |  | 0 | 0 | 0
12.19.6 | Tunnel facilities/ Tunelski objekti
| Construction of Power Station/ Izgradnja elektro-stanice | 1715517.92 |  |  | 0 | 0 | 0
| Construction of antifire reservoir/ Izgradnja protivpožarnog rezervoara | 573049.66 |  |  | 0 | 0 | 0
12.19.7 | Tunnel Equipment/ Tunelska oprema | 1094349.55 | 42 |  | 0 | 0 | 0
| 90% (Equipment installed/Oprema postavljena) |  |  |  | 0 | 0 | 0
| 10% (Equipment tested/Oprema ispitana) |  |  |  | 0 | 0 | 0
12.19.8 | Engineering structures/ Inženjerske konstrukcije
12.19.8.1 | Culvert/ Propust |  |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.19 | 10719840.5 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 12.20 | Road Works/ Radovi na putevima (LK35+285.000—LK35+425.000, RK35+290.000—RK35+480.000
Completion of/Završetak:
12.20.1 | Subgrade/ Posteljica
12.20.1.1 | Top soil removal/ Uklanjanje humusa | 33357.45 | 19 |  | 0 | 0 | 0
12.20.1.2 | Earthworks/ Zemljani radovi | 661189.77 | 36 |  | 0 | 0 | 0
12.20.1.3 | Road Foundation/ Temelj puta | 160406.05 | 38 |  | 0 | 0 | 0
12.20.2 | Engineering structures/ Inženjerske konstrukcije
12.20.2.1 | Concrete wall/ Betonski zid | 220182.46 | 32 |  | 0 | 0 | 0
12.20.2.2 | Reinforced earth wall (it will be splitted after MD approval)/ Ojačani zemljani zid (podijeliće se nakon odobrenja GP) | 179474.13 |  |  | 0 | 0 | 0
12.20.3 | Water drainage/ Drenaža vode
12.20.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 46604.38 | 39 |  | 0 | 0 | 0
12.20.4 | Pavement structure/ Kolovozna konstrukcija | 20505.97 | 40-42 |  | 0 | 0 | 0
| Sub Total / Suma stavke 12.20 | 1321720.21 |  |  | 0 | 0 | 0
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 12 | 85277015.32 |  |  | 1124681.7032 | 2125520.3966 | 3250202.0997

## COST CENTER 13
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
COST CENTER 13/TROŠKOVNI CENTAR 13 rev Tunnel
Cost center No./ Troškovno mjesto Br. | 13 | Subsection/ Podsekcija 4.2 (LK35+425.00-LK36+894.00, RK35+480.00-RK36+924.439)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost center/ Troškovno mjesto 13.1 | Road Works/ Radovi na putevima (LK35+425.00-LK36+439.00,RK35+480.00-RK36+564.439.00)
Completion of/Završetak:
13.1.1 | Subgrade/ Posteljica
13.1.1.1 | Top soil removal/ Uklanjanje humusa
13.1.1.1.1 | 0 - 14.000 m (LK); 0 - 84.439 m (RK) | 380332.62 | 18 |  | 0 | 0 | 0
13.1.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and certain high (after MD approval)/Na svakih 250m i određenoj visini (nakon odobrenja GP) | 5398531.75 | 34 |  | 0 | 0 | 0
13.1.1.3 | Road Foundation/ Temelj puta
13.1.1.3.1 | 0 - 84.439 m right side/ desna strana | 352904.9257 | 35 |  | 0 | 0 | 0
13.1.1.3.2 | 0 - 14.000 m left side/ lijeva strana | 58511.6943 | 35 |  | 0 | 0 | 0
13.1.2 | Engineering structures/ Inženjerske konstrukcije
13.1.2.1 | Concrete wall / Betonski zid |  | 30
95% for the concrete wall, the milestone is 50m lenth, no matter the hight; 5% for the "after work" the whole lenth of each retaining wall / 95% za betonski zid, reper je 50 m dužine, bez obzira na visinu; 5% za "kasnije radove" čitava dužina potpornog zida
13.1.2.1.1 | Concrete wall/ Betonski zid RK35+510.0 - RK35+599.439 (89.44m),
13.1.2.1.1.1 | Layer 1, RK35+510.0 - RK35+560 - 95% (50m) | 19847.3088 |  |  | 0 | 0 | 0
13.1.2.1.1.2 | Layer 2, RK35+560.0 - RK35+599.439 - 95% (35.5) | 15655.1602 |  |  | 0 | 0 | 0
13.1.2.1.1.3 | Concrete wall/ Betonski zid RK35+510.0 - RK35+599.439 - After work 5% | 1868.551 |  |  | 0 | 0 | 0
13.1.3 | Water drainage/ Drenaža vode
13.1.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 976317.97 | 39 |  | 0 | 0 | 0
13.1.4 | Pavement structure/ Kolovozna konstrukcija
13.1.4.1 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana 0-500m | 238213.5882 | 39 |  | 0 | 0 | 0
13.1.4.2 | asphalt concrete layer/ sloj asfaltnog betona 1 left side/ lijeva strana 0-500m | 39495.8518 | 39 |  | 0 | 0 | 0
13.1.4.3 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana 500-1030m | 238213.5882 | 40 |  | 0 | 0 | 0
13.1.4.4 | asphalt concrete layer/ sloj asfaltnog betona 1 left side/ lijeva strana 500-1030m | 39495.8518 | 40 |  | 0 | 0 | 0
13.1.4.5 | asphalt concrete layer/ sloj asfaltnog betona 2 right side/ desna strana 0-500m | 264697.4925 | 41 |  | 0 | 0 | 0
13.1.4.6 | asphalt concrete layer/ sloj asfaltnog betona 2 left side/ lijeva strana 0-500m | 43886.8875 | 41 |  | 0 | 0 | 0
| Sub Total / Suma stavke 13.1 | 8067973.24 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 13.2 | Construction of tunnel/ Izgradnja tunela Jabucki Krs (LK 35+439.000- LK 36+894.00, RK 35+564.439- RK 36+924.439)
Completion of/ Završetak:
13.2.1 | Portal construction/ Izgradnja portala
13.2.1.1 | 20% complete/ završeno (portal 1) | 72868.88 | 18 | 19 | 72868.88 | 0 | 72868.88
13.2.1.2 | 40% complete/ završeno (portal 2) | 72868.88 | 19 | 19 | 72868.88 | 0 | 72868.88
13.2.1.3 | 60% complete/ završeno (portal 3) | 72868.88 | 20 |  | 0 | 0 | 0
13.2.1.4 | 80% complete/ završeno (portal 4) | 72868.88 | 20 |  | 0 | 0 | 0
13.2.1.5 | 85% (portal 1 complete/ završen) | 18217.22 | 38 |  | 0 | 0 | 0
13.2.1.6 | 90% (portal 2 complete/ završen) | 18217.22 | 38 |  | 0 | 0 | 0
13.2.1.7 | 95% (portal 3 complete/ završen) | 18217.22 | 38 |  | 0 | 0 | 0
13.2.1.8 | 100% (portal 4 complete/ završen) | 18217.22 | 38 |  | 0 | 0 | 0
13.2.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
13.2.2.1 | 40 m(S-L,LK 35+451.0 - LK 35+491.0) | 257069.82 | 19 | 21 | 257069.82 | 0 | 257069.82
13.2.2.2 | 80 m(N-L,LK 36+882.0 - LK 36+842.0) | 257069.82 | 19 | 21 | 257069.82 | 0 | 257069.82
13.2.2.3 | 120 m(S-L,LK 35+491.0 - LK 35+531.0) | 257069.82 | 19 | 21 | 257069.82 | 0 | 257069.82
13.2.2.4 | 160 m(N-R,RK 36+832.4 - RK 36+792.4) | 257069.82 | 19 | 22 | 257069.82 | 0 | 257069.82
13.2.2.5 | 200 m(N-R,RK 36+872.4 - RK 36+832.4) | 257069.82 | 20 | 22 | 257069.82 | 0 | 257069.82
13.2.2.6 | 240 m(N-L,LK 36+842.0 - LK 36+802.0) | 257069.82 | 20 | 22 | 257069.82 | 0 | 257069.82
13.2.2.7 | 280 m(S-L,LK 35+531.0 - LK 35+571.0) | 257069.82 | 20 | 21 | 257069.82 | 0 | 257069.82
13.2.2.8 | 320 m(N-L, LK 36+802.0 - LK 36+762.0) | 257069.82 | 20 | 22 | 257069.82 | 0 | 257069.82
13.2.2.9 | 360 m(N-L, LK 36+762.0 - LK 36+722.0) | 257069.82 | 21 | 22 | 257069.82 | 0 | 257069.82
13.2.2.10 | 400 m (N-R, RK 36+792.4 - RK 36+752.4) | 257069.82 | 21 | 24 | 257069.82 | 0 | 257069.82
13.2.2.11 | 440 m (S-L, LK35+571.0 - LK 35+611) | 257069.82 | 21 | 24 | 257069.82 | 0 | 257069.82
13.2.2.12 | 480 m (N-L, LK 36+772.0 - LK 36+862.0) | 257069.82 | 21 | 24 | 257069.82 | 0 | 257069.82
13.2.2.13 | 520 m (N-R, RK 36+752.4 - RK 36+712.4) | 257069.82 | 22 | 28 | 257069.82 | 0 | 257069.82
13.2.2.14 | 560 m(N-L,LK36+682.0—LK36+642.0) | 257069.82 | 22 | 24 | 257069.82 | 0 | 257069.82
13.2.2.15 | 600 m(N-R,RK36+712.4—RK36+672.4) | 257069.82 | 22 | 24 | 257069.82 | 0 | 257069.82
13.2.2.16 | 640 m(S-R,RK35+679.4—RK35+719.4) | 257069.82 | 22 | 24 | 257069.82 | 0 | 257069.82
13.2.2.17 | 680 m (N-R,RK36+912.4—RK36+872.4) | 257069.82 | 23 | 24 | 257069.82 | 0 | 257069.82
13.2.2.18 | 720 m (S-R,RK35+639.4—RK35+679.4) | 257069.82 | 23 | 24 | 257069.82 | 0 | 257069.82
13.2.2.19 | 760 m (N-R,RK36+672.4—RK36+632.4) | 257069.82 | 23 | 25 | 257069.82 | 0 | 257069.82
13.2.2.20 | 800 m (S-L,LK35+611.0—LK35+651.0) | 257069.82 | 23 | 24 | 257069.82 | 0 | 257069.82
13.2.2.21 | 840 m (S-R, RK35+599.4—RK35+639.4) | 257069.82 | 24 | 24 | 257069.82 | 0 | 257069.82
13.2.2.22 | 880 m (N-L,LK36+642.0—LK36+602.0) | 257069.82 | 24 | 24 | 257069.82 | 0 | 257069.82
13.2.2.23 | 920 m (S-L,LK 35+651.0—LK35+691.0) | 257069.82 | 24 | 25 | 257069.82 | 0 | 257069.82
13.2.2.24 | 960 m (S-R, RK35+759.4—RK35+799.4) | 257069.82 | 24 | 25 | 257069.82 | 0 | 257069.82
13.2.2.25 | 1000 m (S-R, RK35+719.4—RK35+659.4) | 257069.82 | 25 | 25 | 257069.82 | 0 | 257069.82
13.2.2.26 | 1040 m (S-L, LK35+691.0—LK35+731.0) | 257069.82 | 25 | 25 | 257069.82 | 0 | 257069.82
13.2.2.27 | 1080 m (N-R,RK36+632.4—RK36+592.4) | 257069.82 | 25 | 25 | 257069.82 | 0 | 257069.82
13.2.2.28 | 1120 m (N-L, LK36+602.0—RK36+562.0) | 257069.82 | 25 | 25 | 257069.82 | 0 | 257069.82
13.2.2.29 | 1160 m (S-L, LK35+731.0—LK35+771.0) | 257069.82 | 25 | 25 | 257069.82 | 0 | 257069.82
13.2.2.30 | 1200 m (S-R, RK35+799.4—RK35+839.4) | 257069.82 | 26 | 25 | 257069.82 | 0 | 257069.82
13.2.2.31 | 1240 m (S-R, RK35+839.4—RK35+879.4) | 257069.82 | 26 | 25 | 257069.82 | 0 | 257069.82
13.2.2.32 | 1280 m (N-L, LK36+562.0—RK36+522.0) | 257069.82 | 26 | 25 | 257069.82 | 0 | 257069.82
13.2.2.33 | 1320 m (S-L, LK35+771.0—LK35+811.0) | 257069.82 | 26 | 26 | 257069.82 | 0 | 257069.82
13.2.2.34 | 1360 m (S-L, LK35+811.0—LK35+851.0) | 257069.82 | 26 | 26 | 257069.82 | 0 | 257069.82
13.2.2.35 | 1400 m (N-L, LK36+522.0—RK36+482.0) | 257069.82 | 27 | 26 | 257069.82 | 0 | 257069.82
13.2.2.36 | 1440 m (S-R, RK35+879.4—RK35+919.4) | 257069.82 | 27 | 26 | 257069.82 | 0 | 257069.82
13.2.2.37 | 1480 m (N-R,RK36+592.4—RK36+552.4) | 257069.82 | 27 | 26 | 257069.82 | 0 | 257069.82
13.2.2.38 | 1520 m (S-R, RK35+919.4—RK35+959.4) | 257069.82 | 27 | 26 | 257069.82 | 0 | 257069.82
13.2.2.39.1 | 1540 m | 131956.5586 | 27 |  | 0 | 0 | 0
13.2.2.39.2 | 1560 m | 131956.5586 | 27 |  | 0 | 0 | 0
13.2.2.40 | 1600 m (S-L, LK35+851.0—LK35+891.0) | 257069.82 | 28 | 27 | 257069.82 | 0 | 257069.82
13.2.2.41 | 1640 m (N-R,RK36+552.4—RK36+512.4) | 257069.82 | 28 | 27 | 257069.82 | 0 | 257069.82
13.2.2.42.1 | 1660 m | 131956.5586 | 28 |  | 0 | 0 | 0
13.2.2.42.2 | 1680 m | 131956.5586 | 28 |  | 0 | 0 | 0
13.2.2.43 | 1720 m (S-R, RK35+959.4—RK35+999.4) | 257069.82 | 28 | 27 | 257069.82 | 0 | 257069.82
13.2.2.44.1 | 1740m | 131956.5586 | 28 |  | 0 | 0 | 0
13.2.2.44.2 | 1760m | 131956.5586 | 28 |  | 0 | 0 | 0
13.2.2.45 | 1800 m (S-L, LK35+891.0—LK35+931.0) | 257069.82 | 29 | 28 | 257069.82 | 0 | 257069.82
13.2.2.46.1 | 1820m | 131956.5586 | 29 | 29 | 0 | 0 | 0
13.2.2.46.2 | 1840m | 131956.5586 | 29 | 29 | 0 | 0 | 0
13.2.2.47 | 1880 m (S-R, RK35+959.4—RK36+039.4) | 257069.82 | 29 | 28 | 257069.82 | 0 | 257069.82
13.2.2.48 | 1920 m (S-L, LK35+931.0—LK35+971.0) | 257069.82 | 29 | 28 | 257069.82 | 0 | 257069.82
13.2.2.49 | 1960 m (N-L, LK36+362.0—RK36+322.0) | 257069.82 | 29 | 28 | 257069.82 | 0 | 257069.82
13.2.2.50 | 2000 m (S-R, RK36+039.4—RK36+079.4) | 257069.82 | 30 | 28 | 257069.82 | 0 | 257069.82
13.2.2.51.1 | 2020m | 131956.5586 | 30 | 29 | 0 | 0 | 0
13.2.2.51.2 | 2040m | 131956.5586 | 30 | 29 | 0 | 0 | 0
13.2.2.52 | 2080 m (S-L, LK35+971.0—LK36+011.0) | 257069.82 | 30 | 28 | 257069.82 | 0 | 257069.82
13.2.2.53 | 2100 m (S-L, LK36+011.0 - LK36+031.0) | 131956.5586 | 30 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.54 | 2120 m (S-L, LK36+031.0 - LK36+051.0) | 131956.5586 | 30 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.55 | 2140 m (S-L, LK36+051.0 - LK36+071.0) | 131956.5586 | 30 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.56 | 2160 m (S-L, LK36+071.0 - LK36+091.0) | 131956.5586 | 30 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.57 | 2180 m (S-L, LK36+091.0 - LK36+111.0) | 131956.5586 | 30 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.58 | 2200 m (S-L, LK36+111.0 - LK36+131.0) | 131956.5586 | 31 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.59 | 2220 m (S-R, RK36+079.4 - RK36+099.4) | 131956.5586 | 31 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.60 | 2240m (S-R, RK36+099.4 - RK36+119.4) | 131956.5586 | 31 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.61 | 2260 m (S-R, RK36+119.4 - RK36+139.4) | 131956.5586 | 31 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.62 | 2280 m (S-R, RK36+139.4 - RK36+159.4) | 131956.5586 | 31 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.63 | 2300 m (S-R, RK36+159.4 - RK36+179.4) | 131956.5586 | 31 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.64 | 2320 m (S-R, RK36+179.4 - RK36+199.4) | 131956.5586 | 31 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.65 | 2340 m (N-L, LK36+322.0 - LK36+302.0) | 131956.5586 | 31 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.66 | 2360 m (N-L, LK36+302.0 - LK36+282.0) | 131956.5586 | 31 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.67 | 2380 m (N-L, LK36+282.0 - LK36+262.0) | 131956.5586 | 32 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.68 | 2400 m (N-L, LK36+262.0 - LK36+242.0) | 131956.5586 | 32 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.69 | 2420 m (N-L, LK36+242.0 - LK36+222.0) | 131956.5586 | 32 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.70 | 2440 m (N-L, LK36+222.0 - LK36+202.0) | 131956.5586 | 32 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.71 | 2460 m (N-L, LK36+202.0 - LK36+182.0) | 131956.5586 | 32 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.72 | 2480 m (N-L, LK36+182.0 - LK36+162.0) | 131956.5586 | 32 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.73 | 2500 m (N-R, RK36+432.4 - RK36+412.4) | 131956.5586 | 32 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.74 | 2520 m (N-R, RK36+412.4 - RK36+392.4) | 131956.5586 | 32 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.75 | 2540 m (N-R, RK36+392.4 - RK36+372.4) | 131956.5586 | 32 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.76 | 2560 m (N-R, RK36+372.4 - RK36+352.4) | 131956.5586 | 32 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.77 | 2580 m (N-R, RK36+352.4 - RK36+332.4) | 131956.5586 | 33 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.78 | 2600 m (N-R, RK36+332.4 - RK36+312.4) | 131956.5586 | 33 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.79 | 2620 m (N-R, RK36+312.4 - RK36+292.4) | 131956.5586 | 33 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.80 | 2640 m (N-R, RK36+292.4 - RK36+272.4) | 131956.5586 | 33 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.81 | 2660 m (N-R, RK36+272.4 - RK36+252.4) | 131956.5586 | 33 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.82 | 2680 m (N-R, RK36+252.4 - RK36+232.4) | 131956.5586 | 33 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.83 | 2700 m (N-R, RK36+232.4 - RK36+212.4) | 131956.5586 | 33 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.84 | 2720 m (S-L, LK35+131.0 - LK35+151.0) | 131956.5586 | 33 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.85 | 2740 m (S-L, LK35+151.0 - LK35+162.0) | 131956.5586 | 33 | 29 | 131956.5586 | 0 | 131956.5586
13.2.2.86 | 2744 m (N-R, RK36+212.4 - RK36+199.4) | 26391.3117 | 33 | 29 | 26391.3117 | 0 | 26391.3117
13.2.3 | Construction of waterproofing and drainage & Construction of secondary lining / Konstrukcija hidroizolacije i drenaže & Konstrukcija sekundarne obloge
13.2.3.1 | 20 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.2 | 40 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.3 | 60 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.4 | 80 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.5 | 100 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.6 | 120 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.7 | 140 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.8 | 160 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.9 | 180 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.10 | 200 m | 61954.4944 | 22 |  | 0 | 0 | 0
13.2.3.11 | 220 m | 61954.4944 | 22 |  | 0 | 0 | 0
13.2.3.12 | 240 m | 61954.4944 | 22 |  | 0 | 0 | 0
13.2.3.13 | 260 m | 61954.4944 | 22 |  | 0 | 0 | 0
13.2.3.14 | 280 m | 61954.4944 | 22 |  | 0 | 0 | 0
13.2.3.15 | 300 m | 61954.4944 | 22 |  | 0 | 0 | 0
13.2.3.16 | 320 m | 61954.4944 | 22 |  | 0 | 0 | 0
13.2.3.17 | 340 m | 61954.4944 | 22 |  | 0 | 0 | 0
13.2.3.18 | 360 m | 61954.4944 | 20 |  | 0 | 0 | 0
13.2.3.19 | 380 m | 61954.4944 | 20 |  | 0 | 0 | 0
13.2.3.20 | 400 m | 61954.4944 | 20 |  | 0 | 0 | 0
13.2.3.21 | 420 m | 61954.4944 | 20 |  | 0 | 0 | 0
13.2.3.22 | 440 m | 61954.4944 | 20 |  | 0 | 0 | 0
13.2.3.23 | 460 m | 61954.4944 | 20 |  | 0 | 0 | 0
13.2.3.24 | 480 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.25 | 500 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.26 | 520 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.27 | 540 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.28 | 560 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.29 | 580 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.30 | 600 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.31 | 620 m | 61954.4944 | 21 |  | 0 | 0 | 0
13.2.3.32 | 640 m | 61954.4944 | 23 |  | 0 | 0 | 0
13.2.3.33 | 660 m | 61954.4944 | 23 |  | 0 | 0 | 0
13.2.3.34 | 680 m | 61954.4944 | 23 |  | 0 | 0 | 0
13.2.3.35 | 700 m | 61954.4944 | 23 |  | 0 | 0 | 0
13.2.3.36 | 720 m | 61954.4944 | 23 |  | 0 | 0 | 0
13.2.3.37 | 740 m | 61954.4944 | 23 |  | 0 | 0 | 0
13.2.3.38 | 760 m | 61954.4944 | 23 |  | 0 | 0 | 0
13.2.3.39 | 780 m | 61954.4944 | 23 |  | 0 | 0 | 0
13.2.3.40 | 800 m | 61954.4944 | 24 |  | 0 | 0 | 0
13.2.3.41 | 820 m | 61954.4944 | 24 |  | 0 | 0 | 0
13.2.3.42 | 840 m | 61954.4944 | 24 |  | 0 | 0 | 0
13.2.3.43 | 860 m | 61954.4944 | 24 |  | 0 | 0 | 0
13.2.3.44 | 880 m | 61954.4944 | 24 |  | 0 | 0 | 0
13.2.3.45 | 900 m | 61954.4944 | 24 |  | 0 | 0 | 0
13.2.3.46 | 920 m | 61954.4944 | 24 |  | 0 | 0 | 0
13.2.3.47 | 940 m | 61954.4944 | 24 |  | 0 | 0 | 0
13.2.3.48 | 960 m | 61954.4944 | 25 |  | 0 | 0 | 0
13.2.3.49 | 980 m | 61954.4944 | 25 |  | 0 | 0 | 0
13.2.3.50 | 1000 m | 61954.4944 | 25 |  | 0 | 0 | 0
13.2.3.51 | 1020 m | 61954.4944 | 25 |  | 0 | 0 | 0
13.2.3.52 | 1040 m | 61954.4944 | 25 |  | 0 | 0 | 0
13.2.3.53 | 1060 m | 61954.4944 | 25 |  | 0 | 0 | 0
13.2.3.54 | 1080 m | 61954.4944 | 25 |  | 0 | 0 | 0
13.2.3.55 | 1100 m | 61954.4944 | 25 |  | 0 | 0 | 0
13.2.3.56 | 1120 m | 61954.4944 | 26 |  | 0 | 0 | 0
13.2.3.57 | 1140 m | 61954.4944 | 26 |  | 0 | 0 | 0
13.2.3.58 | 1160 m | 61954.4944 | 26 |  | 0 | 0 | 0
13.2.3.59 | 1180 m | 61954.4944 | 26 |  | 0 | 0 | 0
13.2.3.60 | 1200 m | 61954.4944 | 26 |  | 0 | 0 | 0
13.2.3.61 | 1220 m | 61954.4944 | 26 |  | 0 | 0 | 0
13.2.3.62 | 1240 m | 61954.4944 | 26 |  | 0 | 0 | 0
13.2.3.63 | 1260 m | 61954.4944 | 26 |  | 0 | 0 | 0
13.2.3.64 | 1280 m | 61954.4944 | 27 |  | 0 | 0 | 0
13.2.3.65 | 1300 m | 61954.4944 | 27 |  | 0 | 0 | 0
13.2.3.66 | 1320 m | 61954.4944 | 27 |  | 0 | 0 | 0
13.2.3.67 | 1340 m | 61954.4944 | 27 |  | 0 | 0 | 0
13.2.3.68 | 1360 m | 61954.4944 | 27 |  | 0 | 0 | 0
13.2.3.69 | 1380 m | 61954.4944 | 27 |  | 0 | 0 | 0
13.2.3.70 | 1400 m | 61954.4944 | 27 |  | 0 | 0 | 0
13.2.3.71 | 1420 m | 61954.4944 | 27 |  | 0 | 0 | 0
13.2.3.72 | 1440 m | 61954.4944 | 28 |  | 0 | 0 | 0
13.2.3.73 | 1460 m | 61954.4944 | 28 |  | 0 | 0 | 0
13.2.3.74 | 1480 m | 61954.4944 | 28 |  | 0 | 0 | 0
13.2.3.75 | 1500 m | 61954.4944 | 28 |  | 0 | 0 | 0
13.2.3.76 | 1520 m | 61954.4944 | 28 |  | 0 | 0 | 0
13.2.3.77 | 1540 m | 61954.4944 | 28 |  | 0 | 0 | 0
13.2.3.78 | 1560 m | 61954.4944 | 28 |  | 0 | 0 | 0
13.2.3.79 | 1580 m | 61954.4944 | 28 |  | 0 | 0 | 0
13.2.3.80 | 1600 m | 61954.4944 | 29 |  | 0 | 0 | 0
13.2.3.81 | 1620 m | 61954.4944 | 29 |  | 0 | 0 | 0
13.2.3.82 | 1640 m | 61954.4944 | 29 |  | 0 | 0 | 0
13.2.3.83 | 1660 m | 61954.4944 | 29 |  | 0 | 0 | 0
13.2.3.84 | 1680 m | 61954.4944 | 29 |  | 0 | 0 | 0
13.2.3.85 | 1700 m | 61954.4944 | 29 |  | 0 | 0 | 0
13.2.3.86 | 1720 m | 61954.4944 | 29 |  | 0 | 0 | 0
13.2.3.87 | 1740 m | 61954.4944 | 29 |  | 0 | 0 | 0
13.2.3.88 | 1760 m | 61954.4944 | 30 |  | 0 | 0 | 0
13.2.3.89 | 1780 m | 61954.4944 | 30 |  | 0 | 0 | 0
13.2.3.90 | 1800 m | 61954.4944 | 30 |  | 0 | 0 | 0
13.2.3.91 | 1820 m | 61954.4944 | 30 |  | 0 | 0 | 0
13.2.3.92 | 1840 m | 61954.4944 | 30 |  | 0 | 0 | 0
13.2.3.93 | 1860 m | 61954.4944 | 30 |  | 0 | 0 | 0
13.2.3.94 | 1880 m | 61954.4944 | 30 |  | 0 | 0 | 0
13.2.3.95 | 1900 m | 61954.4944 | 30 |  | 0 | 0 | 0
13.2.3.96 | 1920 m | 61954.4944 | 31 |  | 0 | 0 | 0
13.2.3.97 | 1940 m | 61954.4944 | 31 |  | 0 | 0 | 0
13.2.3.98 | 1960 m | 61954.4944 | 31 |  | 0 | 0 | 0
13.2.3.99 | 1980 m | 61954.4944 | 31 |  | 0 | 0 | 0
13.2.3.100 | 2000 m | 61954.4944 | 31 |  | 0 | 0 | 0
13.2.3.101 | 2020 m | 61954.4944 | 31 |  | 0 | 0 | 0
13.2.3.102 | 2040 m | 61954.4944 | 31 |  | 0 | 0 | 0
13.2.3.103 | 2060 m | 61954.4944 | 31 |  | 0 | 0 | 0
13.2.3.104 | 2080 m | 61954.4944 | 32 |  | 0 | 0 | 0
13.2.3.105 | 2100 m | 61954.4944 | 32 |  | 0 | 0 | 0
13.2.3.106 | 2120 m | 61954.4944 | 32 |  | 0 | 0 | 0
13.2.3.107 | 2140 m | 61954.4944 | 32 |  | 0 | 0 | 0
13.2.3.108 | 2160 m | 61954.4944 | 32 |  | 0 | 0 | 0
13.2.3.109 | 2180 m | 61954.4944 | 32 |  | 0 | 0 | 0
13.2.3.110 | 2200 m | 61954.4944 | 32 |  | 0 | 0 | 0
13.2.3.111 | 2220 m | 61954.4944 | 32 |  | 0 | 0 | 0
13.2.3.112 | 2240m | 61954.4944 | 33 |  | 0 | 0 | 0
13.2.3.113 | 2260 m | 61954.4944 | 33 |  | 0 | 0 | 0
13.2.3.114 | 2280 m | 61954.4944 | 33 |  | 0 | 0 | 0
13.2.3.115 | 2300 m | 61954.4944 | 33 |  | 0 | 0 | 0
13.2.3.116 | 2320 m | 61954.4944 | 33 |  | 0 | 0 | 0
13.2.3.117 | 2340 m | 61954.4944 | 33 |  | 0 | 0 | 0
13.2.3.118 | 2360 m | 61954.4944 | 33 |  | 0 | 0 | 0
13.2.3.119 | 2380 m | 61954.4944 | 33 |  | 0 | 0 | 0
13.2.3.120 | 2400 m | 61954.4944 | 34 |  | 0 | 0 | 0
13.2.3.121 | 2420 m | 61954.4944 | 34 |  | 0 | 0 | 0
13.2.3.122 | 2440 m | 61954.4944 | 34 |  | 0 | 0 | 0
13.2.3.123 | 2460 m | 61954.4944 | 34 |  | 0 | 0 | 0
13.2.3.124 | 2480 m | 61954.4944 | 34 |  | 0 | 0 | 0
13.2.3.125 | 2500 m | 61954.4944 | 34 |  | 0 | 0 | 0
13.2.3.126 | 2520 m | 61954.4944 | 34 |  | 0 | 0 | 0
13.2.3.127 | 2540 m | 61954.4944 | 34 |  | 0 | 0 | 0
13.2.3.128 | 2560 m | 61954.4944 | 34 |  | 0 | 0 | 0
13.2.3.129 | 2580 m | 61954.4944 | 34 |  | 0 | 0 | 0
13.2.3.130 | 2600 m | 61954.4944 | 35 |  | 0 | 0 | 0
13.2.3.131 | 2620 m | 61954.4944 | 35 |  | 0 | 0 | 0
13.2.3.132 | 2640 m | 61954.4944 | 35 |  | 0 | 0 | 0
13.2.3.133 | 2660 m | 61954.4944 | 35 |  | 0 | 0 | 0
13.2.3.134 | 2680 m | 61954.4944 | 35 |  | 0 | 0 | 0
13.2.3.135 | 2700 m | 61954.4944 | 35 |  | 0 | 0 | 0
13.2.3.136 | 2720 m | 61954.4944 | 35 |  | 0 | 0 | 0
13.2.3.137 | 2740 m | 61954.4944 | 35 |  | 0 | 0 | 0
13.2.3.138 | 2744 m | 12390.8989 | 35 |  | 0 | 0 | 0
13.2.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi I ploca, drenazni sistem)
13.2.4.1 | 200 m | 80000 | 23 |  | 0 | 0 | 0
13.2.4.2 | 400 m | 80000 | 22 |  | 0 | 0 | 0
13.2.4.3 | 600 m | 80000 | 24 |  | 0 | 0 | 0
13.2.4.4 | 800 m | 80000 | 25 |  | 0 | 0 | 0
13.2.4.5 | 1000 m | 80000 | 26 |  | 0 | 0 | 0
13.2.4.6 | 1200 m | 80000 | 27 |  | 0 | 0 | 0
13.2.4.7 | 1400 m | 80000 | 28 |  | 0 | 0 | 0
13.2.4.8 | 1600 m | 80000 | 30 |  | 0 | 0 | 0
13.2.4.9 | 1800 m | 80000 | 31 |  | 0 | 0 | 0
13.2.4.10 | 2000 m | 80000 | 32 |  | 0 | 0 | 0
13.2.4.11 | 2200 m | 80000 | 33 |  | 0 | 0 | 0
13.2.4.12 | 2400 m | 80000 | 35 |  | 0 | 0 | 0
13.2.4.13 | 2600 m | 80000 | 36 |  | 0 | 0 | 0
13.2.4.14 | 2744 m | 57600 | 21 |  | 0 | 0 | 0
13.2.5 | Construction of pavement/ Izgradnja kolovoza
13.2.5.1 | Left tube/ Lijeva cijev
0-500 m
13.2.5.1.1 | Layer/ Sloj 1 | 38768.3 | 37 |  | 0 | 0 | 0
13.2.5.1.2 | Layer/ Sloj 2 | 38768.3 | 38 |  | 0 | 0 | 0
13.2.5.1.3 | Layer/ Sloj 3 | 43614.33 | 38 |  | 0 | 0 | 0
500-1000 m
13.2.5.1.4 | Layer/ Sloj 1 | 38768.3 | 37 |  | 0 | 0 | 0
13.2.5.1.5 | Layer/ Sloj 2 | 38768.3 | 38 |  | 0 | 0 | 0
13.2.5.1.6 | Layer/ Sloj 3 | 43614.33 | 38 |  | 0 | 0 | 0
1000-1459 m
13.2.5.1.7 | Layer/ Sloj 1 | 35589.3 | 37 |  | 0 | 0 | 0
13.2.5.1.8 | Layer/ Sloj 2 | 35589.3 | 38 |  | 0 | 0 | 0
13.2.5.1.9 | Layer/ Sloj 3 | 40037.94 | 38 |  | 0 | 0 | 0
13.2.5.2 | Right tube/ Desna cijev
0-500 m
13.2.5.2.1 | Layer/ Sloj 1 | 38768.3 | 37 |  | 0 | 0 | 0
13.2.5.2.2 | Layer/ Sloj 2 | 38768.3 | 38 |  | 0 | 0 | 0
13.2.5.2.3 | Layer/ Sloj 3 | 43614.33 | 38 |  | 0 | 0 | 0
500-1000 m
13.2.5.2.4 | Layer/ Sloj 1 | 38768.3 | 37 |  | 0 | 0 | 0
13.2.5.2.5 | Layer/ Sloj 2 | 38768.3 | 38 |  | 0 | 0 | 0
13.2.5.2.6 | Layer/ Sloj 3 | 43614.33 | 38 |  | 0 | 0 | 0
1000-1356 m
13.2.5.2.7 | Layer/ Sloj 1 | 27603.03 | 37 |  | 0 | 0 | 0
13.2.5.2.8 | Layer/ Sloj 2 | 27603.03 | 38 |  | 0 | 0 | 0
13.2.5.2.9 | Layer/ Sloj 3 | 31053.39 | 38 |  | 0 | 0 | 0
13.2.6 | Tunnel Equipment/ Tunelska oprema
13.2.6.1 | Right tube/ Desna cijev
13.2.6.1.1 | 90% (Equipment installed/Oprema postavljena) | 1357200.92 | 39 |  | 0 | 0 | 0
13.2.6.1.2 | 10% (Equipment tested/Oprema ispitana) | 150800.1 | 39 |  | 0 | 0 | 0
13.2.6.2 | Left tube/ Lijeva cijev
13.2.6.2.1 | 90% (Equipment installed/Oprema postavljena) | 1457539.7 | 39 |  | 0 | 0 | 0
13.2.6.2.2 | 10% (Equipment tested/Oprema ispitana) | 161946.63 | 39 |  | 0 | 0 | 0
| Sub Total / Suma stavke 13.2 | 31554472.96 |  |  | 16608977.0444 | 0 | 16608977.0444
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 13 | 39622446.2 |  |  | 16608977.0444 | 0 | 16608977.0444

## COST CENTER 14
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
COST CENTER 14//TROŠKOVNI CENTAR 14 rev Bridge Piers and Open Route
Cost center No./ Troškovno mjesto Br. | 14 | Subsection/Podsekcija 4.3 (LK36+894.000-LK37+733.287, RK36+924.439 - RK38+366.284)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost center/ Troškovno mjesto 14.1 | Road Works/Radovi na putevima LK36+894.000—LK36+989.000 RK36+924.439—RK36+949.884
Completion of/Završetak:
14.1.1 | Subgrade/ Posteljica
14.1.1.1 | Top soil removal/ Uklanjanje humusa
14.1.1.1.1 | RK36+924.439—RK36+949.884 (Inc.0 - 95.000 m (LK); 0 - 25.445 m (RK)) | 26543.09 | 18 |  | 0 | 0 | 0
14.1.1.2 | Earthworks/ Zemljani radovi |  | 37
At every 250 m 4m height/Na svakih 250m i određenoj 4m visini
14.1.1.2 | Embankment RK36+924.439 - RK37+017.884 Layers 1,2,3,4,5,6,7,8
14.1.1.2.1 | RK36+924.439 - RK37+017.884 Layer 1 | 49849.1626 |  |  | 0 | 0 | 0
14.1.1.2.2 | RK36+924.439 - RK37+017.884 Layer 2 | 49849.1626 |  |  | 0 | 0 | 0
14.1.1.2.3 | RK36+924.439 - RK37+017.884 Layer 3 | 49849.1626 |  |  | 0 | 0 | 0
14.1.1.2.4 | RK36+924.439 - RK37+017.884 Layer 4 | 49849.1626 |  |  | 0 | 0 | 0
14.1.1.2.5 | RK36+924.439 - RK37+017.884 Layer 5 | 49849.1626 |  |  | 0 | 0 | 0
14.1.1.2.6 | RK36+924.439 - RK37+017.884 Layer 6 | 49849.1626 |  |  | 0 | 0 | 0
14.1.1.2.7 | RK36+924.439 - RK37+017.884 Layer 7 | 49849.1626 |  |  | 0 | 0 | 0
14.1.1.2.8 | RK36+924.439 - RK37+017.884 Layer 8 | 15951.732 |  |  | 0 | 0 | 0
14.1.1.3 | Road Foundation/ Temelj puta
14.1.1.3.1 | 0 - 25.445 m, right side/ desna strana | 14356.21 | 40 |  | 0 | 0 | 0
14.1.1.3.2 | 0 - 95.000 m, left side/ lijeva strana | 14356.2 | 41 |  | 0 | 0 | 0
14.1.2 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
14.1.2.1 | LK36+894.000—LK36+989.000 (95 m) | 53742.0154 | 41 |  | 0 | 0 | 0
14.1.2.2 | RK36+924.439—RK36+949.884 (25.445 m) | 14394.3746 | 41 |  | 0 | 0 | 0
14.1.3 | Pavement structure/ Kolovozna konstrukcija
14.1.3.1 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana | 4094.4173 | 41 |  | 0 | 0 | 0
14.1.3.2 | asphalt concrete layer/ sloj asfaltnog betona 1 left side/ lijeva strana | 15286.6827 | 41 |  | 0 | 0 | 0
14.1.3.3 | asphalt concrete layer/ sloj asfaltnog betona 2 right side/ desna strana | 4094.4173 | 42 |  | 0 | 0 | 0
14.1.3.4 | asphalt concrete layer/ sloj asfaltnog betona 2 left side/ lijeva strana | 15286.6827 | 42 |  | 0 | 0 | 0
14.1.3.5 | asphalt concrete layer/ sloj asfaltnog betona 3 right side/ desna strana | 4549.6239 | 43 |  | 0 | 0 | 0
14.1.3.6 | asphalt concrete layer/ sloj asfaltnog betona 3 left side/ lijeva strana | 16986.2161 | 43 |  | 0 | 0 | 0
14.1.4 | Underpass/Podvožnjak km 36+930,55
14.1.4.1 | Foundation (excavation and concreting)/ Temelj (iskopavanje i betoniranje) | 161098.96 | 20 |  | 0 | 0 | 0
14.1.4.2 | Box culvert/Kutijasti propust (100% complete/ završeno) | 165980.75 | 21 |  | 0 | 0 | 0
14.1.4.3 | Remaining works/ Preostali radovi | 161098.97 | 22 |  | 0 | 0 | 0
14.1.5 | Engineering structures/ Inženjerske konstrukcije
14.1.5.1 | Concrete wall / Betonski zid
95% for the concrete wall, the milestone is 50m lenth, no matter the hight; 5% for the "after work" the whole lenth of each retaining wall / 95% za betonski zid, reper je 50 m dužine, bez obzira na visinu; 5% za "kasnije radove" čitava dužina potpornog zida
14.1.5.1.1 | Concrete wall/ Betonski zid RK36+931.98 - RK36+941.98 (10m)
14.1.5.1.1.1 | Concrete wall/ Betonski zid RK36+931.98 - RK36+941.98 - 95% | 11269.85 |  |  | 0 | 0 | 0
14.1.5.1.1.2 | Concrete wall/ Betonski zid RK36+931.98 - RK36+941.98- After work 5% | 593.15 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 14.1 | 1048627.48 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 14.2 | Construction of bridge/Izgradnja mosta Preslo (RK 36+949.884- RK 37+017.884)
Completion of/Završetak:
Right bridge/ Desni most
14.2.1 | Foundation concrete/ Temeljni beton
14.2.1.1 | A1 | 111521.31 | 18 |  | 0 | 0 | 0
14.2.1.2 | P1 | 94681.77 | 18 |  | 0 | 0 | 0
14.2.1.3 | P2 | 94681.77 | 18 | 28 | 94681.77 | 0 | 94681.77
14.2.1.4 | A2 | 111521.31 | 18 |  | 0 | 0 | 0
14.2.2 | Abutments and Piers elevation/ Elevacija mosnih stubova
14.2.2.1 | A1 | 135403.09 | 26 |  | 0 | 0 | 0
14.2.2.2 | P1 stage 1 (1.7m) | 3958.0666 | 27 |  | 0 | 0 | 0
14.2.2.3 | P1 stage 2 (2m) | 4656.5489 | 27 |  | 0 | 0 | 0
14.2.2.4 | P1 stage 3 (1m) | 4656.5489 | 27 |  | 0 | 0 | 0
14.2.2.5 | P1 stage 4 (2m) | 4656.5489 | 27 |  | 0 | 0 | 0
14.2.2.6 | P1 stage 5 (2m) | 4656.5489 | 28 |  | 0 | 0 | 0
14.2.2.7 | P1 stage 6 (2m) | 0 | 28 |  | 0 | 0 | 0
14.2.2.8 | P1 stage 7 (2m) | 4656.5489 | 28 |  | 0 | 0 | 0
14.2.2.9 | P1 stage 8 (2m) | 4656.5489 | 28 |  | 0 | 0 | 0
14.2.2.10 | P1 stage 9 (1.43m) | 3329.4325 | 28 |  | 0 | 0 | 0
14.2.2.11 | P2 stage 1 (2.7m) | 6286.3411 | 28 | 30 | 0 | 6286.3411 | 6286.3411
14.2.2.12 | P2 stage 2 (2m) | 4656.5489 | 28 | 30 | 0 | 4656.5489 | 4656.5489
14.2.2.13 | P2 stage 3 (2m) | 4656.5489 | 28 | 30 | 0 | 4656.5489 | 4656.5489
14.2.2.14 | P2 stage 4 (2m) | 4656.5489 | 28 | 30 | 0 | 4656.5489 | 4656.5489
14.2.2.15 | P2 stage 5 (2m) | 4656.5489 | 29 | 30 | 0 | 4656.5489 | 4656.5489
14.2.2.16 | P2 stage 6 (2m) | 4656.5489 | 29 | 30 | 0 | 4656.5489 | 4656.5489
14.2.2.17 | P2 stage 7 (2m) | 4656.5489 | 29 | 30 | 0 | 4656.5489 | 4656.5489
14.2.2.18 | P2 stage 8 (1.43m) | 3329.4325 | 29 |  | 0 | 0 | 0
14.2.2.19 | A2 | 135403.09 | 30 |  | 0 | 0 | 0
14.2.3 | Spans/ Rasponi
14.2.3.1 | A1-P1
14.2.3.2 | Bridge superstructure/ Gornji stroj mosta | 112912.31 | 27 |  | 0 | 0 | 0
14.2.3.3 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 12545.81 | 28 |  | 0 | 0 | 0
14.2.3.4 | P1-P2
14.2.3.5 | Bridge superstructure/ Gornji stroj mosta | 139796.19 | 29 |  | 0 | 0 | 0
14.2.3.6 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15532.91 | 30 |  | 0 | 0 | 0
14.2.3.7 | P2-A2
14.2.3.8 | Bridge superstructure/ Gornji stroj mosta | 112912.31 | 31 |  | 0 | 0 | 0
14.2.3.9 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 12545.82 | 32 |  | 0 | 0 | 0
14.2.4 | Bridge furniture/ Mosna estetika
14.2.4.1 | 62 m | 126877.85 | 24 |  | 0 | 0 | 0
14.2.5 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
14.2.5.1 | Asphalt/Asfalt 1 + waterproofing/ hidroizolacija | 25516.29 | 23 |  | 0 | 0 | 0
14.2.5.2 | Asphalt/Asfalt 2 + joints/ spojnice | 8342.87 | 24 |  | 0 | 0 | 0
| Sub Total / Suma stavke 14.2 | 1322976.56 |  |  | 94681.77 | 34225.6347 | 128907.4047
Cost center/ Troškovno mjesto 14.3 | Road Works/ Radovi na putevima (RK37+017.884—RK37+033.000)
Completion of/Završetak:
14.3.1 | Subgrade/ Posteljica
14.3.1.1 | Top soil removal/ Uklanjanje humusa
14.3.1.1.1 | RK37+017.884—RK37+033.000 (Inc.0 - 15.116 m (RK)) | 2838.36 |  |  | 0 | 0 | 0
14.3.1.2 | Earthworks/ Zemljani radovi
At every 250 m 4m height/Na svakih 250m i određenoj 4m visini
14.3.1.2 | Embankment RK37+017.884—RK37+033.000 Layers 1,2,3,4,5,6,7
14.3.1.2.1 | RK37+017.884—RK37+033.000 Layer 1 | 6339.6271 |  |  | 0 | 0 | 0
14.3.1.2.2 | RK37+017.884—RK37+033.000 Layer 2 | 6339.6271 |  |  | 0 | 0 | 0
14.3.1.2.3 | RK37+017.884—RK37+033.000 Layer 3 | 6339.6271 |  |  | 0 | 0 | 0
14.3.1.2.4 | RK37+017.884—RK37+033.000 Layer 4 | 6339.6271 |  |  | 0 | 0 | 0
14.3.1.2.5 | RK37+017.884—RK37+033.000 Layer 5 | 6339.6271 |  |  | 0 | 0 | 0
14.3.1.2.6 | RK37+017.884—RK37+033.000 Layer 6 | 6339.6271 |  |  | 0 | 0 | 0
14.3.1.2.7 | RK37+017.884—RK37+033.000 Layer 7 | 2250.5676 |  |  | 0 | 0 | 0
14.3.1.3 | Road Foundation/ Temelj puta
14.3.1.3.1 | 0 - 15.116 m, right side/ desna strana | 3070.33 |  |  | 0 | 0 | 0
14.3.2 | Water drainage/ Drenaža vode
per one direction of 500m /Na 500m dužine u jednom pravcu
14.3.2.1 | RK37+017.884—RK37+033.000 (15.116 m) | 7286.1 |  |  | 0 | 0 | 0
14.3.3 | Pavement structure/ Kolovozna konstrukcija
14.3.3.1 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana | 2072.5 | 40 |  | 0 | 0 | 0
14.3.3.2 | asphalt concrete layer/ sloj asfaltnog betona 2 right side/ desna strana | 2072.5 | 41 |  | 0 | 0 | 0
14.3.3.3 | asphalt concrete layer/ sloj asfaltnog betona 3 right side/ desna strana | 2302.91 | 42 |  | 0 | 0 | 0
| Sub Total / Suma stavke 14.3 | 59931.03 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 14.4 | Construction of tunnel/Izgradnja tunela Preslo (LK 36+989.000- LK 37+484.00, RK 37+433.00- RK 37+433.000)
Completion of/Završetak:
14.4.1 | Portal construction/ Izgradnja portala
14.4.1.1 | 20% complete/ završeno (portal 1) | 75126.83 | 31 |  | 0 | 0 | 0
14.4.1.2 | 40% complete/ završeno (portal 2) | 75126.83 | 32 |  | 0 | 0 | 0
14.4.1.3 | 60% complete/ završeno (portal 3) | 75126.83 | 33 |  | 0 | 0 | 0
14.4.1.4 | 80% complete/ završeno (portal 4) | 75126.83 | 33 |  | 0 | 0 | 0
14.4.1.5 | 85% (portal 1 complete/ završen) | 18781.7075 | 45 |  | 0 | 0 | 0
14.4.1.6 | 90% (portal 2 complete/ završen) | 18781.7075 | 45 |  | 0 | 0 | 0
14.4.1.7 | 95% (portal 3 complete/ završen) | 18781.7075 | 45 |  | 0 | 0 | 0
14.4.1.8 | 100% (portal 4 complete/ završen) | 18781.7175 | 45 |  | 0 | 0 | 0
14.4.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
14.4.2.1 | 20 m | 139692.0566 | 34 |  | 0 | 0 | 0
14.4.2.2 | 40 m | 139692.0566 | 34 |  | 0 | 0 | 0
14.4.2.3 | 60 m | 139692.0566 | 34 |  | 0 | 0 | 0
14.4.2.4 | 80 m | 139692.0566 | 34 |  | 0 | 0 | 0
14.4.2.5 | 100 m | 139692.0566 | 35 |  | 0 | 0 | 0
14.4.2.6 | 120 m | 139692.0566 | 35 |  | 0 | 0 | 0
14.4.2.7 | 140 m | 139692.0566 | 35 |  | 0 | 0 | 0
14.4.2.8 | 160 m | 139692.0566 | 35 |  | 0 | 0 | 0
14.4.2.9 | 180 m | 139692.0566 | 36 |  | 0 | 0 | 0
14.4.2.10 | 200 m | 139692.0566 | 36 |  | 0 | 0 | 0
14.4.2.11 | 220 m | 139692.0566 | 36 |  | 0 | 0 | 0
14.4.2.12 | 240 m | 139692.0566 | 36 |  | 0 | 0 | 0
14.4.2.13 | 260 m | 139692.0566 | 36 |  | 0 | 0 | 0
14.4.2.14 | 280 m | 139692.0566 | 36 |  | 0 | 0 | 0
14.4.2.15 | 300 m | 139692.0566 | 37 |  | 0 | 0 | 0
14.4.2.16 | 320 m | 139692.0566 | 37 |  | 0 | 0 | 0
14.4.2.17 | 340 m | 139692.0566 | 37 |  | 0 | 0 | 0
14.4.2.18 | 360 m | 139692.0566 | 37 |  | 0 | 0 | 0
14.4.2.19 | 380 m | 139692.0566 | 37 |  | 0 | 0 | 0
14.4.2.20 | 400 m | 139692.0566 | 37 |  | 0 | 0 | 0
14.4.2.21 | 420 m | 139692.0566 | 38 |  | 0 | 0 | 0
14.4.2.22 | 440 m | 139692.0566 | 38 |  | 0 | 0 | 0
14.4.2.23 | 460 m | 139692.0566 | 38 |  | 0 | 0 | 0
14.4.2.24 | 480 m | 139692.0566 | 38 |  | 0 | 0 | 0
14.4.2.25 | 500 m | 139692.0566 | 38 |  | 0 | 0 | 0
14.4.2.26 | 520 m | 139692.0566 | 38 |  | 0 | 0 | 0
14.4.2.27 | 540 m | 139692.0566 | 39 |  | 0 | 0 | 0
14.4.2.28 | 560 m | 139692.0566 | 39 |  | 0 | 0 | 0
14.4.2.29 | 580 m | 139692.0566 | 39 |  | 0 | 0 | 0
14.4.2.30 | 600 m | 139692.0566 | 39 |  | 0 | 0 | 0
14.4.2.31 | 620 m | 139692.0566 | 39 |  | 0 | 0 | 0
14.4.2.32 | 640 m | 139692.0566 | 39 |  | 0 | 0 | 0
14.4.2.33 | 660 m | 139692.0566 | 40 |  | 0 | 0 | 0
14.4.2.34 | 680 m | 139692.0566 | 40 |  | 0 | 0 | 0
14.4.2.35 | 700 m | 139692.0566 | 40 |  | 0 | 0 | 0
14.4.2.36 | 720 m | 139692.0566 | 40 |  | 0 | 0 | 0
14.4.2.37 | 740 m | 139692.0566 | 40 |  | 0 | 0 | 0
14.4.2.38 | 760 m | 139692.0566 | 40 |  | 0 | 0 | 0
14.4.2.39 | 780 m | 139692.0566 | 41 |  | 0 | 0 | 0
14.4.2.40 | 800 m | 139692.0566 | 41 |  | 0 | 0 | 0
14.4.2.41 | 820 m | 139692.0566 | 41 |  | 0 | 0 | 0
14.4.2.42 | 840 m | 139692.0566 | 41 |  | 0 | 0 | 0
14.4.2.43 | 848 m | 55876.8226 | 41 |  | 0 | 0 | 0
14.4.3 | Construction of waterproofing and drainage & Construction of secondary lining / Konstrukcija hidroizolacije i drenaže & Konstrukcija sekundarne obloge
14.4.3.1 | 20 m | 70485.8658 | 35 |  | 0 | 0 | 0
14.4.3.2 | 40 m | 70485.8658 | 35 |  | 0 | 0 | 0
14.4.3.3 | 60 m | 70485.8658 | 36 |  | 0 | 0 | 0
14.4.3.4 | 80 m | 70485.8658 | 36 |  | 0 | 0 | 0
14.4.3.5 | 100 m | 70485.8658 | 36 |  | 0 | 0 | 0
14.4.3.6 | 120 m | 70485.8658 | 36 |  | 0 | 0 | 0
14.4.3.7 | 140 m | 70485.8658 | 36 |  | 0 | 0 | 0
14.4.3.8 | 160 m | 70485.8658 | 36 |  | 0 | 0 | 0
14.4.3.9 | 180 m | 70485.8658 | 37 |  | 0 | 0 | 0
14.4.3.10 | 200 m | 70485.8658 | 37 |  | 0 | 0 | 0
14.4.3.11 | 220 m | 70485.8658 | 37 |  | 0 | 0 | 0
14.4.3.12 | 240 m | 70485.8658 | 37 |  | 0 | 0 | 0
14.4.3.13 | 260 m | 70485.8658 | 37 |  | 0 | 0 | 0
14.4.3.14 | 280 m | 70485.8658 | 37 |  | 0 | 0 | 0
14.4.3.15 | 300 m | 70485.8658 | 38 |  | 0 | 0 | 0
14.4.3.16 | 320 m | 70485.8658 | 38 |  | 0 | 0 | 0
14.4.3.17 | 340 m | 70485.8658 | 38 |  | 0 | 0 | 0
14.4.3.18 | 360 m | 70485.8658 | 38 |  | 0 | 0 | 0
14.4.3.19 | 380 m | 70485.8658 | 38 |  | 0 | 0 | 0
14.4.3.20 | 400 m | 70485.8658 | 38 |  | 0 | 0 | 0
14.4.3.21 | 420 m | 70485.8658 | 39 |  | 0 | 0 | 0
14.4.3.22 | 440 m | 70485.8658 | 39 |  | 0 | 0 | 0
14.4.3.23 | 460 m | 70485.8658 | 39 |  | 0 | 0 | 0
14.4.3.24 | 480 m | 70485.8658 | 39 |  | 0 | 0 | 0
14.4.3.25 | 500 m | 70485.8658 | 39 |  | 0 | 0 | 0
14.4.3.26 | 520 m | 70485.8658 | 39 |  | 0 | 0 | 0
14.4.3.27 | 540 m | 70485.8658 | 40 |  | 0 | 0 | 0
14.4.3.28 | 560 m | 70485.8658 | 40 |  | 0 | 0 | 0
14.4.3.29 | 580 m | 70485.8658 | 40 |  | 0 | 0 | 0
14.4.3.30 | 600 m | 70485.8658 | 40 |  | 0 | 0 | 0
14.4.3.31 | 620 m | 70485.8658 | 40 |  | 0 | 0 | 0
14.4.3.32 | 640 m | 70485.8658 | 40 |  | 0 | 0 | 0
14.4.3.33 | 660 m | 70485.8658 | 41 |  | 0 | 0 | 0
14.4.3.34 | 680 m | 70485.8658 | 41 |  | 0 | 0 | 0
14.4.3.35 | 700 m | 70485.8658 | 41 |  | 0 | 0 | 0
14.4.3.36 | 720 m | 70485.8658 | 41 |  | 0 | 0 | 0
14.4.3.37 | 740 m | 70485.8658 | 41 |  | 0 | 0 | 0
14.4.3.38 | 760 m | 70485.8658 | 41 |  | 0 | 0 | 0
14.4.3.39 | 780 m | 70485.8658 | 42 |  | 0 | 0 | 0
14.4.3.40 | 800 m | 70485.8658 | 42 |  | 0 | 0 | 0
14.4.3.41 | 820 m | 70485.8658 | 42 |  | 0 | 0 | 0
14.4.3.42 | 840 m | 70485.8658 | 42 |  | 0 | 0 | 0
14.4.3.43 | 848 m | 28194.3463 | 42 |  | 0 | 0 | 0
14.4.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi I ploca, drenazni sistem)
14.4.4.1 | 200 m | 80000 | 37 |  | 0 | 0 | 0
14.4.4.2 | 400 m | 80000 | 39 |  | 0 | 0 | 0
14.4.4.3 | 600 m | 80000 | 41 |  | 0 | 0 | 0
14.4.4.4 | 800 m | 80000 | 42 |  | 0 | 0 | 0
14.4.4.5 | 848 m | 19200 | 43 |  | 0 | 0 | 0
14.4.5 | Construction of pavement/ Izgradnja kolovoza
14.4.5.1 | Left tube/ Lijeva cijev
0-510 m
14.4.5.1.1 | Layer/ Sloj 1 | 39067.9 | 43 |  | 0 | 0 | 0
14.4.5.1.2 | Layer/ Sloj 2 | 39067.9 | 44 |  | 0 | 0 | 0
14.4.5.1.3 | Layer/ Sloj 3 | 43951.38 | 44 |  | 0 | 0 | 0
14.4.5.2 | Right tube/ Desna cijev
0-431 m
14.4.5.2.1 | Layer/ Sloj 1 | 33016.2 | 43 |  | 0 | 0 | 0
14.4.5.2.2 | Layer/ Sloj 2 | 33016.2 | 44 |  | 0 | 0 | 0
14.4.5.2.3 | Layer/ Sloj 3 | 37143.24 | 44 |  | 0 | 0 | 0
14.4.6 | Tunnel Equipment/ Tunelska oprema
14.4.6.1 | Right tube/ Desna cijev
14.4.6.1.1 | 90% (Equipment installed/Oprema postavljena) | 431381.71 | 46 |  | 0 | 0 | 0
14.4.6.1.2 | 10% (Equipment tested/Oprema ispitana) | 47931.3 | 46 |  | 0 | 0 | 0
14.4.6.2 | Left tube/ Lijeva cijev
14.4.6.2.1 | 90% (Equipment installed/Oprema postavljena) | 505637.41 | 45 |  | 0 | 0 | 0
14.4.6.2.2 | 10% (Equipment tested/Oprema ispitana) | 56184.16 | 46 |  | 0 | 0 | 0
| Sub Total / Suma stavke 14.4 | 10892775.47 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 14.5 | Road Works/Radovi na putevima (LK37+484.000—LK37+545.087, RK37+433.00—RK37+581.884)
Completion of/Završetak:
14.5.1 | Subgrade/ Posteljica
14.5.1.1 | Top soil removal/ Uklanjanje humusa
14.5.1.1.1 | RK37+433.000—RK37+581.884 (Inc. 0 - 61.087 m (LK); 0 - 148.884 m (RK)) | 30785.84 | 18 |  | 0 | 0 | 0
14.5.1.2 | Earthworks/ Zemljani radovi |  | 36
At every 250 m 4m height/Na svakih 250m i određenoj 4m visini
14.5.1.2.1 | Embankment RK37+433.000—RK37+581.884 Layers 1,2,3,4,5,6,7,8,9,10
14.5.1.2.1.1 | RK37+433.000—RK37+581.884 Layer 1 | 30361.3616 |  |  | 0 | 0 | 0
14.5.1.2.1.2 | RK37+433.000—RK37+581.884 Layer 2 | 30361.3616 |  |  | 0 | 0 | 0
14.5.1.2.1.3 | RK37+433.000—RK37+581.884 Layer 3 | 30361.3616 |  |  | 0 | 0 | 0
14.5.1.2.1.4 | RK37+433.000—RK37+581.884 Layer 4 | 30361.3616 |  |  | 0 | 0 | 0
14.5.1.2.1.5 | RK37+433.000—RK37+581.884 Layer 5 | 30361.3616 |  |  | 0 | 0 | 0
14.5.1.2.1.6 | RK37+433.000—RK37+581.884 Layer 6 | 30361.3616 |  |  | 0 | 0 | 0
14.5.1.2.1.7 | RK37+433.000—RK37+581.884 Layer 7 | 30361.3616 |  |  | 0 | 0 | 0
14.5.1.2.1.8 | RK37+433.000—RK37+581.884 Layer 8 | 30361.3616 |  |  | 0 | 0 | 0
14.5.1.2.1.9 | RK37+433.000—RK37+581.884 Layer 9 | 30361.3616 |  |  | 0 | 0 | 0
14.5.1.2.1.10 | RK37+433.000—RK37+581.884 Layer 10 | 35143.276 |  |  | 0 | 0 | 0
14.5.1.3 | Road Foundation/ Temelj puta
14.5.1.3.1 | 0 - 148.884 m, right side/ desna strana | 16650.96 | 38 |  | 0 | 0 | 0
14.5.1.3.2 | 0 - 61.087 m, left side/ lijeva strana | 16650.96 | 39 |  | 0 | 0 | 0
14.5.2 | Water drainage/ Drenaža vode
per one direction of 500m / Na 500m dužine u jednom pravcu
14.5.2.1 | LK37+484.000—LK37+545.087 (61.087 m) | 22991.5454 | 34 |  | 0 | 0 | 0
14.5.2.2 | RK37+433.000—RK37+581.884 (148.884 m) | 56036.0346 | 34 |  | 0 | 0 | 0
14.5.3 | Pavement structure/ Kolovozna konstrukcija
14.5.3.1 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana | 15939.2124 | 40 |  | 0 | 0 | 0
14.5.3.2 | asphalt concrete layer/ sloj asfaltnog betona 1 left side/ lijeva strana | 6539.8476 | 40 |  | 0 | 0 | 0
14.5.3.3 | asphalt concrete layer/ sloj asfaltnog betona 2 right side/ desna strana | 15939.2124 | 41 |  | 0 | 0 | 0
14.5.3.4 | asphalt concrete layer/ sloj asfaltnog betona 2 left side/ lijeva strana | 6539.8476 | 41 |  | 0 | 0 | 0
14.5.3.5 | asphalt concrete layer/ sloj asfaltnog betona 3 right side/ desna strana | 17711.2831 | 42 |  | 0 | 0 | 0
14.5.3.6 | asphalt concrete layer/ sloj asfaltnog betona 3 left side/ lijeva strana | 7266.9269 | 42 |  | 0 | 0 | 0
14.5.4 | Engineering structures/ Inženjerske konstrukcije
Concrete wall / Betonski zid
80% for the concrete wall, the milestone is 50m lenth, no matter the hight+ 5% for the "after work" the whole lenth of each retaining wall + 5% for the "correction of the crown" the whole lenth of each retaining wall+10% for the "wall surface" the whole lenth of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
14.5.4.1.1 | Concrete wall/ Betonski zid RK37+433.0 - RK37+530.0 (97m),
14.5.4.1.1.1 | Layer 1, RK37+433- RK37+530 - 80% (50m) | 26929.0052 |  |  | 0 | 0 | 0
14.5.4.1.1.2 | Layer 2,RK37+433- RK37+530 - 80% (47m) | 25313.2649 |  |  | 0 | 0 | 0
14.5.4.1.1.3 | Concrete wall/ Betonski zid RK37+433.0 - RK37+530.0 - After work 5% | 3265.1419 |  |  | 0 | 0 | 0
14.5.4.1.1.4 | Concrete wall/ Betonski zid RK37+433.0 - RK37+530.0 - Correction of the crown 5% | 3265.1419 |  |  | 0 | 0 | 0
| Concrete wall/ Betonski zid RK37+433.0 - RK37+530.0 - 10% Wall surface | 6530.2838 |  |  | 0 | 0 | 0
14.5.4.1.2 | Concrete wall/ Betonski zid RK37+465.0 - RK37+550.0 (85m),
14.5.4.1.2.1 | Layer 1, RK37+465 - RK37+550 - 80% (50m) | 26929.0052 |  |  | 0 | 0 | 0
14.5.4.1.2.2 | Layer 2,RK37+465 - RK37+550 - 80% (35m) | 18850.3037 |  |  | 0 | 0 | 0
14.5.4.1.2.3 | Concrete wall/ Betonski zid RK37+465.0 - RK37+550.0 - After work 5% | 2861.2068 |  |  | 0 | 0 | 0
14.5.4.1.2.4 | Concrete wall/ Betonski zid RK37+465.0 - RK37+550.0 - Correction of the crown 5% | 2861.2068 |  |  | 0 | 0 | 0
| Concrete wall/ Betonski zid RK37+465.0 - RK37+550.0 - 10% Wall surface | 5722.4136 |  |  | 0 | 0 | 0
14.5.4.1.3 | Concrete wall/ Betonski zid RK37+568.484 - RK37+577.484 (9m)
14.5.4.1.3.1 | Concrete wall/ Betonski zid RK37+568.484 - RK37+577.484 - 80% | 4847.2209 |  |  | 0 | 0 | 0
14.5.4.1.3.2 | Concrete wall/ Betonski zid RK37+568.484 - RK37+577.484 - After work 5% | 302.9513 |  |  | 0 | 0 | 0
14.5.4.1.3.3 | Concrete wall/ Betonski zid RK37+568.484 - RK37+577.484 - Correction of the crown 5% | 302.9513 |  |  | 0 | 0 | 0
| Concrete wall/ Betonski zid RK37+568.484 - RK37+577.484 - 10% Wall surface | 605.9026 |  |  | 0 | 0 | 0
| Sub Total / Suma stavke 14.5 | 650033.2 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 14.6 | Construction of bridge/Izgradnja mosta Jabuka (LK 37+545.087 - LK 37+617.087, LK 37.733.287- LK 38+309.087, RK 37+581.884- 38+366.284)
Completion of/Završetak:
Left bridge/ Lijevi most
14.6.1 | Foundation piles/ Temeljni šipovi
14.6.1.1 | A1 | 346413.55 | 18 | 29 | 346413.55 | 0 | 346413.55
14.6.1.2 | P1 | 230965.06 | 18 | 29 | 230965.06 | 0 | 230965.06
14.6.1.3 | P2 | 180422.31 | 18 | 27 | 180422.31 | 0 | 180422.31
14.6.1.4 | P3 | 180422.31 | 18 |  | 0 | 0 | 0
14.6.1.5 | P4 | 180422.31 | 18 | 28 | 180422.31 | 0 | 180422.31
14.6.1.6 | P5 | 180422.31 | 18 | 27 | 180422.31 | 0 | 180422.31
14.6.1.7 | P6 | 180422.31 | 19 | 27 | 180422.31 | 0 | 180422.31
14.6.1.8 | P7 | 180422.31 | 19 | 27 | 180422.31 | 0 | 180422.31
14.6.1.9 | P8 | 180422.31 | 19 | 27 | 180422.31 | 0 | 180422.31
14.6.1.10 | P9 | 180422.31 | 19 | 27 | 180422.31 | 0 | 180422.31
14.6.1.11 | P10 | 180422.31 | 19 | 25 | 180422.31 | 0 | 180422.31
14.6.1.12 | P11 | 180422.31 | 19 | 25 | 180422.31 | 0 | 180422.31
14.6.1.13 | P12 | 180422.31 | 19 | 25 | 180422.31 | 0 | 180422.31
14.6.1.14 | P13 | 180422.31 | 20 | 25 | 180422.31 | 0 | 180422.31
14.6.1.15 | P14 | 180422.31 | 20 | 26 | 180422.31 | 0 | 180422.31
14.6.1.16 | P15 | 180422.31 | 20 | 25 | 180422.31 | 0 | 180422.31
14.6.1.17 | P16 | 180422.31 | 20 | 25 | 180422.31 | 0 | 180422.31
14.6.1.18 | P17 | 180422.31 | 20 | 25 | 180422.31 | 0 | 180422.31
14.6.1.19 | P18 | 180422.31 | 20 | 25 | 180422.31 | 0 | 180422.31
14.6.1.20 | P19 | 180422.31 | 20 | 28 | 180422.31 | 0 | 180422.31
14.6.1.21 | P20 | 180422.31 | 20 | 30 | 0 | 180422.31 | 180422.31
14.6.1.22 | A2
14.6.2 | Foundation concrete/ Temeljni beton
14.6.2.1 | A1 | 248447.95 | 19 | 30 | 0 | 248447.95 | 248447.95
14.6.2.2 | P1 | 150574.51 | 19 | 30 | 0 | 150574.51 | 150574.51
14.6.2.3 | P2 | 67220.76 | 20 | 30 | 0 | 67220.76 | 67220.76
14.6.2.4 | P3 | 67220.76 | 20 |  | 0 | 0 | 0
14.6.2.5 | P4 | 67220.76 | 21 | 30 | 0 | 67220.76 | 67220.76
14.6.2.6 | P5 | 67220.76 | 21 | 29 | 67220.76 | 0 | 67220.76
14.6.2.7 | P6 | 67220.76 | 22 | 29 | 67220.76 | 0 | 67220.76
14.6.2.8 | P7 | 67220.76 | 23 | 28 | 67220.76 | 0 | 67220.76
14.6.2.9 | P8 | 67220.76 | 23 | 28 | 67220.76 | 0 | 67220.76
14.6.2.10 | P9 | 67220.76 | 23 | 28 | 67220.76 | 0 | 67220.76
14.6.2.11 | P10 | 67220.76 | 24 | 26 | 67220.76 | 0 | 67220.76
14.6.2.12 | P11 | 67220.76 | 24 | 26 | 67220.76 | 0 | 67220.76
14.6.2.13 | P12 | 67220.76 | 24 | 26 | 67220.76 | 0 | 67220.76
14.6.2.14 | P13 | 67220.76 | 25 | 27 | 67220.76 | 0 | 67220.76
14.6.2.15 | P14 | 67220.76 | 25 | 27 | 67220.76 | 0 | 67220.76
14.6.2.16 | P15 | 67220.76 | 25 | 28 | 67220.76 | 0 | 67220.76
14.6.2.17 | P16 | 67220.76 | 26 | 27 | 67220.76 | 0 | 67220.76
14.6.2.18 | P17 | 67220.76 | 26 | 27 | 67220.76 | 0 | 67220.76
14.6.2.19 | P18 | 67220.76 | 26 | 29 | 67220.76 | 0 | 67220.76
14.6.2.20 | P19 | 67220.76 | 27 | 29 | 67220.76 | 0 | 67220.76
14.6.2.21 | P20 | 67220.76 | 27 |  | 0 | 0 | 0
14.6.2.22 | A2 | 165632.12 | 27 |  | 0 | 0 | 0
14.6.3 | Abutments and Piers elevation/ Elevacija mosnih stubova
14.6.3.1 | A1 | 119324.73 | 19 |  | 0 | 0 | 0
14.6.3.2 | P1 stage 1 (6m) | 16418.0492 | 19 |  | 0 | 0 | 0
14.6.3.3 | P1 stage 2 (3.7m) | 10124.4636 | 19 |  | 0 | 0 | 0
14.6.3.4 | P2 stage 1 (6m) | 16418.0492 | 20 |  | 0 | 0 | 0
14.6.3.5 | P2 stage 2 (6m) | 16418.0492 | 20 |  | 0 | 0 | 0
14.6.3.6 | P2 stage 3 (3.9m) | 10671.7319 | 21 |  | 0 | 0 | 0
14.6.3.7 | P3 stage 1 (6m) | 16418.0492 | 21 |  | 0 | 0 | 0
14.6.3.8 | P3 stage 2 (6m) | 16418.0492 | 23 |  | 0 | 0 | 0
14.6.3.9 | P3 stage 3 (6m) | 16418.0492 | 23 |  | 0 | 0 | 0
14.6.3.10 | P3 stage 4 (3.3m) | 9029.927 | 23 |  | 0 | 0 | 0
14.6.3.11 | P4 stage 1 (6m) | 16418.0492 | 22 |  | 0 | 0 | 0
14.6.3.12 | P4 stage 2 (6m) | 16418.0492 | 22 |  | 0 | 0 | 0
14.6.3.13 | P4 stage 3 (6m) | 16418.0492 | 23 |  | 0 | 0 | 0
14.6.3.14 | P4 stage 4 (6m) | 16418.0492 | 23 |  | 0 | 0 | 0
14.6.3.15 | P4 stage 5 (1.71m) | 4679.144 | 24 |  | 0 | 0 | 0
14.6.3.16 | P5 stage 1 (6m) | 16418.0492 | 23 | 30 | 0 | 16418.0492 | 16418.0492
14.6.3.17 | P5 stage 2 (6m) | 16418.0492 | 23 | 30 | 0 | 16418.0492 | 16418.0492
14.6.3.18 | P5 stage 3 (6m) | 16418.0492 | 24 |  | 0 | 0 | 0
14.6.3.19 | P5 stage 4 (6m) | 16418.0492 | 24 |  | 0 | 0 | 0
14.6.3.20 | P5 stage 5 (4.62m) | 12641.8978 | 25 |  | 0 | 0 | 0
14.6.3.21 | P6 stage 1 (6m) | 16418.0492 | 24 | 30 | 0 | 16418.0492 | 16418.0492
14.6.3.22 | P6 stage 2 (6m) | 16418.0492 | 24 | 30 | 0 | 16418.0492 | 16418.0492
14.6.3.23 | P6 stage 3 (6m) | 16418.0492 | 25 |  | 0 | 0 | 0
14.6.3.24 | P6 stage 4 (6m) | 16418.0492 | 25 |  | 0 | 0 | 0
14.6.3.25 | P6 stage 5 (4.04m) | 11054.8198 | 26 |  | 0 | 0 | 0
14.6.3.26 | P7 stage 1 (6m) | 16418.0492 | 26 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.27 | P7 stage 2 (6m) | 16418.0492 | 26 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.28 | P7 stage 3 (6m) | 16418.0492 | 27 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.29 | P7 stage 4 (6m) | 16418.0492 | 27 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.30 | P7 stage 5 (3.55m) | 9714.0124 | 28 |  | 0 | 0 | 0
14.6.3.31 | P8 stage 1 (6m) | 16418.0492 | 27 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.32 | P8 stage 2 (6m) | 16418.0492 | 27 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.33 | P8 stage 3 (6m) | 16418.0492 | 28 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.34 | P8 stage 4 (6m) | 16418.0492 | 29 | 30 | 0 | 16418.0492 | 16418.0492
14.6.3.35 | P8 stage 5 (2.66m) | 7278.6685 | 29 |  | 0 | 0 | 0
14.6.3.36 | P9 stage 1 (6m) | 16418.0492 | 27 | 28 | 16418.05 | 0 | 16418.05
14.6.3.37 | P9 stage 2 (6m) | 16418.0492 | 27 | 28 | 16418.05 | 0 | 16418.05
14.6.3.38 | P9 stage 3 (6m) | 16418.0492 | 28 | 28 | 16418.05 | 0 | 16418.05
14.6.3.39 | P9 stage 4 (6m) | 16418.0492 | 29 | 28 | 16418.05 | 0 | 16418.05
14.6.3.40 | P9 stage 5 (1.75m) | 4788.5977 | 29 | 28 | 4788.6 | 0 | 4788.6
14.6.3.41 | P10 stage 1 (6m) | 16418.0492 | 29 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.42 | P10 stage 2 (6m) | 16418.0492 | 29 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.43 | P10 stage 3 (6m) | 16418.0492 | 30 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.44 | P10 stage 4 (6m) | 16418.0492 | 31 |  | 0 | 0 | 0
14.6.3.45 | P10 stage 5 (1.05m) | 2873.1586 | 31 |  | 0 | 0 | 0
14.6.3.46 | P11 stage 1 (2m) | 5472.6831 | 29 | 29 | 5472.6831 | 0 | 5472.6831
14.6.3.47 | P11 stage 2 (4m) | 10945.3661 | 29 | 29 | 10945.3661 | 0 | 10945.3661
14.6.3.48 | P11 stage 3 (4m) | 10945.3661 | 30 | 29 | 10945.3661 | 0 | 10945.3661
14.6.3.49 | P11 stage 4 (4m) | 10945.3661 | 30 | 29 | 10945.3661 | 0 | 10945.3661
14.6.3.50 | P11 stage 5 (4m) | 10945.3661 | 30 | 29 | 10945.3661 | 0 | 10945.3661
14.6.3.51 | P11 stage 6 (3m) | 8209.0246 | 31 | 30 | 0 | 8209.0246 | 8209.0246
14.6.3.52 | P11 stage 7 (2.3m) | 6293.5855 | 31 |  | 0 | 0 | 0
14.6.3.53 | P12 stage 1 (6m) | 16418.0492 | 31 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.54 | P12 stage 2 (6m) | 16418.0492 | 31 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.55 | P12 stage 3 (6m) | 16418.0492 | 32 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.56 | P12 stage 4 (4.75m) | 12997.6222 | 33 |  | 0 | 0 | 0
14.6.3.57 | P13 stage 1 (6m) | 16418.0492 | 32 | 28 | 16418.05 | 0 | 16418.05
14.6.3.58 | P13 stage 2 (6m) | 16418.0492 | 32 | 28 | 16418.05 | 0 | 16418.05
14.6.3.59 | P13 stage 3 (6m) | 16418.0492 | 33 | 28 | 16418.05 | 0 | 16418.05
14.6.3.60 | P13 stage 4 (3.75m) | 10261.2807 | 34 | 28 | 10261.28 | 0 | 10261.28
14.6.3.61 | P14 stage 1 (6m) | 16418.0492 | 32 |  | 0 | 0 | 0
14.6.3.62 | P14 stage 2 (6m) | 16418.0492 | 32 |  | 0 | 0 | 0
14.6.3.63 | P14 stage 3 (6m) | 16418.0492 | 33 |  | 0 | 0 | 0
14.6.3.64 | P14 stage 4 (3.05m) | 8345.8417 | 34 |  | 0 | 0 | 0
14.6.3.65 | P15 stage 1 (6m) | 16418.0492 | 34 | 28 | 16418.05 | 0 | 16418.05
14.6.3.66 | P15 stage 2 (6m) | 16418.0492 | 34 | 28 | 16418.05 | 0 | 16418.05
14.6.3.67 | P15 stage 3 (6m) | 16418.0492 | 35 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.68 | P15 stage 4 (3.05m) | 8345.8417 | 35 |  | 0 | 0 | 0
14.6.3.69 | P16 stage 1 (6m) | 16418.0492 | 35 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.70 | P16 stage 2 (6m) | 16418.0492 | 35 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.71 | P16 stage 3 (6m) | 16418.0492 | 36 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.72 | P16 stage 4 (1.85m) | 5062.2318 | 36 |  | 0 | 0 | 0
14.6.3.73 | P17 stage 1 (6m) | 16418.0492 | 35 | 28 | 16418.05 | 0 | 16418.05
14.6.3.74 | P17 stage 2 (6m) | 16418.0492 | 35 | 28 | 16418.05 | 0 | 16418.05
14.6.3.75 | P17 stage 3 (6.45m) | 17649.4028 | 36 |  | 0 | 0 | 0
14.6.3.76 | P18 stage 1 (6m) | 16418.0492 | 36 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.77 | P18 stage 2 (6m) | 16418.0492 | 36 | 29 | 16418.0492 | 0 | 16418.0492
14.6.3.78 | P18 stage 3 (6.05m) | 16554.8662 | 37 |  | 0 | 0 | 0
14.6.3.79 | P19 stage 1 (6m) | 16418.0492 | 37 | 30 | 0 | 16418.0492 | 16418.0492
14.6.3.80 | P19 stage 2 (6m) | 16418.0492 | 37 | 30 | 0 | 16418.0492 | 16418.0492
14.6.3.81 | P19 stage 3 (5.55m) | 15186.6955 | 38 |  | 0 | 0 | 0
14.6.3.82 | P20 stage 1 (6m) | 16418.0492 | 37 |  | 0 | 0 | 0
14.6.3.83 | P20 stage 2 (6m) | 16418.0492 | 38 |  | 0 | 0 | 0
14.6.3.84 | P20 stage 3 (2.45m) | 6704.0367 | 38 |  | 0 | 0 | 0
14.6.3.85 | A2 | 119324.73 | 38 |  | 0 | 0 | 0
14.6.4 | Spans/ Rasponi
14.6.4.1 | A1-P1
14.6.4.2 | Bridge superstructure/ Gornji stroj mosta | 115419.8 | 20 |  | 0 | 0 | 0
14.6.4.3 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 12824.42 | 21 |  | 0 | 0 | 0
14.6.4.4 | P1-P2
14.6.4.5 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 22 |  | 0 | 0 | 0
14.6.4.6 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 23 |  | 0 | 0 | 0
14.6.4.7 | P2-P3
14.6.4.8 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 23 |  | 0 | 0 | 0
14.6.4.9 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 24 |  | 0 | 0 | 0
14.6.4.10 | P3-P4
14.6.4.11 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 24 |  | 0 | 0 | 0
14.6.4.12 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 25 |  | 0 | 0 | 0
14.6.4.13 | P4-P5
14.6.4.14 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 25 |  | 0 | 0 | 0
14.6.4.15 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 26 |  | 0 | 0 | 0
14.6.4.16 | P5-P6
14.6.4.17 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 26 |  | 0 | 0 | 0
14.6.4.18 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 27 |  | 0 | 0 | 0
14.6.4.19 | P6-P7
14.6.4.20 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 27 |  | 0 | 0 | 0
14.6.4.21 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 28 |  | 0 | 0 | 0
14.6.4.22 | P7-P8
14.6.4.23 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 28 |  | 0 | 0 | 0
14.6.4.24 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 29 |  | 0 | 0 | 0
14.6.4.25 | P8-P9
14.6.4.26 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 29 |  | 0 | 0 | 0
14.6.4.27 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 30 |  | 0 | 0 | 0
14.6.4.28 | P9-P10
14.6.4.29 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 30 |  | 0 | 0 | 0
14.6.4.30 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 31 |  | 0 | 0 | 0
14.6.4.31 | P10-P11
14.6.4.32 | Bridge superstructure/ Gornji stroj mosta | 124557.2 | 31 |  | 0 | 0 | 0
14.6.4.33 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 13839.69 | 32 |  | 0 | 0 | 0
14.6.4.34 | P11-P12
14.6.4.35 | Bridge superstructure/ Gornji stroj mosta | 124557.2 | 32 |  | 0 | 0 | 0
14.6.4.36 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 13839.69 | 33 |  | 0 | 0 | 0
14.6.4.37 | P12-P13
14.6.4.38 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 33 |  | 0 | 0 | 0
14.6.4.39 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 34 |  | 0 | 0 | 0
14.6.4.40 | P13-P14
14.6.4.41 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 34 |  | 0 | 0 | 0
14.6.4.42 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 35 |  | 0 | 0 | 0
14.6.4.43 | P14-P15
14.6.4.44 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 35 |  | 0 | 0 | 0
14.6.4.45 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 36 |  | 0 | 0 | 0
14.6.4.46 | P15-P16
14.6.4.47 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 36 |  | 0 | 0 | 0
14.6.4.48 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 37 |  | 0 | 0 | 0
14.6.4.49 | P16-P17
14.6.4.50 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 37 |  | 0 | 0 | 0
14.6.4.51 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 38 |  | 0 | 0 | 0
14.6.4.52 | P17-P18
14.6.4.53 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 36 |  | 0 | 0 | 0
14.6.4.54 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 38 |  | 0 | 0 | 0
14.6.4.55 | P18-P19
14.6.4.56 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 39 |  | 0 | 0 | 0
14.6.4.57 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 40 |  | 0 | 0 | 0
14.6.4.58 | P19-P20
14.6.4.59 | Bridge superstructure/ Gornji stroj mosta | 134656.43 | 40 |  | 0 | 0 | 0
14.6.4.60 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14961.83 | 41 |  | 0 | 0 | 0
14.6.4.61 | P20-A2
14.6.4.62 | Bridge superstructure/ Gornji stroj mosta | 115419.8 | 41 |  | 0 | 0 | 0
14.6.4.63 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 12824.42 | 42 |  | 0 | 0 | 0
14.6.5 | Bridge furniture/ Mosna estetika
14.6.5.1 | 50 m | 81557.44 | 41 |  | 0 | 0 | 0
14.6.5.2 | 100 m | 81557.44 | 41 |  | 0 | 0 | 0
14.6.5.3 | 150 m | 81557.44 | 41 |  | 0 | 0 | 0
14.6.5.4 | 200 m | 81557.44 | 41 |  | 0 | 0 | 0
14.6.5.5 | 250 m | 81557.44 | 41 |  | 0 | 0 | 0
14.6.5.6 | 300 m | 81557.44 | 42 |  | 0 | 0 | 0
14.6.5.7 | 350 m | 81557.44 | 42 |  | 0 | 0 | 0
14.6.5.8 | 400 m | 81557.44 | 42 |  | 0 | 0 | 0
14.6.5.9 | 450 m | 81557.44 | 42 |  | 0 | 0 | 0
14.6.5.10 | 500 m | 81557.44 | 42 |  | 0 | 0 | 0
14.6.5.11 | 550 m | 81557.44 | 42 |  | 0 | 0 | 0
14.6.5.12 | 575.8 m | 42083.56 | 42 |  | 0 | 0 | 0
14.6.6 | Waterproofing and asphalt works/ Hidroizolacija i asfaltni radovi
14.6.6.1 | Asphalt/Asfalt 1 + waterproofing/ hidroizolacija | 195991.37 | 41 |  | 0 | 0 | 0
14.6.6.2 | Asphalt/Asfalt 2 + joints/ spojnice | 49554.75 | 42 |  | 0 | 0 | 0
Right bridge/ Desni most
14.6.7 | Foundation piles/ Temeljni šipovi
14.6.7.1 | A1
14.6.7.2 | P1 | 191748.5 | 18 | 28 | 191748.5 | 0 | 191748.5
14.6.7.3 | P2 | 191748.5 | 18 | 29 | 191748.5 | 0 | 191748.5
14.6.7.4 | P3 | 191748.5 | 18 | 28 | 191748.5 | 0 | 191748.5
14.6.7.5 | P4 | 191748.5 | 18 | 28 | 191748.5 | 0 | 191748.5
14.6.7.6 | P5 | 191748.5 | 18 | 29 | 191748.5 | 0 | 191748.5
14.6.7.7 | P6 | 191748.5 | 18 | 29 | 191748.5 | 0 | 191748.5
14.6.7.8 | P7 | 191748.5 | 18 | 29 | 191748.5 | 0 | 191748.5
14.6.7.9 | P8 | 191748.5 | 18 | 27 | 191748.5 | 0 | 191748.5
14.6.7.10 | P9 | 191748.5 | 19 | 27 | 191748.5 | 0 | 191748.5
14.6.7.11 | P10 | 191748.5 | 19 | 28 | 191748.5 | 0 | 191748.5
14.6.7.12 | P11 | 191748.5 | 19 | 27 | 191748.5 | 0 | 191748.5
14.6.7.13 | P12 | 191748.5 | 19 | 27 | 191748.5 | 0 | 191748.5
14.6.7.14 | P13 | 191748.5 | 19 | 27 | 191748.5 | 0 | 191748.5
14.6.7.15 | P14 | 191748.5 | 19 | 27 | 191748.5 | 0 | 191748.5
14.6.7.16 | P15 | 191748.5 | 19 | 26 | 191748.5 | 0 | 191748.5
14.6.7.17 | P16 | 191748.5 | 19 | 26 | 191748.5 | 0 | 191748.5
14.6.7.18 | P17 | 191748.5 | 19 | 26 | 191748.5 | 0 | 191748.5
14.6.7.19 | P18 | 191748.5 | 19 | 25 | 191748.5 | 0 | 191748.5
14.6.7.20 | P19 | 191748.5 | 20 | 25 | 191748.5 | 0 | 191748.5
14.6.7.21 | P20 | 191748.5 | 20 | 26 | 191748.5 | 0 | 191748.5
14.6.7.22 | P21 | 191748.5 | 20 | 25 | 191748.5 | 0 | 191748.5
14.6.7.23 | P22 | 191748.5 | 20 | 26 | 191748.5 | 0 | 191748.5
14.6.7.24 | P23 | 191748.5 | 20 | 26 | 191748.5 | 0 | 191748.5
14.6.7.25 | P24 | 191748.5 | 20 | 26 | 191748.5 | 0 | 191748.5
14.6.7.26 | P25 | 191748.5 | 20 | 26 | 191748.5 | 0 | 191748.5
14.6.7.27 | P26 | 191748.5 | 20 | 26 | 191748.5 | 0 | 191748.5
14.6.7.28 | P27 | 191748.5 | 20 | 25 | 191748.5 | 0 | 191748.5
14.6.7.29 | P28 | 191748.5 | 20 | 29 | 191748.5 | 0 | 191748.5
14.6.7.30 | A2
14.6.8 | Foundation concrete/ Temeljni beton
14.6.8.1 | A1 | 149807.93 | 19 | 28 | 149807.93 | 0 | 149807.93
14.6.8.2 | P1 | 60798.67 | 19 |  | 0 | 0 | 0
14.6.8.3 | P2 | 136189.03 | 20 |  | 0 | 0 | 0
14.6.8.4 | P3 | 136189.03 | 20 | 30 | 0 | 136189.03 | 136189.03
14.6.8.5 | P4 | 136189.03 | 20 | 30 | 0 | 136189.03 | 136189.03
14.6.8.6 | P5 | 136189.03 | 21 | 30 | 0 | 136189.03 | 136189.03
14.6.8.7 | P6 | 136189.03 | 21 |  | 0 | 0 | 0
14.6.8.8 | P7 | 136189.03 | 21 | 30 | 0 | 136189.03 | 136189.03
14.6.8.9 | P8 | 60798.67 | 22 | 29 | 60798.67 | 0 | 60798.67
14.6.8.10 | P9 | 60798.67 | 22 | 30 | 0 | 60798.67 | 60798.67
14.6.8.11 | P10 | 60798.67 | 22 |  | 0 | 0 | 0
14.6.8.12 | P11 | 60798.67 | 23 | 30 | 0 | 60798.67 | 60798.67
14.6.8.13 | P12 | 60798.67 | 23 | 29 | 60798.67 | 0 | 60798.67
14.6.8.14 | P13 | 60798.67 | 23 | 29 | 60798.67 | 0 | 60798.67
14.6.8.15 | P14 | 60798.67 | 24 | 28 | 60798.67 | 0 | 60798.67
14.6.8.16 | P15 | 60798.67 | 24 | 27 | 60798.67 | 0 | 60798.67
14.6.8.17 | P16 | 60798.67 | 24 | 27 | 60798.67 | 0 | 60798.67
14.6.8.18 | P17 | 60798.67 | 24 | 27 | 60798.67 | 0 | 60798.67
14.6.8.19 | P18 | 60798.67 | 25 | 26 | 60798.67 | 0 | 60798.67
14.6.8.20 | P19 | 60798.67 | 25 | 26 | 60798.67 | 0 | 60798.67
14.6.8.21 | P20 | 60798.67 | 25 | 28 | 60798.67 | 0 | 60798.67
14.6.8.22 | P21 | 60798.67 | 25 | 28 | 60798.67 | 0 | 60798.67
14.6.8.23 | P22 | 60798.67 | 26 | 28 | 60798.67 | 0 | 60798.67
14.6.8.24 | P23 | 60798.67 | 26 | 29 | 60798.67 | 0 | 60798.67
14.6.8.25 | P24 | 60798.67 | 26 | 29 | 60798.67 | 0 | 60798.67
14.6.8.26 | P25 | 60798.67 | 26 | 29 | 60798.67 | 0 | 60798.67
14.6.8.27 | P26 | 60798.67 | 27 | 29 | 60798.67 | 0 | 60798.67
14.6.8.28 | P27 | 60798.67 | 27 | 29 | 60798.67 | 0 | 60798.67
14.6.8.29 | P28 | 60798.67 | 27 | 30 | 0 | 60798.67 | 60798.67
14.6.8.30 | A2 | 149808.13 | 27 |  | 0 | 0 | 0
14.6.9 | Abutments and Piers elevation/ Elevacija mosnih stubova
14.6.9.1 | A1 | 121468.84 | 20 |  | 0 | 0 | 0
14.6.9.2 | P1 stage 1 (6m) | 18291.6297 | 21 |  | 0 | 0 | 0
14.6.9.3 | P1 stage 2 (6m) | 18291.6297 | 22 |  | 0 | 0 | 0
14.6.9.4 | P1 stage 3 (2m) | 6097.2099 | 22 |  | 0 | 0 | 0
14.6.9.5 | P2 stage 1 (6m) | 18291.6297 | 21 |  | 0 | 0 | 0
14.6.9.6 | P2 stage 2 (5.895m) | 17971.5262 | 22 |  | 0 | 0 | 0
14.6.9.7 | P3 stage 1 (6m) | 18291.6297 | 21 |  | 0 | 0 | 0
14.6.9.8 | P3 stage 2 (6.095m) | 18581.2472 | 22 |  | 0 | 0 | 0
14.6.9.9 | P4 stage 1 (6m) | 18291.6297 | 23 |  | 0 | 0 | 0
14.6.9.10 | P4 stage 2 (5.295m) | 16142.3632 | 23 |  | 0 | 0 | 0
14.6.9.11 | P5 stage 1 (6m) | 18291.6297 | 23 |  | 0 | 0 | 0
14.6.9.12 | P5 stage 2 (4.095m) | 12484.0373 | 23 |  | 0 | 0 | 0
14.6.9.13 | P6 stage 1 (6.5m) | 19815.9322 | 23 |  | 0 | 0 | 0
14.6.9.14 | P7stage 1 (6m) | 18291.6297 | 23 |  | 0 | 0 | 0
14.6.9.15 | P7stage 2 (3m) | 9145.8149 | 23 |  | 0 | 0 | 0
14.6.9.16 | P8 stage 1 (6m) | 18291.6297 | 24 |  | 0 | 0 | 0
14.6.9.17 | P8 stage 2 (4m) | 12194.4198 | 24 |  | 0 | 0 | 0
14.6.9.18 | P8 stage 3 (4m) | 12194.4198 | 25 |  | 0 | 0 | 0
14.6.9.19 | P9 stage 1 (6m) | 18291.6297 | 24 | 30 | 0 | 18291.6297 | 18291.6297
14.6.9.20 | P9 stage 2 (6m) | 18291.6297 | 24 | 30 | 0 | 18291.6297 | 18291.6297
14.6.9.21 | P9 stage 3 (6.395m) | 19495.8287 | 25 |  | 0 | 0 | 0
14.6.9.22 | P10 stage 1 (6m) | 18291.6297 | 25 |  | 0 | 0 | 0
14.6.9.23 | P10 stage 2 (6m) | 18291.6297 | 26 |  | 0 | 0 | 0
14.6.9.24 | P10 stage 3 (6m) | 18291.6297 | 27 |  | 0 | 0 | 0
14.6.9.25 | P10 stage 4 (5.095m) | 15532.6423 | 27 |  | 0 | 0 | 0
14.6.9.26 | P11 stage 1 (6m) | 18291.6297 | 26 |  | 0 | 0 | 0
14.6.9.27 | P11 stage 2 (6m) | 18291.6297 | 26 |  | 0 | 0 | 0
14.6.9.28 | P11 stage 3 (6m) | 18291.6297 | 27 |  | 0 | 0 | 0
14.6.9.29 | P11 stage 4 (6m) | 18291.6297 | 27 |  | 0 | 0 | 0
14.6.9.30 | P11 stage 5 (2.995m) | 9130.5718 | 28 |  | 0 | 0 | 0
14.6.9.31 | P12 stage 1 (6m) | 18291.6297 | 26 | 30 | 0 | 18291.6297 | 18291.6297
14.6.9.32 | P12 stage 2 (6m) | 18291.6297 | 26 | 30 | 0 | 18291.6297 | 18291.6297
14.6.9.33 | P12 stage 3 (6m) | 18291.6297 | 27 |  | 0 | 0 | 0
14.6.9.34 | P12 stage 4 (6m) | 18291.6297 | 27 |  | 0 | 0 | 0
14.6.9.35 | P12 stage 5 (5.022m) | 15310.0941 | 28 |  | 0 | 0 | 0
14.6.9.36 | P13 stage 1 (6m) | 18291.6297 | 27 | 30 | 0 | 18291.6297 | 18291.6297
14.6.9.37 | P13 stage 2 (6m) | 18291.6297 | 27 | 30 | 0 | 18291.6297 | 18291.6297
14.6.9.38 | P13 stage 3 (6m) | 18291.6297 | 28 |  | 0 | 0 | 0
14.6.9.39 | P13 stage 4 (6m) | 18291.6297 | 28 |  | 0 | 0 | 0
14.6.9.40 | P13 stage 5 (3.706m) | 11298.13 | 29 |  | 0 | 0 | 0
14.6.9.41 | P14 stage 1 (6m) | 18291.6297 | 28 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.42 | P14 stage 2 (6m) | 18291.6297 | 29 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.43 | P14 stage 3 (6m) | 18291.6297 | 29 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.44 | P14 stage 4 (6m) | 18291.6297 | 30 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.45 | P14 stage 5 (3.278) | 9993.327 | 30 |  | 0 | 0 | 0
14.6.9.46 | P15 stage 1 (6m) | 18291.6297 | 29 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.47 | P15 stage 2 (4m) | 12194.4198 | 29 | 29 | 12194.4198 | 0 | 12194.4198
14.6.9.48 | P15 stage 3 (4m) | 12194.4198 | 30 | 29 | 12194.4198 | 0 | 12194.4198
14.6.9.49 | P15 stage 4 (4m) | 12194.4198 | 30 | 29 | 12194.4198 | 0 | 12194.4198
14.6.9.50 | P15 stage 5 (4m) | 12194.4198 | 31 | 30 | 0 | 12194.4198 | 12194.4198
14.6.9.51 | P15 stage 6 (4.1m) | 12499.2803 | 31 |  | 0 | 0 | 0
14.6.9.52 | P16 stage 1 (6m) | 18291.6297 | 29 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.53 | P16 stage 2 (6m) | 18291.6297 | 29 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.54 | P16 stage 3 (6m) | 18291.6297 | 30 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.55 | P16 stage 4 (6m) | 18291.6297 | 30 |  | 0 | 0 | 0
14.6.9.56 | P16 stage 5 (1.544m) | 4707.0461 | 31 |  | 0 | 0 | 0
14.6.9.57 | P17 stage 1 (6m) | 18291.6297 | 30 | 28 | 18291.63 | 0 | 18291.63
14.6.9.58 | P17 stage 2 (6m) | 18291.6297 | 31 | 28 | 18291.63 | 0 | 18291.63
14.6.9.59 | P17 stage 3 (6m) | 18291.6297 | 32 |  | 0 | 0 | 0
14.6.9.60 | P17 stage 4 (6.844m) | 20864.6523 | 32 |  | 0 | 0 | 0
14.6.9.61 | P18 stage 1 (6m) | 18291.6297 | 32 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.62 | P18 stage 2 (6m) | 18291.6297 | 32 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.63 | P18 stage 3 (6m) | 18291.6297 | 33 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.64 | P18 stage 4 (5.844m) | 17816.0474 | 33 |  | 0 | 0 | 0
14.6.9.65 | P19 stage 1 (6m) | 18291.6297 | 32 |  | 0 | 0 | 0
14.6.9.66 | P19 stage 2 (6m) | 18291.6297 | 32 |  | 0 | 0 | 0
14.6.9.67 | P19 stage 3 (6m) | 18291.6297 | 33 |  | 0 | 0 | 0
14.6.9.68 | P19 stage 4 (4.844m) | 14767.4424 | 34 |  | 0 | 0 | 0
14.6.9.69 | P20 stage 1 (6m) | 18291.6297 | 33 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.70 | P20 stage 2 (6m) | 18291.6297 | 33 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.71 | P20 stage 3 (6m) | 18291.6297 | 34 | 30 | 0 | 18291.6297 | 18291.6297
14.6.9.72 | P20 stage 4 (3.944m) | 12023.6979 | 34 |  | 0 | 0 | 0
14.6.9.73 | P21 stage 1 (6m) | 18291.6297 | 34 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.74 | P21 stage 2 (6m) | 18291.6297 | 34 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.75 | P21 stage 3 (6m) | 18291.6297 | 35 | 30 | 0 | 18291.6297 | 18291.6297
14.6.9.76 | P21 stage 4 (3.444) | 10499.3955 | 35 |  | 0 | 0 | 0
14.6.9.77 | P22 stage 1 (6m) | 18291.6297 | 35 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.78 | P22 stage 2 (4m) | 12194.4198 | 35 | 29 | 12194.4198 | 0 | 12194.4198
14.6.9.79 | P22 stage 3 (4m) | 12194.4198 | 36 | 29 | 12194.4198 | 0 | 12194.4198
14.6.9.80 | P22 stage 4 (4m) | 12194.4198 | 36 | 29 | 12194.4198 | 0 | 12194.4198
14.6.9.81 | P22 stage 5 (2.6m) | 7926.3729 | 36 |  | 0 | 0 | 0
14.6.9.82 | P23 stage 1 (6m) | 18291.6297 | 35 |  | 0 | 0 | 0
14.6.9.83 | P23 stage 2 (6m) | 18291.6297 | 35 |  | 0 | 0 | 0
14.6.9.84 | P23 stage 3 (6m) | 18291.6297 | 36 |  | 0 | 0 | 0
14.6.9.85 | P23 stage 4 (2.644m) | 8060.5115 | 36 |  | 0 | 0 | 0
14.6.9.86 | P24 stage 1 (6m) | 18291.6297 | 35 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.87 | P24 stage 2 (6m) | 18291.6297 | 35 | 29 | 18291.6297 | 0 | 18291.6297
14.6.9.88 | P24 stage 3 (6m) | 18291.6297 | 36 |  | 0 | 0 | 0
14.6.9.89 | P24 stage 4 (1.644m) | 5011.9065 | 36 |  | 0 | 0 | 0
14.6.9.90 | P25 stage 1 (6m) | 18291.6297 | 36 | 29 | 18291.63 | 0 | 18291.63
14.6.9.91 | P25 stage 2 (6m) | 18291.6297 | 36 | 29 | 18291.63 | 0 | 18291.63
14.6.9.92 | P25 stage 3 (6.844m) | 20864.6523 | 37 |  | 0 | 0 | 0
14.6.9.93 | P26 stage 1 (6m) | 18291.6297 | 37 | 29 | 18291.63 | 0 | 18291.63
14.6.9.94 | P26 stage 2 (6m) | 18291.6297 | 37 | 29 | 18291.63 | 0 | 18291.63
14.6.9.95 | P26 stage 3 (6.344m) | 19340.3498 | 38 |  | 0 | 0 | 0
14.6.9.96 | P27 stage 1 (6m) | 18291.6297 | 37 | 30 | 0 | 18291.6297 | 18291.6297
14.6.9.97 | P27 stage 2 (6m) | 18291.6297 | 37 | 30 | 0 | 18291.6297 | 18291.6297
14.6.9.98 | P27 stage 3 (5.635m) | 17178.8889 | 38 |  | 0 | 0 | 0
14.6.9.99 | P28 stage 1 (6m) | 18291.6297 | 37 |  | 0 | 0 | 0
14.6.9.100 | P28 stage 2 (6m) | 18291.6297 | 38 |  | 0 | 0 | 0
14.6.9.101 | P28 stage 3 (2.244m) | 6841.0695 | 38 |  | 0 | 0 | 0
14.6.9.102 | A2 | 121468.84 | 38 |  | 0 | 0 | 0
14.6.10 | Spans/ Rasponi
14.6.10.1 | A1-P1
14.6.10.2 | Bridge superstructure/ Gornji stroj mosta | 118514.75 | 20 |  | 0 | 0 | 0
14.6.10.3 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 13168.31 | 21 |  | 0 | 0 | 0
14.6.10.4 | P1-P2
14.6.10.5 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 22 |  | 0 | 0 | 0
14.6.10.6 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 23 |  | 0 | 0 | 0
14.6.10.7 | P2-P3
14.6.10.8 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 23 |  | 0 | 0 | 0
14.6.10.9 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 24 |  | 0 | 0 | 0
14.6.10.10 | P3-P4
14.6.10.11 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 24 |  | 0 | 0 | 0
14.6.10.12 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 25 |  | 0 | 0 | 0
14.6.10.13 | P4-P5
14.6.10.14 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 25 |  | 0 | 0 | 0
14.6.10.15 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 26 |  | 0 | 0 | 0
14.6.10.16 | P5-P6
14.6.10.17 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 26 |  | 0 | 0 | 0
14.6.10.18 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 27 |  | 0 | 0 | 0
14.6.10.19 | P6-P7
14.6.10.20 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 27 |  | 0 | 0 | 0
14.6.10.21 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 28 |  | 0 | 0 | 0
14.6.10.22 | P7-P8
14.6.10.23 | Bridge superstructure/ Gornji stroj mosta | 122959.06 | 28 |  | 0 | 0 | 0
14.6.10.24 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 13662.12 | 29 |  | 0 | 0 | 0
14.6.10.25 | P8-P9
14.6.10.26 | Bridge superstructure/ Gornji stroj mosta | 122959.06 | 29 |  | 0 | 0 | 0
14.6.10.27 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 13662.12 | 30 |  | 0 | 0 | 0
14.6.10.28 | P9-P10
14.6.10.29 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 30 |  | 0 | 0 | 0
14.6.10.30 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 31 |  | 0 | 0 | 0
14.6.10.31 | P10-P11
14.6.10.32 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 31 |  | 0 | 0 | 0
14.6.10.33 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 32 |  | 0 | 0 | 0
14.6.10.34 | P11-P12
14.6.10.35 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 32 |  | 0 | 0 | 0
14.6.10.36 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 33 |  | 0 | 0 | 0
14.6.10.37 | P12-P13
14.6.10.38 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 33 |  | 0 | 0 | 0
14.6.10.39 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 34 |  | 0 | 0 | 0
14.6.10.40 | P13-P14
14.6.10.41 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 34 |  | 0 | 0 | 0
14.6.10.42 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 35 |  | 0 | 0 | 0
14.6.10.43 | P14-P15
14.6.10.44 | Bridge superstructure/ Gornji stroj mosta | 118020.94 | 35 |  | 0 | 0 | 0
14.6.10.45 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 13113.44 | 36 |  | 0 | 0 | 0
14.6.10.46 | P15-P16
14.6.10.47 | Bridge superstructure/ Gornji stroj mosta | 122959.06 | 36 |  | 0 | 0 | 0
14.6.10.48 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 13662.12 | 37 |  | 0 | 0 | 0
14.6.10.49 | P16-P17
14.6.10.50 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 37 |  | 0 | 0 | 0
14.6.10.51 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 38 |  | 0 | 0 | 0
14.6.10.52 | P17-P18
14.6.10.53 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 38 |  | 0 | 0 | 0
14.6.10.54 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 39 |  | 0 | 0 | 0
14.6.10.55 | P18-P19
14.6.10.56 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 39 |  | 0 | 0 | 0
14.6.10.57 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 40 |  | 0 | 0 | 0
14.6.10.58 | P19-P20
14.6.10.59 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 40 |  | 0 | 0 | 0
14.6.10.60 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 41 |  | 0 | 0 | 0
14.6.10.61 | P20-P21
14.6.10.62 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 35 |  | 0 | 0 | 0
14.6.10.63 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 36 |  | 0 | 0 | 0
14.6.10.64 | P21-P22
14.6.10.65 | Bridge superstructure/ Gornji stroj mosta | 122959.06 | 36 |  | 0 | 0 | 0
14.6.10.66 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 13662.12 | 37 |  | 0 | 0 | 0
14.6.10.67 | P22-P23
14.6.10.68 | Bridge superstructure/ Gornji stroj mosta | 122959.06 | 36 |  | 0 | 0 | 0
14.6.10.69 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 13662.12 | 37 |  | 0 | 0 | 0
14.6.10.70 | P23-P24
14.6.10.71 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 37 |  | 0 | 0 | 0
14.6.10.72 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 38 |  | 0 | 0 | 0
14.6.10.73 | P24-P25
14.6.10.74 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 37 |  | 0 | 0 | 0
14.6.10.75 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 38 |  | 0 | 0 | 0
14.6.10.76 | P25-P26
14.6.10.77 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 38 |  | 0 | 0 | 0
14.6.10.78 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 39 |  | 0 | 0 | 0
14.6.10.79 | P26-P27
14.6.10.80 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 38 |  | 0 | 0 | 0
14.6.10.81 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 39 |  | 0 | 0 | 0
14.6.10.82 | P27-P28
14.6.10.83 | Bridge superstructure/ Gornji stroj mosta | 138267.21 | 39 |  | 0 | 0 | 0
14.6.10.84 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15363.02 | 40 |  | 0 | 0 | 0
14.6.10.85 | P28-A2
14.6.10.86 | Bridge superstructure/ Gornji stroj mosta | 118514.75 | 41 |  | 0 | 0 | 0
14.6.10.87 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 13168.47 | 42 |  | 0 | 0 | 0
14.6.11 | Bridge furniture/ Mosna estetika
14.6.11.1 | 50 m | 80531.07 | 41 |  | 0 | 0 | 0
14.6.11.2 | 100 m | 80531.07 | 41 |  | 0 | 0 | 0
14.6.11.3 | 150 m | 80531.07 | 41 |  | 0 | 0 | 0
14.6.11.4 | 200 m | 80531.07 | 41 |  | 0 | 0 | 0
14.6.11.5 | 250 m | 80531.07 | 41 |  | 0 | 0 | 0
14.6.11.6 | 300 m | 80531.07 | 41 |  | 0 | 0 | 0
14.6.11.7 | 350 m | 80531.07 | 41 |  | 0 | 0 | 0
14.6.11.8 | 400 m | 80531.07 | 42 |  | 0 | 0 | 0
14.6.11.9 | 450 m | 80531.07 | 42 |  | 0 | 0 | 0
14.6.11.10 | 500 m | 80531.07 | 42 |  | 0 | 0 | 0
14.6.11.11 | 550 m | 80531.07 | 42 |  | 0 | 0 | 0
14.6.11.12 | 600 m | 80531.07 | 42 |  | 0 | 0 | 0
14.6.11.13 | 650 m | 80531.07 | 42 |  | 0 | 0 | 0
14.6.11.14 | 700 m | 80531.07 | 42 |  | 0 | 0 | 0
14.6.11.15 | 750 m | 80531.07 | 42 |  | 0 | 0 | 0
14.6.11.16 | 784.4 m | 55405.05 | 42 |  | 0 | 0 | 0
14.6.12 | Waterproofing and asphalt works/ Hidroizolacija i asfaltni radovi
0-500 m
14.6.12.1 | Asphalt/Asfalt 1 + waterproofing/ hidroizolacija | 172964.11 | 41 |  | 0 | 0 | 0
14.6.12.2 | Asphalt/Asfalt 2 + joints/ spojnice | 43116.92 | 42 |  | 0 | 0 | 0
500-784.4 m
14.6.12.3 | Asphalt/Asfalt 1 + waterproofing/ hidroizolacija | 98381.98 | 42 |  | 0 | 0 | 0
14.6.12.4 | Asphalt/Asfalt 2 + joints/ spojnice | 24524.91 | 42 |  | 0 | 0 | 0
Left bridge/ Lijevi most
14.6.13.1 | Foundation piles/ Temeljni šipovi
14.6.13.1.1 | A1 |  | 18 |  | 0 | 0 | 0
14.6.13.1.2 | P1 | 117059.6554 | 18 | 27 | 117059.66 | 0 | 117059.66
14.6.13.1.3 | P2 | 117059.6554 | 18 | 28 | 117059.66 | 0 | 117059.66
14.6.13.1.4 | A2 | 257531.2418 | 18 | 28 | 257531.24 | 0 | 257531.24
14.6.13.2 | Foundation concrete/ Temeljni beton
14.6.13.2.1 | A1 | 68858.6208 | 20 |  | 0 | 0 | 0
14.6.13.2.2 | P1 | 68858.6208 | 21 | 29 | 68858.6208 | 0 | 68858.6208
14.6.13.2.3 | P2 | 68858.6208 | 22 | 30 | 0 | 68858.6208 | 68858.6208
14.6.13.2.4 | A2 | 162506.3451 | 23 | 30 | 0 | 162506.3451 | 162506.3451
14.6.14 | Abutments and Piers elevation/ Elevacija mosnih stubova
14.6.14.1 | A1 | 195377.41 | 25 |  | 0 | 0 | 0
14.6.14.2 | P1 stage 1 (1.2m) | 6394.1994 | 26 |  | 0 | 0 | 0
14.6.14.3 | P1 stage 2 (2m) | 10656.999 | 26 |  | 0 | 0 | 0
14.6.14.4 | P1 stage 3 (3.6m) | 19182.5982 | 26 |  | 0 | 0 | 0
14.6.14.5 | P1 stage 4 (2m) | 10656.999 | 26 |  | 0 | 0 | 0
14.6.14.6 | P1 stage 5 (1.33m) | 7086.9043 | 26 |  | 0 | 0 | 0
14.6.14.7 | P2 stage 1 (2.7m) | 14386.9487 | 27 |  | 0 | 0 | 0
14.6.14.8 | P2 stage 2 (2m) | 10656.999 | 27 |  | 0 | 0 | 0
14.6.14.9 | P2 stage 3 (2.1m) | 11189.849 | 27 |  | 0 | 0 | 0
14.6.14.10 | P2 stage 4 (2m) | 10656.999 | 27 |  | 0 | 0 | 0
14.6.14.11 | P2 stage 5 (1.33m) | 7086.9043 | 27 |  | 0 | 0 | 0
14.6.14.12 | A2 | 195377.41 | 28 |  | 0 | 0 | 0
14.6.15 | Spans/ Rasponi
14.6.15.1 | A1-P1
14.6.15.2 | Bridge superstructure/ Gornji stroj mosta | 158698.61 | 28 |  | 0 | 0 | 0
14.6.15.3 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 17633.18 | 29 |  | 0 | 0 | 0
14.6.15.4 | P1-P2
14.6.15.5 | Bridge superstructure/ Gornji stroj mosta | 201980.05 | 29 |  | 0 | 0 | 0
14.6.15.6 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 22442.23 | 30 |  | 0 | 0 | 0
14.6.15.7 | P2-A2
14.6.15.8 | Bridge superstructure/ Gornji stroj mosta | 158698.61 | 30 |  | 0 | 0 | 0
14.6.15.9 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 17633.2 | 31 |  | 0 | 0 | 0
14.6.16 | Bridge furniture/ Mosna estetika
14.6.16.1 | 50 m | 91922.13 | 41 |  | 0 | 0 | 0
14.6.16.2 | 72 m | 40445.71 | 42 |  | 0 | 0 | 0
14.6.17 | Waterproofing, joints and Asphalt Works/ Hidroizolacija, spojnice i asfaltni radovi
14.6.17.1 | asphalt layer 1 including waterproofing/sloj asfalta 1 uključujući hidroizolaciju | 38201.94 | 41 |  | 0 | 0 | 0
14.6.17.2 | asphalt layer 2 including joints/sloj asfalta 2 uključujući spojnice | 63741.62 | 42 |  | 0 | 0 | 0
| Sub Total / Suma stavke 14.6 | 29314076.39 |  |  | 12834732.9264 | 1990649.4717 | 14825382.3981
Cost center/ Troškovno mjesto 14.7 | Road Works/ Radovi na putevima (LK37+617.087 —LK37+733.287)
Completion of/Završetak:
14.7.1 | Subgrade/ Posteljica
14.7.1.1 | Top soil removal/ Uklanjanje humusa
14.7.1.1.1 | LK37+617.087—LK37+733.287 (Inc.0 - 116.200 m (LK)) | 15984.24 | 18 |  | 0 | 0 | 0
14.7.1.2 | Earthworks/ Zemljani radovi |  | 35
At every 250 m 4m height/Na svakih 250m i određenoj 4m visini
14.7.1.2.1 | Embankment LK37+617.087—LK37+733.287 Layers 1,2,3,4,5,6,7
14.7.1.2.1.1 | LK37+617.087—LK37+733.287 Layer 1 | 33990.1378 |  |  | 0 | 0 | 0
14.7.1.2.1.2 | LK37+617.087—LK37+733.287 Layer 2 | 33990.1378 |  |  | 0 | 0 | 0
14.7.1.2.1.3 | LK37+617.087—LK37+733.287 Layer 3 | 33990.1378 |  |  | 0 | 0 | 0
14.7.1.2.1.4 | LK37+617.087—LK37+733.287 Layer 4 | 33990.1378 |  |  | 0 | 0 | 0
14.7.1.2.1.5 | LK37+617.087—LK37+733.287 Layer 5 | 33990.1378 |  |  | 0 | 0 | 0
14.7.1.2.1.6 | LK37+617.087—LK37+733.287 Layer 6 | 33990.1378 |  |  | 0 | 0 | 0
14.7.1.2.1.7 | LK37+617.087—LK37+733.287 Layer 7 | 22943.343 |  |  | 0 | 0 | 0
14.7.1.3 | Road Foundation/ Temelj puta
14.7.1.3.1 | 0 - 116.200 m, left side/ lijeva strana | 17290.61 | 40 |  | 0 | 0 | 0
14.7.2 | Engineering structures/ Inženjerske konstrukcije |  | 31
14.7.2.1 | 80% for the concrete wall, the milestone is 50m lenth, no matter the hight+ 5% for the "after work" the whole lenth of each retaining wall + 5% for the "correction of the crown" the whole lenth of each retaining wall+10% for the "wall surface" the whole lenth of each retaining wall / 80% za betonski zid, reper je 50 m dužine, bez obzira na visinu + 5% za "kasnije radove" čitava dužina potpornog zida + 5% za "popravku krune zida" čitava dužina potpornog zida+10% za obradu površinu čitave dužine potpornog zida
14.7.2.1.1 | Concrete wall/ Betonski zid LK37+621.5 - RKLK37+728.88 (107.38m),
14.7.2.1.1.1 | Layer 1, LK37+621.5 - LK37+671.5 - 80% (50m) | 59616.8337 |  |  | 0 | 0 | 0
14.7.2.1.1.2 | Layer 2,LK37+671.5 - LK37+721.5 - 80% (50m) | 59616.8337 |  |  | 0 | 0 | 0
14.7.2.1.1.3 | Layer 3, LK37+721.5 - LK37+728.88 - 80% (7.38m) | 8799.4447 |  |  | 0 | 0 | 0
14.7.2.1.1.4 | Concrete wall/ Betonski zid LK37+621.5 - RKLK37+728.88 - After work 5% | 8002.0695 |  |  | 0 | 0 | 0
14.7.2.1.1.5 | Concrete wall/ Betonski zid LK37+621.5 - RKLK37+728.88 - Correction of the crown 5% | 8002.0695 |  |  | 0 | 0 | 0
14.7.2.1.1.6 | Concrete wall/ Betonski zid LK37+621.5 - RKLK37+728.88 - 10% Wall surface | 16004.139 |  |  | 0 | 0 | 0
14.7.3 | Water drainage/ Drenaža vode
per one direction of 500m /Na 500m dužine u jednom pravcu
14.7.3.1 | LK37+617.087—LK37+733.287 (116.20 m) | 41031.73 | 40 |  | 0 | 0 | 0
14.7.4 | Pavement structure/ Kolovozna konstrukcija |  | 40 |  | 0 | 0 | 0
14.7.4.1 | asphalt concrete layer/ sloj asfaltnog betona 1 left side/ lijeva strana | 11671.3 | 41 |  | 0 | 0 | 0
14.7.4.2 | asphalt concrete layer/ sloj asfaltnog betona 2 left side/ lijeva strana | 11671.3 | 42 |  | 0 | 0 | 0
14.7.4.3 | asphalt concrete layer/ sloj asfaltnog betona 3 left side/ lijeva strana | 12968.88 | 43 |  | 0 | 0 | 0
| Sub Total / Suma stavke 14.7 | 497543.62 |  |  | 0 | 0 | 0
| TOTAL COST CENTER / UKUPNO TROSKOVNI CENTAR 14 | 43785963.75 |  |  | 12929414.6964 | 2024875.1065 | 14954289.8029

## COST CENTER 15
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
| COST CENTER 15//TROŠKOVNI CENTAR 15 | rev Bridge Piers
Cost center No./ Troškovno mjesto Br. | 15 | Subsection/ Podsekcija 4.4 (LK38+309.087-LK40+798.773 RK38+366.284-RK40+817.854)
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost center/ Troškovno mjesto 15.1 | Road Works/Radovi na putevima (LK38+309.087—LK38+381.440, RK38+366.284—RK38+675.997)
Completion of/Završetak:
15.1.1 | Subgrade/ Posteljica
15.1.1.1 | Top soil removal/ Uklanjanje humusa
15.1.1.1.1 | 0 - 72.353 m (LK); 0 - 309.713 m (RK) | 73255.88 | 19 |  | 0 | 0 | 0
15.1.1.2 | Earthworks/Zemljani radovi
| At every 250 m and certain high (after MD approval)/Na svakih 250m i određenoj visini (nakon odobrenja GP) | 1039811.46 | 33 |  | 0 | 0 | 0
15.1.1.3 | Road Foundation/Temelj puta
15.1.1.3.1 | right side/ desna strana | 39621.49 | 34 |  | 0 | 0 | 0
15.1.1.3.2 | left side/ lijeva strana | 39621.48 | 35 |  | 0 | 0 | 0
15.1.2 | Engineering structures/Inženjerske konstrukcije
15.1.2.1 | Concrete wall (it will be splitted after MD approval)/ Betonski zid (biće podijeljen nakon odobrenja GP) |  | 25
95% for the concrete wall, the milestone is 50m lenth, no matter the hight; 5% for the "after work" the whole lenth of each retaining wall / 95% za betonski zid, reper je 50 m dužine, bez obzira na visinu; 5% za "kasnije radove" čitava dužina potpornog zida
15.1.2.1.1 | Concrete wall/ Betonski zid LK38+315.0 - LK38+430.0 (115m)
15.1.2.1.1.1 | Layer 1, LK38+315.0 - LK38+365.0 - 95% (50m) | 6727.119 |  |  | 0 | 0 | 0
15.1.2.1.1.2 | Layer 2, LK38+365.0 - LK38+415.0 - 95% (50m) | 6727.119 |  |  | 0 | 0 | 0
15.1.2.1.1.3 | Layer 3, LK38+415.0 - LK38+430.0 - 95% (15m) | 2018.1357 |  |  | 0 | 0 | 0
15.1.2.1.1.4 | Concrete wall/ Betonski zid LK38+315.0 - LK38+430.0 - After work 5% | 814.3355 |  |  | 0 | 0 | 0
15.1.2.1.2 | Concrete wall/ Betonski zid LK38+314.94 - LK38+325.93 (11m)
15.1.2.1.2.1 | Concrete wall/ Betonski zid LK38+314.94 - LK38+325.93 - 95% | 1479.9662 |  |  | 0 | 0 | 0
15.1.2.1.2.2 | Concrete wall/ Betonski zid LK38+314.94 - LK38+325.93 - After work 5% | 77.893 |  |  | 0 | 0 | 0
15.1.2.1.3 | Concrete wall/ Betonski zid RK38+372.14 - RK38+383.0 (14.5m)
15.1.2.1.3.1 | Concrete wall/ Betonski zid RK38+372.14 - RK38+383.0 - 95% | 1950.8645 |  |  | 0 | 0 | 0
15.1.2.1.3.2 | Concrete wall/ Betonski zid RK38+372.14 - RK38+383.0 - After work 5% | 102.6771 |  |  | 0 | 0 | 0
15.1.3 | Water drainage/ Drenaža vode
15.1.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 188048.65 | 36 |  | 0 | 0 | 0
15.1.4 | Pavement structure/ Kolovozna konstrukcija
15.1.4.1 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana | 10129.4939 | 44 |  | 0 | 0 | 0
15.1.4.2 | asphalt concrete layer/ sloj asfaltnog betona 1 left side/ lijeva strana | 43360.1361 | 44 |  | 0 | 0 | 0
15.1.4.3 | asphalt concrete layer/ sloj asfaltnog betona 2 right side/ desna strana | 10129.4939 | 45 |  | 0 | 0 | 0
15.1.4.4 | asphalt concrete layer/ sloj asfaltnog betona 2 left side/ lijeva strana | 43360.1361 | 45 |  | 0 | 0 | 0
15.1.4.5 | asphalt concrete layer/ sloj asfaltnog betona 3 right side/ desna strana | 11255.6612 | 46 |  | 0 | 0 | 0
15.1.4.6 | asphalt concrete layer/ sloj asfaltnog betona 3 left side/ lijeva strana | 48180.7888 | 46 |  | 0 | 0 | 0
| Sub Total / Suma stavke 15.1 | 1566672.78 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 15.2 | Construction of Matesevo interchange/ Izgradnja petlje Mateševo ( LK38+381.440- LK 39+188.394, RK 38+675.997- RK 39.246.583)
Completion of/Završetak:
15.2.1 | Subgrade/ Posteljica
15.2.1.1 | Top soil removal/ Uklanjanje humusa
15.2.1.1.1 | 0 - 250 m (LK&RK) | 88447.9543 | 19 |  | 0 | 0 | 0
15.2.1.1.2 | 250 - 500 m (LK&RK) | 88447.9543 | 19 |  | 0 | 0 | 0
15.2.1.1.3 | 500 - 750 m (LK); 500 - 570.586 m (RK) | 56710.3518 | 19 |  | 0 | 0 | 0
15.2.1.1.4 | 750 - 806.954 m (LK) | 10074.9296 | 19 |  | 0 | 0 | 0
15.2.1.2 | Earthworks/Zemljani radovi
| At every 250 m and certain high (after MD approval)/Na svakih 250m i određenoj visini (nakon odobrenja GP) | 3458868.82 | 35 |  | 0 | 0 | 0
15.2.1.3 | Road Foundation/ Temelj puta
15.2.1.3.1 | 0 - 250 m right side/ desna strana | 47838.335 | 36 |  | 0 | 0 | 0
15.2.1.3.2 | 0 - 250 m left side/ lijeva strana | 47838.335 | 36 |  | 0 | 0 | 0
15.2.1.3.3 | 250 - 500 m right side/ desna strana | 47838.335 | 37 |  | 0 | 0 | 0
15.2.1.3.4 | 250 - 500 m left side/ lijeva strana | 47838.335 | 37 |  | 0 | 0 | 0
15.2.1.3.5 | 500 - 570.586 m right side/ desna strana | 13506.8669 | 38 |  | 0 | 0 | 0
15.2.1.3.6 | 500 - 750 m left side/ lijeva strana | 47838.335 | 38 |  | 0 | 0 | 0
15.2.1.3.7 | 750 - 806.954 m left side/ lijeva strana | 10898.3381 | 38 |  | 0 | 0 | 0
15.2.2 | Water drainage/ Drenaža vode
15.2.2.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 625532.26 | 38 |  | 0 | 0 | 0
15.2.3 | Pavement structure/ Kolovozna konstrukcija
15.2.3.1 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana 0-500m | 64582.5021 | 43 |  | 0 | 0 | 0
15.2.3.2 | asphalt concrete layer/ sloj asfaltnog betona 1 left side/ lijeva strana 0-500m | 64582.5021 | 43 |  | 0 | 0 | 0
15.2.3.3 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana 500-570.586m | 9117.241 | 44 |  | 0 | 0 | 0
15.2.3.4 | asphalt concrete layer/ sloj asfaltnog betona 1 left side/ lijeva strana 500-806.954m | 39647.7147 | 44 |  | 0 | 0 | 0
15.2.3.5 | asphalt concrete layer/ sloj asfaltnog betona 2 right side/ desna strana 0-500m | 64582.5021 | 45 |  | 0 | 0 | 0
15.2.3.6 | asphalt concrete layer/ sloj asfaltnog betona 2 left side/ lijeva strana 0-500m | 64582.5021 | 45 |  | 0 | 0 | 0
15.2.3.7 | asphalt concrete layer/ sloj asfaltnog betona 2 right side/ desna strana 500-570.586m | 9117.241 | 46 |  | 0 | 0 | 0
15.2.3.8 | asphalt concrete layer/ sloj asfaltnog betona 2 left side/ lijeva strana 500-806.954m | 39647.7147 | 46 |  | 0 | 0 | 0
15.2.3.9 | asphalt concrete layer/ sloj asfaltnog betona 3 right side/ desna strana 0-500m | 71762.5985 | 47 |  | 0 | 0 | 0
15.2.3.10 | asphalt concrete layer/ sloj asfaltnog betona 3 left side/ lijeva strana 0-500m | 71762.5985 | 47 |  | 0 | 0 | 0
15.2.3.11 | asphalt concrete layer/ sloj asfaltnog betona 3 right side/ desna strana 500-570.586m | 10130.8696 | 48 |  | 0 | 0 | 0
15.2.3.12 | asphalt concrete layer/ sloj asfaltnog betona 3 left side/ lijeva strana 500-806.954m | 44055.6333 | 48 |  | 0 | 0 | 0
Overpasses/ Nadvožnjaci
15.2.4 | Matesevo #1
Foundation piles/ Temeljni šipovi
15.2.4.1 | A1 | 140678.56 | 27 |  | 0 | 0 | 0
15.2.4.2 | A2 | 140678.56 | 27 |  | 0 | 0 | 0
Foundation concrete/ Temeljni beton
15.2.4.3 | A1 | 97782.82 | 28 |  | 0 | 0 | 0
15.2.4.4 | A2 | 69607.64 | 29 |  | 0 | 0 | 0
Abutments and Piers elevation/ Elevacija mosnih stubova
15.2.4.5 | A1 | 153932.24 | 28 |  | 0 | 0 | 0
15.2.4.6 | A2 | 153932.24 | 29 |  | 0 | 0 | 0
Bridge deck superstructure/ Gornji stroj mosne ploče
A1-A2
15.2.4.7 | Bridge superstructure/ Gornji stroj mosta | 269760.55 | 30 |  | 0 | 0 | 0
15.2.4.8 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 29973.39 | 30 |  | 0 | 0 | 0
Bridge furniture/ Mosna estetika
15.2.4.9 | 28 m | 50783.97 | 31 |  | 0 | 0 | 0
Waterproofing and asphalt works/ Hidroizolacija i asfaltni radovi
15.2.4.10 | asphalt layer/ asfaltni sloj 1 + waterproofing/ hidroizolacija | 20870.78 | 31 |  | 0 | 0 | 0
15.2.4.11 | asphalt layer/ asfaltni sloj 2 + joints/ spojnice | 74063.06 | 31 |  | 0 | 0 | 0
15.2.5 | Matesevo #2
Foundation piles/ Temeljni šipovi
15.2.5.1 | A1 | 78244.92 | 32 |  | 0 | 0 | 0
15.2.5.2 | P1 | 81508.25 | 33 |  | 0 | 0 | 0
15.2.5.3 | P2 | 81508.25 | 33 |  | 0 | 0 | 0
15.2.5.4 | P3 | 81508.25 | 34 |  | 0 | 0 | 0
15.2.5.5 | P4 | 81508.26 | 34 |  | 0 | 0 | 0
15.2.5.6 | P5
15.2.5.7 | A2
Foundation concrete/ Temeljni beton
15.2.5.8 | A1 | 58376.14 | 33 |  | 0 | 0 | 0
15.2.5.9 | P1 | 29502.22 | 34 |  | 0 | 0 | 0
15.2.5.10 | P2 | 29502.22 | 34 |  | 0 | 0 | 0
15.2.5.11 | P3 | 29502.22 | 35 |  | 0 | 0 | 0
15.2.5.12 | P4 | 29502.22 | 35 |  | 0 | 0 | 0
15.2.5.13 | P5 | 34419.25 | 36 |  | 0 | 0 | 0
15.2.5.14 | A2 | 36484.38 | 36 |  | 0 | 0 | 0
Abutments and Piers elevation/ Elevacija mosnih stubova
15.2.5.15 | A1 | 203808.36 | 34
15.2.5.16 | P1 stage 1 (6m) | 20521.7041 | 35 |  | 0 | 0 | 0
15.2.5.17 | P1 stage 2 (6m) | 20521.7041 | 36 |  | 0 | 0 | 0
15.2.5.18 | P1 stage 3 (0.932m) | 3187.7047 | 36 |  | 0 | 0 | 0
15.2.5.19 | P2 stage 1 (6m) | 20521.7041 | 36 |  | 0 | 0 | 0
15.2.5.20 | P2 stage 2 (6m) | 20521.7041 | 36 |  | 0 | 0 | 0
15.2.5.21 | P2 stage 3 (1.98m) | 6772.1624 | 37 |  | 0 | 0 | 0
15.2.5.22 | P3 stage 1 (6m) | 20521.7041 | 37 |  | 0 | 0 | 0
15.2.5.23 | P3 stage 2 (6m) | 20521.7041 | 37 |  | 0 | 0 | 0
15.2.5.24 | P3 stage 3 (3.22m) | 11013.3145 | 38 |  | 0 | 0 | 0
15.2.5.25 | P4 stage 1 (6m) | 20521.7041 | 37 |  | 0 | 0 | 0
15.2.5.26 | P4 stage 2 (6m) | 20521.7041 | 38 |  | 0 | 0 | 0
15.2.5.27 | P4 stage 3 (2.59m) | 8858.5356 | 38 |  | 0 | 0 | 0
15.2.5.28 | P5 stage 1 (6m) | 20521.7041 | 37 |  | 0 | 0 | 0
15.2.5.29 | P5 stage 2 (6m) | 20521.7041 | 38 |  | 0 | 0 | 0
15.2.5.30 | P5 stage 3 (1.59m) | 5438.2516 | 38 |  | 0 | 0 | 0
15.2.5.31 | A2 | 141231.81 | 38 |  | 0 | 0 | 0
Spans/ Rasponi
A1-P1
15.2.5.27 | Bridge superstructure/ Gornji stroj mosta | 67023.78 | 35 |  | 0 | 0 | 0
15.2.5.28 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 7447.09 | 36 |  | 0 | 0 | 0
P1-P2
15.2.5.29 | Bridge superstructure/ Gornji stroj mosta | 89365.04 | 36 |  | 0 | 0 | 0
15.2.5.30 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 9929.45 | 37 |  | 0 | 0 | 0
P2-P3
15.2.5.31 | Bridge superstructure/ Gornji stroj mosta | 89365.04 | 37 |  | 0 | 0 | 0
15.2.5.32 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 9929.45 | 38 |  | 0 | 0 | 0
P3-P4
15.2.5.33 | Bridge superstructure/ Gornji stroj mosta | 89365.04 | 38 |  | 0 | 0 | 0
15.2.5.34 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 9929.45 | 39 |  | 0 | 0 | 0
P4-P5
15.2.5.35 | Bridge superstructure/ Gornji stroj mosta | 89365.04 | 39 |  | 0 | 0 | 0
15.2.5.36 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 9929.45 | 40 |  | 0 | 0 | 0
P5-A2
15.2.5.37 | Bridge superstructure/ Gornji stroj mosta | 67023.78 | 40 |  | 0 | 0 | 0
15.2.5.38 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 7447.09 | 40 |  | 0 | 0 | 0
Bridge furniture/ Mosna estetika
15.2.5.39 | 50 m | 55217.28 | 39 |  | 0 | 0 | 0
15.2.5.40 | 100 m | 55217.28 | 39 |  | 0 | 0 | 0
15.2.5.41 | 150 m | 55217.28 | 40 |  | 0 | 0 | 0
15.2.5.42 | 176 m | 28713.01 | 40 |  | 0 | 0 | 0
Waterproofing and asphalt works/ Hidroizolacija i asfaltni radovi
15.2.5.43 | asphalt layer/ asfaltni sloj 1 + waterproofing/ hidroizolacija | 45595.3 | 40 |  | 0 | 0 | 0
15.2.5.44 | asphalt layer/ asfaltni sloj 2 + joints/ spojnice | 52467.22 | 40 |  | 0 | 0 | 0
| Sub Total / Suma stavke 15.2 | 8422955.41 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 15.3 | Construction of bridge/ Izgradnja mosta Tara 1 (LK 38+646.087- LK 38+880.087, RK 38+686.584- RK 38+920.584)
Completion of/Završetak:
Left bridge/ Lijevi most
15.3.1 | Foundation piles/ Temeljni šipovi
15.3.1.1 | A1 | 93791.03 | 19 |  | 0 | 0 | 0
15.3.1.2 | P1 | 62527.35 | 20 |  | 0 | 0 | 0
15.3.1.3 | P2 | 62527.35 | 21 |  | 0 | 0 | 0
15.3.1.4 | P3 | 62527.35 | 22 |  | 0 | 0 | 0
15.3.1.5 | P4 | 62527.35 | 23 |  | 0 | 0 | 0
15.3.1.6 | P5 | 62527.35 | 23 |  | 0 | 0 | 0
15.3.1.7 | P6 | 62527.35 | 24 |  | 0 | 0 | 0
15.3.1.8 | A2 | 93791.03 | 24 |  | 0 | 0 | 0
15.3.2 | Foundation concrete/ Temeljni beton
15.3.2.1 | A1 | 77551.28 | 20 |  | 0 | 0 | 0
15.3.2.2 | P1 | 47000.78 | 21 |  | 0 | 0 | 0
15.3.2.3 | P2 | 47000.78 | 22 |  | 0 | 0 | 0
15.3.2.4 | P3 | 47000.78 | 23 |  | 0 | 0 | 0
15.3.2.5 | P4 | 47000.78 | 24 |  | 0 | 0 | 0
15.3.2.6 | P5 | 47000.78 | 25 |  | 0 | 0 | 0
15.3.2.7 | P6 | 47000.78 | 26 |  | 0 | 0 | 0
15.3.2.8 | A2 | 77551.24 | 26 |  | 0 | 0 | 0
15.3.3 | Abutments and Piers elevation/ Elevacija mosnih stubova
15.3.3.1 | A1 | 92765.6 | 21 |  | 0 | 0 | 0
15.3.3.2 | P1 stage 1 (6m) | 25670.1271 | 22 |  | 0 | 0 | 0
15.3.3.3 | P1 stage 2 (4.87m) | 20835.5865 | 22 |  | 0 | 0 | 0
15.3.3.4 | P2 stage 1 (6m) | 25670.1271 | 23 |  | 0 | 0 | 0
15.3.3.5 | P2 stage 2 (6m) | 25670.1271 | 23 |  | 0 | 0 | 0
15.3.3.6 | P2 stage 3 (3.37m) | 14418.0547 | 24 |  | 0 | 0 | 0
15.3.3.7 | P3 stage 1 (6m) | 25670.1271 | 25 |  | 0 | 0 | 0
15.3.3.8 | P3 stage 2 (6m) | 25670.1271 | 25 |  | 0 | 0 | 0
15.3.3.9 | P3 stage 3 (6m) | 25670.1271 | 26 |  | 0 | 0 | 0
15.3.3.10 | P3 stage 4 (5.87m) | 25113.941 | 26 |  | 0 | 0 | 0
15.3.3.11 | P4 stage 1 (6m) | 25670.1271 | 27 |  | 0 | 0 | 0
15.3.3.12 | P4 stage 2 (6m) | 25670.1271 | 27 |  | 0 | 0 | 0
15.3.3.13 | P4 stage 3 (2.87m) | 12278.8775 | 27 |  | 0 | 0 | 0
15.3.3.14 | P5 stage 1 (6m) | 25670.1271 | 28 |  | 0 | 0 | 0
15.3.3.15 | P5 stage 2 (6m) | 25670.1271 | 28 |  | 0 | 0 | 0
15.3.3.16 | P5 stage 3 (2.87m) | 12278.8775 | 29 |  | 0 | 0 | 0
15.3.3.17 | P6 stage 1 (6m) | 25670.1271 | 29 |  | 0 | 0 | 0
15.3.3.18 | P6 stage 2 (6m) | 25670.1271 | 29 |  | 0 | 0 | 0
15.3.3.19 | P6 stage 3 (2.87m) | 12278.8775 | 30 |  | 0 | 0 | 0
15.3.3.20 | A2 | 247654.76 | 30 |  | 0 | 0 | 0
15.3.4 | Spans/ Rasponi
15.3.4.1 | A1-P1
15.3.4.2 | Bridge superstructure/ Gornji stroj mosta | 199575.17 | 25 |  | 0 | 0 | 0
15.3.4.3 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 22175.02 | 26 |  | 0 | 0 | 0
15.3.4.4 | P1-P2
15.3.4.5 | Bridge superstructure/ Gornji stroj mosta | 242341.28 | 26 |  | 0 | 0 | 0
15.3.4.6 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 26926.81 | 27 |  | 0 | 0 | 0
15.3.4.7 | P2-P3
15.3.4.8 | Bridge superstructure/ Gornji stroj mosta | 242341.28 | 27 |  | 0 | 0 | 0
15.3.4.9 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 26926.81 | 28 |  | 0 | 0 | 0
15.3.4.10 | P3-P4
15.3.4.11 | Bridge superstructure/ Gornji stroj mosta | 299362.76 | 28 |  | 0 | 0 | 0
15.3.4.12 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 33262.53 | 29 |  | 0 | 0 | 0
15.3.4.13 | P4-P5
15.3.4.14 | Bridge superstructure/ Gornji stroj mosta | 242341.28 | 29 |  | 0 | 0 | 0
15.3.4.15 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 26926.81 | 30 |  | 0 | 0 | 0
15.3.4.16 | P5-P6
15.3.4.17 | Bridge superstructure/ Gornji stroj mosta | 242341.28 | 30 |  | 0 | 0 | 0
15.3.4.18 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 26926.81 | 31 |  | 0 | 0 | 0
15.3.4.19 | P6-A2
15.3.4.20 | Bridge superstructure/ Gornji stroj mosta | 199575.17 | 31 |  | 0 | 0 | 0
15.3.4.21 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 22174.97 | 32 |  | 0 | 0 | 0
15.3.5 | Bridge furniture/ Mosna estetika
15.3.5.1 | 50 m | 74451.56 | 33 |  | 0 | 0 | 0
15.3.5.2 | 100 m | 74451.56 | 34 |  | 0 | 0 | 0
15.3.5.3 | 150 m | 74451.56 | 35 |  | 0 | 0 | 0
15.3.5.4 | 200 m | 74451.56 | 36 |  | 0 | 0 | 0
15.3.5.5 | 234 m | 50627.14 | 36 |  | 0 | 0 | 0
15.3.6 | Waterproofing and asphalt works/ Hidroizolacija i asfaltni radovi
15.3.6.1 | Asphalt/Asfalt 1 + waterproofing/ hidroizolacija | 104632.82 | 36 |  | 0 | 0 | 0
15.3.6.2 | Asphalt/Asfalt 2 + joints/ spojnice | 91822.72 | 36 |  | 0 | 0 | 0
Right bridge/ Desni most
15.3.7 | Foundation piles/ Temeljni šipovi
15.3.7.1 | A1 | 99510.72 | 19 |  | 0 | 0 | 0
15.3.7.2 | P1 | 66340.48 | 20 |  | 0 | 0 | 0
15.3.7.3 | P2 | 66340.48 | 21 |  | 0 | 0 | 0
15.3.7.4 | P3 | 66340.48 | 22 |  | 0 | 0 | 0
15.3.7.5 | P4 | 66340.48 | 23 |  | 0 | 0 | 0
15.3.7.6 | P5 | 66340.48 | 23 |  | 0 | 0 | 0
15.3.7.7 | P6 | 66340.48 | 24 |  | 0 | 0 | 0
15.3.7.8 | A2 | 99510.72 | 24 |  | 0 | 0 | 0
15.3.8 | Foundation concrete/ Temeljni beton
15.3.8.1 | A1 | 88966.29 | 20 |  | 0 | 0 | 0
15.3.8.2 | P1 | 53918.96 | 21 |  | 0 | 0 | 0
15.3.8.3 | P2 | 53918.96 | 22 |  | 0 | 0 | 0
15.3.8.4 | P3 | 53918.96 | 23 |  | 0 | 0 | 0
15.3.8.5 | P4 | 53918.96 | 24 |  | 0 | 0 | 0
15.3.8.6 | P5 | 53918.96 | 25 |  | 0 | 0 | 0
15.3.8.7 | P6 | 53918.96 | 26 |  | 0 | 0 | 0
15.3.8.8 | A2 | 126324.43 | 26 |  | 0 | 0 | 0
15.3.9 | Abutments and Piers elevation/ Elevacija mosnih stubova
15.3.9.1 | A1 | 140158.81 | 21 |  | 0 | 0 | 0
15.3.9.2 | P1 stage 1 (6m) | 30381.9029 | 22 |  | 0 | 0 | 0
15.3.9.3 | P1 stage 2 (5.14m) | 26027.1635 | 22 |  | 0 | 0 | 0
15.3.9.4 | P2 stage 1 (6m) | 30381.9029 | 23 |  | 0 | 0 | 0
15.3.9.5 | P2 stage 2 (6m) | 30381.9029 | 23 |  | 0 | 0 | 0
15.3.9.6 | P2 stage 3 (3.14m) | 15899.8625 | 24 |  | 0 | 0 | 0
15.3.9.7 | P3 stage 1 (6m) | 30381.9029 | 25 |  | 0 | 0 | 0
15.3.9.8 | P3 stage 2 (6m) | 30381.9029 | 25 |  | 0 | 0 | 0
15.3.9.9 | P3 stage 3 (6m) | 30381.9029 | 26 |  | 0 | 0 | 0
15.3.9.10 | P3 stage 4 (0.14m) | 708.9111 | 26 |  | 0 | 0 | 0
15.3.9.11 | P4 stage 1 (6m) | 30381.9029 | 27 |  | 0 | 0 | 0
15.3.9.12 | P4 stage 2 (6m) | 30381.9029 | 27 |  | 0 | 0 | 0
15.3.9.13 | P4 stage 3 (3.64m) | 18431.6878 | 28 |  | 0 | 0 | 0
15.3.9.14 | P5 stage 1 (6m) | 30381.9029 | 29 |  | 0 | 0 | 0
15.3.9.15 | P5 stage 2 (6m) | 30381.9029 | 29 |  | 0 | 0 | 0
15.3.9.16 | P5 stage 3 (3.14m) | 15899.8625 | 30 |  | 0 | 0 | 0
15.3.9.17 | P6 stage 1 (6m) | 30381.9029 | 29 |  | 0 | 0 | 0
15.3.9.18 | P6 stage 2 (6m) | 30381.9029 | 29 |  | 0 | 0 | 0
15.3.9.19 | P6 stage 3 (2.64m) | 13368.0373 | 30 |  | 0 | 0 | 0
15.3.9.20 | A2 | 502791.93 | 30 |  | 0 | 0 | 0
15.3.10 | Spans/ Rasponi
15.3.10.1 | A1-P1
15.3.10.2 | Bridge superstructure/ Gornji stroj mosta | 192493.47 | 25 |  | 0 | 0 | 0
15.3.10.3 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 21388.16 | 26 |  | 0 | 0 | 0
15.3.10.4 | P1-P2
15.3.10.5 | Bridge superstructure/ Gornji stroj mosta | 233742.08 | 26 |  | 0 | 0 | 0
15.3.10.6 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 25971.34 | 27 |  | 0 | 0 | 0
15.3.10.7 | P2-P3
15.3.10.8 | Bridge superstructure/ Gornji stroj mosta | 233742.08 | 27 |  | 0 | 0 | 0
15.3.10.9 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 25971.34 | 28 |  | 0 | 0 | 0
15.3.10.10 | P3-P4
15.3.10.11 | Bridge superstructure/ Gornji stroj mosta | 288740.21 | 28 |  | 0 | 0 | 0
15.3.10.12 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 32082.25 | 29 |  | 0 | 0 | 0
15.3.10.13 | P4-P5
15.3.10.14 | Bridge superstructure/ Gornji stroj mosta | 233742.08 | 29 |  | 0 | 0 | 0
15.3.10.15 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 25971.34 | 30 |  | 0 | 0 | 0
15.3.10.16 | P5-P6
15.3.10.17 | Bridge superstructure/ Gornji stroj mosta | 233742.08 | 30 |  | 0 | 0 | 0
15.3.10.18 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 25971.34 | 31 |  | 0 | 0 | 0
15.3.10.19 | P6-A2
15.3.10.20 | Bridge superstructure/ Gornji stroj mosta | 192493.47 | 31 |  | 0 | 0 | 0
15.3.10.21 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 21388.18 | 32 |  | 0 | 0 | 0
15.3.11 | Bridge furniture/ Mosna estetika
15.3.11.1 | 50 m | 64314.46 | 33 |  | 0 | 0 | 0
15.3.11.2 | 100 m | 64314.46 | 34 |  | 0 | 0 | 0
15.3.11.3 | 150 m | 64314.46 | 35 |  | 0 | 0 | 0
15.3.11.4 | 200 m | 64314.46 | 36 |  | 0 | 0 | 0
15.3.11.5 | 234 m | 43733.85 | 36 |  | 0 | 0 | 0
15.3.12 | Waterproofing and asphalt works/ Hidroizolacija i asfaltni radovi
15.3.12.1 | Asphalt/Asfalt 1 + waterproofing/ hidroizolacija | 118120.61 | 36 |  | 0 | 0 | 0
15.3.12.2 | Asphalt/Asfalt 2 + joints/ spojnice | 90663.07 | 36 |  | 0 | 0 | 0
| Sub Total / Suma stavke 15.3 | 8674559.05 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 15.4 | Road Works/ Radovi na putevima (LK39+188.394—LK39+376.887, RK39+246.583—RK39+436.384)
Completion of/Završetak:
15.4.1 | Subgrade/ Posteljica
15.4.1.1 | Top soil removal/ Uklanjanje humusa
15.4.1.1.1 | 0 - 188.493 m (LK); 0 - 189.801 m (RK) | 97223.94 | 19 |  | 0 | 0 | 0
15.4.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and certain high (after MD approval)/Na svakih 250m i određenoj visini (nakon odobrenja GP) | 1380019.68 | 28 |  | 0 | 0 | 0
15.4.1.3 | Road Foundation/ Temelj puta
15.4.1.3.1 | 0 - 189.801 m, right side/ desna strana | 52584.95 | 39 |  | 0 | 0 | 0
15.4.1.3.2 | 0 - 188.493 m, left side/ lijeva strana | 52584.95 | 40 |  | 0 | 0 | 0
15.4.2 | Water drainage/ Drenaža vode
15.4.2.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 249574.9 | 36 |  | 0 | 0 | 0
15.4.3 | Pavement structure/ Kolovozna konstrukcija
15.4.3.1 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana | 35495.25 | 39 |  | 0 | 0 | 0
15.4.3.2 | asphalt concrete layer/ sloj asfaltnog betona 1 left side/ lijeva strana | 35495.25 | 40 |  | 0 | 0 | 0
15.4.3.3 | asphalt concrete layer/ sloj asfaltnog betona 2 right side/ desna strana | 35495.25 | 40 |  | 0 | 0 | 0
15.4.3.4 | asphalt concrete layer/ sloj asfaltnog betona 2 left side/ lijeva strana | 35495.25 | 40 |  | 0 | 0 | 0
15.4.3.5 | asphalt concrete layer/ sloj asfaltnog betona 3 right side/ desna strana | 39441.52 | 41 |  | 0 | 0 | 0
15.4.3.6 | asphalt concrete layer/ sloj asfaltnog betona 3 left side/ lijeva strana | 39441.51 | 41 |  | 0 | 0 | 0
| Sub Total / Suma stavke 15.4 | 2052852.45 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 15.5 | Construction of bridge/ Izgradnja mosta Tara 2 (LK39+376.887-LK 39+830.687, RK 39+436.384- RK 39+834.184)
Completion of/Završetak:
Left bridge/ Lijevi most
15.5.1 | Foundation piles/ Temeljni šipovi
15.5.1.1 | A1 | 126204.82 | 19 |  | 0 | 0 | 0
15.5.1.2 | P1 | 63096.46 | 20 |  | 0 | 0 | 0
15.5.1.3 | P2 | 63096.46 | 20 |  | 0 | 0 | 0
15.5.1.4 | P3 | 63096.46 | 21 |  | 0 | 0 | 0
15.5.1.5 | P4 | 63096.46 | 21 |  | 0 | 0 | 0
15.5.1.6 | P5 | 63096.46 | 21 |  | 0 | 0 | 0
15.5.1.7 | P6 | 63096.46 | 22 |  | 0 | 0 | 0
15.5.1.8 | P7 | 63096.46 | 22 |  | 0 | 0 | 0
15.5.1.9 | P8 | 63096.46 | 22 |  | 0 | 0 | 0
15.5.1.10 | P9 | 63096.46 | 23 |  | 0 | 0 | 0
15.5.1.11 | P10 | 63096.46 | 23 |  | 0 | 0 | 0
15.5.1.12 | P11 | 63096.46 | 23 |  | 0 | 0 | 0
15.5.1.13 | P12 | 63096.46 | 24 |  | 0 | 0 | 0
15.5.1.14 | P13 | 63096.46 | 24 |  | 0 | 0 | 0
15.5.1.15 | P14 | 63096.46 | 24 |  | 0 | 0 | 0
15.5.1.16 | P15 | 63096.42 | 24 |  | 0 | 0 | 0
15.5.1.17 | P16
15.5.1.18 | A2
15.5.2 | Foundation concrete/ Temeljni beton
15.5.2.1 | A1 | 262919.7 | 20 |  | 0 | 0 | 0
15.5.2.2 | P1 | 88624.62 | 21 |  | 0 | 0 | 0
15.5.2.3 | P2 | 88624.62 | 22 |  | 0 | 0 | 0
15.5.2.4 | P3 | 88624.62 | 23 |  | 0 | 0 | 0
15.5.2.5 | P4 | 88624.62 | 24 |  | 0 | 0 | 0
15.5.2.6 | P5 | 88624.62 | 24 |  | 0 | 0 | 0
15.5.2.7 | P6 | 88624.62 | 25 |  | 0 | 0 | 0
15.5.2.8 | P7 | 88624.62 | 25 |  | 0 | 0 | 0
15.5.2.9 | P8 | 88624.62 | 26 |  | 0 | 0 | 0
15.5.2.10 | P9 | 88624.62 | 26 |  | 0 | 0 | 0
15.5.2.11 | P10 | 88624.62 | 27 |  | 0 | 0 | 0
15.5.2.12 | P11 | 88624.62 | 27 |  | 0 | 0 | 0
15.5.2.13 | P12 | 88624.62 | 28 |  | 0 | 0 | 0
15.5.2.14 | P13 | 88624.62 | 28 |  | 0 | 0 | 0
15.5.2.15 | P14 | 88624.62 | 29 |  | 0 | 0 | 0
15.5.2.16 | P15 | 88624.62 | 29 |  | 0 | 0 | 0
15.5.2.17 | P16 | 122508.76 | 30 |  | 0 | 0 | 0
15.5.2.18 | A2 | 170513.78 | 30 |  | 0 | 0 | 0
15.5.3 | Abutments and Piers elevation/ Elevacija mosnih stubova
15.5.3.1 | A1 | 284358.8 | 20 |  | 0 | 0 | 0
15.5.3.2 | P1 stage 1 (6m) | 18755.8098 | 21 |  | 0 | 0 | 0
15.5.3.3 | P1 stage 2 (6m) | 18755.8098 | 22 |  | 0 | 0 | 0
15.5.3.4 | P1 stage 3 (3.7m) | 11566.0827 | 22 |  | 0 | 0 | 0
15.5.3.5 | P2 stage 1 (6m) | 18755.8098 | 21 |  | 0 | 0 | 0
15.5.3.6 | P2 stage 2 (6m) | 18755.8098 | 21 |  | 0 | 0 | 0
15.5.3.7 | P2 stage 3 (4.7m) | 14692.051 | 22 |  | 0 | 0 | 0
15.5.3.8 | P3 stage 1 (6m) | 18755.8098 | 21 |  | 0 | 0 | 0
15.5.3.9 | P3 stage 2 (6m) | 18755.8098 | 21 |  | 0 | 0 | 0
15.5.3.10 | P3 stage 3 (4.69m) | 14660.7914 | 22 |  | 0 | 0 | 0
15.5.3.11 | P4 stage 1 (6m) | 18755.8098 | 21 |  | 0 | 0 | 0
15.5.3.12 | P4 stage 2 (6m) | 18755.8098 | 21 |  | 0 | 0 | 0
15.5.3.13 | P4 stage 3 (4.879m) | 15251.5994 | 22 |  | 0 | 0 | 0
15.5.3.14 | P5 stage 1 (6m) | 18755.8098 | 23 |  | 0 | 0 | 0
15.5.3.15 | P5 stage 2 (6m) | 18755.8098 | 23 |  | 0 | 0 | 0
15.5.3.16 | P5 stage 3 (5.879) | 18377.5677 | 24 |  | 0 | 0 | 0
15.5.3.17 | P6 stage 1 (6m) | 18755.8098 | 23 |  | 0 | 0 | 0
15.5.3.18 | P6 stage 2 (6m) | 18755.8098 | 23 |  | 0 | 0 | 0
15.5.3.19 | P6 stage 3 (6m) | 18755.8098 | 24 |  | 0 | 0 | 0
15.5.3.20 | P6 stage 4 (0.364m) | 1137.8525 | 24 |  | 0 | 0 | 0
15.5.3.21 | P7 stage 1 (6m) | 18755.8098 | 22 |  | 0 | 0 | 0
15.5.3.22 | P7 stage 2 (6m) | 18755.8098 | 23 |  | 0 | 0 | 0
15.5.3.23 | P7 stage 3 (6m) | 18755.8098 | 23 |  | 0 | 0 | 0
15.5.3.24 | P7 stage 4 (1.864m) | 5826.8049 | 24 |  | 0 | 0 | 0
15.5.3.25 | P8 stage 1 (6m) | 18755.8098 | 23 |  | 0 | 0 | 0
15.5.3.26 | P8 stage 2 (6m) | 18755.8098 | 24 |  | 0 | 0 | 0
15.5.3.27 | P8 stage 3 (6m) | 18755.8098 | 24 |  | 0 | 0 | 0
15.5.3.28 | P8 stage 4 (1.864m) | 5826.8049 | 25 |  | 0 | 0 | 0
15.5.3.29 | P9 stage 1 (6m) | 18755.8098 | 25 |  | 0 | 0 | 0
15.5.3.30 | P9 stage 2 (6m) | 18755.8098 | 25 |  | 0 | 0 | 0
15.5.3.31 | P9 stage 3 (6m) | 18755.8098 | 26 |  | 0 | 0 | 0
15.5.3.32 | P9 stage 4 (1.2m) | 3751.162 | 26 |  | 0 | 0 | 0
15.5.3.33 | P10 stage 1 (6m) | 18755.8098 | 25 |  | 0 | 0 | 0
15.5.3.34 | P10 stage 2 (6m) | 18755.8098 | 25 |  | 0 | 0 | 0
15.5.3.35 | P10 stage 3 (6m) | 18755.8098 | 26 |  | 0 | 0 | 0
15.5.3.36 | P10 stage 4 (2.3m) | 7189.7271 | 27 |  | 0 | 0 | 0
15.5.3.37 | P11 stage 1 (6m) | 18755.8098 | 25 |  | 0 | 0 | 0
15.5.3.38 | P11 stage 2 (6m) | 18755.8098 | 26 |  | 0 | 0 | 0
15.5.3.39 | P11 stage 3 (6m) | 18755.8098 | 27 |  | 0 | 0 | 0
15.5.3.40 | P11 stage 4 (3.864m) | 12078.7415 | 27 |  | 0 | 0 | 0
15.5.3.41 | P12 stage 1 (6m) | 18755.8098 | 26 |  | 0 | 0 | 0
15.5.3.42 | P12 stage 2 (6m) | 18755.8098 | 27 |  | 0 | 0 | 0
15.5.3.43 | P12 stage 3 (6m) | 18755.8098 | 27 |  | 0 | 0 | 0
15.5.3.44 | P12 stage 4 (3.864m) | 12078.7415 | 28 |  | 0 | 0 | 0
15.5.3.45 | P13 stage 1 (6m) | 18755.8098 | 27 |  | 0 | 0 | 0
15.5.3.46 | P13 stage 2 (6m) | 18755.8098 | 28 |  | 0 | 0 | 0
15.5.3.47 | P13 stage 3 (6m) | 18755.8098 | 28 |  | 0 | 0 | 0
15.5.3.48 | P13 stage 4 (2.564m) | 8014.9827 | 29 |  | 0 | 0 | 0
15.5.3.49 | P14 stage 1 (6m) | 18755.8098 | 28 |  | 0 | 0 | 0
15.5.3.50 | P14 stage 2 (6m) | 18755.8098 | 29 |  | 0 | 0 | 0
15.5.3.51 | P14 stage 3 (6m) | 18755.8098 | 29 |  | 0 | 0 | 0
15.5.3.52 | P14 stage 4 (2.364m) | 7389.7891 | 30 |  | 0 | 0 | 0
15.5.3.53 | P15 stage 1 (6m) | 18755.8098 | 28 |  | 0 | 0 | 0
15.5.3.54 | P15 stage 2 (6m) | 18755.8098 | 28 |  | 0 | 0 | 0
15.5.3.55 | P15 stage 3 (6m) | 18755.8098 | 29 |  | 0 | 0 | 0
15.5.3.56 | P15 stage 4 (2.364m) | 7389.7891 | 30 |  | 0 | 0 | 0
15.5.3.57 | P16 stage 1 (6m) | 18755.8098 | 29 |  | 0 | 0 | 0
15.5.3.58 | P16 stage 2 (6m) | 18755.8098 | 29 |  | 0 | 0 | 0
15.5.3.59 | P16 stage 3 (6m) | 18755.8098 | 30 |  | 0 | 0 | 0
15.5.3.60 | P16 stage 4 (3.5m) | 10940.8891 | 30 |  | 0 | 0 | 0
15.5.3.61 | A2 | 133937.12 | 30 |  | 0 | 0 | 0
15.5.4 | Spans/ Rasponi
15.5.4.1 | A1-P1
15.5.4.2 | Bridge superstructure/ Gornji stroj mosta | 136315.02 | 24 |  | 0 | 0 | 0
15.5.4.3 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15146.11 | 25 |  | 0 | 0 | 0
15.5.4.4 | P1-P2
15.5.4.5 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 25 |  | 0 | 0 | 0
15.5.4.6 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 26 |  | 0 | 0 | 0
15.5.4.7 | P2-P3
15.5.4.8 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 26 |  | 0 | 0 | 0
15.5.4.9 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 27 |  | 0 | 0 | 0
15.5.4.10 | P3-P4
15.5.4.11 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 27 |  | 0 | 0 | 0
15.5.4.12 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 28 |  | 0 | 0 | 0
15.5.4.13 | P4-P5
15.5.4.14 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 28 |  | 0 | 0 | 0
15.5.4.15 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 29 |  | 0 | 0 | 0
15.5.4.16 | P5-P6
15.5.4.17 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 29 |  | 0 | 0 | 0
15.5.4.18 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 30 |  | 0 | 0 | 0
15.5.4.19 | P6-P7
15.5.4.20 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 30 |  | 0 | 0 | 0
15.5.4.21 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 31 |  | 0 | 0 | 0
15.5.4.22 | P7-P8
15.5.4.23 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 31 |  | 0 | 0 | 0
15.5.4.24 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 32 |  | 0 | 0 | 0
15.5.4.25 | P8-P9
15.5.4.26 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 31 |  | 0 | 0 | 0
15.5.4.27 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 32 |  | 0 | 0 | 0
15.5.4.28 | P9-P10
15.5.4.29 | Bridge superstructure/ Gornji stroj mosta | 141891.54 | 32 |  | 0 | 0 | 0
15.5.4.30 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15765.73 | 33 |  | 0 | 0 | 0
15.5.4.31 | P10-P11
15.5.4.32 | Bridge superstructure/ Gornji stroj mosta | 141891.54 | 32 |  | 0 | 0 | 0
15.5.4.33 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15765.73 | 33 |  | 0 | 0 | 0
15.5.4.34 | P11-P12
15.5.4.35 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 33 |  | 0 | 0 | 0
15.5.4.36 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 34 |  | 0 | 0 | 0
15.5.4.37 | P12-P13
15.5.4.38 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 33 |  | 0 | 0 | 0
15.5.4.39 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 34 |  | 0 | 0 | 0
15.5.4.40 | P13-P14
15.5.4.41 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 34 |  | 0 | 0 | 0
15.5.4.42 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 35 |  | 0 | 0 | 0
15.5.4.43 | P14-P15
15.5.4.44 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 34 |  | 0 | 0 | 0
15.5.4.45 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 35 |  | 0 | 0 | 0
15.5.4.46 | P15-P16
15.5.4.47 | Bridge superstructure/ Gornji stroj mosta | 173491.84 | 35 |  | 0 | 0 | 0
15.5.4.48 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 19276.87 | 36 |  | 0 | 0 | 0
15.5.4.49 | P16-A2
15.5.4.50 | Bridge superstructure/ Gornji stroj mosta | 136315.02 | 35 |  | 0 | 0 | 0
15.5.4.51 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15146.11 | 36 |  | 0 | 0 | 0
15.5.5 | Bridge furniture/ Mosna estetika
15.5.5.1 | 50 m | 61062.09 | 36 |  | 0 | 0 | 0
15.5.5.2 | 100 m | 61062.09 | 36 |  | 0 | 0 | 0
15.5.5.3 | 150 m | 61062.09 | 36 |  | 0 | 0 | 0
15.5.5.4 | 200 m | 61062.09 | 36 |  | 0 | 0 | 0
15.5.5.5 | 250 m | 61062.09 | 37 |  | 0 | 0 | 0
15.5.5.6 | 300 m | 61062.09 | 37 |  | 0 | 0 | 0
15.5.5.7 | 350 m | 61062.09 | 37 |  | 0 | 0 | 0
15.5.5.8 | 400 m | 61062.09 | 37 |  | 0 | 0 | 0
15.5.5.9 | 453.8 m | 65702.9 | 37 |  | 0 | 0 | 0
15.5.6 | Waterproofing and asphalt works/ Hidroizolacija i asfaltni radovi
15.5.6.1 | Asphalt/Asfalt 1 + waterproofing/ hidroizolacija | 196012.53 | 36 |  | 0 | 0 | 0
15.5.6.2 | Asphalt/Asfalt 2 + joints/ spojnice | 97952.04 | 37 |  | 0 | 0 | 0
Right bridge/ Desni most
15.5.7 | Foundation piles/ Temeljni šipovi
15.5.7.1 | A1 | 58244.06 | 19 |  | 0 | 0 | 0
15.5.7.2 | P1 | 58244.06 | 20 |  | 0 | 0 | 0
15.5.7.3 | P2 | 58244.06 | 20 |  | 0 | 0 | 0
15.5.7.4 | P3 | 58244.06 | 20 |  | 0 | 0 | 0
15.5.7.5 | P4 | 58244.06 | 21 |  | 0 | 0 | 0
15.5.7.6 | P5 | 58244.06 | 21 |  | 0 | 0 | 0
15.5.7.7 | P6 | 58244.06 | 21 |  | 0 | 0 | 0
15.5.7.8 | P7 | 58244.06 | 22 |  | 0 | 0 | 0
15.5.7.9 | P8 | 58244.06 | 22 |  | 0 | 0 | 0
15.5.7.10 | P9 | 58244.06 | 22 |  | 0 | 0 | 0
15.5.7.11 | P10 | 58244.06 | 23 |  | 0 | 0 | 0
15.5.7.12 | P11 | 58244.06 | 23 |  | 0 | 0 | 0
15.5.7.13 | P12 | 58244.06 | 23 |  | 0 | 0 | 0
15.5.7.14 | P13 | 58244.06 | 24 |  | 0 | 0 | 0
15.5.7.15 | P14 | 58244.06 | 24 |  | 0 | 0 | 0
15.5.7.16 | A2 | 58244.06 | 24 |  | 0 | 0 | 0
15.5.8 | Foundation concrete/ Temeljni beton
15.5.8.1 | A1 | 117255.16 | 20 |  | 0 | 0 | 0
15.5.8.2 | P1 | 39524.21 | 21 |  | 0 | 0 | 0
15.5.8.3 | P2 | 39524.21 | 22 |  | 0 | 0 | 0
15.5.8.4 | P3 | 39524.21 | 23 |  | 0 | 0 | 0
15.5.8.5 | P4 | 39524.21 | 24 |  | 0 | 0 | 0
15.5.8.6 | P5 | 39524.21 | 25 |  | 0 | 0 | 0
15.5.8.7 | P6 | 39524.21 | 25 |  | 0 | 0 | 0
15.5.8.8 | P7 | 39524.21 | 26 |  | 0 | 0 | 0
15.5.8.9 | P8 | 39524.21 | 26 |  | 0 | 0 | 0
15.5.8.10 | P9 | 39524.21 | 27 |  | 0 | 0 | 0
15.5.8.11 | P10 | 39524.21 | 27 |  | 0 | 0 | 0
15.5.8.12 | P11 | 39524.21 | 28 |  | 0 | 0 | 0
15.5.8.13 | P12 | 39524.21 | 29 |  | 0 | 0 | 0
15.5.8.14 | P13 | 39524.21 | 29 |  | 0 | 0 | 0
15.5.8.15 | P14 | 39524.21 | 30 |  | 0 | 0 | 0
15.5.8.16 | A2 | 76044.62 | 30 |  | 0 | 0 | 0
15.5.9 | Abutments and Piers elevation/ Elevacija mosnih stubova
15.5.9.1 | A1 | 341358.33 | 21 |  | 0 | 0 | 0
15.5.9.2 | P1 stage 1 (6m) | 18458.6139 | 21 |  | 0 | 0 | 0
15.5.9.3 | P1 stage 2 (6m) | 18458.6139 | 22 |  | 0 | 0 | 0
15.5.9.4 | P1 stage 3 (3.295m) | 10136.8554 | 22 |  | 0 | 0 | 0
15.5.9.5 | P2 stage 1 (6m) | 18458.6139 | 22 |  | 0 | 0 | 0
15.5.9.6 | P2 stage 2 (6m) | 18458.6139 | 22 |  | 0 | 0 | 0
15.5.9.7 | P2 stage 3 (5.295m) | 16289.7267 | 23 |  | 0 | 0 | 0
15.5.9.8 | P3 stage 1 (6m) | 18458.6139 | 23 |  | 0 | 0 | 0
15.5.9.9 | P3 stage 2 (6m) | 18458.6139 | 24 |  | 0 | 0 | 0
15.5.9.10 | P3 stage 3 (6m) | 18458.6139 | 24 |  | 0 | 0 | 0
15.5.9.11 | P4 stage 1 (6m) | 18458.6139 | 23 |  | 0 | 0 | 0
15.5.9.12 | P4 stage 2 (6m) | 18458.6139 | 23 |  | 0 | 0 | 0
15.5.9.13 | P4 stage 3 (5.809m) | 17871.0147 | 24 |  | 0 | 0 | 0
15.5.9.14 | P5 stage 1 (6m) | 18458.6139 | 25 |  | 0 | 0 | 0
15.5.9.15 | P5 stage 2 (6m) | 18458.6139 | 25 |  | 0 | 0 | 0
15.5.9.16 | P5 stage 3 (6m) | 18458.6139 | 26 |  | 0 | 0 | 0
15.5.9.17 | P5 stage 4 (0.519m) | 1596.6701 | 26 |  | 0 | 0 | 0
15.5.9.18 | P6 stage 1 (6m) | 18458.6139 | 25 |  | 0 | 0 | 0
15.5.9.19 | P6 stage 2 (6m) | 18458.6139 | 25 |  | 0 | 0 | 0
15.5.9.20 | P6 stage 3 (6m) | 18458.6139 | 26 |  | 0 | 0 | 0
15.5.9.21 | P6 stage 4 (1.43m) | 4399.303 | 26 |  | 0 | 0 | 0
15.5.9.22 | P7 stage 1 (6m) | 18458.6139 | 25 |  | 0 | 0 | 0
15.5.9.23 | P7 stage 2 (6m) | 18458.6139 | 26 |  | 0 | 0 | 0
15.5.9.24 | P7 stage 3 (6m) | 18458.6139 | 27 |  | 0 | 0 | 0
15.5.9.25 | P7 stage 4 (2.533m) | 7792.6115 | 27 |  | 0 | 0 | 0
15.5.9.26 | P8 stage 1 (6m) | 18458.6139 | 26 |  | 0 | 0 | 0
15.5.9.27 | P8 stage 2 (6m) | 18458.6139 | 27 |  | 0 | 0 | 0
15.5.9.28 | P8 stage 3 (6m) | 18458.6139 | 28 |  | 0 | 0 | 0
15.5.9.29 | P8 stage 4 (2.3m) | 7075.802 | 28 |  | 0 | 0 | 0
15.5.9.30 | P9 stage 1 (6m) | 18458.6139 | 27 |  | 0 | 0 | 0
15.5.9.31 | P9 stage 2 (6m) | 18458.6139 | 27 |  | 0 | 0 | 0
15.5.9.32 | P9 stage 3 (4.833m) | 14868.4135 | 28 |  | 0 | 0 | 0
15.5.9.33 | P10 stage 1 (6m) | 18458.6139 | 28 |  | 0 | 0 | 0
15.5.9.34 | P10 stage 2 (6m) | 18458.6139 | 28 |  | 0 | 0 | 0
15.5.9.35 | P10 stage 3 (6m) | 18458.6139 | 28 |  | 0 | 0 | 0
15.5.9.36 | P10 stage 4 (5.533m) | 17021.9184 | 28 |  | 0 | 0 | 0
15.5.9.37 | P11 stage 1 (6m) | 18458.6139 | 28 |  | 0 | 0 | 0
15.5.9.38 | P11 stage 2 (6m) | 18458.6139 | 28 |  | 0 | 0 | 0
15.5.9.39 | P11 stage 3 (6m) | 18458.6139 | 29 |  | 0 | 0 | 0
15.5.9.40 | P11 stage 4 (1.133m) | 3485.6016 | 29 |  | 0 | 0 | 0
15.5.9.41 | P12 stage 1 (6m) | 18458.6139 | 29 |  | 0 | 0 | 0
15.5.9.42 | P12 stage 2 (6m) | 18458.6139 | 29 |  | 0 | 0 | 0
15.5.9.43 | P12 stage 3 (6m) | 18458.6139 | 30 |  | 0 | 0 | 0
15.5.9.44 | P12 stage 4 (1.333m) | 4100.8887 | 30 |  | 0 | 0 | 0
15.5.9.45 | P13 stage 1 (6m) | 18458.6139 | 29 |  | 0 | 0 | 0
15.5.9.46 | P13 stage 2 (6m) | 18458.6139 | 29 |  | 0 | 0 | 0
15.5.9.47 | P13 stage 3 (6m) | 18458.6139 | 30 |  | 0 | 0 | 0
15.5.9.48 | P13 stage 4 (1.033m) | 3177.958 | 30 |  | 0 | 0 | 0
15.5.9.49 | P14 stage 1 (6m) | 18458.6139 | 29 |  | 0 | 0 | 0
15.5.9.50 | P14 stage 2 (6m) | 18458.6139 | 29 |  | 0 | 0 | 0
15.5.9.51 | P14 stage 3 (2.033m) | 6254.3937 | 30 |  | 0 | 0 | 0
15.5.9.52 | A2 | 106674.48 | 30 |  | 0 | 0 | 0
15.5.10 | Spans/ Rasponi
15.5.10.1 | A1-P1
15.5.10.2 | Bridge superstructure/ Gornji stroj mosta | 133635.51 | 25 |  | 0 | 0 | 0
15.5.10.3 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14848.39 | 26 |  | 0 | 0 | 0
15.5.10.4 | P1-P2
15.5.10.5 | Bridge superstructure/ Gornji stroj mosta | 170081.56 | 26 |  | 0 | 0 | 0
15.5.10.6 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 18897.95 | 27 |  | 0 | 0 | 0
15.5.10.7 | P2-P3
15.5.10.8 | Bridge superstructure/ Gornji stroj mosta | 170081.56 | 27 |  | 0 | 0 | 0
15.5.10.9 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 18897.95 | 28 |  | 0 | 0 | 0
15.5.10.10 | P3-P4
15.5.10.11 | Bridge superstructure/ Gornji stroj mosta | 170081.56 | 28 |  | 0 | 0 | 0
15.5.10.12 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 18897.95 | 29 |  | 0 | 0 | 0
15.5.10.13 | P4-P5
15.5.10.14 | Bridge superstructure/ Gornji stroj mosta | 170081.56 | 29 |  | 0 | 0 | 0
15.5.10.15 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 18897.95 | 30 |  | 0 | 0 | 0
15.5.10.16 | P5-P6
15.5.10.17 | Bridge superstructure/ Gornji stroj mosta | 170081.56 | 30 |  | 0 | 0 | 0
15.5.10.18 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 18897.95 | 31 |  | 0 | 0 | 0
15.5.10.19 | P6-P7
15.5.10.20 | Bridge superstructure/ Gornji stroj mosta | 170081.56 | 31 |  | 0 | 0 | 0
15.5.10.21 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 18897.95 | 32 |  | 0 | 0 | 0
15.5.10.22 | P7-P8
15.5.10.23 | Bridge superstructure/ Gornji stroj mosta | 139102.42 | 32 |  | 0 | 0 | 0
15.5.10.24 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15455.82 | 33 |  | 0 | 0 | 0
15.5.10.25 | P8-P9
15.5.10.26 | Bridge superstructure/ Gornji stroj mosta | 139102.42 | 33 |  | 0 | 0 | 0
15.5.10.27 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 15455.82 | 34 |  | 0 | 0 | 0
15.5.10.28 | P9-P10
15.5.10.29 | Bridge superstructure/ Gornji stroj mosta | 170081.56 | 34 |  | 0 | 0 | 0
15.5.10.30 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 18897.95 | 35 |  | 0 | 0 | 0
15.5.10.31 | P10-P11
15.5.10.32 | Bridge superstructure/ Gornji stroj mosta | 170081.56 | 34 |  | 0 | 0 | 0
15.5.10.33 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 18897.95 | 36 |  | 0 | 0 | 0
15.5.10.34 | P11-P12
15.5.10.35 | Bridge superstructure/ Gornji stroj mosta | 170081.56 | 35 |  | 0 | 0 | 0
15.5.10.36 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 18897.95 | 36 |  | 0 | 0 | 0
15.5.10.37 | P12-P13
15.5.10.38 | Bridge superstructure/ Gornji stroj mosta | 170081.56 | 35 |  | 0 | 0 | 0
15.5.10.39 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 18897.95 | 36 |  | 0 | 0 | 0
15.5.10.40 | P13-P14
15.5.10.41 | Bridge superstructure/ Gornji stroj mosta | 170081.56 | 36 |  | 0 | 0 | 0
15.5.10.42 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 18897.95 | 36 |  | 0 | 0 | 0
15.5.10.43 | P14-A2
15.5.10.44 | Bridge superstructure/ Gornji stroj mosta | 133635.51 | 36 |  | 0 | 0 | 0
15.5.10.45 | Superstructure prestressing/ Prednaprezanje gornjeg stroja | 14848.39 | 36 |  | 0 | 0 | 0
15.5.11 | Bridge furniture/ Mosna estetika
15.5.11.1 | 50 m | 59035.75 | 36 |  | 0 | 0 | 0
15.5.11.2 | 100 m | 59035.75 | 36 |  | 0 | 0 | 0
15.5.11.3 | 150 m | 59035.75 | 36 |  | 0 | 0 | 0
15.5.11.4 | 200 m | 59035.75 | 37 |  | 0 | 0 | 0
15.5.11.5 | 250 m | 59035.75 | 37 |  | 0 | 0 | 0
15.5.11.6 | 300 m | 59035.75 | 37 |  | 0 | 0 | 0
15.5.11.7 | 350 m | 59035.75 | 37 |  | 0 | 0 | 0
15.5.11.8 | 397.8 m | 56438.21 | 37 |  | 0 | 0 | 0
15.5.12 | Waterproofing and asphalt works/ Hidroizolacija i asfaltni radovi
15.5.12.1 | Asphalt/Asfalt 1 + waterproofing/ hidroizolacija | 178739.53 | 36 |  | 0 | 0 | 0
15.5.12.2 | Asphalt/Asfalt 2 + joints/ spojnice | 92162.38 | 37 |  | 0 | 0 | 0
| Sub Total / Suma stavke 15.5 | 14660392.18 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 15.6 | Road Works/ Radovi na putevima (LK39+830+687—LK39+872.817, RK39+834.184—RK39+892.714)
Completion of/Završetak:
15.6.1 | Subgrade/ Posteljica
15.6.1.1 | Top soil removal/ Uklanjanje humusa
15.6.1.1.1 | 0 - 42.130 m (LK); 0 - 58.530 m (RK) | 19704.97 | 19 |  | 0 | 0 | 0
15.6.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and certain high (after MD approval)/Na svakih 250m i određenoj visini (nakon odobrenja GP) | 279697.03 | 34 |  | 0 | 0 | 0
15.6.1.3 | Road Foundation/ Temelj puta
15.6.1.3.1 | 0 - 58.530 m, right side/ desna strana | 10657.72 | 39 |  | 0 | 0 | 0
15.6.1.3.2 | 0 - 42.130 m, left side/ lijeva strana | 10657.71 | 40 |  | 0 | 0 | 0
15.6.2 | Engineering structures/ Inženjerske konstrukcije
15.6.2.1 | Concrete wall (it will be splitted after MD approval)/ Betonski zid (biće podijeljen nakon odobrenja GP) |  | 35
95% for the concrete wall, the milestone is 50m lenth, no matter the hight; 5% for the "after work" the whole lenth of each retaining wall / 95% za betonski zid, reper je 50 m dužine, bez obzira na visinu; 5% za "kasnije radove" čitava dužina potpornog zida
15.6.2.1.1 | Concrete wall/ Betonski zid LK39+835.09 - LK39+867.00 (35.39m)
15.6.2.1.1.1 | Concrete wall/ Betonski zid LK39+835.09 - LK39+867.00 - 95% | 17966.57 |  |  | 0 | 0 | 0
15.6.2.1.1.2 | Concrete wall/ Betonski zid LK39+835.09 - LK39+867.00 - After work 5% | 945.6089 |  |  | 0 | 0 | 0
15.6.2.1.2 | Concrete wall/ Betonski zid RK39+838.20 - RK39+843.0 (5.52m)
15.6.2.1.2.1 | Concrete wall/ Betonski zid RK39+838.20 - RK39+843.0 - 95% | 2802.3585 |  |  | 0 | 0 | 0
15.6.2.1.2.2 | Concrete wall/ Betonski zid RK39+838.20 - RK39+843.0 - After work 5% | 147.4926 |  |  | 0 | 0 | 0
15.6.3 | Water drainage/ Drenaža vode
15.6.3.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 50582.87 | 41 |  | 0 | 0 | 0
15.6.4 | Pavement structure/ Kolovozna konstrukcija
15.6.4.1 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana | 8366.1268 | 46 |  | 0 | 0 | 0
15.6.4.2 | asphalt concrete layer/ sloj asfaltnog betona 1 left side/ lijeva strana | 6021.9532 | 46 |  | 0 | 0 | 0
15.6.4.3 | asphalt concrete layer/ sloj asfaltnog betona 2 right side/ desna strana | 8366.1268 | 47 |  | 0 | 0 | 0
15.6.4.4 | asphalt concrete layer/ sloj asfaltnog betona 2 left side/ lijeva strana | 6021.9532 | 47 |  | 0 | 0 | 0
15.6.4.5 | asphalt concrete layer/ sloj asfaltnog betona 3 right side/ desna strana | 9296.2514 | 48 |  | 0 | 0 | 0
15.6.4.6 | asphalt concrete layer/ sloj asfaltnog betona 3 left side/ lijeva strana | 6691.4586 | 48 |  | 0 | 0 | 0
| Sub Total / Suma stavke 15.6 | 437926.2 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 15.7 | Construction of tunnel/ Izgradnja tunela Matesevo (LK39+872.817 - LK 40+424.817, RK 39+892.714- RK 40+452.714)
Completion of/Završetak:
15.7.1 | Portal construction/ Izgradnja portala
15.7.1.1 | 20% complete/ završeno (portal 1) | 118033.81 | 19 |  | 0 | 0 | 0
15.7.1.2 | 40% complete/ završeno (portal 2) | 118033.81 | 20 |  | 0 | 0 | 0
15.7.1.3 | 60% complete/ završeno (portal 3) | 118033.81 | 21 |  | 0 | 0 | 0
15.7.1.4 | 80% complete/ završeno (portal 4) | 118033.81 | 21 |  | 0 | 0 | 0
15.7.1.5 | 85% (portal 1 complete/ završen) | 29508.4525 | 37 |  | 0 | 0 | 0
15.7.1.6 | 90% (portal 2 complete/ završen) | 29508.4525 | 37 |  | 0 | 0 | 0
15.7.1.7 | 95% (portal 3 complete/ završen) | 29508.4525 | 37 |  | 0 | 0 | 0
15.7.1.8 | 100% (portal 4 complete/ završen) | 29508.4425 | 37 |  | 0 | 0 | 0
15.7.2 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
15.7.2.1 | 20 m | 127512.6058 | 22 |  | 0 | 0 | 0
15.7.2.2 | 40 m | 127512.6058 | 22 |  | 0 | 0 | 0
15.7.2.3 | 60 m | 127512.6058 | 22 |  | 0 | 0 | 0
15.7.2.4 | 80 m | 127512.6058 | 22 |  | 0 | 0 | 0
15.7.2.5 | 100 m | 127512.6058 | 23 |  | 0 | 0 | 0
15.7.2.6 | 120 m | 127512.6058 | 23 |  | 0 | 0 | 0
15.7.2.7 | 140 m | 127512.6058 | 23 |  | 0 | 0 | 0
15.7.2.8 | 160 m | 127512.6058 | 23 |  | 0 | 0 | 0
15.7.2.9 | 180 m | 127512.6058 | 24 |  | 0 | 0 | 0
15.7.2.10 | 200 m | 127512.6058 | 24 |  | 0 | 0 | 0
15.7.2.11 | 220 m | 127512.6058 | 24 |  | 0 | 0 | 0
15.7.2.12 | 240 m | 127512.6058 | 24 |  | 0 | 0 | 0
15.7.2.13 | 260 m | 127512.6058 | 25 |  | 0 | 0 | 0
15.7.2.14 | 280 m | 127512.6058 | 25 |  | 0 | 0 | 0
15.7.2.15 | 300 m | 127512.6058 | 25 |  | 0 | 0 | 0
15.7.2.16 | 320 m | 127512.6058 | 25 |  | 0 | 0 | 0
15.7.2.17 | 340 m | 127512.6058 | 26 |  | 0 | 0 | 0
15.7.2.18 | 360 m | 127512.6058 | 26 |  | 0 | 0 | 0
15.7.2.19 | 380 m | 127512.6058 | 26 |  | 0 | 0 | 0
15.7.2.20 | 400 m | 127512.6058 | 26 |  | 0 | 0 | 0
15.7.2.21 | 420 m | 127512.6058 | 27 |  | 0 | 0 | 0
15.7.2.22 | 440 m | 127512.6058 | 27 |  | 0 | 0 | 0
15.7.2.23 | 460 m | 127512.6058 | 27 |  | 0 | 0 | 0
15.7.2.24 | 480 m | 127512.6058 | 27 |  | 0 | 0 | 0
15.7.2.25 | 500 m | 127512.6058 | 28 |  | 0 | 0 | 0
15.7.2.26 | 520 m | 127512.6058 | 28 |  | 0 | 0 | 0
15.7.2.27 | 540 m | 127512.6058 | 28 |  | 0 | 0 | 0
15.7.2.28 | 560 m | 127512.6058 | 28 |  | 0 | 0 | 0
15.7.2.29 | 580 m | 127512.6058 | 29 |  | 0 | 0 | 0
15.7.2.30 | 600 m | 127512.6058 | 29 |  | 0 | 0 | 0
15.7.2.31 | 620 m | 127512.6058 | 29 |  | 0 | 0 | 0
15.7.2.32 | 640 m | 127512.6058 | 29 |  | 0 | 0 | 0
15.7.2.33 | 660 m | 127512.6058 | 29 |  | 0 | 0 | 0
15.7.2.34 | 680 m | 127512.6058 | 29 |  | 0 | 0 | 0
15.7.2.35 | 700 m | 127512.6058 | 29 |  | 0 | 0 | 0
15.7.2.36 | 720 m | 127512.6058 | 30 |  | 0 | 0 | 0
15.7.2.37 | 740 m | 127512.6058 | 30 |  | 0 | 0 | 0
15.7.2.38 | 760 m | 127512.6058 | 30 |  | 0 | 0 | 0
15.7.2.39 | 780 m | 127512.6058 | 30 |  | 0 | 0 | 0
15.7.2.40 | 800 m | 127512.6058 | 30 |  | 0 | 0 | 0
15.7.2.41 | 820 m | 127512.6058 | 30 |  | 0 | 0 | 0
15.7.2.42 | 840 m | 127512.6058 | 31 |  | 0 | 0 | 0
15.7.2.43 | 860 m | 127512.6058 | 31 |  | 0 | 0 | 0
15.7.2.44 | 880 m | 127512.6058 | 31 |  | 0 | 0 | 0
15.7.2.45 | 900 m | 127512.6058 | 31 |  | 0 | 0 | 0
15.7.2.46 | 920 m | 127512.6058 | 31 |  | 0 | 0 | 0
15.7.2.47 | 940 m | 127512.6058 | 31 |  | 0 | 0 | 0
15.7.2.48 | 960 m | 127512.6058 | 32 |  | 0 | 0 | 0
15.7.2.49 | 980 m | 127512.6058 | 32 |  | 0 | 0 | 0
15.7.2.50 | 1000 m | 127512.6058 | 32 |  | 0 | 0 | 0
15.7.2.51 | 1020 m | 127512.6058 | 32 |  | 0 | 0 | 0
15.7.2.52 | 1040 m | 127512.6058 | 32 |  | 0 | 0 | 0
15.7.2.53 | 1046.9 m | 43991.849 | 32 |  | 0 | 0 | 0
15.7.3 | Excavation and Construction of Preliminary Bracing/ Iskopavanje i konstrukcija preliminarne podgrade
15.7.3.1 | 20 m | 65197.6823 | 23 |  | 0 | 0 | 0
15.7.3.2 | 40 m | 65197.6823 | 23 |  | 0 | 0 | 0
15.7.3.3 | 60 m | 65197.6823 | 24 |  | 0 | 0 | 0
15.7.3.4 | 80 m | 65197.6823 | 24 |  | 0 | 0 | 0
15.7.3.5 | 100 m | 65197.6823 | 24 |  | 0 | 0 | 0
15.7.3.6 | 120 m | 65197.6823 | 24 |  | 0 | 0 | 0
15.7.3.7 | 140 m | 65197.6823 | 25 |  | 0 | 0 | 0
15.7.3.8 | 160 m | 65197.6823 | 25 |  | 0 | 0 | 0
15.7.3.9 | 180 m | 65197.6823 | 25 |  | 0 | 0 | 0
15.7.3.10 | 200 m | 65197.6823 | 25 |  | 0 | 0 | 0
15.7.3.11 | 220 m | 65197.6823 | 26 |  | 0 | 0 | 0
15.7.3.12 | 240 m | 65197.6823 | 26 |  | 0 | 0 | 0
15.7.3.13 | 260 m | 65197.6823 | 26 |  | 0 | 0 | 0
15.7.3.14 | 280 m | 65197.6823 | 26 |  | 0 | 0 | 0
15.7.3.15 | 300 m | 65197.6823 | 27 |  | 0 | 0 | 0
15.7.3.16 | 320 m | 65197.6823 | 27 |  | 0 | 0 | 0
15.7.3.17 | 340 m | 65197.6823 | 27 |  | 0 | 0 | 0
15.7.3.18 | 360 m | 65197.6823 | 27 |  | 0 | 0 | 0
15.7.3.19 | 380 m | 65197.6823 | 28 |  | 0 | 0 | 0
15.7.3.20 | 400 m | 65197.6823 | 28 |  | 0 | 0 | 0
15.7.3.21 | 420 m | 65197.6823 | 28 |  | 0 | 0 | 0
15.7.3.22 | 440 m | 65197.6823 | 28 |  | 0 | 0 | 0
15.7.3.23 | 460 m | 65197.6823 | 29 |  | 0 | 0 | 0
15.7.3.24 | 480 m | 65197.6823 | 29 |  | 0 | 0 | 0
15.7.3.25 | 500 m | 65197.6823 | 29 |  | 0 | 0 | 0
15.7.3.26 | 520 m | 65197.6823 | 29 |  | 0 | 0 | 0
15.7.3.27 | 540 m | 65197.6823 | 29 |  | 0 | 0 | 0
15.7.3.28 | 560 m | 65197.6823 | 29 |  | 0 | 0 | 0
15.7.3.29 | 580 m | 65197.6823 | 30 |  | 0 | 0 | 0
15.7.3.30 | 600 m | 65197.6823 | 30 |  | 0 | 0 | 0
15.7.3.31 | 620 m | 65197.6823 | 30 |  | 0 | 0 | 0
15.7.3.32 | 640 m | 65197.6823 | 30 |  | 0 | 0 | 0
15.7.3.33 | 660 m | 65197.6823 | 30 |  | 0 | 0 | 0
15.7.3.34 | 680 m | 65197.6823 | 30 |  | 0 | 0 | 0
15.7.3.35 | 700 m | 65197.6823 | 31 |  | 0 | 0 | 0
15.7.3.36 | 720 m | 65197.6823 | 31 |  | 0 | 0 | 0
15.7.3.37 | 740 m | 65197.6823 | 31 |  | 0 | 0 | 0
15.7.3.38 | 760 m | 65197.6823 | 31 |  | 0 | 0 | 0
15.7.3.39 | 780 m | 65197.6823 | 31 |  | 0 | 0 | 0
15.7.3.40 | 800 m | 65197.6823 | 31 |  | 0 | 0 | 0
15.7.3.41 | 820 m | 65197.6823 | 32 |  | 0 | 0 | 0
15.7.3.42 | 840 m | 65197.6823 | 32 |  | 0 | 0 | 0
15.7.3.43 | 860 m | 65197.6823 | 32 |  | 0 | 0 | 0
15.7.3.44 | 880 m | 65197.6823 | 32 |  | 0 | 0 | 0
15.7.3.45 | 900 m | 65197.6823 | 32 |  | 0 | 0 | 0
15.7.3.46 | 920 m | 65197.6823 | 32 |  | 0 | 0 | 0
15.7.3.47 | 940 m | 65197.6823 | 33 |  | 0 | 0 | 0
15.7.3.48 | 960 m | 65197.6823 | 33 |  | 0 | 0 | 0
15.7.3.49 | 980 m | 65197.6823 | 33 |  | 0 | 0 | 0
15.7.3.50 | 1000 m | 65197.6823 | 33 |  | 0 | 0 | 0
15.7.3.51 | 1020 m | 65197.6823 | 33 |  | 0 | 0 | 0
15.7.3.52 | 1040 m | 65197.6823 | 33 |  | 0 | 0 | 0
15.7.3.53 | 1046.9 m | 22493.2004 | 33 |  | 0 | 0 | 0
15.7.4 | Finishes (kerb, cable duct and slab, drainage system) / Zavrsna obrada (ivicnjaci, kablovski vodovi I ploca, drenazni sistem)
15.7.4.1 | 200 m | 80000 | 26 |  | 0 | 0 | 0
15.7.4.2 | 400 m | 80000 | 28 |  | 0 | 0 | 0
15.7.4.3 | 600 m | 80000 | 30 |  | 0 | 0 | 0
15.7.4.4 | 800 m | 80000 | 32 |  | 0 | 0 | 0
15.7.4.5 | 1000 m | 80000 | 34 |  | 0 | 0 | 0
15.7.4.6 | 1046.9 m | 18760 | 34 |  | 0 | 0 | 0
15.7.5 | Construction of pavement/ Izgradnja kolovoza
15.7.5.1 | Left tube/ Lijeva cijev
0-549.63 m
15.7.5.1.1 | Layer/ Sloj 1 | 42104.12 | 35 |  | 0 | 0 | 0
15.7.5.1.2 | Layer/ Sloj 2 | 42104.12 | 36 |  | 0 | 0 | 0
15.7.5.1.3 | Layer/ Sloj 3 | 47367.14 | 36 |  | 0 | 0 | 0
15.7.5.2 | Right tube/ Desna cijev
0-538 m
15.7.5.2.1 | Layer/ Sloj 1 | 41213.06 | 35 |  | 0 | 0 | 0
15.7.5.2.2 | Layer/ Sloj 2 | 41213.06 | 36 |  | 0 | 0 | 0
15.7.5.2.3 | Layer/ Sloj 3 | 46364.69 | 36 |  | 0 | 0 | 0
15.7.6 | Tunnel Equipment/ Tunelska oprema
15.7.6.1 | Right tube/ Desna cijev
15.7.6.1.1 | 90% (Equipment installed/Oprema postavljena) | 538476.47 | 36 |  | 0 | 0 | 0
15.7.6.1.2 | 10% (Equipment tested/Oprema ispitana) | 59830.72 | 36 |  | 0 | 0 | 0
15.7.6.2 | Left tube/ Lijeva cijev
15.7.6.2.1 | 90% (Equipment installed/Oprema postavljena) | 539407.32 | 36 |  | 0 | 0 | 0
15.7.6.2.2 | 10% (Equipment tested/Oprema ispitana) | 59935.26 | 36 |  | 0 | 0 | 0
| Sub Total / Suma stavke 15.7 | 12554365.03 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto 15.8 | Road Works/ Radovi na putevima (LK40+424.817—LK40+798.773, RK40+452.714—RK40+871.854)
Completion of/Završetak:
15.8.1 | Subgrade/ Posteljica
15.8.1.1 | Top soil removal/ Uklanjanje humusa
15.8.1.1.1 | 0 - 250 m (LK&RK) | 92394.48 | 18 |  | 0 | 0 | 0
15.8.1.1.2 | 250 - 341.133 m (LK); 250 - 365.140 m (RK) | 47928.72 | 19 |  | 0 | 0 | 0
15.8.1.2 | Earthworks/ Zemljani radovi
| At every 250 m and certain high (after MD approval)/Na svakih 250m i određenoj visini (nakon odobrenja GP) | 1991780.73 | 36 |  | 0 | 0 | 0
15.8.1.3 | Road Foundation/ Temelj puta
15.8.1.3.1 | 0 - 250 m right side/ desna strana | 49972.87 | 37 |  | 0 | 0 | 0
15.8.1.3.2 | 0 - 250 m left side/ lijeva strana | 49972.87 | 38 |  | 0 | 0 | 0
15.8.1.3.3 | 250 - 365.140 m, right side/ desna strana | 25922.91 | 39 |  | 0 | 0 | 0
15.8.1.3.4 | 250 - 341.133 m, left side/ lijeva strana | 25922.91 | 40 |  | 0 | 0 | 0
15.8.2 | Water drainage/ Drenaža vode
15.8.2.1 | per one direction of 500m (after MD approval)/Na 500m dužine u jednom pravcu (nakon odobrenja GP) | 360211.14 | 41 |  | 0 | 0 | 0
15.8.3 | Pavement structure/ Kolovozna konstrukcija
15.8.3.1 | asphalt concrete layer/ sloj asfaltnog betona 1 right side/ desna strana | 52971.6177 | 46 |  | 0 | 0 | 0
15.8.3.2 | asphalt concrete layer/ sloj asfaltnog betona 1 left side/ lijeva strana | 49488.8723 | 46 |  | 0 | 0 | 0
15.8.3.3 | asphalt concrete layer/ sloj asfaltnog betona 2 right side/ desna strana | 52971.6177 | 47 |  | 0 | 0 | 0
15.8.3.4 | asphalt concrete layer/ sloj asfaltnog betona 2 left side/ lijeva strana | 49488.8723 | 47 |  | 0 | 0 | 0
15.8.3.5 | asphalt concrete layer/ sloj asfaltnog betona 3 right side/ desna strana | 58860.8588 | 48 |  | 0 | 0 | 0
15.8.3.6 | asphalt concrete layer/ sloj asfaltnog betona 3 left side/ lijeva strana | 54990.9112 | 48 |  | 0 | 0 | 0
15.8.4 | Underpass/ Podvožnjak km 40+735,79
15.8.4.1 | Foundation (excavation and concreting)/ Temelji (iskopavanje i betoniranje) | 161098.96 | 24 |  | 0 | 0 | 0
15.8.4.2 | Box culvert/ Kutijasti propust (100% complete/ završeno) | 165980.75 | 26 |  | 0 | 0 | 0
15.8.4.3 | Remaining works/ Preostali radovi | 164884.39 | 28 |  | 0 | 0 | 0
| Sub Total / Suma stavke 15.8 | 3454843.48 |  |  | 0 | 0 | 0
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 15 | 51824566.58 |  |  | 0 | 0 | 0

## COST CENTER C
Highway/Autoput Bar-Boljare, Section/Dionica Smokovac-Uvac-Matesevo
Schedule of Milestone Payments/Raspored repera plaćanja
COST CENTER C//TROŠKOVNI CENTAR C
Cost center No./ Troškovno mjesto Br. | C | Parts/Dijelovi 1-4
|  | Amount/Iznos (EUR) | Planned Month/ Planirano za mjesec | Actual Month/ Stvarno za mjesec | Previous Cumulative/ Kumulativno prethodno | This Period/ Ovaj Period | Total Value to Date/ Ukupan iznos do danas
Cost center/ Troškovno mjesto C.1 | Guardrails /Zaštitne ograde
C.1.1 | 0 - 1000
C.1.1.1 | Right/ Desno 1 | 30967.87 | 38 |  | 0 | 0 | 0
C.1.1.2 | Right/ Desno 2 | 30967.87 | 39 |  | 0 | 0 | 0
C.1.1.3 | Left/ Lijevo 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.1.4 | Left/ Lijevo 2 | 30967.85 | 41 |  | 0 | 0 | 0
C.1.2 | 1000 - 2000
C.1.2.1 | Right/ Desno 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.2.2 | Right/ Desno 2 | 30967.87 | 41 |  | 0 | 0 | 0
C.1.2.3 | Left/ Lijevo 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.2.4 | Left/ Lijevo 2 | 30967.85 | 43 |  | 0 | 0 | 0
C.1.3 | 2000 - 3000
C.1.3.1 | Right/ Desno 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.3.2 | Right/ Desno 2 | 30967.87 | 43 |  | 0 | 0 | 0
C.1.3.3 | Left/ Lijevo 1 | 30967.87 | 44 |  | 0 | 0 | 0
C.1.3.4 | Left/ Lijevo 2 | 30967.85 | 45 |  | 0 | 0 | 0
C.1.4 | 3000 - 4000
C.1.4.1 | Right/ Desno 1 | 30967.87 | 38 |  | 0 | 0 | 0
C.1.4.2 | Right/ Desno 2 | 30967.87 | 39 |  | 0 | 0 | 0
C.1.4.3 | Left/ Lijevo 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.4.4 | Left/ Lijevo 2 | 30967.85 | 41 |  | 0 | 0 | 0
C.1.5 | 4000 - 5000
C.1.5.1 | Right/ Desno 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.5.2 | Right/ Desno 2 | 30967.87 | 41 |  | 0 | 0 | 0
C.1.5.3 | Left/ Lijevo 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.5.4 | Left/ Lijevo 2 | 30967.85 | 43 |  | 0 | 0 | 0
C.1.6 | 5000 - 6000
C.1.6.1 | Right/ Desno 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.6.2 | Right/ Desno 2 | 30967.87 | 43 |  | 0 | 0 | 0
C.1.6.3 | Left/ Lijevo 1 | 30967.87 | 44 |  | 0 | 0 | 0
C.1.6.4 | Left/ Lijevo 2 | 30967.85 | 45 |  | 0 | 0 | 0
C.1.7 | 6000 - 7000
C.1.7.1 | Right/ Desno 1 | 30967.87 | 38 |  | 0 | 0 | 0
C.1.7.2 | Right/ Desno 2 | 30967.87 | 39 |  | 0 | 0 | 0
C.1.7.3 | Left/ Lijevo 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.7.4 | Left/ Lijevo 2 | 30967.85 | 41 |  | 0 | 0 | 0
C.1.8 | 7000 - 8000
C.1.8.1 | Right/ Desno 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.8.2 | Right/ Desno 2 | 30967.87 | 41 |  | 0 | 0 | 0
C.1.8.3 | Left/ Lijevo 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.8.4 | Left/ Lijevo 2 | 30967.85 | 43 |  | 0 | 0 | 0
C.1.9 | 8000 - 9000
C.1.9.1 | Right/ Desno 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.9.2 | Right/ Desno 2 | 30967.87 | 43 |  | 0 | 0 | 0
C.1.9.3 | Left/ Lijevo 1 | 30967.87 | 44 |  | 0 | 0 | 0
C.1.9.4 | Left/ Lijevo 2 | 30967.85 | 45 |  | 0 | 0 | 0
C.1.10 | 9000 - 10000
C.1.10.1 | Right/ Desno 1 | 30967.87 | 38 |  | 0 | 0 | 0
C.1.10.2 | Right/ Desno 2 | 30967.87 | 39 |  | 0 | 0 | 0
C.1.10.3 | Left/ Lijevo 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.10.4 | Left/ Lijevo 2 | 30967.85 | 41 |  | 0 | 0 | 0
C.1.11 | 10000 - 11000
C.1.11.1 | Right/ Desno 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.11.2 | Right/ Desno 2 | 30967.87 | 41 |  | 0 | 0 | 0
C.1.11.3 | Left/ Lijevo 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.11.4 | Left/ Lijevo 2 | 30967.85 | 43 |  | 0 | 0 | 0
C.1.12 | 11000 - 12000
C.1.12.1 | Right/ Desno 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.12.2 | Right/ Desno 2 | 30967.87 | 43 |  | 0 | 0 | 0
C.1.12.3 | Left/ Lijevo 1 | 30967.87 | 44 |  | 0 | 0 | 0
C.1.12.4 | Left/ Lijevo 2 | 30967.85 | 45 |  | 0 | 0 | 0
C.1.13 | 12000 - 13000
C.1.13.1 | Right/ Desno 1 | 30967.87 | 38 |  | 0 | 0 | 0
C.1.13.2 | Right/ Desno 2 | 30967.87 | 39 |  | 0 | 0 | 0
C.1.13.3 | Left/ Lijevo 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.13.4 | Left/ Lijevo 2 | 30967.85 | 41 |  | 0 | 0 | 0
C.1.14 | 13000 - 14000
C.1.14.1 | Right/ Desno 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.14.2 | Right/ Desno 2 | 30967.87 | 41 |  | 0 | 0 | 0
C.1.14.3 | Left/ Lijevo 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.14.4 | Left/ Lijevo 2 | 30967.85 | 43 |  | 0 | 0 | 0
C.1.15 | 14000 - 15000
C.1.15.1 | Right/ Desno 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.15.2 | Right/ Desno 2 | 30967.87 | 43 |  | 0 | 0 | 0
C.1.15.3 | Left/ Lijevo 1 | 30967.87 | 44 |  | 0 | 0 | 0
C.1.15.4 | Left/ Lijevo 2 | 30967.85 | 45 |  | 0 | 0 | 0
C.1.16 | 15000 - 16000
C.1.16.1 | Right/ Desno 1 | 30967.87 | 38 |  | 0 | 0 | 0
C.1.16.2 | Right/ Desno 2 | 30967.87 | 39 |  | 0 | 0 | 0
C.1.16.3 | Left/ Lijevo 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.16.4 | Left/ Lijevo 2 | 30967.85 | 41 |  | 0 | 0 | 0
C.1.17 | 16000 - 17000
C.1.17.1 | Right/ Desno 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.17.2 | Right/ Desno 2 | 30967.87 | 41 |  | 0 | 0 | 0
C.1.17.3 | Left/ Lijevo 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.17.4 | Left/ Lijevo 2 | 30967.85 | 43 |  | 0 | 0 | 0
C.1.18 | 17000 - 18000
C.1.18.1 | Right/ Desno 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.18.2 | Right/ Desno 2 | 30967.87 | 43 |  | 0 | 0 | 0
C.1.18.3 | Left/ Lijevo 1 | 30967.87 | 44 |  | 0 | 0 | 0
C.1.18.4 | Left/ Lijevo 2 | 30967.85 | 45 |  | 0 | 0 | 0
C.1.19 | 18000 - 19000
C.1.19.1 | Right/ Desno 1 | 30967.87 | 38 |  | 0 | 0 | 0
C.1.19.2 | Right/ Desno 2 | 30967.87 | 39 |  | 0 | 0 | 0
C.1.19.3 | Left/ Lijevo 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.19.4 | Left/ Lijevo 2 | 30967.85 | 41 |  | 0 | 0 | 0
C.1.20 | 19000 - 20000
C.1.20.1 | Right/ Desno 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.20.2 | Right/ Desno 2 | 30967.87 | 41 |  | 0 | 0 | 0
C.1.20.3 | Left/ Lijevo 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.20.4 | Left/ Lijevo 2 | 30967.85 | 43 |  | 0 | 0 | 0
C.1.21 | 20000 - 21000
C.1.21.1 | Right/ Desno 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.21.2 | Right/ Desno 2 | 30967.87 | 43 |  | 0 | 0 | 0
C.1.21.3 | Left/ Lijevo 1 | 30967.87 | 44 |  | 0 | 0 | 0
C.1.21.4 | Left/ Lijevo 2 | 30967.85 | 45 |  | 0 | 0 | 0
C.1.22 | 21000 - 22000
C.1.22.1 | Right/ Desno 1 | 30967.87 | 38 |  | 0 | 0 | 0
C.1.22.2 | Right/ Desno 2 | 30967.87 | 39 |  | 0 | 0 | 0
C.1.22.3 | Left/ Lijevo 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.22.4 | Left/ Lijevo 2 | 30967.85 | 41 |  | 0 | 0 | 0
C.1.23 | 22000 - 23000
C.1.23.1 | Right/ Desno 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.23.2 | Right/ Desno 2 | 30967.87 | 41 |  | 0 | 0 | 0
C.1.23.3 | Left/ Lijevo 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.23.4 | Left/ Lijevo 2 | 30967.85 | 43 |  | 0 | 0 | 0
C.1.24 | 23000 - 24000
C.1.24.1 | Right/ Desno 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.24.2 | Right/ Desno 2 | 30967.87 | 43 |  | 0 | 0 | 0
C.1.24.3 | Left/ Lijevo 1 | 30967.87 | 44 |  | 0 | 0 | 0
C.1.24.4 | Left/ Lijevo 2 | 30967.85 | 45 |  | 0 | 0 | 0
C.1.25 | 24000 - 25000
C.1.25.1 | Right/ Desno 1 | 30967.87 | 38 |  | 0 | 0 | 0
C.1.25.2 | Right/ Desno 2 | 30967.87 | 39 |  | 0 | 0 | 0
C.1.25.3 | Left/ Lijevo 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.25.4 | Left/ Lijevo 2 | 30967.85 | 41 |  | 0 | 0 | 0
C.1.26 | 25000 - 26000
C.1.26.1 | Right/ Desno 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.26.2 | Right/ Desno 2 | 30967.87 | 41 |  | 0 | 0 | 0
C.1.26.3 | Left/ Lijevo 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.26.4 | Left/ Lijevo 2 | 30967.85 | 43 |  | 0 | 0 | 0
C.1.27 | 26000 - 27000
C.1.27.1 | Right/ Desno 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.27.2 | Right/ Desno 2 | 30967.87 | 43 |  | 0 | 0 | 0
C.1.27.3 | Left/ Lijevo 1 | 30967.87 | 44 |  | 0 | 0 | 0
C.1.27.4 | Left/ Lijevo 2 | 30967.85 | 45 |  | 0 | 0 | 0
C.1.28 | 27000 - 28000
C.1.28.1 | Right/ Desno 1 | 30967.87 | 38 |  | 0 | 0 | 0
C.1.28.2 | Right/ Desno 2 | 30967.87 | 39 |  | 0 | 0 | 0
C.1.28.3 | Left/ Lijevo 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.28.4 | Left/ Lijevo 2 | 30967.85 | 41 |  | 0 | 0 | 0
C.1.29 | 28000 - 29000
C.1.29.1 | Right/ Desno 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.29.2 | Right/ Desno 2 | 30967.87 | 41 |  | 0 | 0 | 0
C.1.29.3 | Left/ Lijevo 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.29.4 | Left/ Lijevo 2 | 30967.85 | 43 |  | 0 | 0 | 0
C.1.30 | 29000 - 30000
C.1.30.1 | Right/ Desno 1 | 30967.87 | 42 |  | 0 | 0 | 0
C.1.30.2 | Right/ Desno 2 | 30967.87 | 43 |  | 0 | 0 | 0
C.1.30.3 | Left/ Lijevo 1 | 30967.87 | 44 |  | 0 | 0 | 0
C.1.30.4 | Left/ Lijevo 2 | 30967.85 | 45 |  | 0 | 0 | 0
C.1.31 | 30000 - 31000
C.1.31.1 | Right/ Desno 1 | 30967.87 | 38 |  | 0 | 0 | 0
C.1.31.2 | Right/ Desno 2 | 30967.87 | 39 |  | 0 | 0 | 0
C.1.31.3 | Left/ Lijevo 1 | 30967.87 | 40 |  | 0 | 0 | 0
C.1.31.4 | Left/ Lijevo 2 | 30967.85 | 41 |  | 0 | 0 | 0
C.1.32 | 31000 - 31554
C.1.32.1 | Right/ Desno 1 | 17156.19 | 40 |  | 0 | 0 | 0
C.1.32.2 | Right/ Desno 2 | 17156.19 | 41 |  | 0 | 0 | 0
C.1.32.3 | Left/ Lijevo 1 | 17156.19 | 42 |  | 0 | 0 | 0
C.1.32.4 | Left/ Lijevo 2 | 17156.17 | 43 |  | 0 | 0 | 0
C.1.33 | 31554 - 32000
C.1.33.1 | Right/ Desno 1 | 8864.11 | 42 |  | 0 | 0 | 0
C.1.33.2 | Right/ Desno 2 | 8864.11 | 43 |  | 0 | 0 | 0
C.1.33.3 | Left/ Lijevo 1 | 8864.11 | 44 |  | 0 | 0 | 0
C.1.33.4 | Left/ Lijevo 2 | 8864.12 | 45 |  | 0 | 0 | 0
C.1.34 | 32000 - 33000
C.1.34.1 | Right/ Desno 1 | 19874.69 | 38 |  | 0 | 0 | 0
C.1.34.2 | Right/ Desno 2 | 19874.69 | 39 |  | 0 | 0 | 0
C.1.34.3 | Left/ Lijevo 1 | 19874.69 | 40 |  | 0 | 0 | 0
C.1.34.4 | Left/ Lijevo 2 | 19874.7 | 41 |  | 0 | 0 | 0
C.1.35 | 33000 - 34000
C.1.35.1 | Right/ Desno 1 | 19874.69 | 40 |  | 0 | 0 | 0
C.1.35.2 | Right/ Desno 2 | 19874.69 | 41 |  | 0 | 0 | 0
C.1.35.3 | Left/ Lijevo 1 | 19874.69 | 42 |  | 0 | 0 | 0
C.1.35.4 | Left/ Lijevo 2 | 19874.7 | 43 |  | 0 | 0 | 0
C.1.36 | 34000 - 35000
C.1.36.1 | Right/ Desno 1 | 19874.69 | 42 |  | 0 | 0 | 0
C.1.36.2 | Right/ Desno 2 | 19874.69 | 43 |  | 0 | 0 | 0
C.1.36.3 | Left/ Lijevo 1 | 19874.69 | 44 |  | 0 | 0 | 0
C.1.36.4 | Left/ Lijevo 2 | 19874.7 | 45 |  | 0 | 0 | 0
C.1.37 | 35000 - 36000
C.1.37.1 | Right/ Desno 1 | 19874.69 | 38 |  | 0 | 0 | 0
C.1.37.2 | Right/ Desno 2 | 19874.69 | 39 |  | 0 | 0 | 0
C.1.37.3 | Left/ Lijevo 1 | 19874.69 | 40 |  | 0 | 0 | 0
C.1.37.4 | Left/ Lijevo 2 | 19874.7 | 41 |  | 0 | 0 | 0
C.1.38 | 36000 - 37000
C.1.38.1 | Right/ Desno 1 | 19874.69 | 40 |  | 0 | 0 | 0
C.1.38.2 | Right/ Desno 2 | 19874.69 | 41 |  | 0 | 0 | 0
C.1.38.3 | Left/ Lijevo 1 | 19874.69 | 42 |  | 0 | 0 | 0
C.1.38.4 | Left/ Lijevo 2 | 19874.7 | 43 |  | 0 | 0 | 0
C.1.39 | 37000 - 38000
C.1.39.1 | Right/ Desno 1 | 19874.69 | 42 |  | 0 | 0 | 0
C.1.39.2 | Right/ Desno 2 | 19874.69 | 43 |  | 0 | 0 | 0
C.1.39.3 | Left/ Lijevo 1 | 19874.69 | 44 |  | 0 | 0 | 0
C.1.39.4 | Left/ Lijevo 2 | 19874.7 | 45 |  | 0 | 0 | 0
C.1.40 | 38000 - 39000
C.1.40.1 | Right/ Desno 1 | 19874.69 | 38 |  | 0 | 0 | 0
C.1.40.2 | Right/ Desno 2 | 19874.69 | 39 |  | 0 | 0 | 0
C.1.40.3 | Left/ Lijevo 1 | 19874.69 | 40 |  | 0 | 0 | 0
C.1.40.4 | Left/ Lijevo 2 | 19874.7 | 41 |  | 0 | 0 | 0
C.1.41 | 39000 - 40000
C.1.41.1 | Right/ Desno 1 | 19874.69 | 40 |  | 0 | 0 | 0
C.1.41.2 | Right/ Desno 2 | 19874.69 | 41 |  | 0 | 0 | 0
C.1.41.3 | Left/ Lijevo 1 | 19874.69 | 42 |  | 0 | 0 | 0
C.1.41.4 | Left/ Lijevo 2 | 19874.7 | 43 |  | 0 | 0 | 0
C.1.42 | 40000 - 40871
C.1.42.1 | Right/ Desno 1 | 17310.85 | 42 |  | 0 | 0 | 0
C.1.42.2 | Right/ Desno 2 | 17310.85 | 43 |  | 0 | 0 | 0
C.1.42.3 | Left/ Lijevo 1 | 17310.85 | 44 |  | 0 | 0 | 0
C.1.42.4 | Left/ Lijevo 2 | 17310.84 | 45 |  | 0 | 0 | 0
| Sub Total / Suma stavke C.1 | 4649330 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto C.2 | Road marking and signalization/ Oznake i signalizacija na putu
C.2.1 | 0 - 5000 Right/ Desno | 273128.98 | 35 |  | 0 | 0 | 0
C.2.2 | 0 - 5000 Left/ Lijevo | 273128.98 | 36 |  | 0 | 0 | 0
C.2.3 | 5000 - 11200 Right/ Desno | 338679.93 | 37 |  | 0 | 0 | 0
C.2.4 | 5000 - 11200 Left/ Lijevo | 338679.93 | 38 |  | 0 | 0 | 0
C.2.5 | 11200 - 16200 Right/ Desno | 273128.98 | 39 |  | 0 | 0 | 0
C.2.6 | 11200 - 16200 Left/ Lijevo | 273128.98 | 40 |  | 0 | 0 | 0
C.2.7 | 16200 - 22692 Right/ Desno | 354630.67 | 41 |  | 0 | 0 | 0
C.2.8 | 16200 - 22692 Left/ Lijevo | 354630.67 | 42 |  | 0 | 0 | 0
C.2.9 | 22692 - 27692 Right/ Desno | 273128.98 | 43 |  | 0 | 0 | 0
C.2.10 | 22692 - 27692 Left/ Lijevo | 273128.98 | 44 |  | 0 | 0 | 0
C.2.11 | 27692 - 31550 Right/ Desno | 210746.32 | 45 |  | 0 | 0 | 0
C.2.12 | 27692 - 31550 Left/ Lijevo | 210746.31 | 45 |  | 0 | 0 | 0
C.2.13 | 31550 - 36550 Right/ Desno | 285303.9 | 46 |  | 0 | 0 | 0
C.2.14 | 31550 - 36550 Left/ Lijevo | 285303.9 | 46 |  | 0 | 0 | 0
C.2.15 | 36550 - 40871 Right/ Desno | 246559.63 | 47 |  | 0 | 0 | 0
C.2.16 | 36550 - 40871 Left/ Lijevo | 246559.62 | 47 |  | 0 | 0 | 0
| Sub Total / Suma stavke C.2 | 4510614.76 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto C.3 | Traffic control equipment/ Oprema za kontrolu saobraćaja
C.3.1 | 0-1000
C.3.1.1 | Right - installation/ Desno - postavljanje | 264309.51 | 35 |  | 0 | 0 | 0
C.3.1.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 36 |  | 0 | 0 | 0
C.3.1.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 37 |  | 0 | 0 | 0
C.3.1.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 38 |  | 0 | 0 | 0
C.3.2 | 1000 -2000
C.3.2.1 | Right - installation/ Desno - postavljanje | 264309.51 | 35 |  | 0 | 0 | 0
C.3.2.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 36 |  | 0 | 0 | 0
C.3.2.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 37 |  | 0 | 0 | 0
C.3.2.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 38 |  | 0 | 0 | 0
C.3.3 | 2000 - 3000
C.3.3.1 | Right - installation/ Desno - postavljanje | 264309.51 | 36 |  | 0 | 0 | 0
C.3.3.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 37 |  | 0 | 0 | 0
C.3.3.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 38 |  | 0 | 0 | 0
C.3.3.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 39 |  | 0 | 0 | 0
C.3.4 | 3000 - 4000
C.3.4.1 | Right - installation/ Desno - postavljanje | 264309.51 | 36 |  | 0 | 0 | 0
C.3.4.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 37 |  | 0 | 0 | 0
C.3.4.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 38 |  | 0 | 0 | 0
C.3.4.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 39 |  | 0 | 0 | 0
C.3.5 | 4000 - 5000
C.3.5.1 | Right - installation/ Desno - postavljanje | 264309.51 | 37 |  | 0 | 0 | 0
C.3.5.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 38 |  | 0 | 0 | 0
C.3.5.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 39 |  | 0 | 0 | 0
C.3.5.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 40 |  | 0 | 0 | 0
C.3.6 | 5000 - 6000
C.3.6.1 | Right - installation/ Desno - postavljanje | 264309.51 | 37 |  | 0 | 0 | 0
C.3.6.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 38 |  | 0 | 0 | 0
C.3.6.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 39 |  | 0 | 0 | 0
C.3.6.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 40 |  | 0 | 0 | 0
C.3.7 | 6000 - 7000
C.3.7.1 | Right - installation/ Desno - postavljanje | 264309.51 | 37 |  | 0 | 0 | 0
C.3.7.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 38 |  | 0 | 0 | 0
C.3.7.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 39 |  | 0 | 0 | 0
C.3.7.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 40 |  | 0 | 0 | 0
C.3.8 | 7000 - 8000
C.3.8.1 | Right - installation/ Desno - postavljanje | 264309.51 | 38 |  | 0 | 0 | 0
C.3.8.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 39 |  | 0 | 0 | 0
C.3.8.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 40 |  | 0 | 0 | 0
C.3.8.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 41 |  | 0 | 0 | 0
C.3.9 | 8000 - 9000
C.3.9.1 | Right - installation/ Desno - postavljanje | 264309.51 | 38 |  | 0 | 0 | 0
C.3.9.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 39 |  | 0 | 0 | 0
C.3.9.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 40 |  | 0 | 0 | 0
C.3.9.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 41 |  | 0 | 0 | 0
C.3.10 | 9000 - 10000
C.3.10.1 | Right - installation/ Desno - postavljanje | 264309.51 | 39 |  | 0 | 0 | 0
C.3.10.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 40 |  | 0 | 0 | 0
C.3.10.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 41 |  | 0 | 0 | 0
C.3.10.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 42 |  | 0 | 0 | 0
C.3.11 | 10000 - 11000
C.3.11.1 | Right - installation/ Desno - postavljanje | 264309.51 | 39 |  | 0 | 0 | 0
C.3.11.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 40 |  | 0 | 0 | 0
C.3.11.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 41 |  | 0 | 0 | 0
C.3.11.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 42 |  | 0 | 0 | 0
C.3.12 | 11000 - 12000
C.3.12.1 | Right - installation/ Desno - postavljanje | 264309.51 | 39 |  | 0 | 0 | 0
C.3.12.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 40 |  | 0 | 0 | 0
C.3.12.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 41 |  | 0 | 0 | 0
C.3.12.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 42 |  | 0 | 0 | 0
C.3.13 | 12000 - 13000
C.3.13.1 | Right - installation/ Desno - postavljanje | 264309.51 | 40 |  | 0 | 0 | 0
C.3.13.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 41 |  | 0 | 0 | 0
C.3.13.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 42 |  | 0 | 0 | 0
C.3.13.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 43 |  | 0 | 0 | 0
C.3.14 | 13000 - 14000
C.3.14.1 | Right - installation/ Desno - postavljanje | 264309.51 | 40 |  | 0 | 0 | 0
C.3.14.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 41 |  | 0 | 0 | 0
C.3.14.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 42 |  | 0 | 0 | 0
C.3.14.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 43 |  | 0 | 0 | 0
C.3.15 | 14000 - 15000
C.3.15.1 | Right - installation/ Desno - postavljanje | 264309.51 | 40 |  | 0 | 0 | 0
C.3.15.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 41 |  | 0 | 0 | 0
C.3.15.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 42 |  | 0 | 0 | 0
C.3.15.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 43 |  | 0 | 0 | 0
C.3.16 | 15000 - 16000
C.3.16.1 | Right - installation/ Desno - postavljanje | 264309.51 | 41 |  | 0 | 0 | 0
C.3.16.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 42 |  | 0 | 0 | 0
C.3.16.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.16.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.17 | 16000 - 17000
C.3.17.1 | Right - installation/ Desno - postavljanje | 264309.51 | 41 |  | 0 | 0 | 0
C.3.17.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 42 |  | 0 | 0 | 0
C.3.17.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.17.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.18 | 17000 - 18000
C.3.18.1 | Right - installation/ Desno - postavljanje | 264309.51 | 41 |  | 0 | 0 | 0
C.3.18.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 42 |  | 0 | 0 | 0
C.3.18.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.18.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.19 | 18000 - 19000
C.3.19.1 | Right - installation/ Desno - postavljanje | 264309.51 | 42 |  | 0 | 0 | 0
C.3.19.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 43 |  | 0 | 0 | 0
C.3.19.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 44 |  | 0 | 0 | 0
C.3.19.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 45 |  | 0 | 0 | 0
C.3.20 | 19000 - 20000
C.3.20.1 | Right - installation/ Desno - postavljanje | 264309.51 | 42 |  | 0 | 0 | 0
C.3.20.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 43 |  | 0 | 0 | 0
C.3.20.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 44 |  | 0 | 0 | 0
C.3.20.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 45 |  | 0 | 0 | 0
C.3.21 | 20000 - 21000
C.3.21.1 | Right - installation/ Desno - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.21.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.21.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 45 |  | 0 | 0 | 0
C.3.21.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 46 |  | 0 | 0 | 0
C.3.22 | 21000 - 22000
C.3.22.1 | Right - installation/ Desno - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.22.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.22.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 45 |  | 0 | 0 | 0
C.3.22.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 46 |  | 0 | 0 | 0
C.3.23 | 22000 - 23000
C.3.23.1 | Right - installation/ Desno - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.23.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.23.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 45 |  | 0 | 0 | 0
C.3.23.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 46 |  | 0 | 0 | 0
C.3.24 | 23000 - 24000
C.3.24.1 | Right - installation/ Desno - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.24.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.24.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 45 |  | 0 | 0 | 0
C.3.24.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 46 |  | 0 | 0 | 0
C.3.25 | 24000 - 25000
C.3.25.1 | Right - installation/ Desno - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.25.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.25.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 45 |  | 0 | 0 | 0
C.3.25.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 46 |  | 0 | 0 | 0
C.3.26 | 25000 - 26000
C.3.26.1 | Right - installation/ Desno - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.26.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.26.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 45 |  | 0 | 0 | 0
C.3.26.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 46 |  | 0 | 0 | 0
C.3.27 | 26000 - 27000
C.3.27.1 | Right - installation/ Desno - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.27.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.27.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 45 |  | 0 | 0 | 0
C.3.27.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 46 |  | 0 | 0 | 0
C.3.28 | 27000 - 28000
C.3.28.1 | Right - installation/ Desno - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.28.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.28.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 45 |  | 0 | 0 | 0
C.3.28.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 46 |  | 0 | 0 | 0
C.3.29 | 28000 - 29000
C.3.29.1 | Right - installation/ Desno - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.29.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.29.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 45 |  | 0 | 0 | 0
C.3.29.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 46 |  | 0 | 0 | 0
C.3.30 | 29000 - 30000
C.3.30.1 | Right - installation/ Desno - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.30.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.30.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 45 |  | 0 | 0 | 0
C.3.30.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 46 |  | 0 | 0 | 0
C.3.31 | 30000 - 31000
C.3.31.1 | Right - installation/ Desno - postavljanje | 264309.51 | 43 |  | 0 | 0 | 0
C.3.31.2 | Right - commissioning/ Desno - puštanje u rad | 29367.72 | 44 |  | 0 | 0 | 0
C.3.31.3 | Left - installation/ Lijevo - postavljanje | 264309.51 | 45 |  | 0 | 0 | 0
C.3.31.4 | Left - commissioning/ Lijevo - puštanje u rad | 29367.72 | 46 |  | 0 | 0 | 0
C.3.32 | 31000 - 31554
C.3.32.1 | Right - installation/ Desno - postavljanje | 146427.46 | 43 |  | 0 | 0 | 0
C.3.32.2 | Right - commissioning/ Desno - puštanje u rad | 16269.72 | 44 |  | 0 | 0 | 0
C.3.32.3 | Left - installation/ Lijevo - postavljanje | 146427.29 | 45 |  | 0 | 0 | 0
C.3.32.4 | Left - commissioning/ Lijevo - puštanje u rad | 16269.7 | 46 |  | 0 | 0 | 0
C.3.33 | 31554 - 32000
C.3.33.1 | Right - installation/ Desno - postavljanje | 101270.57 | 43 |  | 0 | 0 | 0
C.3.33.2 | Right - commissioning/ Desno - puštanje u rad | 11252.29 | 44 |  | 0 | 0 | 0
C.3.33.3 | Left - installation/ Lijevo - postavljanje | 101270.57 | 45 |  | 0 | 0 | 0
C.3.33.4 | Left - commissioning/ Lijevo - puštanje u rad | 11252.29 | 46 |  | 0 | 0 | 0
C.3.34 | 32000 - 33000
C.3.34.1 | Right - installation/ Desno - postavljanje | 227064.08 | 43 |  | 0 | 0 | 0
C.3.34.2 | Right - commissioning/ Desno - puštanje u rad | 25229.34 | 44 |  | 0 | 0 | 0
C.3.34.3 | Left - installation/ Lijevo - postavljanje | 227064.08 | 45 |  | 0 | 0 | 0
C.3.34.4 | Left - commissioning/ Lijevo - puštanje u rad | 25229.34 | 46 |  | 0 | 0 | 0
C.3.35 | 33000 - 34000
C.3.35.1 | Right - installation/ Desno - postavljanje | 227064.08 | 43 |  | 0 | 0 | 0
C.3.35.2 | Right - commissioning/ Desno - puštanje u rad | 25229.34 | 44 |  | 0 | 0 | 0
C.3.35.3 | Left - installation/ Lijevo - postavljanje | 227064.08 | 45 |  | 0 | 0 | 0
C.3.35.4 | Left - commissioning/ Lijevo - puštanje u rad | 25229.34 | 46 |  | 0 | 0 | 0
C.3.36 | 34000 - 35000
C.3.36.1 | Right - installation/ Desno - postavljanje | 227064.08 | 44 |  | 0 | 0 | 0
C.3.36.2 | Right - commissioning/ Desno - puštanje u rad | 25229.34 | 45 |  | 0 | 0 | 0
C.3.36.3 | Left - installation/ Lijevo - postavljanje | 227064.08 | 46 |  | 0 | 0 | 0
C.3.36.4 | Left - commissioning/ Lijevo - puštanje u rad | 25229.34 | 47 |  | 0 | 0 | 0
C.3.37 | 35000 - 36000
C.3.37.1 | Right - installation/ Desno - postavljanje | 227064.08 | 44 |  | 0 | 0 | 0
C.3.37.2 | Right - commissioning/ Desno - puštanje u rad | 25229.34 | 45 |  | 0 | 0 | 0
C.3.37.3 | Left - installation/ Lijevo - postavljanje | 227064.08 | 46 |  | 0 | 0 | 0
C.3.37.4 | Left - commissioning/ Lijevo - puštanje u rad | 25229.34 | 47 |  | 0 | 0 | 0
C.3.38 | 36000 - 37000
C.3.38.1 | Right - installation/ Desno - postavljanje | 227064.08 | 44 |  | 0 | 0 | 0
C.3.38.2 | Right - commissioning/ Desno - puštanje u rad | 25229.34 | 45 |  | 0 | 0 | 0
C.3.38.3 | Left - installation/ Lijevo - postavljanje | 227064.08 | 46 |  | 0 | 0 | 0
C.3.38.4 | Left - commissioning/ Lijevo - puštanje u rad | 25229.34 | 47 |  | 0 | 0 | 0
C.3.39 | 37000 - 38000
C.3.39.1 | Right - installation/ Desno - postavljanje | 227064.08 | 44 |  | 0 | 0 | 0
C.3.39.2 | Right - commissioning/ Desno - puštanje u rad | 25229.34 | 45 |  | 0 | 0 | 0
C.3.39.3 | Left - installation/ Lijevo - postavljanje | 227064.08 | 46 |  | 0 | 0 | 0
C.3.39.4 | Left - commissioning/ Lijevo - puštanje u rad | 25229.34 | 47 |  | 0 | 0 | 0
C.3.40 | 38000 - 39000
C.3.40.1 | Right - installation/ Desno - postavljanje | 227064.08 | 44 |  | 0 | 0 | 0
C.3.40.2 | Right - commissioning/ Desno - puštanje u rad | 25229.34 | 45 |  | 0 | 0 | 0
C.3.40.3 | Left - installation/ Lijevo - postavljanje | 227064.08 | 46 |  | 0 | 0 | 0
C.3.40.4 | Left - commissioning/ Lijevo - puštanje u rad | 25229.34 | 47 |  | 0 | 0 | 0
C.3.41 | 39000 - 40000
C.3.41.1 | Right - installation/ Desno - postavljanje | 227064.08 | 44 |  | 0 | 0 | 0
C.3.41.2 | Right - commissioning/ Desno - puštanje u rad | 25229.34 | 45 |  | 0 | 0 | 0
C.3.41.3 | Left - installation/ Lijevo - postavljanje | 227064.08 | 46 |  | 0 | 0 | 0
C.3.41.4 | Left - commissioning/ Lijevo - puštanje u rad | 25229.34 | 47 |  | 0 | 0 | 0
C.3.42 | 40000 - 40871
C.3.42.1 | Right - installation/ Desno - postavljanje | 197772.8 | 44 |  | 0 | 0 | 0
C.3.42.2 | Right - commissioning/ Desno - puštanje u rad | 21974.76 | 45 |  | 0 | 0 | 0
C.3.42.3 | Left - installation/ Lijevo - postavljanje | 197772.75 | 46 |  | 0 | 0 | 0
C.3.42.4 | Left - commissioning/ Lijevo - puštanje u rad | 21974.75 | 47 |  | 0 | 0 | 0
| Sub Total / Suma stavke C.3 | 23234617.93 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto C.4 | Low voltage equipment/ Niskonaponska oprema
C.4.1 | 0 - 5000 Right/ Desno
C.4.1.1 | Right - installation/ Desno - postavljanje | 39965.96 | 37 |  | 0 | 0 | 0
C.4.1.2 | Right - commissioning/ Desno - puštanje u rad | 4440.66 | 38 |  | 0 | 0 | 0
C.4.1.3 | Left - installation/ Lijevo - postavljanje | 39965.96 | 39 |  | 0 | 0 | 0
C.4.1.4 | Left - commissioning/ Lijevo - puštanje u rad | 4440.66 | 40 |  | 0 | 0 | 0
C.4.2 | 5000 - 11200
C.4.2.1 | Right - installation/ Desno - postavljanje | 49557.78 | 38 |  | 0 | 0 | 0
C.4.2.2 | Right - commissioning/ Desno - puštanje u rad | 5506.42 | 39 |  | 0 | 0 | 0
C.4.2.3 | Left - installation/ Lijevo - postavljanje | 49557.78 | 40 |  | 0 | 0 | 0
C.4.2.4 | Left - commissioning/ Lijevo - puštanje u rad | 5506.42 | 41 |  | 0 | 0 | 0
C.4.3 | 11200 - 16200
C.4.3.1 | Right - installation/ Desno - postavljanje | 39965.96 | 39 |  | 0 | 0 | 0
C.4.3.2 | Right - commissioning/ Desno - puštanje u rad | 4440.66 | 40 |  | 0 | 0 | 0
C.4.3.3 | Left - installation/ Lijevo - postavljanje | 39965.96 | 41 |  | 0 | 0 | 0
C.4.3.4 | Left - commissioning/ Lijevo - puštanje u rad | 4440.66 | 42 |  | 0 | 0 | 0
C.4.4 | 16200 - 22692
C.4.4.1 | Right - installation/ Desno - postavljanje | 51891.8 | 40 |  | 0 | 0 | 0
C.4.4.2 | Right - commissioning/ Desno - puštanje u rad | 5765.76 | 41 |  | 0 | 0 | 0
C.4.4.3 | Left - installation/ Lijevo - postavljanje | 51891.8 | 42 |  | 0 | 0 | 0
C.4.4.4 | Left - commissioning/ Lijevo - puštanje u rad | 5765.76 | 43 |  | 0 | 0 | 0
C.4.5 | 22692 - 27692
C.4.5.1 | Right - installation/ Desno - postavljanje | 39965.96 | 41 |  | 0 | 0 | 0
C.4.5.2 | Right - commissioning/ Desno - puštanje u rad | 4440.66 | 42 |  | 0 | 0 | 0
C.4.5.3 | Left - installation/ Lijevo - postavljanje | 39965.96 | 43 |  | 0 | 0 | 0
C.4.5.4 | Left - commissioning/ Lijevo - puštanje u rad | 4440.66 | 44 |  | 0 | 0 | 0
C.4.6 | 27692 - 31550
C.4.6.1 | Right - installation/ Desno - postavljanje | 30837.74 | 42 |  | 0 | 0 | 0
C.4.6.2 | Right - commissioning/ Desno - puštanje u rad | 3426.41 | 43 |  | 0 | 0 | 0
C.4.6.3 | Left - installation/ Lijevo - postavljanje | 30837.74 | 44 |  | 0 | 0 | 0
C.4.6.4 | Left - commissioning/ Lijevo - puštanje u rad | 3426.41 | 45 |  | 0 | 0 | 0
C.4.7 | 31550 - 36550
C.4.7.1 | Right - installation/ Desno - postavljanje | 34392.47 | 43 |  | 0 | 0 | 0
C.4.7.2 | Right - commissioning/ Desno - puštanje u rad | 3821.39 | 44 |  | 0 | 0 | 0
C.4.7.3 | Left - installation/ Lijevo - postavljanje | 34392.47 | 45 |  | 0 | 0 | 0
C.4.7.4 | Left - commissioning/ Lijevo - puštanje u rad | 3821.39 | 46 |  | 0 | 0 | 0
C.4.8 | 36550 - 40871
C.4.8.1 | Right - installation/ Desno - postavljanje | 29721.96 | 44 |  | 0 | 0 | 0
C.4.8.2 | Right - commissioning/ Desno - puštanje u rad | 3302.38 | 45 |  | 0 | 0 | 0
C.4.8.3 | Left - installation/ Lijevo - postavljanje | 29721.96 | 46 |  | 0 | 0 | 0
C.4.8.4 | Left - commissioning/ Lijevo - puštanje u rad | 3302.44 | 47 |  | 0 | 0 | 0
| Sub Total / Suma stavke C.4 | 702888 |  |  | 0 | 0 | 0
Cost center/ Troškovno mjesto C.5 | Tolling system and station/ Sistem i stanice za naplatu putarine
C.5.1 | 100% complete/završeno (it will be splitted by location/biće podijeljeno prema lokaciji) | 5203807.64 | 40 |  | 0 | 0 | 0
| Sub Total / Suma stavke C.5 | 5203807.64 |  |  | 0 | 0 | 0
| TOTAL COST CENTER / UKUPNO TROSKOVNO MJESTO 15 | 38301258.33 |  |  | 0 | 0 | 0